## Subgrade Construction
|  |  |  | Process Control Plan |  | LQS-QA-6069 | Approved |  | Signature
|  |  |  | Contract Name: | Lower Queen St - Bridge Redevelopment |  | FH Engineer
|  |  |  | Procedure: | Subgrade & Basecourse Construction |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | LQS-CS-7069 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | — | Check Drawing Register | Site Engineer
3 | Survey Setout | W | Set out pegs installed at required intervals to achive required crossfall. | Prior to commencement | Survey | — | Photos | Site Engineer
4 | Material Compliance | H | Material Imported to the site & used in the construction of the pavement is checked that the material complies with the Specifications | Prior to commencement | Document Review | Grading tests for quarried aggregates | Lab Test Results | Site Engineer | Engineers Rep
5 | Subgrade Preparation (1) | W | Carry out a Level Check on the trimmed subgrade | Prior to placing Subbase | Survey | Tolerance = -50mm +20mm | As builts | Site Engineer
5 | Subgrade Preparation (2) | H | Proof Roll - Site Engineer and Engineers Rep to undertake a Proof Roll test on the trimmed subgrade. 1 pass minimum per lane | Prior to placing Subbase | Over whole area requiring construction | Check for consistency. Areas with excessive flex to carry out additional scala testing. | Photos | Site Engineer | Engineers Rep
5 | Subgrade Preparation (3) | H | Scala Testing/Plateau Testing - Scala testing to 10m centres staggered. If Proof Roll Fails undertake additional Scala testing to 2m centres staggered in the area. If Scalas not sufficient, Plateau Testing to be carried out to prove compaction requirements | Prior to placing Subbase | Scala worksheet, Plateau Testing | Scala results recorded, Plateau Testing sheet | LQS-CS-4003, Photos | Site Engineer | Engineers Rep
5 | Subgrade Preparation (4) | H | Undercut - Pending results from proof roll and Scala, undercut areas to be marked out, excavated and constructed | Prior to placing Subbase | Scala worksheet, inferred CBR | Asbuilt & Survey to pick up undercut area. | LQS-CS-4003, Photos | Site Engineer | Engineers Rep
6 | Subbase Construction (1) | M | Subbase compaction | 1 per 50m2 staggered (min 5 tests per lot) | Visual Inspection, NDM Lab Testing | Compaction of material is being followed within the guidelines set in the specifications. Avg. >= 95% MDD and Min. >= 92% MDD | Photos, Pavement Lab Testing Spreadsheet | Site Engineer
6 | Subbase Construction (2) | W | Carry out a Level Check on the trimmed Subbase once placed and compacted | 1/20m | Measurement | Tolerance = -25mm/+10mm | Photos, As-builts | Site Engineer
6 | Basecourse Construction (1) | W | Plateau Density Testing for Basecourse Layers | Trial pad prior to use | NDM Lab Testing | To establish roller pattern | Pavement Lab Testing Spreadsheet | Site Engineer
6 | Basecourse Construction (2) | M | Basecourse compaction | 1 per 50m2 staggered (min 5 tests per lot) | Visual Inspection, NDM Lab Testing | Compaction of material is being followed within the guidelines set in the specifications. Avg. >= 98% MDD and Min. >= 95% MDD | Photos, Pavement Lab Testing Spreadsheet | Site Engineer
6 | Basecourse Construction (3) | W | Carry out a Level Check on the trimmed basecourse | 1/20m | Measurement | Tolerance = -10mm/+5mm | Photos, As-builts | Site Engineer | Engineers Rep
6 | Basecourse Construction (4) | H | Benkelman Beam Testing | Wheel Path in each lane, every 10m staggered along alignment | Benkelman Beam Test | Desired result - average <1.0mm with no reading over 1.5mm | Pavement Lab Testing Spreadsheet | Site Engineer
6 | Basecourse Construction (5) | H | Pavement Cross fall/Shape check | 1/10m | Survey check & Measurement | Crossfall, shape and surface complies with agreed design | Photos | Site Engineer
7 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for pavement testing as per Specifications | At completion of Lot | Document Review | — | Pavement Lab Testing Spreadsheet | Site Engineer | Engineers Rep
8 | As-builts | H | As-built documentation provided per contract requirements | At the completion of the Lot of work | Drawings | Ensure all Asbuilts uploaded into CONQA | Asbuilt Drawing | Site Engineer | Engineers Rep
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: