## Asphalt - Surfacing
|  |  |  | Process Control Plan |  | LQS-QA-6076 | Approved |  | Signature
|  |  |  | Contract Name: | Lower Queen St - Bridge Redevelopment |  | FH Engineer
|  |  |  | Procedure: | Asphalt - Surfacing |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | LQS--CS-7076 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | — | Check Drawing Register | Site Engineer
3 | Previous Lots Completed | W | All previous pavement lots signed off | Prior to commencement | Document Review | Previous ITP must be completed |  | Site Engineer
4 | Survey Setout | W | Determine paving run start/stop locations | Prior to commencement | Survey | Mark out on site | Subcontractor QA Records | Site Engineer
5 | Material Compliance | H | Mix Design approved | Prior to commencement | Submission | Material is approved by a Notice to Supplier being issued | Mix Design | Site Engineer | Engineer Rep
6 | Tack Coat | H | Membrane Coat to be used in between Asphalt and Granular pavament, or structures | Prior to placing Surfacing AC | Lab Testing and measurements | The application rate shall be applied to ensure a continuous film, per contract requirements | Subcontractor QA Records | Site Engineer | Engineer Rep
7 | Bond coat on Concrete Bridge decks | W | Bond coat and DG Mix 10 levelling to be used in between the Concrete Bridge Decks and the Surfacing AC, if required | Prior to laying Surfacing AC | Lab Testing and measurements | Binder content and application rate | Subcontractor QA Records | Site Engineer | Engineer Rep
8 | Construction of Surfacing Asphaltic Concrete | W | Site team QA Checks | During Construction | Site Measurements | Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing | Subcontractor QA Records | Site Engineer
9 | Layer checksheets | H | Each shift the Pavement Layers Checksheet LQS-CS-4055 is to be filled in and approved by the Project Manager | At completion of each shift | Document and result review | — | LQS-CS-4055 | Site Engineer | Engineer Rep
10 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for pavement testing as per Specifications | At completion of Lot | Document Review | — | Pavement Lab Testing Spreadsheet | Site Engineer | Engineer Rep
11 | As-builts | H | As-builts and QA submitted per contract requirements | At the completion of the Lot of work | Drawings | — | Asbuilt Drawing | Site Engineer | Engineer Rep
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: