## Asphalt - Surfacing
[5 empty] | Process Control Plan |  | LQS-QA-6077 | Approved |  | Signature
[5 empty] | Contract Name: | Lower Queen St - Bridge Redevelopment |  | FH Engineer
[5 empty] | Procedure: | Chipseal - Surfacing |  | FH Project Manager
Inspection & Test Plan / Checklist
| Lot No: |  |  |  | Corresponding Work Instruction: |  | LQS--CS-7077 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
| 1 | Permits | W | Obtain Permits | As required | Document Review | Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
| 2 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | — | Check Drawing Register | Site Engineer
| 3 | Previous Lots Completed | W | All previous pavement lots signed off | Prior to commencement | Document Review | Previous ITP must be completed |  | Site Engineer
| 4 | Survey Setout | W | Determine chipsealing runs start/stop locations, extent of area to be chipsealed | Prior to commencement | Measure, Inspect | Mark out on site | Chipsealing Dept QA Records | Site Engineer
| 5 | Material Compliance | H | Bitumen/Emulsion Mix Design approved | Prior to commencement | Submission | Material is approved by a Notice to Supplier being issued | Mix Design | Site Engineer | Engineer Rep
| 6 | Chip grade and application rates | H | Chip grade and application rates determined and submitted for approval | Prior to commencement | Submission | Material is approved by a Notice to Supplier being issued | Mix Design | Site Engineer | Engineer Rep
` | 7 | Pavement approval to have Chipsealing commence | H | Subgrade and Basecourse to be at an acceptable standard. Surface to have mosaic surface prepared for bitumen/emulsion application. | Prior to commencement | Review | Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing | Subcontractor QA Records, Pre-seal checklist | Site Engineer | Engineer Rep
| 8 | Chipsealing new surface | W | Chipsealing team QA Checks | During Construction | Site Measurements | Confirmation of application rates, site QA documentation developed by sealing dept | Subcontractor QA Records, Photos | Site Engineer
| 9 | Post seal Checks | W | Post sealing review the surface to make sure chip has set. Road Sweeping to be carried out after sealed surface is sound (~48 hours afer sealing) | Post Sealing | Site Measurements | Confirmation of application rates, site QA documentation developed by sealing dept | Photos | Site Engineer
| 10 | Linemarking | W | Linemarking to be painted per design requirements | Post Sealing | Site Measurements, review | Linemarking is placed per drawings, or as agreed with Engineer | Photos | Site Engineer
| 11 | As-builts | H | As-builts and QA submitted per contract requirements | At the completion of the Lot of work | Drawings | Uploaded to CONQA | Asbuilt Drawing | Site Engineer | Engineer Rep
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
| QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
| QA checked By Project Manager: |  |  |  |  | Signature: |  |  | Date:
| Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: