## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | LQS-QA-6006 - ITP - Insitu Concrete | itp |  |  |  |  | LQS-QA-6006 - ITP - Insitu Concrete
section | Insitu Concrete
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Set out design features as per Issued For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - Survey receipt
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - Engineer approval
label | RECORDS - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | FREQUENCY - Prior to pouring concrete
label | INSPECTION / TEST METHOD - Concrete Delivery Dockets
label | RECORDS - Concrete Delivery Dockets
checkpoint | 5 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | FREQUENCY - Prior to ordering steel
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
label | RECORDS - Detail Sheets and Mill Certificates
checkpoint | 5 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any welding or mechanical splicing to be approved by the Design Engineer
label | FREQUENCY - Prior to welding or splicing
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any reinforcement requiring cutting or bending on site to be approved by the Design Engineer
label | FREQUENCY - Prior to cutting or bending on site
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Foundation Acceptance by Engineer's Rep
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Inspection by Engineer
label | CONFORMANCE CRITERIA - Inspection and Acceptance of Structure Foundations
label | RECORDS - Photos, checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Blinding Concrete
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If required, once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Inspection by Engineer
label | CONFORMANCE CRITERIA - Engineer approval
label | RECORDS - Sign off this document
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork) (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Formwork to be constructed to design and set to correct line and level as set out by the surveyor
label | FREQUENCY - Daily Visual Inspection
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - LQS-CS-4008, photos
checkpoint | 8 - Temporary Works (Formwork) (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - LQS-CS-4008
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
label | FREQUENCY - Daily Visual Inspection
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - LQS-CS-4008, Photos
checkpoint | 9 - Reinforcing (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check for any cast in items and ensure they are fixed correctly
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - LQS-CS-4008
checkpoint | 10 - Concrete Pumping Operations
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure the Permit to Concrete Pump Checksheet has been completed before concrete pumping commences
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - Permit to Pump Checksheet
label | RECORDS - LQS-CS-4029
checkpoint | 11 - Concreting (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The MSQA Engineer shall be advised at least 48 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORDS - LQS-CS-4008
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Concreting (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken i.e. Slump test
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Test Results
label | CONFORMANCE CRITERIA - NZS 3112, Concrete Inspection Record
label | RECORDS - LQS-CS-4090
checkpoint | 11 - Concreting (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Concrete surface finishes shall be:
label | ○ Concealed Form Surfaces: F1
label | ○ Exposed Formed Surfaces: F4
label | ○ Exposed Uniformed Surfaces: U2
label | ○ Concealed Uniformed Surfaces: U1
label | FREQUENCY - At completion of pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - LQS-CS-4008
checkpoint | 12 - Remove formwork
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Remove formwork as per the approved work method
label | FREQUENCY - At completion of pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - LQS-CS-4008
checkpoint | 13 - As-builts
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As-built documentation provided per contract requirements
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION / TEST METHOD - Drawings
label | CONFORMANCE CRITERIA - Required Asbuilts uploaded into CONQA
label | RECORDS - Asbuilt Drawing
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6031 - ITP - Bored Pile | itp |  |  |  |  | LQS-QA-6031 - ITP - Bored Pile
section | Bored Pile
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), Notify Worksafe NZ if req. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Sub-Contract and Supplier Agreements are signed, TMP is approved all Sub-Contractors and Suppliers are inducted to site
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Signed Subcontract and Supplier Agreements, TMP on M-Files and Induction Register updated
label | RECORDS - Subcontract and Supplier Agreements, Approved TMP & Updated Induction Register on sharefile
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 4 - Survey Setout (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Set out grid around pile location. As per contract drawings and specification.
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - As-built, photos
checkpoint | 4 - Survey Setout (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Verification of pile set-out by surveyor
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Survey
label | CONFORMANCE CRITERIA - Consistency with setout
label | RECORDS - As-built, photos
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | FREQUENCY - Prior to pouring concrete
label | INSPECTION / TEST METHOD - Concrete Delivery Dockets
label | RECORDS - Concrete Delivery Dockets
checkpoint | 5 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | FREQUENCY - Prior to ordering steel
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
label | RECORDS - Detail Sheets and Mill Certificates
checkpoint | 5 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to welding or splicing
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to cutting or bending on site
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Pile Line
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check if the bench has been excavated/filled can accommodate the entire pile line
label | FREQUENCY - Prior to Commencement
label | INSPECTION / TEST METHOD - Visual Inspection
label | CONFORMANCE CRITERIA - Relevant Drawing
label | RECORDS - LQS-CS-4011
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Permanent Steel Liners (If required) (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check fabrication of casings
label | FREQUENCY - Prior to Commencement
label | INSPECTION / TEST METHOD - Visual Inspection
label | CONFORMANCE CRITERIA - Piling Specification
label | RECORDS - Photos
checkpoint | 7 - Permanent Steel Liners (If required) (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check installation of casings
label | FREQUENCY - Each Pile
label | INSPECTION / TEST METHOD - Visual Inspection
label | CONFORMANCE CRITERIA - Piling Specification
label | RECORDS - Photos, As-Built
checkpoint | 8 - Drill Rig Set Up
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check drilling performance, verticality and position
label | FREQUENCY - Each Pile
label | INSPECTION / TEST METHOD - Visual Inspection
label | CONFORMANCE CRITERIA - Piling Specification, Relevant Drawings
label | RECORDS - LQS-CS-4011 & LQS-CS-4083
checkpoint | 9 - Pile Bore Condition & Logs
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Inspect pile bore condition, pile depth, rock socket length and toe level
label | FREQUENCY - Each Pile
label | INSPECTION / TEST METHOD - Measure
label | CONFORMANCE CRITERIA - Checklist completed
label | RECORDS - LQS-CS-4011 & LQS-CS-4083
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Plug Driving Operations
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check driving performance, verticality and position
label | FREQUENCY - Each Pile
label | INSPECTION / TEST METHOD - Checksheet
label | CONFORMANCE CRITERIA - Piling Specification, Relevant Drawings
label | RECORDS - LQS-CS-4099
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Reinforcement Cage (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check supply and installation of reinforcement cage
label | FREQUENCY - Each Cage
label | INSPECTION / TEST METHOD - Document Review & Visual Inspection
label | CONFORMANCE CRITERIA - Relevant Drawings
label | RECORDS - LQS-CS-4011, Photos
checkpoint | 11 - Reinforcement Cage (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Arrange for inspection of installed reinforcement cage
label | FREQUENCY - Min 48 hours prior to pour
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORDS - LQS-CS-4011
checkpoint | 12 - Concreting (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The Design Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORDS - LQS-CS-4011
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Concreting (2)
label | ACTION (Hold, Monitor, Witness) - w
label | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken if applicable
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Test Results
label | CONFORMANCE CRITERIA - Concrete Dockets
label | RECORDS - LQS-CS-4090
checkpoint | 13 - As Builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Survey final position and R.L. of each pile, produce As-Built drawings. Any other documentation provided per contract requirements
label | FREQUENCY - Each Pile
label | INSPECTION / TEST METHOD - Measurement / Survey/As-built Diagram
label | CONFORMANCE CRITERIA - As-Built Drawing uploaded into CONQA
label | RECORDS - Pile As-Built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6040 - ITP - Precast Installation | itp |  |  |  |  | LQS-QA-6040 - ITP - Precast Installation
section | Precast Installation
checkpoint | 1 - Permits (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 1 - Permits (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Permit to Lift &/or Lift Study to be carried out
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Approval given by Project Manager
label | RECORDS - Permit to Lift
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Survey
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - Survey receipt
checkpoint | 4 - Precast Installation (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - No Precast Components are to be installed until FHIMS-QA-6049 has been completed and signed off for that item
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Process Control Plan, Checksheets & any other associated documentation is provided
label | RECORDS - LQS-QA-6049
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Precast Installation (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial to be done by the manufacturer onsite & an OFI to be completed
label | FREQUENCY - Prior to unloading
label | INSPECTION / TEST METHOD - Visual
label | CONFORMANCE CRITERIA - No Damage
label | RECORDS - Delivery Dockets
checkpoint | 4 - Precast Installation (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that other components are installed correctly (Rubber Pad etc.) and are approval given from Designer team before precast components are lifted into their final positions
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Visual
label | CONFORMANCE CRITERIA - Pads installed correctly
label | RECORDS - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Precast Installation (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the risk control plan
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - RCP
checkpoint | 5 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - As-built documentation provided per contract requirements
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION / TEST METHOD - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6049 - ITP - Precast Concrete | itp |  |  |  |  | LQS-QA-6049 - ITP - Precast Concrete
section | Precast Concrete
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 2 - Design (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 2 - Design (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Produce Shop Drawings and Submit for approval
label | FREQUENCY - Prior to Commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Drawing Register
label | RECORDS - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Formwork Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Visual Inspection / Measure
label | CONFORMANCE CRITERIA - Consistency with Construction Drawing
label | RECORDS - FHIMS-CS-4008
checkpoint | 4 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Design Engineer Approval
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | FREQUENCY - Prior to pouring concrete
label | INSPECTION / TEST METHOD - Concrete Delivery Dockets
label | RECORDS - Concrete Delivery Dockets
checkpoint | 4 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | FREQUENCY - Prior to ordering steel
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
label | RECORDS - Detail Sheets and Mill Certificates
checkpoint | 4 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to welding or splicing
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
label | FREQUENCY - Prior to cutting or bending on site
label | INSPECTION / TEST METHOD - Document review
label | RECORDS - Mark Up As Built Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Reinforcing (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
label | FREQUENCY - Daily Visual Inspection
label | INSPECTION / TEST METHOD - Document review
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008, Photos
checkpoint | 5 - Reinforcing (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008, Photos
checkpoint | 5 - Reinforcing (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check for any cast in items and ensure they are fixed correctly
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008, Photos
checkpoint | 6 - Post-tensioning (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Review Strand stressing / extension calculations comply with Specifications
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - FHIMS-CS-4008
checkpoint | 6 - Post-tensioning (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check Strand Size and type complies with Specifications
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORDS - FHIMS-CS-4008
checkpoint | 6 - Post-tensioning (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Check Debound lengths, and compliance with strand schedule
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORDS - FHIMS-CS-4008
checkpoint | 6 - Post-tensioning (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check Actual Strand Stress/Extension with theoretical value.
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORDS - FHIMS-CS-4008
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Concreting (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORDS - FHIMS-CS-4008
checkpoint | 7 - Concreting (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken
label | FREQUENCY - Prior to concrete pour
label | INSPECTION / TEST METHOD - Test Results
label | CONFORMANCE CRITERIA - NZS 3104
label | RECORDS - FHIMS-CS-4090
checkpoint | 7 - Concreting (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish
label | FREQUENCY - At completion of pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 8 - Striking of formwork and curing of Units
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Stripping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing
label | FREQUENCY - At completion of pour
label | INSPECTION / TEST METHOD - Visual inspection
label | CONFORMANCE CRITERIA - Concrete Inspection Record
label | RECORDS - FHIMS-CS-4008
checkpoint | 9 - Beam Hog
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - To be Measured prior to site delivery. Deck slab thickness to be adjusted if required.
label | FREQUENCY - Prior to Precast Unit Delivery
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORDS - FHIMS-CS-4008
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - As-built documentation provided per contract requirements
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION / TEST METHOD - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6069 - ITP - Subgrade and Basecourse | itp |  |  |  |  | LQS-QA-6069 - ITP - Subgrade and Basecourse
section | Subgrade and Basecourse
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Set out pegs installed at required intervals to achive required crossfall.
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Survey
label | RECORDS - Photos
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Material Imported to the site & used in the construction of the pavement is checked that the material complies with the Specifications
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Grading tests for quarried aggregates
label | RECORDS - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subgrade Preparation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Carry out a Level Check on the trimmed subgrade
label | FREQUENCY - Prior to placing Subbase
label | INSPECTION / TEST METHOD - Survey
label | CONFORMANCE CRITERIA - Tolerance = -50mm +20mm
label | RECORDS - As builts
checkpoint | 5 - Subgrade Preparation (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Proof Roll - Site Engineer and Engineers Rep to undertake a Proof Roll test on the trimmed subgrade. 1 pass minimum per lane
label | FREQUENCY - Prior to placing Subbase
label | INSPECTION / TEST METHOD - Over whole area requiring construction
label | CONFORMANCE CRITERIA - Check for consistency. Areas with excessive flex to carry out additional scala testing.
label | RECORDS - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subgrade Preparation (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Scala Testing/Plateau Testing - Scala testing to 10m centres staggered. If Proof Roll Fails undertake additional Scala testing to 2m centres staggered in the area. If Scalas not sufficient, Plateau Testing to be carried out to prove compaction requirements
label | FREQUENCY - Prior to placing Subbase
label | INSPECTION / TEST METHOD - Scala worksheet, Plateau Testing
label | CONFORMANCE CRITERIA - Scala results recorded, Plateau Testing sheet
label | RECORDS - LQS-CS-4003, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subgrade Preparation (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Undercut - Pending results from proof roll and Scala, undercut areas to be marked out, excavated and constructed
label | FREQUENCY - Prior to placing Subbase
label | INSPECTION / TEST METHOD - Scala worksheet, inferred CBR
label | CONFORMANCE CRITERIA - Asbuilt & Survey to pick up undercut area.
label | RECORDS - LQS-CS-4003, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Subbase Construction (1)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Subbase compaction
label | FREQUENCY - 1 per 50m2 staggered (min 5 tests per lot)
label | INSPECTION / TEST METHOD - Visual Inspection, NDM Lab Testing
label | CONFORMANCE CRITERIA - Compaction of material is being followed within the guidelines set in the specifications. Avg. >= 95% MDD and Min. >= 92% MDD
label | RECORDS - Photos, Pavement Lab Testing Spreadsheet
checkpoint | 6 - Subbase Construction (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Carry out a Level Check on the trimmed Subbase once placed and compacted
label | FREQUENCY - 1/20m
label | INSPECTION / TEST METHOD - Measurement
label | CONFORMANCE CRITERIA - Tolerance = -25mm/+10mm
label | RECORDS - Photos, As-builts
checkpoint | 6 - Basecourse Construction (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Plateau Density Testing for Basecourse Layers
label | FREQUENCY - Trial pad prior to use
label | INSPECTION / TEST METHOD - NDM Lab Testing
label | CONFORMANCE CRITERIA - To establish roller pattern
label | RECORDS - Pavement Lab Testing Spreadsheet
checkpoint | 6 - Basecourse Construction (2)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Basecourse compaction
label | FREQUENCY - 1 per 50m2 staggered (min 5 tests per lot)
label | INSPECTION / TEST METHOD - Visual Inspection, NDM Lab Testing
label | CONFORMANCE CRITERIA - Compaction of material is being followed within the guidelines set in the specifications. Avg. >= 98% MDD and Min. >= 95% MDD
label | RECORDS - Photos, Pavement Lab Testing Spreadsheet
checkpoint | 6 - Basecourse Construction (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Carry out a Level Check on the trimmed basecourse
label | FREQUENCY - 1/20m
label | INSPECTION / TEST METHOD - Measurement
label | CONFORMANCE CRITERIA - Tolerance = -10mm/+5mm
label | RECORDS - Photos, As-builts
checkpoint | 6 - Basecourse Construction (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Benkelman Beam Testing
label | FREQUENCY - Wheel Path in each lane, every 10m staggered along alignment
label | INSPECTION / TEST METHOD - Benkelman Beam Test
label | CONFORMANCE CRITERIA - Desired result - average <1.0mm with no reading over 1.5mm
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Basecourse Construction (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Pavement Cross fall/Shape check
label | FREQUENCY - 1/10m
label | INSPECTION / TEST METHOD - Survey check & Measurement
label | CONFORMANCE CRITERIA - Crossfall, shape and surface complies with agreed design
label | RECORDS - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure correct no. of test sets performed for pavement testing as per Specifications
label | FREQUENCY - At completion of Lot
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - As-built documentation provided per contract requirements
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION / TEST METHOD - Drawings
label | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6076 - ITP - Asphalt - Surfacing | itp |  |  |  |  | LQS-QA-6076 - ITP - Asphalt - Surfacing
section | Asphalt - Surfacing
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 3 - Previous Lots Completed
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All previous pavement lots signed off
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Previous ITP must be completed
label | RECORDS -
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Determine paving run start/stop locations
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Survey
label | CONFORMANCE CRITERIA - Mark out on site
label | RECORDS - Subcontractor QA Records
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Mix Design approved
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Submission
label | CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued
label | RECORDS - Mix Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Tack Coat
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Membrane Coat to be used in between Asphalt and Granular pavament, or structures
label | FREQUENCY - Prior to placing Surfacing AC
label | INSPECTION / TEST METHOD - Lab Testing and measurements
label | CONFORMANCE CRITERIA - The application rate shall be applied to ensure a continuous film, per contract requirements
label | RECORDS - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Bond coat on Concrete Bridge decks
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Bond coat and DG Mix 10 levelling to be used in between the Concrete Bridge Decks and the Surfacing AC, if required
label | FREQUENCY - Prior to laying Surfacing AC
label | INSPECTION / TEST METHOD - Lab Testing and measurements
label | CONFORMANCE CRITERIA - Binder content and application rate
label | RECORDS - Subcontractor QA Records
checkpoint | 8 - Construction of Surfacing Asphaltic Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Site team QA Checks
label | FREQUENCY - During Construction
label | INSPECTION / TEST METHOD - Site Measurements
label | CONFORMANCE CRITERIA - Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing
label | RECORDS - Subcontractor QA Records
checkpoint | 9 - Layer checksheets
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Each shift the Pavement Layers Checksheet LQS-CS-4055 is to be filled in and approved by the Project Manager
label | FREQUENCY - At completion of each shift
label | INSPECTION / TEST METHOD - Document and result review
label | RECORDS - LQS-CS-4055
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure correct no. of test sets performed for pavement testing as per Specifications
label | FREQUENCY - At completion of Lot
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - As-builts and QA submitted per contract requirements
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION / TEST METHOD - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP
checklist | LQS-QA-6077 - ITP - Chipseal - Surfacing | itp |  |  |  |  | LQS-QA-6077 - ITP - Chipseal - Surfacing
section | Chipseal - Surfacing
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Obtain Permits
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS - Permit attached or permit number noted
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 3 - Previous Lots Completed
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All previous pavement lots signed off
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Document Review
label | CONFORMANCE CRITERIA - Previous ITP must be completed
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Determine chipsealing runs start/stop locations, extent of area to be chipsealed
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Measure, Inspect
label | CONFORMANCE CRITERIA - Mark out on site
label | RECORDS - Chipsealing Dept QA Records
checkpoint | 5 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bitumen/Emulsion Mix Design approved
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Submission
label | CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued
label | RECORDS - Mix Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Chip grade and application rates
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Chip grade and application rates determined and submitted for approval
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Submission
label | CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued
label | RECORDS - Mix Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Pavement approval to have Chipsealing commence
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Subgrade and Basecourse to be at an acceptable standard. Surface to have mosaic surface prepared for bitumen/emulsion application.
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD - Review
label | CONFORMANCE CRITERIA - Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing
label | RECORDS - Subcontractor QA Records, Pre-seal checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Chipsealing new surface
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Chipsealing team QA Checks
label | FREQUENCY - During Construction
label | INSPECTION / TEST METHOD - Site Measurements
label | CONFORMANCE CRITERIA - Confirmation of application rates, site QA documentation developed by sealing dept
label | RECORDS - Subcontractor QA Records, Photos
checkpoint | 9 - Post seal Checks
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Post sealing review the surface to make sure chip has set. Road Sweeping to be carried out after sealed surface is sound (~48 hours afer sealing)
label | FREQUENCY - Post Sealing
label | INSPECTION / TEST METHOD - Site Measurements
label | CONFORMANCE CRITERIA - Confirmation of application rates, site QA documentation developed by sealing dept
label | RECORDS - Photos
checkpoint | 10 - Linemarking
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Linemarking to be painted per design requirements
label | FREQUENCY - Post Sealing
label | INSPECTION / TEST METHOD - Site Measurements, review
label | CONFORMANCE CRITERIA - Linemarking is placed per drawings, or as agreed with Engineer
label | RECORDS - Photos
checkpoint | 11 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - As-builts and QA submitted per contract requirements
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION / TEST METHOD - Drawings
label | CONFORMANCE CRITERIA - Uploaded to CONQA
label | RECORDS - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Project Manager:
textbox | Accepted By Design Engineer:
signoff | Sign ITP