## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f64218b3-8e19-431a-b25d-20657d73fd20 | checklist | FHIMS-QA-6000-ITP-Compliance Record | itp | FHIMS-QA-6000-ITP-Compliance Record
420be76b-efb0-4d29-ad78-07d43589f0f0 | section | Compliance Record
7bfcb0fd-437b-4c24-9b94-4902316632f0 | checkpoint | 1 - Pre-construction sign-offs
58969c01-1c3b-5b56-a2ac-f2e48333a135 | note | ACTION (Hold, Monitor, Witness) - H
b2f88702-607e-57c3-b0c8-609483e6abf0 | note | DETAIL - Is there a Safe Work Method Statement for this task?
0215df5a-1194-5fc0-a568-634b91d381b4 | note | FREQUENCY - Prior to commencement
5cca4469-50f0-54c8-aaec-eca145c46d31 | note | INSPECTION - Document Review, Submission
94b55413-c852-52f7-ac80-4a8b4e2863f1 | note | CONFORMANCE CRITERIA - Relevant parties to review, Note Method statement in the Comments
2074fb97-a2d1-5a38-9eee-d556b86da24b | note | RECORDS - Sign off this task
a3fb4fb8-d133-42b3-852c-81d1db5e3865 | signoff | HOLD POINT
7d3f3778-082f-4443-94fd-2eff73b4bdfc | checkpoint | 2 - Design
13e6e83e-2892-5583-9ffc-3a73479e0cc9 | note | ACTION (Hold, Monitor, Witness) - H
57c325a2-c551-59f0-8bdc-edec6cb082ca | note | DETAIL - Review relevent design / task characteristics and identify hold points
0a1adbd9-2f1d-5dcd-8e6a-33481cdf72dd | note | FREQUENCY - Prior to commencement
b3686d6c-e59b-5dce-8588-d746e2b530f0 | note | INSPECTION - Document Review
ca1bd5f6-db99-5888-89e0-0499bf464e1d | note | CONFORMANCE CRITERIA - All design requirements are met
0fa08d36-ecd3-554a-be3b-08231179dacc | note | RECORDS - Sign off this task
7b66efba-41ae-4711-94b9-eefd29c363dc | signoff | HOLD POINT
9a5ccd61-8b59-4669-9fbe-5d468df18aa9 | checkpoint | 2.1 - Design
b89de0bc-7eaf-52b0-9602-fbbe50ad9ccb | note | ACTION (Hold, Monitor, Witness) - H
f388d12b-f7b2-5fcf-a75c-69146e259dc9 | note | DETAIL - Is a temporary works design required for this task?
8d9b89c4-3cb9-5914-8464-6b90bce79d96 | note | FREQUENCY - Prior to commencement
8aae3034-75d6-5663-9336-c2bc653da87c | note | INSPECTION - Document Review, Submission
ebcf35cd-2eb9-5e98-8f93-fb5424c6c7d5 | note | CONFORMANCE CRITERIA - Temporary Works design completed and attached
2c0f5f73-dd33-5595-bce7-0841ba34d3a3 | note | RECORDS - TW design, Sign off this task
08f077f6-fcdf-4be3-a8c7-01ed6884b063 | signoff | HOLD POINT
20dd9c48-0ff7-4a55-8223-d9ee34e572f8 | checkpoint | 3 - Technical Reports
9b02cf85-b251-5d54-9144-daab8bc79c9e | note | ACTION (Hold, Monitor, Witness) - H
64d055c3-d72c-5b89-8eb4-cc45d26e5117 | note | DETAIL - If relevant attach technical reports
b0234137-8090-58fb-a4f4-14188d7bfbbf | note | FREQUENCY - Prior to commencement
a9f22b85-31fc-5b37-800d-b55439bf24ec | note | INSPECTION - Document Review
72dfc47c-9885-577c-a2cd-63e8c6c15810 | note | CONFORMANCE CRITERIA - All related reports attached
1bc97107-a845-5996-bfa0-59093075b4da | note | RECORDS - Sign off this task
c3339843-2102-4ca9-a9aa-f820c38693b3 | signoff | HOLD POINT
15c41743-799b-4f19-a921-eb0443cf6cb7 | checkpoint | 4 - Materials
e8757246-86b8-583f-96f0-a9f279af06fb | note | ACTION (Hold, Monitor, Witness) - W
4641949a-127c-53ea-b148-bbaa2242d972 | note | DETAIL - If required provide required laboratory testing reports, material designs and attach i.e. grading curves, concrete design, steel certs etc.
d823be53-a57d-5f03-8e42-ee57b969a02d | note | FREQUENCY - Prior to commencement
6fb7a455-1bc8-57a6-92ea-45969ead744f | note | INSPECTION - Document Review, submission
7bb32483-195f-5f81-ae8a-ff5bd48b6e59 | note | CONFORMANCE CRITERIA - All related reports are attached
ec8a33cc-69e3-5177-96f0-66c70e0cf5f8 | note | RECORDS - Laboratory test results, Sign off this task
c7f29900-a877-45cd-b68b-5ec02a12052e | checkpoint | 5 - Field Compliance
b8614fa6-2975-5e42-9f69-adbeccee4c76 | note | ACTION (Hold, Monitor, Witness) - W
2afd2df8-2aaa-5e14-af6c-5668660d5ffd | note | DETAIL - Complete any field testing and Checksheets required by permanent design or temporary works design
f5279319-5966-5bf0-acb3-10a4e152709f | note | FREQUENCY - During construction
7044ca1c-5e00-5913-9c42-fc6990718b28 | note | INSPECTION - Testing
96abd539-af0b-5ef4-98b1-94a8a35b2498 | note | CONFORMANCE CRITERIA - All related reports are attached
c01d9e8c-31dc-5788-8309-14ef0813f68d | note | RECORDS - Field Test, Sign off this task
03b6ae93-42db-418a-9c69-1b47a189ba73 | checkpoint | 6 - Photo Records
b56400db-b04b-55e2-a538-c0542f30bf41 | note | ACTION (Hold, Monitor, Witness) - H
40c2e45f-6fcd-50d3-bb59-c11429399610 | note | DETAIL - Attach photo records
9f1877da-89ee-5f2d-9989-e5aed765b203 | note | FREQUENCY - As completed
30c56fe8-c7b5-5e9d-a5c3-69e461e122b0 | note | INSPECTION - Document Review
beb0cc88-3ed7-59c3-bf06-d1644d8949e8 | note | CONFORMANCE CRITERIA - All related photos are attached
757c56ad-1fee-582a-86ae-77b4c137d2d8 | note | RECORDS - Photo records, Sign off this task
14488912-2f9d-43f1-878d-3f4c4434dca7 | signoff | HOLD POINT
a317194a-43ac-47ab-989a-92dd85683ac9 | checkpoint | Final Inspection
f467018f-5b0c-5ded-b2f2-95e650941bbb | textbox | QA Compiled By:
633f6133-aab6-5863-ad3b-67156e4d4263 | textbox | QA checked By Discipline Manager:
1095bc04-9f76-58d7-80a6-8d573cf45ad0 | textbox | QA checked By Quality Manager:
de00997d-9cd4-54a2-94ab-c399610ea3e4 | textbox | Accepted By Design Engineer:
31fbf1dc-0f6d-5467-87e8-3c72a8896281 | date | Date:
cf1058b2-a7e9-4b8c-b741-f3dfdd454f04 | signoff | Sign ITP
aa63539b-3ff1-4e75-84af-92a5420a7148 | checklist | FHIMS-QA-6006-ITP-Insitu Concrete | itp | FHIMS-QA-6006-ITP-Insitu Concrete
99b205f2-1d4f-4390-bafc-4c65d6f0ed6f | section | Insitu Concrete
e77d864c-29fb-4ca0-a68a-10f5ffc4d483 | checkpoint | 1 - Permits
aa743995-73a0-55b4-9292-b108bb39297d | note | ACTION (Hold, Monitor, Witness) - H
e669cd4c-36bc-5e4a-84be-027d4565591a | note | DETAIL - Obtain Permits
d7eadb8f-6180-5fdc-b663-25ace45e0dea | note | FREQUENCY - As required
361bdaea-1dd9-502a-b093-2723e6fce352 | note | INSPECTION - Document Review
31161144-c967-55cd-b7a1-45a35b4f5aa1 | note | CONFORMANCE CRITERIA - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
659f857d-22af-5384-a69d-87fdf934e985 | note | RECORDS - Permit attached or permit number noted
70261763-5ccb-4972-b896-1f6198484732 | signoff | HOLD POINT
61b34c43-533e-4034-ae6e-26b16ca2fa98 | checkpoint | 3 - Design
f34761cb-15ce-5420-a3d1-c4129dd96e7c | note | ACTION (Hold, Monitor, Witness) - H
62663995-afb5-51cd-8fe6-9c84f5e8e803 | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
b2cd99a2-74c9-5c12-a940-614ab1d3a54c | note | FREQUENCY - Prior to commencement
56b14a01-c6f5-55d7-8c36-58b3bb73ddfa | note | INSPECTION - Document Review
5855b31f-7ddd-5a59-84c6-674cd3eb122a | note | RECORDS - Check Drawing Register
8db84b20-888d-4f8f-b411-1870943a0b96 | signoff | HOLD POINT
198e3140-8905-4d87-80e2-b1e4d94f058d | checkpoint | 4 - Survey Setout
255878b4-77e0-5ff1-b7fa-8560c2a044d4 | note | ACTION (Hold, Monitor, Witness) - H
d235a9e1-c423-506c-8da4-56f5952f512f | note | DETAIL - Set out design features as per Issued For Construction drawings (Cast in items, Ducting, Penetrations)
7a35acd3-5dc0-55f8-88f8-d7237364b368 | note | FREQUENCY - Prior to commencement
20edd304-1dbd-59a0-8d05-1b5dcba82e83 | note | INSPECTION - Survey
e0e1f5b2-eccc-553a-8a73-39a554a31ea6 | note | CONFORMANCE CRITERIA - Consistency with Construction Drawing
7e62a6d0-f00a-5a8a-97d6-274f80465422 | note | RECORDS - Survey receipt
d9a6d6b8-5399-4c84-9822-05f6d8bb4c43 | signoff | HOLD POINT
80b1dac1-61f4-4e6a-b283-ae7db68af7cc | checkpoint | 5 - Material Compliance (1)
3073c4ec-a86e-5347-8694-3e4cf45fca61 | note | ACTION (Hold, Monitor, Witness) - H
7149f722-7a47-5bf2-a4d7-1ce997745b03 | note | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before
5f3182f1-7233-51f6-8cd6-e62e06ead822 | note | FREQUENCY - Prior to commencement
06444004-dbe6-5fae-902c-359337fa3541 | note | INSPECTION - Document review
00abaeb4-cf00-559c-a7db-8adfda8af768 | note | CONFORMANCE CRITERIA - Engineer approval
73a1774d-9b73-57da-ae69-68ceb632999d | note | RECORDS - Design Engineer Approval
c29dd671-ae89-4f0f-bed7-326b42b0c34c | signoff | HOLD POINT
d2bb2e07-ad88-4268-9d10-c07346335786 | checkpoint | 5 - Material Compliance (2)
d072174f-ec52-5b26-8629-f2e3cfbac6b8 | note | ACTION (Hold, Monitor, Witness) - H
df664bc8-7cee-5734-b924-1e5a28c63adc | note | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
44fc7c91-c6ba-5687-a8a9-ba4305afd990 | note | FREQUENCY - Prior to pouring concrete
46e3fb19-974c-56f5-9385-9d57f50eca6f | note | INSPECTION - Concrete Delivery Dockets
396c083b-b80b-5d69-9b8f-b85edda817bc | note | RECORDS - Concrete Delivery Dockets
5ee9bea5-8610-4f1e-80c2-c15da3f56f60 | signoff | HOLD POINT
dbfb4eec-5f8e-435d-8aa8-2925317a76d7 | checkpoint | 5 - Material Compliance (3)
833f2384-7bde-58d2-905d-751a391fb61c | note | ACTION (Hold, Monitor, Witness) - H
333b4b15-d9ac-59d2-b453-fd20fa21dd19 | note | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
c623c99c-6da7-59e6-a8f5-763ce6d58e80 | note | FREQUENCY - Prior to ordering steel
0fd0fd6b-f4ee-5ec0-8c3c-df8c9454f7cc | note | INSPECTION - Document review
bd84b5e1-1a6d-57f3-a66d-691082274084 | note | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
412e4306-54e3-56ee-8f6e-e2fa0c354ba7 | note | RECORDS - Detail Sheets and Mill Certificates
a6b9ff1b-7f99-4a43-a6cf-fb2596570abc | signoff | HOLD POINT
5373d2fd-da6a-491f-ada3-2eb2c2083971 | checkpoint | 5 - Material Compliance (4)
f508b9de-3a97-5b16-8821-9c5887425976 | note | ACTION (Hold, Monitor, Witness) - H
9f28ed5d-b41b-5e27-b546-b30763b3e1ab | note | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
1e4d9d7c-5f62-591c-a9f3-c0ca299c937d | note | FREQUENCY - Prior to welding or splicing
1ac55040-a67e-5d24-abb9-1d9369c7b056 | note | INSPECTION - Document review
508580f3-3387-574c-aee0-428d54aab3d6 | note | RECORDS - Mark Up As Built Drawings
2cf6cf7d-9e52-4cda-8b62-83c19fef2240 | signoff | HOLD POINT
99c72975-cc9f-4406-80fc-cd8c5a7019de | checkpoint | 5 - Material Compliance (5)
be725327-567d-581c-a76f-3cad667ee6f0 | note | ACTION (Hold, Monitor, Witness) - H
1ac3e933-fdce-58e4-9156-e7c214c90413 | note | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
ff88443c-9d89-5140-ad71-5f33aeafe815 | note | FREQUENCY - Prior to cutting or bending on site
f9760e2c-9078-538e-acc5-dd59368c1a12 | note | INSPECTION - Document review
b187f23d-5701-5f4d-b282-7f3ca42c55fc | note | RECORDS - Mark Up As Built Drawings
b8598a8d-f2d1-4532-afb3-7e63c9ef4d84 | signoff | HOLD POINT
40c8ee49-a1e2-4cb7-947e-da38183e8f66 | checkpoint | 6 - Foundation Acceptance by Engineer's Rep
16f09fbc-21c2-5db2-8afd-fecdf94251c5 | note | ACTION (Hold, Monitor, Witness) - H
24c70cd4-8df2-5ec1-84fd-021cf0e9fedb | note | DETAIL - Approval given by engineer's Rep and Signed off Subgrade Approval Checksheet
10ea3fe1-8746-5a81-95d8-0f3ed5170d04 | note | FREQUENCY - Prior to commencement
66986778-ff57-5d6e-a9c2-17cc00b67a77 | note | INSPECTION - Inspection by Engineer
b944e20e-93da-5de5-b45b-82219acd5579 | note | CONFORMANCE CRITERIA - Inspection and Acceptance of Structure Foundations
65a2df1c-2fd0-5ada-92a8-56ae77d41c29 | note | RECORDS - FHIMS - CS-4100
534358de-7fea-4308-9f08-60b6f0546c4d | signoff | HOLD POINT
c12f364f-5cfa-46dc-a858-cfa78fa1435d | checkpoint | 7 - Blinding Concrete
74e8d9e8-6da1-5fbc-825c-f623e2e8f677 | note | ACTION (Hold, Monitor, Witness) - H
4e979b91-732c-5eb7-a059-bb4b70bc1538 | note | DETAIL - Once blinding concrete layer has been completed the Engineer's Rep to inspect and give approval for the rest of the works to commence
b208ec38-ad40-524b-a2fe-4679890593b0 | note | FREQUENCY - Prior to commencement
20b44627-cf29-585a-acf8-dd7e8b457b6c | note | INSPECTION - Inspection by Engineer
a118c685-0c42-5b01-8e24-4cf9fd5fd819 | note | CONFORMANCE CRITERIA - Engineer approval
c4986d37-2a0b-5f36-b49e-67fa48e11bb1 | note | RECORDS - Sign off this document
83ca0d08-e4f2-490f-a865-579518d377ed | signoff | HOLD POINT
a5009b79-ddb7-4ae6-846e-67509b31c861 | checkpoint | 8 - Temporary Works (Formwork) (1)
630eca98-d7d6-5486-a4ae-d7e555244c14 | note | ACTION (Hold, Monitor, Witness) - W
5e9d068e-988a-5447-a824-52b5eb2c293e | note | DETAIL - Formwork to be constructed to design and set to correct line and level as set out by the surveyor
a5da74c8-b3c2-5390-9aae-db143ba2ccb9 | note | FREQUENCY - Daily Visual Inspection
bb6edb28-09f7-5a2b-8e38-176757c256af | note | INSPECTION - Visual inspection
a6ffa27e-c278-5bec-9e9f-f0122e4b3a5c | note | CONFORMANCE CRITERIA - Concrete Inspection Record
ecf75ee2-5775-572b-a221-43c5d3ea12f8 | note | RECORDS - FHIMS-CS-4008
553d4a6b-2f5b-42d7-a778-25aecb6440d3 | checkpoint | 8 - Temporary Works (Formwork) (2)
1625e849-aca6-5731-800f-2918b4eacfa0 | note | ACTION (Hold, Monitor, Witness) - H
e55f81b7-5cfe-5fbf-8f11-32562c4c7350 | note | DETAIL - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
b888eeb0-8e37-554f-9fec-e9a16966291a | note | FREQUENCY - Prior to concrete pour
d37deb66-58e4-5b7b-8a53-e774bb3bf0ec | note | INSPECTION - Visual inspection
2d76a3d6-9445-5dfc-9ab7-4ed110f74fba | note | CONFORMANCE CRITERIA - Concrete Inspection Record
e3540c50-5df2-525d-b102-073761d6b0a6 | note | RECORDS - FHIMS-CS-4008
23874385-e036-4635-b2b3-6885cf4f13ec | signoff | HOLD POINT
62989523-9348-4658-b85e-afe21830158e | checkpoint | 9 - Reinforcing (1)
de47361e-4541-5567-a79d-2fbe6b249fe4 | note | ACTION (Hold, Monitor, Witness) - W
f3d80b01-fd04-5415-a22b-d3e851d91739 | note | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
ef088ab2-c374-5c8c-8c9c-d5b6b1c3ebd0 | note | FREQUENCY - Daily Visual Inspection
b8eccccd-6414-5074-8061-731134f43a3f | note | INSPECTION - Document review
98765446-95ae-5e04-bb78-7d9ef06d5acb | note | CONFORMANCE CRITERIA - Concrete Inspection Record
7761e867-a99a-51c0-9dc9-618cce6922a5 | note | RECORDS - FHIMS-CS-4008
df5dca2e-c270-469e-9ea1-f70343fe1846 | checkpoint | 9 - Reinforcing (2)
bc1606d6-8ef6-5356-acbc-7537f814faa4 | note | ACTION (Hold, Monitor, Witness) - H
fc358a99-e9a6-50c5-aed3-f17bbf2806a4 | note | DETAIL - Check for any cast in items and ensure they are fixed correctly
e47da025-5549-578c-9c74-670d1350a7b6 | note | FREQUENCY - Prior to concrete pour
50a6ff7c-feca-5369-9d61-893bce400639 | note | INSPECTION - Visual inspection
0873f4b1-d7c9-544a-8811-ddd4db408050 | note | CONFORMANCE CRITERIA - Concrete Inspection Record
f454d763-c132-5800-a66f-d3b8e89028e1 | note | RECORDS - FHIMS-CS-4008
dadeec66-cd30-4a95-863c-4f923f4a8261 | signoff | HOLD POINT
229fd826-2b38-4fa2-8737-44617ca58ee3 | checkpoint | 10 - Concrete Pumping Operations
ebda07f0-63d5-5e25-b752-7f54a1435fe5 | note | ACTION (Hold, Monitor, Witness) - W
55b493b5-33c2-54d6-9cfe-cfedeb17c5d9 | note | DETAIL - Ensure the Permit to Concrete Pump Checksheet has been completed before concrete pumping commences
a000167c-7832-593a-8c3f-9495d092b2fd | note | FREQUENCY - Prior to commencement
6de1716b-09af-510e-8f64-4cd946532ab7 | note | INSPECTION - Document review
6fbd00cc-af7d-593e-bc94-390ab9697cca | note | CONFORMANCE CRITERIA - Permit to Pump Checkseet
04d1b4f6-32c8-5b20-ab4a-bd570ccdce7f | note | RECORDS - FHIMS-CS-4029
48a31145-ee47-4f63-91de-5ce1439511b2 | checkpoint | 11 - Concreting (1)
8f3d74a5-afe0-5f18-aba6-0cc7d9eafca8 | note | ACTION (Hold, Monitor, Witness) - H
bd3cb031-ef6b-5dd6-8e68-988e5c002d5f | note | DETAIL - The MSQA Engineer shall be advised at least 48 working hours before the proposed time for concreting that a pre-pour inspection is required
e26eea00-83e9-5336-ac12-985eb57c4983 | note | FREQUENCY - Prior to concrete pour
971cae17-c4fb-545b-87ad-e913d627d355 | note | INSPECTION - Visual inspection
0d8faf16-5e21-5e46-ab42-2e53690d32cf | note | RECORDS - FHIMS-CS-4008
abf86eef-9622-4f30-9508-43f890cd5223 | signoff | HOLD POINT
af8a1187-3c5c-4213-be06-6dbe66b607d4 | checkpoint | 11 - Concreting (2)
d9dba178-fab4-5551-a166-d1dad95d533c | note | ACTION (Hold, Monitor, Witness) - H
296a0f9f-87d2-526a-a930-36e3d4e3f5e9 | note | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken i.e. Slump test
25613e66-d615-5264-9845-d177e35ca955 | note | FREQUENCY - Prior to concrete pour
4828e396-e173-5971-84c4-df36a888dea8 | note | INSPECTION - Test Results
964af23a-0b9e-5a27-9f81-556cdef69002 | note | CONFORMANCE CRITERIA - NZS 3112, Concrete Inspection Record
b83793a7-cc68-5685-a8ed-a907cd072d60 | note | RECORDS - FHIMS-CS-4090
b02e3952-bf18-4e3b-8489-4846ee3cbd4e | signoff | HOLD POINT
877f8360-49da-4710-8ed0-f0a91b04aa55 | checkpoint | 11 - Concreting (3)
e12cfcaf-b9cd-5d88-9f8d-5664eb247d5c | note | ACTION (Hold, Monitor, Witness) - H
82e26be7-e43f-5fc3-b351-660e1576b179 | note | DETAIL - Concrete surface finishes shall be
05e87bd1-ff43-5c9a-9da4-ff38e1586040 | note | ○ Concealed Form Surfaces: F1
5a719c5e-2d5b-52ba-a88c-0f92e2387715 | note | ○ Exposed Formed Surfaces: F4
ff27a1da-32d9-5928-889c-610f9473f97f | note | ○ Exposed Uniformed Surfaces: U2
b6ebe194-220b-5507-a768-ebee3950a8db | note | ○ Concealed Uniformed Surfaces: U1
00015d41-eacd-5f43-b4b8-3a805e282882 | note | FREQUENCY - At completion of pour
ebdd7fc8-f99c-5f15-9f63-71838fd13b04 | note | INSPECTION - Visual inspection
0d196e28-a458-53d5-a850-1196e734b05a | note | CONFORMANCE CRITERIA - Concrete Inspection Record
41fc909c-253b-5699-9d08-4590cb4eaf18 | note | RECORDS - FHIMS-CS-4008
6ea8f557-0f7a-4815-98fe-31a58865db25 | signoff | HOLD POINT
060963bf-5a6d-4be8-b587-2c5c9de0eae1 | checkpoint | 12 - Remove formwork
219899aa-b32a-5c2f-bfe2-4853ccc2732d | note | ACTION (Hold, Monitor, Witness) - W
c119b790-7242-550f-af20-96ef31600422 | note | DETAIL - Remove formwork as per the approved work method
f0678877-e4a0-5609-a692-6d29572555fc | note | FREQUENCY - At completion of pour
f81832c5-4532-5563-97f1-909b8aa82728 | note | INSPECTION - Visual inspection
75ec1a6b-de6f-51ab-8567-1d50d7fed404 | note | CONFORMANCE CRITERIA - Concrete Inspection Record
f711c5fa-c286-5002-baa6-1e6b50255ad9 | note | RECORDS - FHIMS-CS-4008
774bb27a-31f5-4428-b394-4076def45144 | checkpoint | 13 - As-builts
7a4b166e-8448-56cd-ad29-79801d438ad3 | note | ACTION (Hold, Monitor, Witness) - H
7ab14664-ed4d-5da9-a323-019df4c3c594 | note | DETAIL - Red pen mark up drawings to be included in QA file
f04af3d6-5871-5e9f-95eb-2b4076870f8e | note | FREQUENCY - At the completion of the Lot of work
ab24e31f-c859-59de-a75a-eddd6661cbc2 | note | INSPECTION - Drawings
f768cb44-3da3-5c7c-9da6-ea15ab80e82f | note | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
36da77b1-0ca1-5bc2-9194-b5c627ddc5ec | note | RECORDS - Asbuilt Drawing
5a346a7e-a4d0-42ef-8750-f84fc7ba08d0 | signoff | HOLD POINT
3792379e-04d8-4473-888e-347184b37f9d | checkpoint | 14 - Lot Number QA File
2ac6278e-8b36-560b-8a72-c25a4c7b9906 | note | ACTION (Hold, Monitor, Witness) - W
cf5064f9-58b0-5086-af1b-ae519b535848 | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
ccd1231c-e26a-5d13-974f-b49f85621067 | note | FREQUENCY - At completion of Lot
49ed2f14-c684-52e8-ab98-8c25b80e6e94 | note | INSPECTION - Document Review
3a684ee5-1281-5edf-9f2d-ac592072d649 | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
d06ec8ac-8e96-58f6-81ec-4f3d00e0f6c8 | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
28809342-bf46-41bf-b919-6782b8bbf05f | checkpoint | Final Inspection
abc48224-d7fe-5f32-b9a2-1f69c927e443 | textbox | QA Compiled By:
6abcc04f-3d02-5b95-81c9-13df6a39ad09 | textbox | QA checked By Discipline Manager:
cf5e0b65-61b1-5ae4-b7d3-a91162275d94 | textbox | QA checked By Quality Manager:
54e843d6-558f-5ebe-aeed-505b0477f660 | textbox | Accepted By Design Engineer:
b9f11d8d-b495-5e4a-bfe7-f3fb66cabf32 | date | Date:
17624418-8fda-4921-a07c-4ef64881860b | signoff | Sign ITP
6b729c10-603f-4095-a292-22fd4d00a2db | checklist | FHIMS-QA-6007-ITP-Drainage Installation | itp | FHIMS-QA-6007-ITP-Drainage Installation
c705db1c-1973-4c96-835e-5c48e21c237c | section | Drainage Installation
373a8d3b-6b0f-4acf-9d8a-f143c82b14e8 | checkpoint | 1 - Permits
e65b85a6-5f2c-53f3-b262-13d13127e34d | note | ACTION (Hold, Monitor, Witness) - H
59f5fd10-3518-5418-addf-cbc06f28f717 | note | DETAIL - Obtain Permits
9427aa3c-bd72-52ac-9385-6afb1bd56022 | note | FREQUENCY - As required
c614cd5c-dbef-5385-bac9-59f136d51efb | note | INSPECTION - Document Review
fc099885-892d-59ea-a442-54d0b1de11f4 | note | CONFORMANCE CRITERIA - Digging & Excavation Permit, (incl. marking out & potholing existing services), Confined Space Permit if rquired. Notify Worksafe NZ if required.
3661a908-bb3f-5dcc-bea4-5cb7dbddc69c | note | RECORDS - Permit attached or permit number noted
f5c7632f-f33d-4c2c-ab7a-cd4123b7b1a6 | signoff | HOLD POINT
cfda749b-98ab-458b-8539-04607babe979 | checkpoint | 2 - Pre-construction sign offs
e1600079-db7e-5555-bff0-988ad2a98552 | note | ACTION (Hold, Monitor, Witness) - H
cffabceb-a504-5ab6-9ef1-e44e7afcb52a | note | DETAIL - Ensure that Sub-Contract and Supplier Agreements are signed, TMP is approved all Sub-Contractors and Suppliers are inducted to site
800abca1-d116-52e5-93a1-a26ffb930c4c | note | FREQUENCY - Prior to commencement
00d0bf10-77ae-5139-ae27-a5fcedb08c38 | note | INSPECTION - Document Review
4c193e80-53fb-5a28-accd-27b7451d1674 | note | CONFORMANCE CRITERIA - Signed Subcontract and Supplier Agreements, TMP approved
62010a7c-0bcc-5bac-a33e-35e0a5303949 | note | RECORDS - Subbie/Supplier Agreements, Approved TMP, Induction register
bc9c3e57-53e2-4271-b71f-bf1e54ec8438 | signoff | HOLD POINT
72e16a99-5827-47c0-9475-c025169da4f9 | checkpoint | 3 - Design
3936ee14-03da-5f51-a8b2-de2f04e0612d | note | ACTION (Hold, Monitor, Witness) - H
f417cdce-cc77-5338-a3b8-12fc046669bc | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
ca7590a8-974a-5509-acf9-d692e46b488f | note | FREQUENCY - Prior to commencement
261617f1-7b49-5b5e-8678-5a78cbc1baf6 | note | INSPECTION - Document Review
25ccc628-f54e-5aea-8058-6a31aabf091c | note | RECORDS - Check Drawing Register
6f7c5385-d487-4694-a740-1539f96d16ff | signoff | HOLD POINT
6a6ac1f7-5947-4375-b302-c5e99af3458d | checkpoint | 4 - Survey Setout
60ddec4d-a6a0-5fbb-84f7-a1b1738dd7d3 | note | ACTION (Hold, Monitor, Witness) - H
27323ca3-cf17-52a5-bdba-951165e2b076 | note | DETAIL - Setout inlet & outlet points with inverts as required by Contractor to construct to design
28ce58a7-e941-5b95-8b37-350e92a187ce | note | FREQUENCY - Prior to commencement
36d03ece-9884-56bd-b0ee-066587a898ed | note | INSPECTION - Survey
2e2f09b4-32a3-562a-ae4e-2e0e01d2b798 | note | RECORDS - Survey receipt
38134743-f543-48d2-b799-9fcde0a5abad | signoff | HOLD POINT
c2611f37-1d8b-4199-943a-096090dcb24f | checkpoint | 5 - Locate existing services by hand digging or hydrovac
263aaa91-b7db-5ab9-8e9f-dbc6fb9be061 | note | ACTION (Hold, Monitor, Witness) - H
d2280353-4ee9-509e-8941-a4466e45e9cd | note | DETAIL - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydrovac
4685e4f4-a419-5d8d-9dd8-6fc54fe56190 | note | FREQUENCY - Prior to commencement
0b0ad088-94ab-5f64-a3f1-cc61997b3c0f | note | INSPECTION - Potholing
cc71a49b-6d1c-5821-96a7-a3e96c9fa837 | note | CONFORMANCE CRITERIA - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
97ec08b2-dcf5-50c5-85ad-4506803649c7 | note | RECORDS - As-built Drawings Doc. Review
b0d46617-436d-48a7-be2a-068574707df6 | signoff | HOLD POINT
1f7f8eb0-c112-47b2-bb36-cd157dda0636 | checkpoint | 6 - Trenching and Excavation (1)
c2249859-583a-5d2d-aad8-3d3a54b04bdf | note | ACTION (Hold, Monitor, Witness) - W
15224dd5-d128-50c6-9cc2-8d8e508d0347 | note | DETAIL - Inspect trench profile and ensure it is correct to lines and levels to design
15dfecfd-6e4a-5c1b-8b03-32a37e7815f8 | note | FREQUENCY - Daily
3c86c0c2-0074-533d-81b3-f23993c4fce4 | note | INSPECTION - Visual/Inspection
5c79710a-beba-5fb3-ab62-8d418ac83982 | note | CONFORMANCE CRITERIA - Line and level is correct
6cebd77e-900b-5d9e-9459-5785a5a7425e | note | RECORDS - FHIMS-CS-4025
d7fefdcd-7dca-4b43-83a2-43667c37aa00 | checkpoint | 6 - Trenching and Excavation (2)
b1b43f07-bdf4-5c8c-aca8-49f21f2d28ca | note | ACTION (Hold, Monitor, Witness) - W
edf51def-2d67-5f6f-a81b-0b405e13f02f | note | DETAIL - Ensure trench width is sufficient to provide enough space on either side of the pipe for compaction
6010244a-0546-52de-bd1a-94de8f2ab46a | note | FREQUENCY - Daily
8d712bab-5156-592d-b42b-f557131e8c85 | note | INSPECTION - Visual/Inspection
9b875936-16a1-594a-a821-04eef7a58b05 | note | CONFORMANCE CRITERIA - 300mm either side of the pipe
456ac334-778a-56b7-b9fc-f15c2fef9fb9 | note | RECORDS - FHIMS-CS-4025
a754d614-d671-43a0-9635-d7077d761e75 | checkpoint | 7 - Foundation Compliance (1)
538cb7c2-c11a-53e7-be55-ea81978b9217 | note | ACTION (Hold, Monitor, Witness) - H
e839186b-90b4-5257-b7bc-945f7cb39b6e | note | DETAIL - Test formation level on completion of excavation to check if undercut required
cb600390-8ab2-5f08-aa9f-46f0d106dc0f | note | FREQUENCY - One test per 15m linear metres
9a5ba84b-fa3b-58e2-a704-d10aa1693043 | note | INSPECTION - Scala Penetrometer, Visual Inspection by designer
50854033-518b-5407-8d61-6f4876b7451e | note | CONFORMANCE CRITERIA - If CBR is less than 2.5 or 50kPa undercut may be required. Seek engineer guidance for undercut depth
cb01d8de-044b-54d0-be8f-21d5c2a1e2c4 | note | RECORDS - FHIMS-LA-4003, FHIMS-CS-4025
e829d3e8-c6ce-4c14-87be-337924184f3c | signoff | HOLD POINT
405c42d1-734d-4f44-bc51-908842dd9c80 | checkpoint | 7 - Foundation Compliance (2)
0ce03335-b9c1-5db0-8a3b-72329231483f | note | ACTION (Hold, Monitor, Witness) - H
851d6b51-3197-557a-8196-3ddd6340ef5c | note | DETAIL - If water is in the trench backfill with Drainage 40/20 material ensuring Bidium cloth is pinned to the bottom of the trench. 40/20 material to extend to the mid point on the pipe or to the water table (whichever is highest).
6203cf4c-29e4-5b03-953b-c215aad75d54 | note | FREQUENCY - Visual
0c62c2d2-b05f-574f-aa53-3f2949fde3ac | note | INSPECTION - Compaction
34192064-64f3-5273-8bc5-bbddf2337cf0 | note | CONFORMANCE CRITERIA - Ensure material is whacked every 150mm lift
f2d2f8a6-6508-5969-9ca3-e41ff0562791 | note | RECORDS - FHIMS-CS-4025
782cd305-778c-41ac-a6e9-e6b74a6cd54a | signoff | HOLD POINT
f352079a-0510-4092-bdb5-1e21f9d84842 | checkpoint | 8 - Undercut BackFill Material Compliance Testing (1)
b307ec9d-ab24-5868-8fd6-1801aa2b44d2 | note | ACTION (Hold, Monitor, Witness) - H
6ac32130-3c9a-5380-b8b5-3bbbe9742dfa | note | DETAIL - Material to meet specifications dependant on material type selected
d12dba5d-fcf7-5e41-8d88-e97b14fe82ce | note | FREQUENCY - Each material used
ffd1e33a-e05c-56a2-8309-9d40d4926922 | note | INSPECTION - Document Review
5a327717-f936-577d-b2e7-efb4a23f58a9 | note | CONFORMANCE CRITERIA - Compliance with requirements from Specifications
52cde8a0-8ea4-52ac-a81b-d11ce7ee5933 | note | RECORDS - Lab Test Report
06fbde30-15aa-4fd5-b672-bae7b045f27b | signoff | HOLD POINT
4abe8a1a-72b9-47da-80b2-a0f6a8ade66c | checkpoint | 8 - Undercut BackFill Material Compliance Testing (2)
b0c4a1dc-3296-5312-a406-7616a53d8bbf | note | ACTION (Hold, Monitor, Witness) - W
1d35ce63-1e1e-5cb9-a793-b28d05e36b0a | note | DETAIL - Geotextile or Geogrid that is used in the undercut is to be documented on FHIMS-CS-4025
615c2de9-b519-5fc6-84f2-3c48f1d03cce | note | FREQUENCY - Each material used
6fbb646b-507a-587f-8e55-e30cd1b9d23a | note | INSPECTION - Certification
69b9c98e-8fe0-554b-9c6f-b4d264e14ef2 | note | RECORDS - FHIMS-CS-4025
1f04c408-3ecc-46bc-8cf4-c79ddfe1ff24 | checkpoint | 8 - Undercut BackFill Material Compliance Testing (3)
8d3aa32b-2f78-56fb-bee2-6e384d621a4f | note | ACTION (Hold, Monitor, Witness) - H
30b985b0-b6e2-5889-ab49-a0cf83e1729e | note | DETAIL - Backfill Construction Material
1ccaf397-fd25-5dea-8f01-a15819cad007 | note | FREQUENCY - 1 test per 15m
1033c770-00dd-584e-ad0d-9103957582f8 | note | INSPECTION - Lab Testing
fc41edc8-89aa-5a6d-837a-d65c70fdab2e | note | RECORDS - FHIMS-CS-4025
7e2d14f5-57bb-4fcc-861f-2c8a11ec486a | signoff | HOLD POINT
97228d69-14a5-4490-a2c8-ac3f5e085070 | checkpoint | 9 - Pipe Bedding Material Compliance (1)
2cb9d95c-000a-55a4-9c9d-f96e7b5365eb | note | ACTION (Hold, Monitor, Witness) - H
9f8395a5-66d8-5959-82ce-6b270da85a21 | note | DETAIL - Material to meet specifications dependant on material type selected
b3fb2906-42fd-57af-b381-3ebe5583d212 | note | FREQUENCY - Each material used
3f9d59a5-1311-5bfb-98d6-3584ae6da0fa | note | INSPECTION - Document Review
69f80545-4266-514c-8918-9c76ca35340e | note | CONFORMANCE CRITERIA - Compliance with requirements from Specifications
fffa56ca-b232-5f9d-a23e-98827e730751 | note | RECORDS - Lab Test Report
eb85ee2d-d664-4e1b-ad62-354d59a5e365 | signoff | HOLD POINT
fb870a5e-715f-4168-8202-cf51754e7c04 | checkpoint | 9 - Pipe Bedding Material Compliance (2)
eb470971-53f0-5ac5-8a4b-9d37791a802e | note | ACTION (Hold, Monitor, Witness) - H
9e05bc2e-5acc-5424-b74e-fb671fc20769 | note | DETAIL - Backfill Construction Material
32634346-e72a-5fb0-85a0-9d9e7ce7ebe7 | note | FREQUENCY - 1 test per 15m
d8688a8d-22fa-589e-bd68-fea60f9d3c82 | note | INSPECTION - Lab Testing
8f134e64-e017-5476-acc1-9ac213b7855f | note | RECORDS - FHIMS-CS-4025
88d16c40-9766-4457-9cd3-45f08213c5ad | signoff | HOLD POINT
723ed052-0e50-481b-b451-3d5d0d734164 | checkpoint | 10 - Bedding (1)
8f61e084-2583-531c-bd64-ef19333a025c | note | ACTION (Hold, Monitor, Witness) - W
33fa36f6-330f-5cee-a69a-0f9b354057c9 | note | DETAIL - Bedding - Ensure correct thickness of bedding is placed and compacted
6e343ca6-3f18-5c53-a36b-2002068df8a3 | note | FREQUENCY - Daily
954d6e62-42d6-553c-9603-1779b279abf3 | note | INSPECTION - Visual/Inspection
0fa715a2-0b4c-5f2d-b2f1-62c6565337ee | note | CONFORMANCE CRITERIA - 100mm thick bedding for <450mm dia pipe
58100860-da01-5e60-9dc7-310faa6e00da | note | RECORDS - FHIMS-CS-4025
93cbbecc-2755-48c3-8b5c-e424552525ee | checkpoint | 10 - Bedding (2)
48f3466a-9f81-5975-9b49-92e15b15fb40 | note | ACTION (Hold, Monitor, Witness) - W
a830b985-3c57-5694-a5f4-a3ba0ba6ae0e | note | DETAIL - Ensure bedding material is compacted
edf36a63-a450-55ce-b046-bea55a787c8a | note | FREQUENCY - Prior to laying pipe
7a48c901-8d09-53b1-83ff-b0239d27681d | note | INSPECTION - Testing
11ec0375-c09c-58bb-8e68-fc98ee89c32c | note | RECORDS - Lab test results
5da4fd5e-acb4-49f4-820c-7296df2d5337 | checkpoint | 11 - Pipes and Precast Units
66e6fa3d-a76e-5473-860d-6a7ee7661966 | note | ACTION (Hold, Monitor, Witness) - H
97086600-30ea-5248-b3c2-da8e901a7e09 | note | DETAIL - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
1369e3e3-c822-5ad0-ac7e-f0bde3c80404 | note | FREQUENCY - Each delivery to site
cfd2cf09-827e-5c75-bfca-9fbcbc52f7a2 | note | INSPECTION - Certification
ed5d0e94-183d-5dad-8fca-631af9a6adf6 | note | CONFORMANCE CRITERIA - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
37d8cc8f-b56a-5ffe-81dc-3f9ad0ca7ca0 | note | RECORDS - Delivery Dockets
3a4ef006-6a22-4ff0-a442-c6d6ed686431 | signoff | HOLD POINT
051e4132-c4d4-405c-a918-56d40d636972 | checkpoint | 12 - Cast Insitu Drainage Components
5d75dc6a-bfba-5be5-9478-1673aeb43b05 | note | ACTION (Hold, Monitor, Witness) - H
891b71ca-6a6a-54e7-b686-38e74c40d973 | note | DETAIL - If any cast insitu component i.e. Headwalls is to be completed on a separate ITP - FHIMS-QA-6006 Insitu Concrete
3831b0f0-2ba7-5ea4-8a86-3504624cff2e | note | FREQUENCY - Every Cast Insitu Component
095de050-2c41-5c64-abe4-3581867a26ac | note | INSPECTION - Document Review
a2a62de1-f5da-5287-a743-fdeac03a0519 | note | RECORDS - FHIMS-QA-6006
d41ceb73-1946-478a-a79c-545e502d4e58 | signoff | HOLD POINT
d2499767-a74a-42de-8bd2-751fda6a1fe1 | checkpoint | 13 - Pipe Laying (1)
49e2250a-6de2-5ad1-a3d5-8905e72570e5 | note | ACTION (Hold, Monitor, Witness) - W
8ed7bf55-036f-5b7d-9470-d0d1b999b9ae | note | DETAIL - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
3b3c2dc6-e01e-5339-b448-05b8cf1542a9 | note | FREQUENCY - Daily
2b547045-40ed-5185-be50-5ed77984b3ac | note | INSPECTION - Visual/Inspection
5f348272-6a41-5659-bc8e-e5066f5ee371 | note | CONFORMANCE CRITERIA - Invert level <= 5mm and grade <= 3mm from design levels
174a598f-c013-51a1-9a95-33e13cc44381 | note | RECORDS - FHIMS-CS-4025
4386a396-b283-4b7e-a2b8-22c3ee5c6900 | checkpoint | 13 - Pipe Laying (2)
32e359c0-8eb2-51b5-86d8-254c908935ba | note | ACTION (Hold, Monitor, Witness) - W
f08f7df1-d6df-55d4-a290-1d6800e947bf | note | DETAIL - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
b999c028-206a-553a-9d3a-b70ee0b5e94c | note | FREQUENCY - Prior to backfilling
b440d471-1ba3-5118-8133-8bf0ea957853 | note | INSPECTION - Visual/Inspection
eed37944-7352-57e5-b451-2074e1e51045 | note | CONFORMANCE CRITERIA - No defects/ gaps / pipes are aligned correctly
ca28c95c-428f-5bb1-ac3a-498597a2dc24 | note | RECORDS - Photos
eaf1572e-0589-4824-a685-2a00a1f152cc | checkpoint | 13 - Pipe Laying (3)
3a534cf7-e3c6-5bf6-8b7d-f7b4edf0829e | note | ACTION (Hold, Monitor, Witness) - W
305ccb6b-2124-57ea-a36a-1c30d8314c18 | note | DETAIL - As-built survey of pipes installed
6eab9561-1503-5a75-a37a-ddc7b8628c97 | note | FREQUENCY - Once line is completed between 2 structures
ff4eabdf-59d0-53d4-b213-960e444c7e00 | note | INSPECTION - Survey
56664b2d-360e-5bd2-9408-3c755e2e5223 | note | CONFORMANCE CRITERIA - Invert level <= 5mm and grade <= 3mm from design levels
07aebec1-23d3-534d-97fa-969d58c6133c | note | RECORDS - Survey Receipt
00a196cd-a4dd-4db9-a3c0-946840f2c6a4 | checkpoint | 14 - Design Engineer Pre backfill Inspection (1)
7561c0b0-476b-5610-b001-f3c8fda6e5d4 | note | ACTION (Hold, Monitor, Witness) - W
53a3df63-b8fd-5558-9631-8c8d64ca3bc9 | note | DETAIL - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
6c33bde3-3612-5b37-9f61-72181c3ea67c | note | FREQUENCY - Daily
4188d17e-ec14-5ea3-bb4b-476330a75ed0 | note | INSPECTION - Visual Inspection
d4eec7e6-5a9a-5c15-9955-b73b1ca920df | note | CONFORMANCE CRITERIA - Compliance with the Specification
1c497c9a-b2b8-54c9-8206-3c0f56cd6d27 | note | RECORDS - FHIMS-CS-4025
f64d55fc-74ef-4dc0-a6f3-7b5f043fabcb | checkpoint | 14 - Design Engineer Pre backfill Inspection (2)
ac121de5-b20c-5de6-afb2-498e15ca516b | note | ACTION (Hold, Monitor, Witness) - W
5c12e0e6-fa8c-5515-9d1a-70d7f4c08fae | note | DETAIL - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
947c0533-5bb7-5df0-b793-2d1e67a7f017 | note | FREQUENCY - Prior to backfilling
ecb9c203-2b99-5a7f-a424-eefc66c769f9 | note | INSPECTION - Survey
bece37e3-f84d-5a5b-83ac-81001b967696 | note | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm
571123bc-a13a-52c4-9c61-4b90f074334e | note | RECORDS - FHIMS-CS-4025
949652a6-d3cf-40d8-972c-1ec0000fb35d | checkpoint | 14 - Design Engineer Pre backfill Inspection (3)
2a9ed662-f6ae-5109-8f8b-df1bbf4946ab | note | ACTION (Hold, Monitor, Witness) - W
b262dfc6-546f-5730-a30d-ce433f4600f5 | note | DETAIL - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
21abf761-c6dd-515a-9178-3590a812f54d | note | FREQUENCY - Prior to backfilling
54614a53-94f0-5c84-bde6-c9360c2b7c1a | note | INSPECTION - Survey
6765d7c5-2ee2-5054-a839-1064cebe7ab6 | note | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm
dce78a48-c097-53eb-862a-e71f67dd999a | note | RECORDS - FHIMS-CS-4025
1e3b63df-d9a7-4e40-9185-e94c4b754097 | checkpoint | 15 - Pipe Backfill Compliance (1)
bcf28b05-0b12-58e0-a7f7-7c985be2baa6 | note | ACTION (Hold, Monitor, Witness) - H
2f40f6b5-8e3f-52dc-b851-fb226af16a2d | note | DETAIL - Material to meet specifications dependant on material type selected
1c4d1c79-f46d-5f5e-a4ea-29f21cb8be58 | note | FREQUENCY - Each material used
88db7e5b-c6f7-5378-95c8-4cf14fb9b92f | note | INSPECTION - Document Review
799b38a3-6908-5b2e-845c-9c55bb8bce61 | note | CONFORMANCE CRITERIA - Compliance with requirements from Specifications
258d4235-272c-51df-b9c7-8409c5d635ea | note | RECORDS - FHIMS-CS-4025
ca4feffd-1f44-4957-b292-0d948e1a57bb | signoff | HOLD POINT
f8de7822-3802-46fe-ba46-25cfcaacb306 | checkpoint | 15 - Pipe Backfill Compliance (2)
9e82024a-f6d7-5e3f-80c3-29beae3b819c | note | ACTION (Hold, Monitor, Witness) - H
a391201d-aac4-56fe-b7e3-d13892d466e1 | note | DETAIL - Backfill Construction Material
a626797e-7e2d-59f2-b81c-30b46f626e2b | note | FREQUENCY - 1 NDM test per 15m
ab83cf4b-c7d6-5e7e-a77a-ca300514c963 | note | INSPECTION - Lab Testing
37522d85-e3b9-5bfa-94bc-e87e47d10f3c | note | RECORDS - Lab Test Report
bea92f17-66be-41f1-86c9-20caf857d050 | signoff | HOLD POINT
9c68e3db-5dfd-4e4b-a150-9dd07dd189df | checkpoint | 16 - Backfilling
ff174a64-fa26-56f8-86da-d72b460d91d6 | note | ACTION (Hold, Monitor, Witness) - W
69813fb9-5ad3-5a33-9176-62a774d073e8 | note | DETAIL - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade. Remainder of backfill to be done with excavated material.
c946273c-4060-549b-b19a-f557119fdbc3 | note | FREQUENCY - 1 test per 20 m length of trench per 300mm lift
e3971c8b-a07e-5b1a-b994-06da04196efc | note | INSPECTION - Testing
7fa18246-c415-5174-b282-e51b0f80dd12 | note | RECORDS - Lab test results
bdecf917-06d6-4d86-bd05-f46296f990c6 | checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (1)
67bfd618-4d0a-5074-87aa-7abd7fd47748 | note | ACTION (Hold, Monitor, Witness) - W
f987dd45-ce0e-5367-9de3-c6800576cd10 | note | DETAIL - Base of structure to be tested. Scala's to be minimum of 3 blows per 100mm
b36a132b-c85c-5db8-b0fa-7b25c848b0fe | note | FREQUENCY - 1 test per structure
846de9e4-8290-5c71-b159-8cf6429b2080 | note | INSPECTION - Testing
7c416b04-1701-5785-a48b-4bff361cf718 | note | CONFORMANCE CRITERIA - Scala minimum 3 blows/100mm
178b0dfc-88f8-580e-b21d-31ee95316e6f | note | RECORDS - FHIMS-LA-4003
615c4639-88c0-4874-ab31-c68b49c2000f | checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (2)
189e5e68-7c9a-5e0c-a2e7-fcdb3ce52c1b | note | ACTION (Hold, Monitor, Witness) - W
64518de6-4cec-5814-8194-3847c5aca0ca | note | DETAIL - Structures to be installed to the design survey location and level
73c5e7b2-c952-5ce1-b044-4c65ea66d165 | note | FREQUENCY - During structure construction
d3ff419a-df28-52a8-9e05-e1660b8ab591 | note | INSPECTION - Visual/Inspection
7307aff5-4a19-5b25-bac9-8c35d713bc9e | note | CONFORMANCE CRITERIA - As Built Survey
edd247fa-b107-5f70-b935-2fd476995b9a | note | RECORDS - FHIMS-CS-4006 and Survey receipt
11aae492-97a6-461a-82b8-f4d0cfd081d4 | checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (3)
ffe5bad6-10cb-55cd-bb86-b5315e1f6a5a | note | ACTION (Hold, Monitor, Witness) - W
6c0b0778-186f-511b-9ec3-6c738954f8ea | note | DETAIL - All joints are to be sealed including rungs and lids
7aeaa470-eb88-5720-be7c-2e797b7a6c63 | note | FREQUENCY - During structure construction
3f8665c2-e409-533c-8fa7-56ff4d6ba66c | note | INSPECTION - Visual/Inspection
53059a03-a77e-5b62-b4ba-36d0ab5a8512 | note | CONFORMANCE CRITERIA - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
58776f7f-fdce-5570-9f8e-e8f382c6da95 | note | RECORDS - FHIMS-CS-4006
cf157ce2-a0af-4185-8e90-85cd957a1510 | checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall) (4)
cf271514-c0ef-5061-acf4-977fe5b5815a | note | ACTION (Hold, Monitor, Witness) - W
469325d5-3c65-5349-81f6-a58fdf5fcbb9 | note | DETAIL - Arrange as-built survey of the structure and all invert levels
6dabf690-9736-5667-9b8b-dcaf20530be0 | note | FREQUENCY - Once installed
fab00b1f-153d-53a5-bfb0-3defc0294e2f | note | INSPECTION - Survey
4d4f2f14-ad1a-5f6f-9750-9e63ebf681a8 | note | CONFORMANCE CRITERIA - As Built Survey
a0dcc14a-7bf1-5c31-b2cc-d667eb0a9eb6 | note | RECORDS - Survey Receipt
ea02e4ff-30de-4dfd-84d3-65911cc17f5c | checkpoint | 18 - Post Backfill Inspection
a00a943b-fa10-59dc-aacc-ee12a576618c | note | ACTION (Hold, Monitor, Witness) - H
d5342f6e-bb4a-570a-93de-81bbd2db5ae4 | note | DETAIL - On completion of backfilling all lines to be inspected
c1e00b99-eb96-536e-a6aa-228ffe573665 | note | FREQUENCY - One per line
618dc6bc-be30-5441-8015-bdfbb61f515a | note | INSPECTION - Internal Visual Inspection with camera (compliant with Confined Spaces working)
6c2dc174-69b1-51e0-8746-9dfb0f567cf8 | note | CONFORMANCE CRITERIA - Lines must be straight, free from dirt and obstructions, with no ponding.
d55dc063-5315-5221-ad3a-d3907618252d | note | RECORDS - FHIMS-CS-4025
9c280daa-82f3-47e6-96f5-8c7df2a8b2b1 | signoff | HOLD POINT
1b035f69-89b7-46c9-b8ec-615cf94f8e02 | checkpoint | 19 - CCTV
f0b5a3fb-d71c-5d95-80e9-63080b891461 | note | ACTION (Hold, Monitor, Witness) - H
0aaee427-2334-5c14-bbf7-ff05893ade39 | note | DETAIL - For pipes <900mm a CCTV inspection must be completed. Pipes >900mm must be visually inspected
73f37c66-2013-50bd-a2e0-3e36cbcb6190 | note | FREQUENCY - At completion of the works
0ce2fa5e-7664-5ef9-85fe-9b70ca7ae067 | note | INSPECTION - Visual Inspection/ CCTV inspection
5a8a636a-455d-51b1-9761-7f421b27b967 | note | CONFORMANCE CRITERIA - No Defects
dabe68e2-b83a-5227-94c4-e9e4809b7dc2 | note | RECORDS - Inspection Report CCTV DVD
2d6d8ea5-7878-4686-b405-c4e266f4e819 | signoff | HOLD POINT
aadc46b1-4499-4c36-b06e-f0132ca9c3cd | checkpoint | 20 - Testing of Manholes & Pipelines
b9ffd734-f640-54df-b8c3-071e4cd91f03 | note | ACTION (Hold, Monitor, Witness) - H
9eb848a0-9fa9-54ce-bb25-38df74f85198 | note | DETAIL - If called for in the specifications then test results for water tightness in the structures and low pressure air testing of the pipelines is to be carried out - test sheets to be filling in where required
2d89805b-beb8-55c8-a20c-334aa506ac26 | note | FREQUENCY - One per line/structure
94b446ab-d97f-5cdd-b23b-a2c640d0806f | note | INSPECTION - Measurement
be6a7436-10de-5e80-a42b-e16380391a2a | note | CONFORMANCE CRITERIA - Drainage Structure Water Tightness Test Record & Low Pressure Air Test Record
fcb6b68e-e160-57b3-814d-8a647a589f0c | note | RECORDS - FHIMS-CS-4073 & FHIMS-CS-4074
1ddc305a-17ce-49be-8e45-7e5c6f310721 | signoff | HOLD POINT
8cc6fe70-627c-4d7e-af92-ec62cd2b8a44 | checkpoint | 21 - Survey As Built
f0fe1337-3ed6-542f-92a5-27dd75a3b974 | note | ACTION (Hold, Monitor, Witness) - H
7e5845e6-cf04-581b-bbfb-0207efa664f2 | note | DETAIL - Ensure all drainage lines comply with design prior to carrying on with next construction process
5e2ffe5a-c4b3-5b4e-8378-c46a23310ddc | note | FREQUENCY - At completion of drainage line
60f0fa81-ddcc-5717-bee1-4b995ba2ad64 | note | INSPECTION - Measurement
a0dcc14d-d10f-57f4-9a49-ebc5c1d326e0 | note | RECORDS - Survey receipt
2d466760-06cc-4ed1-a48e-35e6be1bd0b6 | signoff | HOLD POINT
4cd7e0cc-10e4-4bf1-9904-674f7aff981e | checkpoint | 22 - As-builts
aefc136f-de7b-5ae2-bb59-02757118dbb1 | note | ACTION (Hold, Monitor, Witness) - H
eb0f4d4a-a393-5566-9f62-f7dc7d73d971 | note | DETAIL - Red pen mark up drawings to be included in QA file
edefb006-bf6e-5bf3-ac1a-eb893b6a14ae | note | FREQUENCY - At the completion of the Lot of work
33cd28f9-2e87-5cfe-a2ef-42b2d48cb91f | note | INSPECTION - Drawings
edd5933d-4908-55a9-a2fb-ce554e582555 | note | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
f91e7026-2c3b-5d90-bc81-1c61916161af | note | RECORDS - Asbuilt Drawing
71f7072a-cafd-48ac-9e9f-947edc81ebe9 | signoff | HOLD POINT
264dde5d-8f33-465d-8f49-f50c9a8d0150 | checkpoint | 23 - Lot Number QA File
414a4e4f-ab73-55f4-a0bc-218a1598c544 | note | ACTION (Hold, Monitor, Witness) - W
d38610cd-368d-5850-ab38-084ecefdbdb5 | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
70dc4707-129f-504e-af64-342c974033bc | note | FREQUENCY - At completion of Lot
b795a90f-54ee-567a-a650-a14db80784f0 | note | INSPECTION - Document Review
cbe4fcca-7658-5bca-a185-f42d1770418c | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
3701c833-bfeb-5462-b958-afefbf295ca6 | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
e8bc2031-9e7a-47ca-b7d4-042f60b4c784 | checkpoint | Final Inspection
faf327dd-381d-53ef-80b2-cc7f4fa8f462 | textbox | QA Compiled By:
ca13be5d-ecb7-5d46-92bf-056cd001548a | textbox | QA checked By Discipline Manager:
101a132f-6267-5bd0-97b5-d6fb29b48cce | textbox | QA checked By Quality Manager:
029b50da-8740-561f-b2bb-6c6ee7d52f08 | textbox | Accepted By Design Engineer:
42b20e24-f739-5ec6-923c-1baaa6ae4601 | date | Date:
32fa516e-6a8d-4943-bb88-c0e2e1ba5560 | signoff | Sign ITP
4370279a-cc94-4ddf-b5a4-f4b02b352223 | checklist | FHIMS-QA-6010-ITP-Subsoil Drainage | itp | FHIMS-QA-6010-ITP-Subsoil Drainage
6dba68dc-ae88-4ef2-98af-cbe9f6fa6863 | section | Subsoil Drainage
8a68f586-05d3-41a0-9ff8-b91fe7d32cde | checkpoint | 1 - Permits
d7403bd1-ff67-556c-8b52-2126cd71bc6a | note | ACTION (Hold, Monitor, Witness) - H
b2896a03-260f-5fc2-b9bb-07b00233aaa7 | note | DETAIL - Obtain Permits
a3943ab4-0cc1-5c6e-ad7c-9228c7310a0a | note | FREQUENCY - As required
919f45b7-18b4-51ea-875f-56208d16e261 | note | INSPECTION - Document Review
fedfe9d9-19e7-54d0-aafe-76540a29ccc7 | note | CONFORMANCE CRITERIA - Digging & Excavation Permit, (incl. marking out & potholing existing services), Confined Space Permit if rquired. Notify Worksafe NZ if required.
7b292ae8-5ee1-544f-bba9-5a56a525a253 | note | RECORDS - Permit attached or permit number noted
9bbaa698-0193-499f-8759-32d86b0f943c | signoff | HOLD POINT
8f457ac1-a8dc-4988-a5c5-7c0d64b2a58d | checkpoint | 2 - Design
32939c2e-498d-58f8-b273-200895381536 | note | ACTION (Hold, Monitor, Witness) - H
073ce7a3-fae9-5368-9d33-a44a5949c543 | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
0bc9c133-6895-523e-93f8-3b23b37f17ec | note | FREQUENCY - Prior to commencement
2c2d2b72-0a59-5f0d-8ced-35d62dbe00ae | note | INSPECTION - Document Review
3ccf857a-a4ab-5333-9387-87e0c76562f8 | note | RECORDS - Check Drawing Register
ecbe7c46-15c4-482a-af80-7468e8e323ef | signoff | HOLD POINT
0878675d-27d4-43b4-b625-068398d542ec | checkpoint | 3 - Survey Setout
5052ca2a-6432-5be3-b1ce-40040a462e43 | note | ACTION (Hold, Monitor, Witness) - W
bb700686-21f6-5ea5-984f-b429014cc8f2 | note | DETAIL - Setout and mark all known services along the line of the Sub-soil Drain.
89a6b102-9a76-5bf2-96d8-862100ee8b78 | note | FREQUENCY - Prior to commencement
a4bfef97-9a4e-5572-8329-134d99ad10a9 | note | INSPECTION - Survey
f628649c-dd17-5f2e-aea2-889b2e33f807 | note | CONFORMANCE CRITERIA - Consistency with Construction Drawing
18b9ce23-2f42-551f-b45e-4b4e08bf2ba7 | note | RECORDS - Survey receipt
4dcd3b9a-c505-4e9e-8125-902789a818e7 | checkpoint | 4 - Material Compliance (1)
636bde81-0784-5914-8350-0959ef28e776 | note | ACTION (Hold, Monitor, Witness) - H
34d9b58e-24a1-51b1-9526-527c60193e06 | note | DETAIL - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110mm diameter Nexus Hiway grade slotted high density polyethelene smooth bore corrugated plastic pipe
16ace79b-cd5d-5eac-9fbe-f72f5f3f7794 | note | FREQUENCY - Upon delivery to site
7c9c618a-27a9-54d4-bc74-cee9a6057b86 | note | INSPECTION - Ensure delivery docket matches materials delivered
ccfc4326-0479-593a-96dc-5e5dd9028661 | note | CONFORMANCE CRITERIA - 110mm diameter Nexus Hiway TNZ F/2 Grade pipe
294327d0-9eac-55ca-ba15-8630fb69f16d | note | RECORDS - Delivery docket
ce34b9cf-aac1-4e60-abec-34e33c8ee508 | signoff | HOLD POINT
42a6fb40-e1c6-455d-99b7-9591000efffc | checkpoint | 4 - Material Compliance (2)
f841074b-f78c-5460-84e6-b081d3dba5cc | note | ACTION (Hold, Monitor, Witness) - H
94eba411-9eda-567a-8bf0-3296d7223fed | note | DETAIL - Ensure drainage material surrounding subsoil pipe conforms to TNZ F/2 and meets the grading limits setout in the NTLDM
c937fc2a-4218-5660-a36f-83454a487037 | note | INSPECTION - Visual inspection
ced27994-6229-5e07-baa5-1bf12efc49c4 | note | CONFORMANCE CRITERIA - TNZ F/2 & NTLDM
e0011a0b-32df-5b3e-a761-729e0f4db70c | note | RECORDS - Delivery docket
0c9c411d-63e8-43bb-9346-c906513c873a | signoff | HOLD POINT
4d3f42e3-07d6-49e9-9e8a-1e0e20f98818 | checkpoint | 4 - Material Compliance (3)
3f4a1733-1049-5698-bb92-4fd54d5f2f7b | note | ACTION (Hold, Monitor, Witness) - H
a77e2fb5-dcee-5770-a8f6-8731fb79b86b | note | DETAIL - Ensure Geotextile Filter Fabric is A29 Bidim, Strength Class C & Filtration Class 1 or equvilant approved by Engineer
60867974-37d6-5b3a-93e0-6e2a5af077e5 | note | FREQUENCY - Upon delivery to site
c8c437f8-6613-5c2d-90ee-632aaffada2c | note | INSPECTION - Ensure delivery docket matches materials delivered
65af0217-810d-57ff-8837-5248b9421425 | note | CONFORMANCE CRITERIA - Ensure geotextile is approved for use
e1f3f554-e43a-5684-92e8-7ff3633fede3 | note | RECORDS - Delivery docket
a5099f28-e6fb-4b42-a617-5ac06958ad89 | signoff | HOLD POINT
1883e3d8-5049-406a-93cf-81cfb13cb0ee | checkpoint | 5 - Trenching (1)
51e5941d-cbe4-530e-b081-77ca56b2d314 | note | ACTION (Hold, Monitor, Witness) - H
10e79f70-89f5-58aa-a4b2-3ec4030efc38 | note | DETAIL - Inspect trench profile and ensure it allows minimum 100mm bedding, side support and surround.
e46968b0-0fcb-57cc-b4c4-07c22b3233ed | note | FREQUENCY - 10m intervals
a0f747ee-b58f-5822-ab54-a8ec46605178 | note | INSPECTION - Visual inspection and measurement
d2519b70-abb1-5a8f-b2a1-3a7bdc05d1f8 | note | CONFORMANCE CRITERIA - Record levels of base of trench on dip sheet
c13960ce-9126-56e9-a885-c3d5ab2981f2 | note | RECORDS - Photo / FHIMS-CS-4001
fba4eccd-e918-439e-a525-df866c537c05 | signoff | HOLD POINT
e25440e0-ce5f-4a68-9083-a593d3cf0f33 | checkpoint | 5 - Trenching (2)
202db303-fdd4-5dcd-a355-b39a6ec8360e | note | ACTION (Hold, Monitor, Witness) - H
7043401e-6283-5d3d-b49c-3d147d565da0 | note | DETAIL - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
c861ebba-ab57-5d80-83b0-87e76428d554 | note | FREQUENCY - 10m intervals
9037f25c-4973-5069-b73f-ba5aa576471c | note | INSPECTION - Visual inspection and measurement
afaa9ac7-d543-5376-8fe4-ded807c2d50f | note | CONFORMANCE CRITERIA - Ensure trench line and levels match the design drawings
2f0e0403-091b-5d19-9bda-4beec8600773 | note | RECORDS - Photo / FHIMS-CS-4001
f208dc16-3761-40fd-ae59-3a8fc45e7795 | signoff | HOLD POINT
e8882a08-2414-42ad-b0c2-517264a8aa1e | checkpoint | 5 - Trenching (3)
8a68c530-bd59-5eb8-a512-9801e179dee0 | note | ACTION (Hold, Monitor, Witness) - H
10eda997-63ba-504f-bd21-5f3cf816008b | note | DETAIL - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
b3698a57-b387-5567-813a-58e89d06e6f5 | note | FREQUENCY - As required
d9bb15d0-42ae-5a97-a4cf-6162fef4f7a8 | note | INSPECTION - Visual Inspection
b4b1b720-75cf-5c9a-971f-9b7cbf2cb33a | note | CONFORMANCE CRITERIA - Design Engineer to instruct action and record on dip sheet and as built drawing
5d2463bf-9d27-5846-b394-3eddd785dd60 | note | RECORDS - Photo / FHIMS-CS-4001
63e8ff0a-4851-4e1b-894e-e6bc6edd12c9 | signoff | HOLD POINT
ce45d351-e602-4504-a7cb-3c3bfa01113d | checkpoint | 6 - Bedding, pipe installation and Backfill (1)
7ca2253f-7aa5-54b9-913b-57d470813529 | note | ACTION (Hold, Monitor, Witness) - H
f2653e04-e819-5c54-8226-4a427966313e | note | DETAIL - Upon completion of trenching A29 Bidim or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
0d441df1-c0dd-51b5-879b-ff8f5ac32305 | note | FREQUENCY - 10m intervals
0cee82b2-a6df-531e-99b9-8cc883e2058c | note | INSPECTION - Visual inspection
4f47aa1f-4739-526b-ac08-9628ac446191 | note | CONFORMANCE CRITERIA - Ensure material covers the trench and is pinned in place
ce01903f-a7bb-51bb-957e-5f4cfd3d53c2 | note | RECORDS - Photo / FHIMS-CS-4001
3369c162-cd61-4487-8c17-f75de961c226 | signoff | HOLD POINT
e5022d44-4a0c-4fcb-8b2b-2bd611812872 | checkpoint | 6 - Bedding, pipe installation and Backfill (2)
1de11e90-e164-515c-80b5-ad54a6f5536f | note | ACTION (Hold, Monitor, Witness) - W
6ca98dfd-5c92-5b29-824e-4aa5824b41d6 | note | DETAIL - Ensure 100mm thick conforming TNZ F/2 bedding is placed in base of trench.
bdb14f5c-7549-58ff-b20f-f9dc48b223cd | note | FREQUENCY - 10m intervals
b1076965-9fb3-5a70-a7c5-305c8cc7dc5b | note | INSPECTION - Visual inspection
0892d837-d813-5d33-a65f-aa377c2b85d0 | note | CONFORMANCE CRITERIA - Record levels of top of bedding on dip sheet
743cabdb-0d85-5940-9181-df9f6a771925 | note | RECORDS - Photo / FHIMS-CS-4001
8a107c18-1e9d-4c28-9ad7-d5d7f6482cb8 | checkpoint | 6 - Bedding, pipe installation and Backfill (3)
4895edd9-d237-50c1-ade2-9ce32d88674f | note | ACTION (Hold, Monitor, Witness) - W
c113c157-9118-59ae-87f9-f62d9dcf5e68 | note | DETAIL - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
48191ee4-a62f-5df1-9e73-ca90b7a97b33 | note | FREQUENCY - 10m intervals
a5f05bb2-dcce-55d4-b6b6-0f14581bb914 | note | INSPECTION - Visual inspection
22029306-5ca2-56a0-96c0-00568de199b5 | note | CONFORMANCE CRITERIA - Consistency with Subsoil Details
bcd740e5-cd2d-5a5d-baf3-027a4b9bc9e6 | note | RECORDS - Photos
c1bfae0f-970d-42dc-b763-b2b27ae2e74e | checkpoint | 6 - Bedding, pipe installation and Backfill (4)
ee4c1971-2bfa-578f-ba99-dfb2099dcf4e | note | ACTION (Hold, Monitor, Witness) - H
52f7ef0d-f259-5ee8-ba0c-016fbb75e953 | note | DETAIL - As built Survey the Pipe before backfill
3aee84d1-80ba-56b6-9bed-2258808e71a4 | note | FREQUENCY - 10m intervals
10bee439-0192-555e-9c37-bbc1cf872773 | note | INSPECTION - Document review
0955494d-6d70-586a-8823-f949a8d98862 | note | CONFORMANCE CRITERIA - Consistency with Subsoil Details
bfd68747-6d7e-5188-b8ba-ed1d92ed1d9b | note | RECORDS - As-built receipt
a44060f7-ee82-4b52-814e-0a5d9ef520c3 | signoff | HOLD POINT
e75cc1e4-72bd-4cac-9ae9-b05fcdbd6b4f | checkpoint | 6 - Bedding, pipe installation and Backfill (5)
bc5d797e-0f90-5dbc-8e97-0915ed020529 | note | ACTION (Hold, Monitor, Witness) - W
cd851858-cacf-5738-b6ab-5328db4867b5 | note | DETAIL - Backfill by tipping conforming TNZ F/2 into the trench
439c2f00-5d4c-5721-b0e7-8a88db0f7b05 | note | INSPECTION - Visual inspection
77cc3129-305f-513e-ad60-52609f4e5e32 | note | CONFORMANCE CRITERIA - Ensure good coverage
3ab2aa7d-5234-5745-a3ca-46c0b28a6f96 | note | RECORDS - Photos
ca369a21-0007-4870-99bb-f694f549419a | checkpoint | 6 - Bedding, pipe installation and Backfill (6)
63c776ff-e9c5-55be-becd-9de6d3f4f60f | note | ACTION (Hold, Monitor, Witness) - W
2c314731-b11f-52a3-9e62-c8a37493e6d1 | note | DETAIL - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
25b5e4b2-7feb-53dc-a56f-8520600022fc | note | INSPECTION - Visual inspection
6d5841c0-dab8-4e8c-a555-3aef7166abc3 | checkpoint | 7 - Catchpit Connection (1)
ab8bda2c-2665-577b-ae85-fe11a19c9823 | note | ACTION (Hold, Monitor, Witness) - W
dc0adfd8-71c8-531c-871c-9961ebaf3cb2 | note | DETAIL - Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
4665e9c1-0585-5611-aa84-21eba2bceea8 | note | FREQUENCY - As required
babbe610-28f7-5d43-91fa-653bc01fc9da | note | INSPECTION - Visual inspection
d96ea30b-1b9b-5e32-a53c-512b14e28894 | note | CONFORMANCE CRITERIA - Consistency with Subsoil Details
a2b708af-9be1-5dce-a98f-61293ab86eaf | note | RECORDS - Photo / FHIMS-CS-4001
a08a3807-fb43-4a72-a809-84e0cca5e748 | checkpoint | 7 - Catchpit Connection (2)
7ee20dac-5a02-5318-8732-4370929f306d | note | ACTION (Hold, Monitor, Witness) - W
d9539189-dc02-5843-8471-411d8cfbea92 | note | DETAIL - Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
e31b560b-d8b9-5e74-a712-01f1f996ba5f | note | FREQUENCY - As required
73a8298a-cee8-5c54-9f97-15a5804f2c02 | note | INSPECTION - Visual inspection
d09079a5-2f8d-5298-9e33-d93fb2d35ae4 | note | CONFORMANCE CRITERIA - Consistency with Subsoil Details
9e3a933e-f7f7-5de9-9318-5ebdb5b05d8f | note | RECORDS - Photos
a8b8d40b-686e-41cc-9d69-83ec6b1ad086 | checkpoint | 8 - Outlet to any open areas
7da2f8d5-4ff0-5c92-a72f-43f4ebda6d72 | note | ACTION (Hold, Monitor, Witness) - W
a4af0479-d114-5d01-8b67-c265c49045fc | note | DETAIL - If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately
1492c6cb-2979-597e-83eb-bb9ec0381a42 | note | FREQUENCY - As required
cc302d58-9b06-5ac4-929f-888b249b5c1a | note | INSPECTION - Survey
d625047d-c3b5-5a7c-9b16-0142497d419b | note | RECORDS - Survey receipt
bda1791a-7c9b-4589-a26c-3ccdc821c491 | checkpoint | 9 - Survey As Built
bbc89bd1-e4fe-527b-a960-9e138e01b685 | note | ACTION (Hold, Monitor, Witness) - H
e911d3e0-b329-5143-845d-01a94cdcdc55 | note | DETAIL - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
7b800364-ccea-5482-a826-64432b272a71 | note | FREQUENCY - At completion of sub soil drainage line
eb907fdf-2d8f-5fc2-9000-f14d7431e487 | note | INSPECTION - Survey
e3e440e3-99dc-5144-908f-46487875511c | note | RECORDS - Survey receipt
1d81ea17-fff9-4c7a-a9f5-fb8f1f18d121 | signoff | HOLD POINT
fda4f1c1-83ef-41f0-9a53-e4dc7723a110 | checkpoint | 10 - As-builts
5407e1ec-9797-52db-9a5f-1c734a41d361 | note | ACTION (Hold, Monitor, Witness) - H
2dff1786-34e7-5f31-b5d2-dff24d01132c | note | DETAIL - Red pen mark up drawings to be included in QA file
bc54348a-303c-5b67-991e-44ca7a57585b | note | FREQUENCY - At the completion of the Lot of work
69b992a5-6763-5de6-bddf-d2ae5da9ca18 | note | INSPECTION - Drawings
b5cd5860-6591-5b94-968b-bd4370550f25 | note | RECORDS - Asbuilt Drawing
8c913c63-fd8c-4157-9fe6-44a3bc6574fe | signoff | HOLD POINT
72df4a6e-0c23-4512-a3ff-bcd5ce12cc1b | checkpoint | 11 - Lot Number QA File
5729a588-e459-5d4f-bfb7-1d92f08d21bf | note | ACTION (Hold, Monitor, Witness) - W
53ee243e-9fa6-5063-9c7f-d8b626d5f00e | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
cc3a234c-4789-5998-a0d7-5d2f658aa410 | note | FREQUENCY - At completion of Lot
0a026753-573f-53d3-9e50-a7a3f3e4cb0c | note | INSPECTION - Document Review
a7268925-3aca-5459-a4b1-e2bd81dcb3f3 | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files
321d2d20-d1b1-52c5-877b-6b1d8f94649c | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
c0340621-5158-4869-ac63-c7325281f5fd | checkpoint | Final Inspection
e493904f-6617-57f9-8383-1e9db3c02c05 | textbox | QA Compiled By:
c3409de6-f833-5828-90d3-f59a1f464f46 | textbox | QA checked By Discipline Manager:
8b6de5ad-b32f-5cfb-a9c9-9cf8899176fa | textbox | QA checked By Quality Manager:
21a6b011-117c-5fb9-af9d-b1d459402fb1 | textbox | Accepted By Design Engineer:
4dd2126f-7b31-58cc-a300-9eea53430a1d | date | Date:
19dda4bd-d0a9-40f3-9178-da8bda221e50 | signoff | Sign ITP
a288ea58-d47c-43f8-a1c0-9feee62fdbbb | checklist | FHIMS-QA-6013-ITP-Gabion Retaining Wall | itp | FHIMS-QA-6013-ITP-Gabion Retaining Wall
0507d16b-e935-4263-94e9-360ba0637eda | section | Gabion Retaining Wall
c267c8e7-89ed-4e3e-9aaf-da4ba4f028cb | checkpoint | 1 - Permits
5eb14435-c6d5-5bd0-a564-bf425fe8dfda | note | ACTION (Hold, Monitor, Witness) - H
875c71cd-e499-56ab-b88b-579db836f56c | note | DETAIL - Obtain Permits
d1f4dcdb-22e0-52f5-a9a2-c373008feac5 | note | FREQUENCY - As required
1f180962-8878-55dc-893f-baf265b9e2a3 | note | INSPECTION - Document Review
94978996-6a00-5e2e-8d28-e851e750870a | note | CONFORMANCE CRITERIA - Digging & Excavation Permit, (incl. marking out & potholing existing services). Notify Worksafe NZ if required.
cf55fe6c-24ba-58a8-b5ee-d63bb6145219 | note | RECORDS - Permit attached or permit number noted
960041ea-afe7-4430-9546-e51fd03f9b76 | signoff | HOLD POINT
2be56878-bfe1-46d2-b9eb-404b5e87a6e4 | checkpoint | 2 - Design
744d051f-4fcc-5db9-9fed-c160ff850edf | note | ACTION (Hold, Monitor, Witness) - H
0f569533-8d6c-5ffd-b710-25211427d969 | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
fd81431a-f080-5edd-8279-7aa01f26089f | note | FREQUENCY - Prior to commencement
2f3bd4ea-20b9-565b-a9fb-130064176b2e | note | INSPECTION - Document Review
5e6c18f6-0416-5513-acfe-61993ee41724 | note | RECORDS - Check Drawing Register
cd3974c9-befc-4624-8dde-cd1216872972 | signoff | HOLD POINT
16349319-6a8e-4a53-8547-850b59f9c7e2 | checkpoint | 3 - Survey Setout
04b1d617-18cb-59a5-b69d-bf638edb0f84 | note | ACTION (Hold, Monitor, Witness) - W
76cac262-4466-5318-aa61-b34bc0266245 | note | DETAIL - Set out base of wall to 1m offset.
58710093-1511-517b-abaf-89fed00e0e1a | note | ○ Setout and mark all known services along the line of the Retaining Wall.
423cfe31-58fd-5c90-8fe2-e0a598e55ef3 | note | FREQUENCY - Prior to commencement
337db413-0fea-5888-a7e1-ee13fd510cdd | note | INSPECTION - Survey
65a7d48b-db68-539c-a4e3-c358c085102b | note | CONFORMANCE CRITERIA - Consistency with Construction Drawing. Designer to confirm extent of MSE Wall
4c4395bf-3f5e-5412-ba1c-aaf2f8908a25 | note | RECORDS - Survey receipt
0fb6e34c-09a2-4daf-8d2c-1e1580da0135 | checkpoint | 4 - Gabion Baskets
97247863-2033-55f3-8c60-8208e003e3ef | note | ACTION (Hold, Monitor, Witness) - W
b4b78f99-d68f-5c77-b223-094e1e80f43e | note | DETAIL - All baskets are to be ordered in accordance with the specifications & drawings
4c62e6f4-12f8-5e00-b02f-42a0999321b2 | note | FREQUENCY - Prior to commencement
644bcf06-bc8e-5b34-a1c0-f96e6f56902b | note | INSPECTION - Review
8a97e418-6d6e-5f4f-9cf2-1a8bf2661bc6 | note | CONFORMANCE CRITERIA - Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately
a8d77871-5e16-537c-8c3e-6174f095c323 | note | RECORDS - Delivery Dockets
7071fb1e-a1c0-4fe4-a10d-a428bcc7cd94 | checkpoint | 5 - Gabion Rock and Backfill Material Compliance Testing
191967c9-9af0-540e-b59f-6a992a88f89c | note | ACTION (Hold, Monitor, Witness) - H
30f6062c-19cf-5ab2-9248-f350aa6994e3 | note | DETAIL - Material to meet specifications and approved by engineer
663e432a-db91-5e8b-b60f-013ac3bf8bb2 | note | FREQUENCY - Each material used
1f520fab-b3b5-5aa5-8236-599d3704b04f | note | INSPECTION - Review
ef0fd0e1-e34e-575b-9aed-d9fd622862b9 | note | CONFORMANCE CRITERIA - Compliance with requirements and approved by engineer
d22c94d5-5cf1-56fc-a003-1638e8ec5911 | note | RECORDS - Delivery Dockets
3f958702-2fbd-40e1-90b3-c85e38d1a185 | signoff | HOLD POINT
b850d2dc-52a1-4ebf-9e00-a8af9f96c4f1 | checkpoint | 6 - Compaction Trial
f4805161-5a4a-5fa9-b6f7-395b0f4b1b48 | note | ACTION (Hold, Monitor, Witness) - W
69747571-c282-55bc-8264-9b0c20d68aa5 | note | DETAIL - Carry out compaction trial minimum of 3x superimposed layers to determine peak achievable compaction (NDM)
2015f4da-56c8-5cec-8a0e-1b5f6ea4373f | note | FREQUENCY - Backfill material
33f34c5c-176a-5b23-bbbf-de41e3622b48 | note | INSPECTION - Review
5a85d754-5e17-55a4-8654-9e4c21a61060 | note | RECORDS - Lab test results
8389370b-39fc-44bc-962c-f57daa0a56be | checkpoint | 7 - Geotextiles & Geogrid
36b82cf7-2673-51e9-ad7f-e4ccf5f5c358 | note | ACTION (Hold, Monitor, Witness) - H
80524bb3-1d1e-554d-83e6-f2bb95e2b6c8 | note | DETAIL - All geotextile & geogrid are to be ordered in accordance with the specifications & drawings
32c7e9f8-899a-51a3-ab2f-ecb991d0235e | note | FREQUENCY - As required
4cdc258c-e636-57d1-a51d-91b9a73615bd | note | INSPECTION - Review
5e36fd8e-df33-50b3-99c6-a1ed4835bf95 | note | CONFORMANCE CRITERIA - Geotextile: Strength Class C, Filtration Class 1. Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
5d333e93-b40d-57d7-a948-b93e8994247e | note | RECORDS - Delivery Dockets
4faa734a-3d08-408e-b868-85095c6814a4 | signoff | HOLD POINT
18c0dd5f-c272-4813-83d3-fad5ae56bf30 | checkpoint | 8 - Excavate Base of Wall (1)
e41dee9b-74c0-5bc8-a7a3-c5b71f357bee | note | ACTION (Hold, Monitor, Witness) - H
ec783cd5-68cc-5720-aa3a-02d88ea1efc3 | note | DETAIL - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
ab7a902d-9e60-594d-899e-74e672752c64 | note | FREQUENCY - As required
98065598-fc01-5279-b073-9a359f97e7f5 | note | INSPECTION - Survey
bf6cb5df-fe16-5269-92d1-86e4c9d4ca27 | note | RECORDS - Survey Receipt
3437749e-85ca-498f-98c6-ec58bc800a8f | signoff | HOLD POINT
768aa00a-9fb6-4a44-a09d-3234dfd885a5 | checkpoint | 8 - Excavate Base of Wall (2)
2fb98964-2237-52c1-ad85-80e01a8f0366 | note | ACTION (Hold, Monitor, Witness) - H
84a4d7a1-8012-5ea4-8dbc-7b0169da8ba0 | note | DETAIL - Base of excavation to be checked by Geotech engineer / Design Engineer
b769af45-853e-5500-b8e2-7cf8ddc04f37 | note | FREQUENCY - As required
e169d3d1-c5c6-583f-aebb-592bcd820d2c | note | INSPECTION - Visual
ddf78f43-d78d-5e5e-9083-bf5bb0ae0c27 | note | RECORDS - FHIMS-CS-4100
7ca4f8a2-d890-4640-b4ef-270e3faef216 | signoff | HOLD POINT
6d82019c-9fc9-4c2b-b626-e66a33587aab | checkpoint | 8 - Excavate Base of Wall (3)
f0b98ba2-c2fa-58f3-b10a-e5442bc15086 | note | ACTION (Hold, Monitor, Witness) - H
fd397de8-cafe-569a-88a4-1f9260677f88 | note | DETAIL - Compact subgrade and test the base to ensure it meets 50kPa.
267047f6-45cc-56a6-aa5b-601f57a57bc7 | note | FREQUENCY - Prior to construction of wall
06826374-0701-5b9e-94b0-bb55bf8b7f4c | note | INSPECTION - Scala
54873f50-f38f-57c6-b071-d5ead5f61d02 | note | CONFORMANCE CRITERIA - 2-3 blows/100mm. If CBR is less than 2.5 or 50kPa undercut may be required. Seek engineer guidance for undercut depth
837869ca-03de-5786-a455-c52646b3fb3e | note | RECORDS - FHIMS-LA-4403
36f41529-43a6-4791-8181-62b82aec79fe | signoff | HOLD POINT
264ed736-15ff-4fb9-8b56-278549104279 | checkpoint | 9 - Subsoil Drainage
4eefc499-bd5a-5011-9e48-934cee599bc6 | note | ACTION (Hold, Monitor, Witness) - H
3f09b177-bf18-5276-a5f2-a81da4ac4e44 | note | DETAIL - If subsoil drainage is required for this wall construction then follow the FHIMS-QA-6010 ITP for Subsoil Drainage
3e62a9a2-4da1-5757-ad3c-f37c0f97bb0b | note | FREQUENCY - Prior to construction of wall
11625b47-191f-5f26-8edd-286679c5196d | note | INSPECTION - Document Review
a8fd6dae-39a3-5b1e-bbd7-5a663e5d8f45 | note | RECORDS - FHIMS-QA-6010
791e5c3a-df45-48be-a22e-d24d69e7d33d | signoff | HOLD POINT
e28981c1-3bb4-4916-a336-5c054b6c68a6 | checkpoint | 10 - Construct Leveling Pad
f573ba78-f1e4-5031-9bae-aea87694718a | note | ACTION (Hold, Monitor, Witness) - W
5babdcdf-f294-5695-aaa2-14c17c31ee20 | note | DETAIL - Leveling pad to be 300mm compacted aggregate, can include 75mm concrete topping without reinforcing steel
d9f91965-d7f0-57c3-848d-f15b1b8bb745 | note | FREQUENCY - Prior to gabion placement
24b00337-df77-5007-8620-9046eb5fc2ca | note | INSPECTION - Visual
8bb67f8d-b761-5e17-a894-9d13e06d0c26 | note | RECORDS - Photos
d7cb9886-b416-40af-abfd-a4bc39129f60 | checkpoint | 11 - Construct Wall (1)
ca083c72-c528-56fe-be30-348661f397b3 | note | ACTION (Hold, Monitor, Witness) - W
dca48e3e-53e7-5b18-811a-df2a482d408d | note | DETAIL - Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level.
05ec8a79-1766-500d-a05d-76b35c438a66 | note | FREQUENCY - As required
4ccb3648-4999-5952-b48b-f496451ef501 | note | INSPECTION - Visual
9de6fccd-105a-5dd2-8fec-f37c325c7f0b | note | RECORDS - Photos
c6881381-d202-4ff8-a8fd-a27e7b5a9d30 | checkpoint | 11 - Construct Wall (2)
6ac8e823-4516-5f0f-81bb-51b171279a29 | note | ACTION (Hold, Monitor, Witness) - W
6165a81b-c067-5682-b4de-8808780cfb6a | note | DETAIL - Tie the 1st layer of baskets together using Manufacturers specs for tying baskets
1c683788-4349-5d1b-93c8-7a3d5bd6239a | note | FREQUENCY - As required
5d8a5a99-811e-5c86-990c-0239457a7650 | note | INSPECTION - Visual
cba3590d-b7f4-5032-81ab-f6464d26676a | note | RECORDS - Photos
503dcb63-6ca0-41a5-a79b-968b759becde | checkpoint | 11 - Construct Wall (3)
eb1d049f-4933-51d2-966c-54a041f77467 | note | ACTION (Hold, Monitor, Witness) - W
1df5f692-5981-538f-8015-e2d5f14a8847 | note | DETAIL - Install geotextile filter fabric, strength class C, filtration class 1
ab9fcf84-8f96-52b7-916f-5352eefbc127 | note | FREQUENCY - As required
264f0c5c-c6e2-5b84-951a-4a01dac5ed7f | note | INSPECTION - Visual
2b8a5c44-3dcd-5588-84a4-5c9f97b7313d | note | CONFORMANCE CRITERIA - Geotextile: Strength Class C, Filtration Class 1.
e00c844f-0a46-5599-bb66-77d742c66f62 | note | RECORDS - Photos
d1bd1ed9-fec5-40ec-a1bb-ca095f3a63b0 | checkpoint | 11 - Construct Wall (4)
da8beef2-fc6f-5d41-8742-7f67213a56f8 | note | ACTION (Hold, Monitor, Witness) - W
ec678b96-a733-5f4d-99ec-99cf41e5f8c3 | note | DETAIL - Place first 100mm layer of filter material
faa6a43b-b5e6-5a50-a60b-9830b80412f5 | note | FREQUENCY - As required
faa1885a-60a4-5cd8-8a7c-fc850d461620 | note | INSPECTION - Visual
959eed43-6e36-567c-9fe6-51c490738a95 | note | CONFORMANCE CRITERIA - NZTA F/2
b8c2a438-0943-5409-9961-3aa564d5085f | note | RECORDS - Photos
e5558dd9-0ad2-41cb-80be-6670b49bb49c | checkpoint | 11 - Construct Wall (5)
8d534542-449a-50ff-90ce-200805f88010 | note | ACTION (Hold, Monitor, Witness) - H
c475bdaa-0018-5f65-acfd-784c41708f2a | note | DETAIL - Install subsoil drainage as per FHIMS-QA-6010 ITP for Subsoil Drainage
fb85df39-febd-59aa-915c-7843291ca5b2 | note | FREQUENCY - Prior to construction of wall
b9459202-40c7-5aea-a75a-a703709db5ef | note | INSPECTION - Document Review
8ce5ac2c-774a-5139-8dfe-43c3cd932ace | note | RECORDS - FHIMS-QA-6010
62f5a38c-7ca3-4272-9ec7-47328a49fa6f | signoff | HOLD POINT
b8b735ea-4dc3-4002-92c3-9aacb1b0acd6 | checkpoint | 11 - Construct Wall (6)
4f099e40-713c-5bb3-ac21-56d5388751ac | note | ACTION (Hold, Monitor, Witness) - W
c40f8795-43d3-574c-9ce0-1de1608bc6a9 | note | DETAIL - Install 1st layer geogrid and attach to gabbion basket
6efb3ae5-1ada-5b42-8e98-7bd1680c44c7 | note | FREQUENCY - As required
6a742f24-79b5-51a1-8380-aba15589c273 | note | INSPECTION - Visual
b17b1ade-bffc-5d79-9ebb-2c9e2934f62f | note | CONFORMANCE CRITERIA - Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
133fa09f-f41e-5854-8f6b-654a3368500a | note | RECORDS - Photos
d12a5fec-9c3d-4274-b492-b39d85525819 | checkpoint | 11 - Construct Wall (7)
622cd349-f237-54a0-9f04-4bd9c784f1b8 | note | ACTION (Hold, Monitor, Witness) - W
6499fbff-92f6-5b91-9685-694b398ba113 | note | DETAIL - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square. Tip Gabion material slowly into the baskets to fill the voids as much as possible
c03b03a9-924d-5028-afe8-791f01f2186a | note | FREQUENCY - Every basket
329bf3b6-aa96-578e-af38-7d0cbd0573af | note | INSPECTION - Visual
870adde3-57c0-5a8c-9a1a-ddf29eaafa85 | note | RECORDS - Photos
30afb709-f410-49b3-9e6b-6aa25799698a | checkpoint | 11 - Construct Wall (8)
b9a08636-2011-5ef9-b4a5-40a8740f34b0 | note | ACTION (Hold, Monitor, Witness) - W
3c573522-0648-5618-b9be-8e9ff49870b8 | note | DETAIL - Backfill 1st layer in accordance with the specifications & drawings
87cee917-54e7-56fc-9abd-a10030a7e793 | note | FREQUENCY - 2x sets of NDMs for each 1m high by 3m wide by 20m long layer
497324af-0d33-5853-b95a-3be9e97e073a | note | INSPECTION - Lab Testing
5bf84d4a-d1d2-581d-bef8-92b1a25cb0d8 | note | CONFORMANCE CRITERIA - 95% of Standard or 92% Vibrating Hammer
0e844f29-4ca6-5057-b8b6-c3887d7ddf26 | note | RECORDS - FHIMS-CS-4020
a66390a5-0870-4369-a4c8-55c618501eb9 | checkpoint | 11 - Construct Wall (9)
8b44e3b8-1f88-5223-9a27-e105330686a0 | note | ACTION (Hold, Monitor, Witness) - W
a732f515-4ac2-5138-b922-873d014a770c | note | DETAIL - Tie 2nd layer of Gabion to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
aa85143b-1686-5418-8353-892c26996950 | note | FREQUENCY - Every basket
9b525412-a6dd-544b-982b-eac68c7c230c | note | INSPECTION - Visual
bde39b2d-7702-5b32-babb-d38165af24ac | note | RECORDS - Photos
5ab6f013-8efb-415a-8115-0f6d0c7562d2 | checkpoint | 11 - Construct Wall (10)
48a7743e-3e64-573f-8d5e-28156c4d37d3 | note | ACTION (Hold, Monitor, Witness) - W
b385d467-762b-5ad1-a2b5-407f7d5dcb58 | note | DETAIL - Install 2nd layer geogrid and attach to gabbion basket.
f3b20b87-1d4e-5ea5-9062-640d66af0394 | note | FREQUENCY - As required
9decd04a-b1bc-5ed6-a85e-4de4443cc4b2 | note | INSPECTION - Visual
a69c9fc1-721f-577e-8968-bdfccf19848a | note | CONFORMANCE CRITERIA - Uniaxial Geogrid: Tensar RE510. Biaxial Geogrid to have same unltimate tensile strength as uniaxial - 16KN/m, 100 yr design life
a1d1111e-7420-5330-b351-e5ebbca0c981 | note | RECORDS - Photos
5e091d00-300d-42db-9ea2-5b06cb45304b | checkpoint | 12 - Survey As Built
8872f091-d3b0-5d6a-8ffc-0dec410d01b1 | note | ACTION (Hold, Monitor, Witness) - H
f2164975-6800-5e3c-9de7-9c1a7ff7d4fb | note | DETAIL - Ensure all works comply with design prior to carrying on with next construction process
0b3b45e1-38ae-5407-ac73-32b3f83a8d57 | note | FREQUENCY - At completion of sub soil drainage line and each gabion layer
dd0b8ef2-92f4-5dda-a54e-3f22270f3159 | note | INSPECTION - Survey
b8c38999-ac12-5330-9579-af68c196d24c | note | RECORDS - Survey receipt
e1c84beb-8834-497a-9cc4-7efcb5d51bdd | signoff | HOLD POINT
37f6a4ba-b59b-4aa2-84c6-8f48708fc128 | checkpoint | 13 - As-builts
199d099c-995a-5812-9d34-2711077fea39 | note | ACTION (Hold, Monitor, Witness) - H
98a1637a-0ff2-5ad1-b296-ee67c2d27b06 | note | DETAIL - Red pen mark up drawings to be included in QA file
4bfc0a66-be1d-591e-8e97-fc1fb3f06d65 | note | FREQUENCY - At the completion of the Lot of work
f0fb34c0-535c-51a1-b4ab-065f77d6f095 | note | INSPECTION - Drawings
6a827274-0984-593e-a95d-7c03c88cf6eb | note | RECORDS - Asbuilt Drawing
e3b4c42f-9c4f-4a9a-a841-1665d899c961 | signoff | HOLD POINT
5e99fd09-806d-4caf-b394-43966fc80b51 | checkpoint | 14 - Lot Number QA File
cc01a392-130a-5030-ba52-19358475f236 | note | ACTION (Hold, Monitor, Witness) - W
178a9341-8458-514d-ab32-526872141cfb | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
0e2ce2e6-4fc6-5448-9da4-0808047e724d | note | FREQUENCY - At completion of Lot
769da84f-08b7-5786-87eb-0d2a564dacc0 | note | INSPECTION - Document Review
6d24746b-9cb6-5908-8c37-e5b225296a48 | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
2f445e4c-5971-53f8-8f4d-8f5d7376b358 | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
5e146243-08f9-4f48-9667-a66d1377c1f9 | checkpoint | Final Inspection
e58efab8-4cd9-5f45-baf0-c746a999399a | textbox | QA Compiled By:
e3a1ed85-78bd-5dec-940d-aacf158bc627 | textbox | QA checked By Discipline Manager:
952bb7f4-d2a7-5de7-8933-1cf927483e98 | textbox | QA checked By Quality Manager:
f1721b32-8199-5231-8190-d61f8f503c5b | textbox | Accepted By Design Engineer:
f5683ceb-8dfd-53cb-86b9-4224492c4beb | date | Date:
25b80b51-5850-4578-9f89-a61f1e1a1c25 | signoff | Sign ITP
43bfc9a0-d359-41a8-bad6-2cc8f9b8239b | checklist | FHIMS-QA-6038-ITP-Steel Fabrication & Painting | itp | FHIMS-QA-6038-ITP-Steel Fabrication & Painting
5ede0252-4fd5-4fd9-b4c1-9458f26fa570 | section | Steel Fabrication & Painting
3f833009-26cf-4001-9a4d-f2d410a7c09a | checkpoint | 1 - Design
5e6a3e6a-0bdc-50ea-b918-bb673eb117a1 | note | ACTION (Hold, Monitor, Witness) - H
0409d476-0cc5-52c1-be1b-28a3525a82ce | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
7b29034e-3f2a-524d-93ed-6bd5860307e2 | note | FREQUENCY - Prior to commencement
3bd572c0-493c-5ddc-a3eb-9ec24f05de3c | note | INSPECTION - Document Review
00f9ca1f-59c6-5611-9066-168a955effd3 | note | RECORDS - Check Drawing Register
81636f25-f439-462c-8fcb-1c271911973f | signoff | HOLD POINT
69683cce-4826-42b4-ad62-2f7b8d0ecc84 | checkpoint | 2 - Shop Drawings
a9832c1a-d8d0-5741-8226-86022ef07965 | note | ACTION (Hold, Monitor, Witness) - H
df5d007c-2240-57fc-8105-42f5b1a8e1ff | note | DETAIL - Shop Drawings have been created by the Subcontractor and approved by the Design Engineer before any fabrication commences
b7fdbaf8-6c9f-5854-a77d-e713e288602b | note | FREQUENCY - Prior to commencement
029e3db6-5c2d-51b3-bb38-c72f1fd73a4a | note | INSPECTION - Document Review
d419fdae-33c2-52f0-b5fc-df2dd369417d | note | CONFORMANCE CRITERIA - Shop Drawings
c0e5e553-d9fb-45a2-948e-b4b46b9d6222 | signoff | HOLD POINT
9f6d98bd-059b-4b5a-8835-46b8a0fad3e3 | checkpoint | 3 - Material Compliance
52c53967-c44d-58af-85d5-50efb6738402 | note | ACTION (Hold, Monitor, Witness) - H
e733bd65-5643-551f-af0b-55219f441890 | note | DETAIL - Subcontractor to supply all material compliance certificates for materials used in construction
7befe452-2717-55ae-8a9d-a01e3727fe9f | note | INSPECTION - Document Review
dc347e1b-71ae-5eb8-8014-19a2c828e900 | note | RECORDS - Subcontractor QA
a37b4a8b-3071-4577-a42c-e87ce15ddfef | signoff | HOLD POINT
a81e4f8d-8e47-4654-8083-0d7a1a58add5 | checkpoint | 4 - Welding (1)
3464bfa7-8b49-5d52-8757-2b1dd996ee27 | note | ACTION (Hold, Monitor, Witness) - H
0c667cd0-7538-519f-b93d-046d1727f20e | note | DETAIL - Welders Qualifications to be supplied
87b02e33-3333-56bf-90cc-98020f0fff99 | note | FREQUENCY - Prior to commencement
39ce70b6-0e4f-59d9-9ccc-fdf121ee8380 | note | INSPECTION - Document Review
e719d598-2410-5334-841c-0e9c2a618c07 | note | RECORDS - Subcontractor QA
56dabcc0-9a24-4a8c-b0a2-0ec7afcaed88 | signoff | HOLD POINT
aa2a0a02-5deb-42fc-ba8a-22b4de97a747 | checkpoint | 4 - Welding (2)
374e63d6-5dfc-5e98-b4c6-91959c27fe79 | note | ACTION (Hold, Monitor, Witness) - H
f5485337-4496-56a0-b2ec-3b73de4e49d1 | note | DETAIL - All welding procedures and testing of welds to be reviewed & approved by Design Engineer before commencing construction
9f61c86a-a99f-5828-a040-7465dce84566 | note | FREQUENCY - Prior to commencement
0e92a2ac-7cf1-5396-a7a7-6d51dbbeec38 | note | INSPECTION - Document Review
0822f288-db07-5654-807c-31fa113599d5 | note | RECORDS - Subcontractor QA
91ccd68c-d9dd-4c03-bfb9-29e9d5b91ed9 | signoff | HOLD POINT
77a8a7ca-bdc8-4809-a60d-c13a6461e6b2 | checkpoint | 5 - Fabrication (1)
6b29fcc3-1a23-5395-b1dc-f71b377602a8 | note | ACTION (Hold, Monitor, Witness) - W
0fdc30ca-ca79-5d9b-9654-22ffbe815aa3 | note | DETAIL - Cutting of Steel - checking the steel grade, dimension inspections and ensuring there are no snags on the edges
71bb77ee-16af-5451-9111-c3af8f01014f | note | FREQUENCY - During Construction
785cbb6e-913b-55af-9cea-b564f4d6284c | note | INSPECTION - Visual Inspection
9aab379f-0acb-56be-a746-81c208c63596 | note | RECORDS - Subcontractor QA
377f5688-d4f8-4736-b902-b91f969725d5 | checkpoint | 5 - Fabrication (2)
c3c69556-4b16-5615-bb0a-eb87ed6fd317 | note | ACTION (Hold, Monitor, Witness) - W
efd04315-96a1-568c-b126-35620d230155 | note | DETAIL - Drilling of hole layout - checking dimensions & de-burr inspections
206e8115-f5c8-55b2-a7e9-ee2fecaba029 | note | FREQUENCY - During Construction
8955b156-5304-5183-a504-8baef401050d | note | INSPECTION - Visual Inspection
7c338153-fcaa-5d2c-a74d-2310b6a51376 | note | RECORDS - Subcontractor QA
a905daf4-55f6-4fce-bed2-889232e8abe7 | checkpoint | 5 - Fabrication (3)
ba075a62-37f2-5bc0-851e-4a29a1e304d5 | note | ACTION (Hold, Monitor, Witness) - W
bcefcd39-5594-59dc-b40a-1359c7ad1d8d | note | DETAIL - Weld stiffeners - Non destruction testing carried out, fillet welds checked and tested
7c3de3fb-3183-50cd-9f44-1c25430bc6c6 | note | FREQUENCY - During Construction
96a766e8-a3e9-5c2c-89aa-fc36751cb213 | note | INSPECTION - Visual & Measured Inspection
bb06a06d-4195-511d-91fa-640de0601d92 | note | RECORDS - Subcontractor QA
fd473086-74fa-44c1-b1d9-f1291feeed9b | checkpoint | 5 - Fabrication (4)
3ec1c91f-1388-5732-b035-efe30cde4c4f | note | ACTION (Hold, Monitor, Witness) - W
2d7dbe47-5cce-5c50-95bb-8e6034a7c60a | note | DETAIL - Stud Layout & Welding - Ensure correct specification & correct positioning
a995a33c-320e-5ad2-8c73-7d66d985f712 | note | FREQUENCY - During Construction
51e30bf2-929d-5553-906d-0bf1df75c134 | note | INSPECTION - Visual & Measured Inspection
bf240f35-2547-5276-8de2-6c2985f137ea | note | RECORDS - Subcontractor QA
d2530427-ba52-4dc5-a852-442a3447726c | checkpoint | 6 - Surface Protection (Painting) (1)
8e2cf910-e6d6-5c27-a5ad-f1cfcfb95d94 | note | ACTION (Hold, Monitor, Witness) - W
f5c6a360-9965-5924-9e6c-de28c9362a99 | note | DETAIL - Surface Preparation - final check for sharp edges, weld splatter and that all holes have been de-burred
d411d686-3eb2-5066-9ee2-33d8fac2a003 | note | FREQUENCY - At Completion of Construction
26f4880d-ade8-58d8-8ea8-f9af67325334 | note | INSPECTION - Visual Inspection
efdbf49a-7c63-5307-a8d1-a8b235390c69 | note | RECORDS - Subcontractor QA
11a7a036-c2cb-4c52-82a1-092dc95e3643 | checkpoint | 6 - Surface Protection (Painting) (2)
187066f0-a3df-5060-bc20-2377fd815ffe | note | ACTION (Hold, Monitor, Witness) - W
d64f4ace-e63d-5e85-ab96-5b203d3912e8 | note | DETAIL - Abrasive Blasting & Seal Coating
d3a38ed3-e091-5a54-8018-d111ee531a34 | note | FREQUENCY - At Completion of Construction
e363cab8-4997-547a-b04b-9fca50aadf92 | note | INSPECTION - Visual Inspection
3685724c-b596-5bba-aa5d-42b2b1dc785b | note | RECORDS - Subcontractor QA
ff7d303f-500a-421e-8208-2d1a437df317 | checkpoint | 6 - Surface Protection (Painting) (3)
0c87475b-b355-5bae-9e72-f213849daea7 | note | ACTION (Hold, Monitor, Witness) - W
d6286435-ee62-5a3c-a149-9ae0f2e3288e | note | DETAIL - Post Primer Inspection - check that it meets the coating specification
8b7f7fee-7595-5ac8-a8eb-bd47db0c628f | note | FREQUENCY - At Completion of Construction
26f36d8e-c055-5e0e-9d9d-99d6af5c6096 | note | INSPECTION - Visual Inspection
9d031b25-6198-510e-9ba9-a6002efc2bfc | note | RECORDS - Subcontractor QA
3af9197d-c85f-4dc8-ba1d-a296b31a8b3e | checkpoint | 7 - Delivery to Construction Site (1)
190898e0-94f8-59d4-9b29-4695c3104c91 | note | ACTION (Hold, Monitor, Witness) - H
b4e168c9-8c70-564e-8665-8a1f86979755 | note | DETAIL - Ensure that the laydown are is prepared for the arrival of all of the steel components. A TMP is in place and the STMS is briefed as to when deliveries are scheduled to arrive
1008d969-0e1e-5eb7-b1bb-a6407b318515 | note | FREQUENCY - Prior to delivery
1a956649-de7f-5dc9-9f72-343c72d0ebef | note | INSPECTION - Visual Inspection
d2da77c9-8430-58f0-8f79-9b69edc957f7 | note | RECORDS - Subcontractor QA
7390158e-cc98-4745-9efa-453e5c0771a4 | signoff | HOLD POINT
3ad402d1-2702-4976-a733-1952ed71b418 | checkpoint | 7 - Delivery to Construction Site (2)
8dacb21b-bba6-5e53-8886-449ab6aacc02 | note | ACTION (Hold, Monitor, Witness) - H
7895a630-f64e-5f49-9312-0cc5810462b9 | note | DETAIL - Permit to Lift (Lift Study) carried out and lifting crew is prepared for the deliveries
0564b8da-7f03-58a8-a0af-24c743c173b7 | note | FREQUENCY - Prior to delivery
6bfc4b37-5e61-5ebb-a0c0-395e5b455c92 | note | INSPECTION - Document Review
8c64b74b-b9aa-54f6-97b7-4e454ef3e976 | note | CONFORMANCE CRITERIA - Permit to Lift (Lift Study)
5fbd77ab-5200-5e75-9290-13a9801e705a | note | RECORDS - Permit
7a0e9eee-c099-4e02-83f1-f55b8b83c305 | signoff | HOLD POINT
79d7b0ee-15f6-4a7b-bc3c-f530243e5186 | checkpoint | 7 - Delivery to Construction Site (3)
82fc4cbf-646d-5fa3-a976-8d35dde800d8 | note | ACTION (Hold, Monitor, Witness) - H
a7e66907-c1fa-5d83-b2a5-30f81e777195 | note | DETAIL - All delivery dockets to be supplied and collected as materials arrive onsite to ensure the correct materials have been supplied
30cff850-bdae-577e-b4f8-1457f2bcf633 | note | FREQUENCY - During Delivery
40cfa9e0-7de7-5f9f-8107-e4ea809bf7b0 | note | INSPECTION - Document Review
12972167-648b-5dd7-9003-5468740b8476 | note | RECORDS - Delivery Dockets
5a8b417a-382b-49a1-b4b5-1f0714dcefaf | signoff | HOLD POINT
a9d7b1d4-4ca8-4a51-b201-39937dfab82e | checkpoint | 8 - Lot Number QA File
fabdc30a-5502-5577-991e-2f0e72a31e3f | note | ACTION (Hold, Monitor, Witness) - W
18d71a23-fe9b-5895-82f4-144f9b4244a4 | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
b5a59d85-5718-5a53-9b5c-4e6892b24f39 | note | FREQUENCY - At completion of Lot
99846f26-e4a3-5fc7-8749-1e44e718cd89 | note | INSPECTION - Document Review
421b46c6-8f85-5682-95ea-721c65f6e1e1 | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
0a4ad0fd-547b-57bb-8d37-8796c175b3c6 | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
e6cd9d81-4835-4216-8277-e4f53587b61f | checkpoint | 9 - As-builts
0ba56043-ec6b-55ea-b8dd-ac26fc1bdc30 | note | ACTION (Hold, Monitor, Witness) - H
03cc61e7-a3d1-5dc8-ba62-e3ca01f7c3fb | note | DETAIL - Red pen mark up drawings to be included in QA file
907e15e4-58ca-5873-8b4b-ea0540122208 | note | FREQUENCY - At the completion of the Lot of work
90f680c6-4bb9-5183-8914-fbf14b88aa13 | note | INSPECTION - Drawings
0cb78546-eb15-5ef2-8fd9-5ac5c9801f28 | note | CONFORMANCE CRITERIA - Ensure all Asbuilts uploaded into CONQA
7321a053-d047-5732-b887-b2a914ecfaa4 | note | RECORDS - Asbuilt Drawing
44d9ed09-4344-4b2c-a3c1-8bfa1f56008c | signoff | HOLD POINT
e7c120cd-718a-489a-b587-3b2c717e7298 | checkpoint | 10 - Lot Number QA File
53c6ecdb-68f0-5f98-9b4c-87e0cb11bb9b | note | ACTION (Hold, Monitor, Witness) - W
7ddd87db-4e96-5919-9bf4-124765249ab2 | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
673e99fa-cd0b-51c5-bc17-d72e422e9fab | note | FREQUENCY - At completion of Lot
577707e1-ec0f-5ede-966e-3904ae5cab4c | note | INSPECTION - Document Review
8e9e5a8a-3750-565e-bc4f-1c654e0dada1 | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
fa90608d-26ed-5668-b54c-321b38b48ff6 | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
520c65c5-ee7e-4472-a5c5-d8c28eaa2257 | checkpoint | Final Inspection
988e6ce9-29dc-5530-ad78-e65f306e7feb | textbox | QA Compiled By:
ee0bf297-76fb-5e09-927e-c6f73472f5e2 | textbox | QA checked By Discipline Manager:
fe258d8c-1961-553a-affa-79f10677cf27 | textbox | QA checked By Quality Manager:
ffd49021-9f40-5fe0-acd1-138a6d93e8dc | textbox | Accepted By Design Engineer:
e47a60f9-61c0-59b6-a2d4-f70224db1afe | date | Date:
70d7c8be-7126-41ec-800b-ab419b97e74a | signoff | Sign ITP
1272694f-3ce7-4951-b311-ab5773f293b2 | checklist | FHIMS-QA-6040-ITP-Precast Installation | itp | FHIMS-QA-6040-ITP-Precast Installation
9f02c030-1526-4065-b1a0-d752ed6b0fef | section | Precast Installation
056503ef-eb88-4a0f-b1d6-0371d5586427 | checkpoint | 1 - Permits (1)
09f51ef2-6906-59c4-99ca-44266440fe6a | note | ACTION (Hold, Monitor, Witness) - H
58f81c74-b1df-59b5-94ba-601f65566584 | note | DETAIL - Obtain Permits
d7106f90-47b4-570c-8254-75b6314e9143 | note | FREQUENCY - As required
ed481733-a3f6-5f70-85be-a4e8b006aa90 | note | INSPECTION - Document Review
11fbc64c-d19c-55b6-afe7-ac7e1a1dee0a | note | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
0347a7d2-1e41-5219-b10c-bcecfe0c6aa6 | note | RECORDS - Permit attached or permit number noted
343b6225-2d8e-4903-887b-09e6a7940335 | signoff | HOLD POINT
b87aa85e-0059-41d7-bc51-c744685721b2 | checkpoint | 1 - Permits (2)
0c83096f-7207-505d-8ee0-17c347b9c937 | note | ACTION (Hold, Monitor, Witness) - H
4a9f3b27-0499-5006-9fb7-f0affef41587 | note | DETAIL - Permit to Lift &/or Lift Study to be carried out
2a9a16b8-c310-5335-82f6-84c26044b303 | note | FREQUENCY - Prior to commencement
a89b882b-818a-57d1-9a60-2e9b67588da9 | note | INSPECTION - Document Review
2b726bf2-4c9b-5bee-ad2b-df31da92c976 | note | CONFORMANCE CRITERIA - Approval given by Construction Manager
1c429e8b-23da-5fb6-a819-b83acadb7087 | note | RECORDS - Permit to Lift
bdc0beff-a180-4285-8a4c-94f8e313e5dd | signoff | HOLD POINT
e17d05c9-e197-4d84-8d23-7922ab80455a | checkpoint | 2 - Design
d5aa781e-3be4-5874-ac79-19782238d799 | note | ACTION (Hold, Monitor, Witness) - H
40118656-05ef-5e9c-b576-d5fc8003e31a | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
a9cc6f2f-3e5f-5a71-9d85-e7bab286bd8d | note | FREQUENCY - Prior to commencement
66dedc7c-f179-5050-ac9d-4350c168e7eb | note | INSPECTION - Document Review
9f1368dc-eff7-508f-8ba1-25815a47661c | note | RECORDS - Check Drawing Register
0c068f89-0190-4f2d-9e50-3160b22582b1 | signoff | HOLD POINT
665d9931-a06d-4179-85bc-9edb3f9ba3b0 | checkpoint | 3 - Survey Setout
cbc4d32e-05cc-5b0c-8620-a55b43122e3c | note | ACTION (Hold, Monitor, Witness) - H
4314a060-0f32-5b45-892c-5e4f74534272 | note | DETAIL - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
f666852a-5db2-5ed2-9a87-c6d807bf21dd | note | FREQUENCY - Prior to commencement
26b9ce22-fa6e-52bf-baa4-375c9ea05a3e | note | INSPECTION - Survey
2f4b6e8e-4791-544b-b592-87251e7309bb | note | CONFORMANCE CRITERIA - Consistency with Construction Drawing
0903c9f7-a987-55ae-bd89-8e8c2ea3d143 | note | RECORDS - Survey receipt
f24a2f2e-cce6-4641-a507-3e5a60193907 | signoff | HOLD POINT
c0cfe4cb-f18c-4821-8a78-82c69865ce93 | checkpoint | 4 - Precast Installation (1)
54aef3cc-6ef3-523a-a023-2a7ad79046b1 | note | ACTION (Hold, Monitor, Witness) - H
83c0039b-20dc-5317-b254-16104e80074a | note | DETAIL - No Precast Components are to be installed until FHIMS-QA-6049 has been completed and signed off for that item
d1c00b69-434a-5f64-9404-d2b2ea71212c | note | FREQUENCY - Prior to commencement
a8694eee-c399-5b8a-88d9-c3fd8ef5ca5b | note | INSPECTION - Document Review
35f65106-a45e-5f84-b40b-47adacee20d9 | note | CONFORMANCE CRITERIA - Process Control Plan, Checksheets & any other associated documentation is provided
7a25dff6-d13f-5bea-a559-106ebaa8d47c | note | RECORDS - FHIMS-QA-6049
b6d655a0-920d-4fbc-9109-32da8732d628 | signoff | HOLD POINT
187215c5-2ae7-435f-8472-24780b0e2fea | checkpoint | 4 - Precast Installation (2)
5247b98d-369c-53fc-b65d-9b9a3922203b | note | ACTION (Hold, Monitor, Witness) - H
75c1401c-bbd6-5b0b-b0f6-27200449789e | note | DETAIL - Delivery Dockets are collected and signed before precast materials are removed from the truck
ef4118e6-0d12-5772-b797-ca2d7f0c702e | note | FREQUENCY - Prior to commencement
62e73f9a-790f-5f88-b637-2502c8e62459 | note | INSPECTION - Document Review
24e7e4fa-bbf1-59d9-9823-4255881de6d8 | note | RECORDS - Delivery Dockets
7d9bf68f-adab-4063-96c7-14c1b06e48b0 | signoff | HOLD POINT
a66b2705-d9fc-48b8-8e18-14e93e8c481a | checkpoint | 4 - Precast Installation (3)
43c42585-d42b-5aa0-91e3-77918be8b1b5 | note | ACTION (Hold, Monitor, Witness) - H
dee08d52-a095-53a9-b195-1cfa6c2b5526 | note | DETAIL - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial to be done by the manufacturer onsite & an OFI to be completed
262af6a3-621c-5fcb-994c-f67080119dd9 | note | FREQUENCY - Prior to unloading
2215e332-70dc-5e6b-a4e7-66477cf826a1 | note | INSPECTION - Visual
8029f576-0720-5688-bc07-77b0a65d28ce | note | RECORDS - Delivery Dockets
6347b52a-a2c0-4d82-95bb-60e722b5d664 | signoff | HOLD POINT
61591758-7b19-46f9-96ab-5ad988d95f00 | checkpoint | 4 - Precast Installation (4)
c79bebc3-b592-5fe4-a1d1-5e417f1e349a | note | ACTION (Hold, Monitor, Witness) - H
ee416f53-847d-5523-ad5b-9fcdbbf1492f | note | DETAIL - Ensure that other components are installed correctly (bearings etc.) and are approval given from Designer team before precast components are lifted into their final positions
99316615-1c42-51e5-9041-62515e351370 | note | FREQUENCY - Prior to commencement
78f651f1-e5a1-52a5-8986-de155ce01d20 | note | INSPECTION - Document Review
215ece0c-0ff6-454e-8606-238573cc5dfa | signoff | HOLD POINT
f84c28e8-f184-4cf2-b1b7-562020423cbe | checkpoint | 4 - Precast Installation (5)
afb79479-cad0-58ef-ba1a-dbf710772a53 | note | ACTION (Hold, Monitor, Witness) - H
d88f1ba7-3eed-57d7-bed7-e3cf33953425 | note | DETAIL - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the risk control plan
950683d4-51df-5998-8825-9f64dbb0085c | note | FREQUENCY - Prior to commencement
5298436e-a1f5-5825-b6dd-84a23b81def5 | note | INSPECTION - Document Review
49e48db7-c365-5fc1-99ef-30d4d3a901f7 | note | RECORDS - RCP
000f34e2-03fc-421f-926f-dd441111c8ad | signoff | HOLD POINT
ce3197b9-351a-45e6-bae0-cfe25e6bb8fc | checkpoint | 5 - As-builts
8824cd58-2c23-5a8b-94e1-c70eb30b81b6 | note | ACTION (Hold, Monitor, Witness) - H
10cbe103-d51a-53f3-a778-6d91df0a96b3 | note | DETAIL - Red pen mark up drawings to be included in QA file
5f0eff8e-d470-5487-9d51-9f287cf589fc | note | FREQUENCY - At the completion of the Lot of work
a5908d74-1ab1-5690-8009-f5c45bc12295 | note | INSPECTION - Drawings
aa9a4d2d-6e59-573d-886f-a21ffa4e8ebf | note | RECORDS - Asbuilt Drawing
83aaa2c8-7bd5-4d64-a501-a811451d5e05 | signoff | HOLD POINT
efb5397e-0e13-4051-a349-b84b8bc0ccd7 | checkpoint | 6 - Lot Number QA File
52902dbd-6534-56b1-8a87-03f2a58ff0ab | note | ACTION (Hold, Monitor, Witness) - W
a8cdb45c-f148-562d-a390-615e5ab38153 | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
b70416c9-98bb-5b46-ac6e-452cee8955ea | note | FREQUENCY - At completion of Lot
743724ad-41b5-5e5a-9cc9-a47508eb2e31 | note | INSPECTION - Document Review
88ef9336-db17-54bb-a4ec-bdbf572c09db | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into CONQA
eb94b170-904b-5498-a9e3-1c0d5c1fe4fb | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
06479c38-d176-455b-a289-356a1f4c81b9 | checkpoint | Final Inspection
1b3afe56-44f1-591e-bf03-143a56d855f9 | textbox | QA Compiled By:
d941acf0-cd78-5cb2-88aa-bdea581a3e92 | textbox | QA checked By Discipline Manager:
0149b4e9-c854-5b8a-8ccf-fd846d7b4e39 | textbox | QA checked By Quality Manager:
4e9eed77-e657-5352-93b7-bc1cf21a6f98 | textbox | Accepted By Design Engineer:
b0583ea0-ffc8-571a-b1f0-014adb98ddae | date | Date:
b92a901a-4cbd-44ae-8dd4-940767ef6b9e | signoff | Sign ITP
5da2e26a-308f-48e9-81f6-b050e14260de | checklist | FHIMS-QA-6049-ITP-Precast Concrete | itp | FHIMS-QA-6049-ITP-Precast Concrete
6f5f9b95-e54d-481f-9abe-1c25e094dcf3 | section | Precast Concrete
7f521a88-ce0c-4dc2-bc79-cd773761e89b | checkpoint | 1 - Permits
9611f42e-e89a-50e4-aebe-34dae47e7ac4 | note | ACTION (Hold, Monitor, Witness) - H
6aa60e2b-a386-55c9-a245-e94dc1f27766 | note | DETAIL - Obtain Permits
89519006-0fa3-5493-91f8-1f59fdf90f94 | note | FREQUENCY - As required
962f54d6-2d7b-5206-9d60-bcf81d39827e | note | INSPECTION - Document Review
2c3bd81c-96d9-5902-a77c-f93a04b3acd0 | note | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works & Controlled Checklists are in place
fbcb5f4f-328f-5884-85da-c57eb71ce519 | note | RECORDS - Permit attached or permit number noted
8d7ec899-40e6-4484-bf10-2748b2f1eab5 | signoff | HOLD POINT
a4e3d28d-0a11-4c68-b7ce-86a95e9bab09 | checkpoint | 2 - Design (1)
a21fb8d2-926d-5883-a11d-6718e8501e6a | note | ACTION (Hold, Monitor, Witness) - H
1ae233ba-9cdf-5d04-8dbf-dd9288f4616b | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
a8e7e975-39e2-5607-8e39-750aa93804c2 | note | FREQUENCY - Prior to commencement
f04ddd51-182f-5470-8cb0-4cb60a1e5a03 | note | INSPECTION - Document Review
c63c9c6e-fa6b-5d99-b9b2-16334f18fde2 | note | RECORDS - Check Drawing Register
f1234a59-894b-49f5-898c-5eb86583bb11 | signoff | HOLD POINT
7eecb66e-3c45-403d-a21c-0f159e7e10d5 | checkpoint | 2 - Design (2)
f8bbb2cb-c822-52d6-adb0-db6a7ef4c740 | note | DETAIL - Produce Shop Drawings and Submit for approval
51ca00e0-a689-557f-962f-83b82ad50ea9 | note | FREQUENCY - Prior to Commencement
f51b8911-99ff-542e-8f85-4e9ab12ff0d9 | note | INSPECTION - Document Review
b1cc25a5-e317-5a7e-b92b-02e6331588bb | note | CONFORMANCE CRITERIA - Drawing Register
bd8cf9d0-3e52-5cba-bfa0-844d920dc9ed | note | RECORDS - Check Drawing Register
e699165a-53a2-43d3-b7f5-f059cc409cbe | checkpoint | 3 - Survey Setout
e63cb5ba-503e-52dc-9f66-f973e998795e | note | ACTION (Hold, Monitor, Witness) - H
0608d272-e00b-516b-944e-45bd2dd6570b | note | DETAIL - Formwork / Mould to be setout to be inspected by Site Engineer prior to concrete being poured
9f10919f-3ef7-5cea-93c2-0bbcd146995e | note | FREQUENCY - Prior to commencement
77da7f55-ffcd-5fca-9539-81038a3ca9f4 | note | INSPECTION - Visual Inspection / Measure
2f3c44dd-c0ed-5a68-935c-a2a87d9ca2f2 | note | CONFORMANCE CRITERIA - Consistency with Construction Drawing
0e8c28a6-c47d-588f-ac6e-438c2178b6b3 | note | RECORDS - FHIMS-CS-4008
ff4f4341-be31-4d1e-b331-dc8e8afa7141 | signoff | HOLD POINT
ae91cdbe-571f-40a9-a129-25b04ac4f4df | checkpoint | 4 - Material Compliance (1)
03bb0454-0483-5f88-955f-0da8824db62b | note | ACTION (Hold, Monitor, Witness) - H
a376a65f-da63-514a-8434-7a2a40b5147f | note | DETAIL - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete
17df00ba-32ca-5810-8912-7106637fc3ec | note | FREQUENCY - Prior to commencement
997c428c-0113-5336-a956-53a0e29f4b07 | note | INSPECTION - Document review
a439053d-c0e1-5d37-8e50-be3734a498d0 | note | RECORDS - Design Engineer Approval
fcdce533-e6b2-4999-ab63-9c0a3e4e0d42 | signoff | HOLD POINT
52c1527d-078d-456d-a631-3a0183752bb7 | checkpoint | 4 - Material Compliance (2)
242bf8e9-96fc-5270-9030-25dfa0d2f98a | note | ACTION (Hold, Monitor, Witness) - H
8bacbb9f-691a-5d06-8bbb-e2bd73a0b0d8 | note | DETAIL - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
4ee891fb-3cab-5b17-ae4d-ab4d8b60599a | note | FREQUENCY - Prior to pouring concrete
e0dc749e-26f2-573b-82ad-7437cc1e7efd | note | INSPECTION - Concrete Delivery Dockets
8f48907a-1dd9-5afc-b867-388b6d4e9409 | note | RECORDS - Concrete Delivery Dockets
76152f82-90c4-47ec-9bd7-c8d652538876 | signoff | HOLD POINT
6be6f62d-2446-438c-b5f1-70d37c1c84fe | checkpoint | 4 - Material Compliance (3)
1cb1370c-01b2-57a2-a52c-72f84627d33e | note | ACTION (Hold, Monitor, Witness) - H
d8604b81-5d72-57da-ae37-4fcc12cd4370 | note | DETAIL - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
7a34e41e-e2a2-5e68-9d46-48a3e47314e8 | note | FREQUENCY - Prior to ordering steel
24629666-50f0-5f84-8fce-866548161ea1 | note | INSPECTION - Document review
e4df38c3-0728-5304-a677-71acd6479d1e | note | CONFORMANCE CRITERIA - AS/NZS4671&NZS3109
cafd3591-c863-5b94-85a0-7ff84a5343ca | note | RECORDS - Detail Sheets and Mill Certificates
4f67146d-c65e-48df-ab74-3636eeacb719 | signoff | HOLD POINT
f3e2f303-bfe3-4dfa-a892-ca1e8f17f0f0 | checkpoint | 4 - Material Compliance (4)
3ebbddd1-52f3-5b44-9370-098499f400f1 | note | ACTION (Hold, Monitor, Witness) - H
f968d921-dc09-5a56-b30f-56e1325d5a9f | note | DETAIL - Any welding or mechanical splicing to be approved in writing by the Design Engineer
8e8f1330-93c4-56c3-8bc4-23521e684222 | note | FREQUENCY - Prior to welding or splicing
7af22bd9-bef1-5370-b0ee-a311e36e0a71 | note | INSPECTION - Document review
2f68c39b-de70-58d4-bf83-5d81da6499c7 | note | RECORDS - Mark Up As Built Drawings
cb320893-d981-42a3-b3f1-0bfb023a0f4b | signoff | HOLD POINT
16695a5f-4191-41aa-aa10-0774a924f380 | checkpoint | 4 - Material Compliance (5)
837054ce-3a58-5901-b673-ef3ccd087a74 | note | ACTION (Hold, Monitor, Witness) - H
dcfcbe30-f608-5b08-beb8-a055e5649654 | note | DETAIL - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
150d3d21-acef-5c20-85d8-17d18a813c9a | note | FREQUENCY - Prior to cutting or bending on site
21d898e2-3f6f-55e5-8013-8d1dde34ab6a | note | INSPECTION - Document review
cec9b1eb-3d00-543c-ba9c-4789baba5931 | note | RECORDS - Mark Up As Built Drawings
ef2d4021-fbf8-4a49-8452-7bb50313e532 | signoff | HOLD POINT
94d6b70b-a21d-474b-bd1a-fc7e6e3b0aa6 | checkpoint | 5 - Reinforcing (1)
1d8f373b-cf03-5e10-a22f-7fa8029ef432 | note | ACTION (Hold, Monitor, Witness) - W
6bfc8c2a-4733-59c5-af06-0ec308da4ca3 | note | DETAIL - Reinforcing steel shall be handled, placed and fixed as per NZS 3109
5fec9056-3157-509c-8750-ce72a63ed12d | note | FREQUENCY - Daily Visual Inspection
476c52fa-af56-5e50-b3f0-505a69066097 | note | INSPECTION - Document review
029f788b-759a-5481-b60b-f2b6d131dd07 | note | CONFORMANCE CRITERIA - Concrete Inspection Record
06acf184-ca79-5128-a24c-4c48d66d78d2 | note | RECORDS - FHIMS-CS-4008
4f2ab18f-550a-4b9c-b030-17910ec1e567 | checkpoint | 5 - Reinforcing (2)
120e571e-6f8f-599f-9f2e-c129a1c0afe2 | note | ACTION (Hold, Monitor, Witness) - H
e19754e4-8eaf-53ae-9c7e-c1c9ef85a817 | note | DETAIL - Check Finished Reinforcing cage to ensure correct spacing, grade, diameter and number of bars
703d565b-4b9d-5e3b-8780-d31aebc9bd7e | note | FREQUENCY - Prior to concrete pour
afc381e7-5512-51ea-80dd-4a9138f3a67c | note | INSPECTION - Visual inspection
d5a8af46-4657-5c64-966b-885843ba71fb | note | CONFORMANCE CRITERIA - Concrete Inspection Record
49373af7-52a9-569b-af85-5d3abe174191 | note | RECORDS - FHIMS-CS-4008
a6bbaa91-cad8-4284-b642-9366f9ddf211 | signoff | HOLD POINT
392c0a2c-caca-49c3-8213-f5055290ef2c | checkpoint | 5 - Reinforcing (3)
d7e44e5e-1cdf-5a31-9d97-c08f32def76b | note | ACTION (Hold, Monitor, Witness) - H
60207b4e-912f-57ef-b8a5-4d75e8d96c38 | note | DETAIL - Check for any cast in items and ensure they are fixed correctly
fa2aaf87-8c8d-563e-9d50-7be7995172d4 | note | FREQUENCY - Prior to concrete pour
2cd0813c-7bbe-5ce8-ae12-cbf34c8ad7f7 | note | INSPECTION - Visual inspection
0babb489-8492-5f7d-ab61-2701c043a677 | note | CONFORMANCE CRITERIA - Concrete Inspection Record
f4f32ce8-2b10-5229-a212-874be80cbb59 | note | RECORDS - FHIMS-CS-4008
8c265c70-9b5d-4e61-aebf-c59eae782c86 | signoff | HOLD POINT
b640e536-a7d4-4ab6-994d-274928e7d18b | checkpoint | 6 - Pre-tensioning (1)
08f47f46-4ccd-5039-a135-d8a193a48b2e | note | ACTION (Hold, Monitor, Witness) - H
a2220564-3b4f-53ab-a240-e0b3f3b12755 | note | DETAIL - Review Strand stressing / extension calculations comply with Specifications
9e14ec33-1852-5fe6-807c-0739bb6a3da0 | note | FREQUENCY - Prior to concrete pour
af8bc929-9b54-5fb9-85af-48cb1adc35d9 | note | INSPECTION - Document Review
72f57a5c-1fb6-5cce-a0fe-c206aedd063d | note | RECORDS - FHIMS-CS-4008
1b60f3bf-e387-4285-bf73-4de7f15ae672 | signoff | HOLD POINT
f66cdf27-1bee-43f0-87fc-9138c522c61a | checkpoint | 6 - Pre-tensioning (2)
72f9b274-90eb-5713-9ff5-7c293d92fafa | note | ACTION (Hold, Monitor, Witness) - H
82a88984-e120-565e-9c2d-f992c70233dd | note | DETAIL - Check Strand Size and type complies with Specifications
2efd5a37-b627-5ec6-96f1-3e5359caac52 | note | FREQUENCY - Prior to concrete pour
4e7f9a3c-12b9-5965-9091-6c35bf2c8e88 | note | INSPECTION - Visual Inspection
5cf5cb59-8abe-5c00-9569-488b72673d54 | note | RECORDS - FHIMS-CS-4008
2528f29e-0e7d-4542-b0ab-a6e45d352168 | signoff | HOLD POINT
018b8b26-7781-4ce1-89c0-e0494e6cf234 | checkpoint | 6 - Pre-tensioning (3)
5cdd17a1-a55e-5178-980d-251afe9dc723 | note | ACTION (Hold, Monitor, Witness) - H
4f1ab91e-bfb4-512a-a720-26271ced8f15 | note | DETAIL - Check Debound lengths, and compliance with strand schedule
45d9528c-c630-566c-8640-7183faa34d29 | note | FREQUENCY - Prior to concrete pour
69253085-e2e5-505c-94bd-a9cb6302b5f9 | note | INSPECTION - Visual Inspection
1e82376d-de72-5331-b59c-f6cdc50f71be | note | RECORDS - FHIMS-CS-4008
349659ac-53ae-4b8a-967e-5825a280fab8 | signoff | HOLD POINT
43d90bda-a31a-4849-805d-b11b1fbe35a8 | checkpoint | 6 - Pre-tensioning (4)
177cd24b-bc20-5bd6-b9a1-5a7dae8d1001 | note | ACTION (Hold, Monitor, Witness) - H
672d1268-5f30-5558-91e8-5ce2ef4433c5 | note | DETAIL - Check Actual Strand Stress/Extension with theoretical value.
07e11951-08ca-58d3-a7e5-c22d8b220aac | note | FREQUENCY - Prior to concrete pour
2cf5a949-36ac-5852-a5f1-7f12ed1eea13 | note | INSPECTION - Visual Inspection
3a4b57d8-5e7c-5697-a470-7487206bcdac | note | RECORDS - FHIMS-CS-4008
ee7a1ac9-7d99-4e49-b132-8ca212df5895 | signoff | HOLD POINT
6dc48c52-3a53-4cc2-b58e-3b85dd4a9a35 | checkpoint | 7 - Concreting (1)
617254e3-2d60-5ab4-a4a4-c070b1ef85a7 | note | ACTION (Hold, Monitor, Witness) - H
87ec6ab3-1b45-586c-939b-821ddbbf7174 | note | DETAIL - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
a2410c81-4f00-5498-941e-2e9a49c1037a | note | FREQUENCY - Prior to concrete pour
8738e651-634d-5c1f-a4c7-7226b4095954 | note | INSPECTION - Visual inspection
0b48fa05-08b0-5e69-913c-e56764688753 | note | RECORDS - FHIMS-CS-4008
eeb14eff-f42b-4fb6-8083-c16a019aa664 | signoff | HOLD POINT
6a3670a6-a275-4f77-8022-446a50a5200b | checkpoint | 7 - Concreting (2)
562a9897-aede-5a91-8b88-e1ec37c9bfed | note | ACTION (Hold, Monitor, Witness) - H
b8e5d1d6-42d6-5f36-abbd-66ac5556bfc3 | note | DETAIL - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
1c8c6424-1357-5db8-baee-bbbfa35e5ab0 | note | FREQUENCY - Prior to concrete pour
3047e3e1-a974-528b-a55e-54c3ea9f9a18 | note | INSPECTION - Test Results
4664a3b4-c2f8-52d1-8e9b-7732a1d392a7 | note | CONFORMANCE CRITERIA - NZS 3104
0fd28f68-0350-5de2-a4ee-0047fcfc243a | note | RECORDS - FHIMS-CS-4090
efe3192e-97cf-420b-8ef2-6aa93d066b4d | signoff | HOLD POINT
a8d1b3f0-e7b1-440d-86a2-ef4ec72171d0 | checkpoint | 7 - Concreting (3)
16747308-369b-5fba-b87c-f03fd5247e05 | note | ACTION (Hold, Monitor, Witness) - H
e0e0f614-a9fd-5794-aa11-d134dfa1676b | note | DETAIL - Concrete surfaces shall be F4 or better for formed surfaces and U2 or better for unformed surfaces, Bridge decks U5 (broom) finish
cf74217b-2124-5f21-bc36-6be05a556811 | note | FREQUENCY - At completion of pour
dccd5424-e069-57bf-874a-a9c3e8c67f0d | note | INSPECTION - Visual inspection
2ad7e777-688c-5a22-8bcc-fa427ddc886c | note | CONFORMANCE CRITERIA - Concrete Inspection Record
febc492e-fd81-5452-98b9-051d5c66e4bb | note | RECORDS - FHIMS-CS-4008
6bf75728-85f4-40e7-9201-bf528021ec77 | signoff | HOLD POINT
1aaadbf2-b1ca-4f16-80ab-7742e354f4a6 | checkpoint | 8 - Striking of formwork and curing of Units
190ace1c-d97d-518a-983d-a8753107b171 | note | ACTION (Hold, Monitor, Witness) - W
d4f8699f-734f-5717-808e-6851acd0d240 | note | DETAIL - Striping of Beams shall only commence when Concrete has reached release strength and minimum 12 hours of curing
b6ea4adc-4a05-5a8d-a1be-a43cd4b1b797 | note | FREQUENCY - At completion of pour
e2ddb0b3-11f9-5596-b0cc-a62c28950d93 | note | INSPECTION - Visual inspection
e222a90a-ddc9-5f1b-8ab4-3e45b2b5f83f | note | CONFORMANCE CRITERIA - Concrete Inspection Record
3beedfa6-c697-53a8-9b88-be2d40f593bd | note | RECORDS - FHIMS-CS-4008
9124b6b1-b334-4534-baa2-4ac801233011 | checkpoint | 9 - Beam Hog
2b76a22c-b540-5d86-a30e-48b358b65102 | note | ACTION (Hold, Monitor, Witness) - M
e3d34e29-3ce8-51e3-97a8-9cce337f00c6 | note | DETAIL - To be Measured prior to site delivery. Deck slab thickness to be adjusted if required.
3333ae5e-7a2e-592a-9fa4-8f52e99860d8 | note | FREQUENCY - Prior to Precast Unit Delivery
826d69e7-23f4-5ee8-b4a1-ae2ede795d83 | note | INSPECTION - Visual Inspection
b08fb503-f630-50b3-b6cd-cdff57eedcbc | note | RECORDS - FHIMS-CS-4008
8f692199-a8dc-4e7a-8c1d-f629cf258f17 | checkpoint | 10 - As-builts
5c54e266-38e6-52f6-861e-5a3e2b209f0b | note | ACTION (Hold, Monitor, Witness) - H
0bd2ed8f-1f22-57d1-8531-bc4ea8bdf764 | note | DETAIL - Red pen mark up drawings to be included in QA file
8047172e-06a6-5df0-832d-e07251606956 | note | FREQUENCY - At the completion of the Lot of work
9e2b14a6-ce78-57ee-97ea-a9b6a7784451 | note | INSPECTION - Drawings
a72d1d45-2c08-5cb5-86fb-0d9c42922050 | note | RECORDS - Asbuilt Drawing
76af5196-bdea-4db2-b301-1264b1a1978e | signoff | HOLD POINT
dacf6ba9-6755-45fb-9456-a927df4f023b | checkpoint | 11 - Lot Number QA File
c8f7674c-0b85-5acc-9723-ca462e4a9903 | note | ACTION (Hold, Monitor, Witness) - W
5b8831ae-2121-5406-a0f7-a6011a8451df | note | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
4458f7e9-7940-55ed-a08e-9760b5b01b61 | note | FREQUENCY - At completion of Lot
57834ed4-1e02-5c60-890d-20df3e25a309 | note | INSPECTION - Document Review
6e4ea86a-fea7-5165-8cf4-190a032dabc7 | note | CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files
9cd4c135-35cf-5b3a-b0d4-74adc88eb315 | note | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
c18e327e-7df7-472e-9009-adac0a2c6072 | checkpoint | Final Inspection
7bba1f5f-0c59-5337-b303-6fbee40ba7eb | textbox | QA Compiled By:
061f9f5c-ac7c-5f52-b0b5-20f4cee87fbb | textbox | QA checked By Discipline Manager:
4f2ba517-57fd-5767-96a7-c00d33c1a635 | textbox | QA checked By Quality Manager:
b024f58c-3317-5591-9d7b-32b866654b1a | textbox | Accepted By Design Engineer:
df90f99d-12bd-57fb-966f-99cc8e4bf358 | date | Date:
c6be577b-1316-42ef-aadf-729461b370f7 | signoff | Sign ITP