## Table 1
Bus Infrastruture Contract 25/26
Site Location
Enabling Works - Timber Retaining Wall
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Everysite | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
1.1 |  | AT and FH Project Managers | Site Set out Plan | Everysite | Site Set out as per IFC plan with reference/set out points provided by designers. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Construction
8 | Timber Retaining Wall | Visual | TDM ST0004 - Version A Timber Retaining Wall Detail | Everysite | 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre. 150 x 50 RS Tanalised H4 Timber Rails. Provide 5-10mm gap between rails Retaining wall slope to be 10:1 grade. Maximum height of wall = 1499mm. Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm Backfill width of 200mm of Drainage metal behind retaining wall pails. | Inprocess Inspection | Photos Material Dockets Dimension checks | Site Engineer
As builts
12 | As built information | RAMM DATA SHEET |  | Every Site | As built drawings and Ramm Sheets Completed | In Process Inspection | Asbuilt records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Ryan Simon | Initial | RS |  | Date:
Approving Delegate |  | Nithin Thomas | Initial | NT |  | Date: