## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Enabling Works - Timber Retaining Wall | itp |  |  |  |  | Generic - Bus Infrastructure - ITP - Enabling Works - Timber Retaining Wall
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1 - Site Set out
label | VERIFICATION ACTIVITY: AT and FH Project Managers
label | METHODS OR REFERENCE: Site Set out Plan
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per IFC plan with reference/set out points provided by designers.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Construction
checkpoint | 8 - Timber Retaining Wall
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM ST0004 - Version A Timber Retaining Wall Detail
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diameter.
label | ○ 150 x 50 RS Tanalised H4 Timber Rails. Provide 5-10mm gap between rails
label | ○ Retaining wall slope to be 10:1 grade. Maximum height of wall = 1499mm.
label | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm
label | ○ Backfill width of 200mm of Drainage metal behind retaining wall pails.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos Material Dockets Dimension checks
label | ONSITE RESPONSIBILITY: Site Engineer
section | As builts
checkpoint | 12 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Ryan Simon
label | Approving Delegate: Nithin Thomas