## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-FIC-009-01 - Pavement Installation | [5 empty] | RR-SEPD-BESS-FIC-009-01 - Pavement Installation
section | Part 1 – Preliminaries
checkpoint | Review of approved construction drawings and specifications
label | All drawings and specifications approved and up to date
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, MRWA-Spec-501 Pavements
label
checkpoint | Lot Map
label | Lot map markup created and uploaded
label | Specifications/Drawings Reference - Principal Project Requirements
checkpoint | Materials compliances
label | Materials for earthworks comply with Design requirements (ie. particle size, moisture content, CBR, Die back certificate)
label | — Subgrade = min. CBR of 6%
label | — Sub-base (Light Duty Road) = min. 30% CBR (Light Duty Road),
label | — Sub-base (Heavy Duty Road) = min. 50% CBR
label | — Basecourse (Light Duty Road) = min. 80% CBR
label | — Basecourse (Heavy Duty Road) = min. Ev 520mpa
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, Test material results, WBS-SS-CI-DRG-0133_0
checkpoint | Verification of permits
label | All relevant permits (GDA/GDP) in place
label | Specifications/Drawings Reference - GDA/GDP
checkpoint | Site access and safety preparation
label | Site access cleared and made safe
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006
checkpoint | Environmental controls in place
label | Dust, noise, and sediment barriers installed and functioning
label | Specifications/Drawings Reference - SEPD environmental requirements
section | Part 2 – Construction of Subgrade
checkpoint | Excavation to design subgrade levels
label | Subgrade = (-15mm, +5mm)
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, SEPDS – TQ -111
checkpoint | Subgrade inspection, compaction & proof roll
label | Subgrade verified, compacted and trimmed.
label | Compaction testing results conformant with project criteria:
label | — Subgrade = min. 95% MMDD
label | Subgrade proof rolled and no excessive deformation found (refer to Proof Roll FIC)
label | Specifications/Drawings Reference - AS 1289, WBS-SS-CI-SPC-0006, WBS-SS-CI-DRG-0133_0
checkpoint | Soft Spots rectified (if applicable) and Proof Rolled again
label | Soft spots identified during proof roll inspections rectified as per the Engineer’s advice.
label | Any areas that were rectified to be proof rolled again until all areas are conformant and no excessive deformation is found
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006
checkpoint | Maximum moisture dryback
label | Dryback testing conducted and all tests conformant as per specifications:
label | — Subgrade = 85% of MOMC
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, WBS-SS-CI-DRG-0133
section | Part 3 – Construction of Subbase & Basecourse
checkpoint | Fill placement in controlled layers
label | Pavement layer placed and compacted to thicknesses as specified in design drawings:
label | — Sub-base (Light Duty Road) = 170mm compacted
label | — Basecourse (Light Duty Road) = 120mm compacted
label | — Sub-base (Heavy Duty Road) = 410mm compacted (2x 205mm layers)
label | — Basecourse (Heavy Duty Road) = 200mm compacted
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, WBS-SS-CI-DRG-0133
checkpoint | Compaction testing
label | Compaction testing results conformant with project criteria:
label | — Sub-base = min. 95% MMDD
label | — Basecourse = min. 98% MMDD
label | Specifications/Drawings Reference - AS 1289, Compaction test results, WBS-SS-CI-SPC-0006, WBS-SS-CI-DRG-0133
checkpoint | Surface finish
label | Surface of pavement layers shall be uniformly tight and free of loose uncompacted material
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006
checkpoint | Proof Roll surface
label | Surface upon which next pavement layer will be constructed to be proof-rolled to confirm stability and detect soft spots.
label | Proof Rolls to be conducted preferably with 12t Smooth Drumm Roller. Alternatively with 700kg DPU if access constrained.
label | Individual Proof Rolls required for each layer of pavement make-up:
label | — Subgrade
label | — Sub-base
label | — Basecourse
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006
checkpoint | Soft Spots rectified (if applicable) and Proof Rolled again
label | Soft spots identified during proof roll inspections rectified as per the Engineer’s advice.
label | Any areas that were rectified to be proof rolled again until all areas are conformant and no excessive deformation is found
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006
checkpoint | Dryback testing
label | Dryback testing conducted and all tests conformant as per specifications:
label | — Sub-base = 85% of MOMC
label | — Basecourse (Light Duty Road) = 70% of MOMC
label | — Basecourse (Heavy Duty Road) = 60% of MOMC
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, WBS-SS-CI-DRG-0133
checkpoint | Layers trimmed to design level, grades and tolerances
label | Levels and grading match design tolerances as specified:
label | — Subgrade = (-15mm, +5mm)
label | — Sub-base = (-15mm, +10mm)
label | — Basecourse = (-10mm, +10mm)
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006, Survey Report
section | Part 4 – Final inspections and acceptance
checkpoint | Final surface inspection
label | Surface is stable, free from defects, and meets design criteria
label | Specifications/Drawings Reference - Site inspection, Proof roll
checkpoint | As-built survey verification
label | As-built levels and layout match design
label | Specifications/Drawings Reference - As-Built Drawings, Survey Report
checkpoint | Final inspection & Punch List sign-off
label | As-built structures inspected with the client, Punch List items (if applicable) closed out. Works handed over
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-0006
section | Document Sign-off
checkpoint | Prepared by:
textbox | ROBAR - Name:
textbox | ROBAR - Position:
date | Date:
signoff | Add Signature