## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
9a203011-531a-4daa-8ffd-38d08a4d6896 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 001 - Base Slab Pour #01 ¦ (WB-04)(WB-05)(WB-09); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
7950fafc-9d14-4f4c-8f44-2feb74405121 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 002 - Base Slab Pour #02 ¦ (WB-06)(WB-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
361f0a78-e462-4e1a-82a5-c2279e400a3d |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 003 - Base Slab Pour #03 ¦ (WB-11); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
09119204-b478-4825-8052-a8c5f6775544 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 004 - Base Slab Pour #04 ¦ (WB-07)(WB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
b3b925d2-81fc-41af-9898-e0bddabdce16 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 005 - Base Slab Pour #05 ¦ (NB-01)(NB-02); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
324c05ff-21e6-43af-b5da-471605e3d750 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 006 - Base Slab Pour #06 ¦ (NB-05)(NB-06); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
2db6a7a8-80b2-43d3-815d-72d12ddd5ece |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 007 - Base Slab Pour #07 ¦ (NB-07)(NB-08a); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
8bf41e61-054e-40e3-80ed-96101fde45b5 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 008 - Base Slab Pour #08 ¦ (NB-08b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
a596cac1-c478-467d-993c-a6d2a172f0a5 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 009 - Retaining Wall Pour #09 ¦ (NB-02); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
a4e64c52-f35c-439b-ba43-ad38cb8dd789 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 010 - Retaining Wall Pour #10 ¦ (WB-09)(WB-11); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
298a3de5-41a5-4e12-96ac-9431afca5b0b |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 011 - Retaining Wall Pour #11 ¦ (NB-01); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
a0d87862-b385-4dae-b796-4522dd01107e |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 012 - Retaining Wall Pour #12 ¦ (NB-07); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
9e4ceb51-3f8d-4d02-bcb1-aa3ef51c4039 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 013 - Retaining Wall Pour #13 ¦ (WB-10)(NB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
ea34685b-d2b0-48e3-9ab3-0de14f2e656a |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 014 - Retaining Wall Pour #14 ¦ (WB-07); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
4148a100-16fe-4558-bdc0-c78f00322b2a |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 015 - Retaining Wall Pour #15 ¦ (NB-06)(NB-08a)(NB-08b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
6f7f6f43-1035-44fa-adcf-4b34012e0571 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 016 - Retaining Wall Pour #16 ¦ (WB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
7d0b97c9-b29a-499b-88f6-5dba51196261 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 017 - Base Slab Pour #17 ¦ (SB-11)(SB-12)(SB-13a); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
5919247c-30c9-4bca-8c70-b90cb21616f4 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 018 - Retaining Wall Pour #18 ¦ (WB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
26de9fe1-cd5d-428c-a17c-6f1bd2b211aa |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 019 - Pour #19 ¦ Bay 13: FTG058(6) FTG059(7-8) FTG060(9-10) Bay 14: FTG053(5-6) FTG054(8) FTG055(9-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
9f311f12-4e4e-48d1-a578-f2266df4e5f0 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 021 - Retaining Wall Pour #21 ¦ (WB-06); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
95650c6d-5fb8-4621-9e78-6ddffc2785ed |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 022 - Pour #22 ¦ Bay 14: FTG054(7) ¦ Bay 16: FTG041(1-2) FTG42(3-4) FTG043(5-6) FTG044(7-8) FTG045(9); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
d432053e-6ae9-46bf-8b89-647141362435 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 023 - Pour #23 ¦ Bay 8 FTG001(2) FTG002(4) FTG003(5-6); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
7dee6254-c897-4d70-b6cd-cfff555d6f34 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 024 - Pour #24 ¦ Bay 8 FTG002(3) FTG004(7-8); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
e30ba24c-d9de-4dc2-820d-20e618135c70 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 025 - Pour #25 ¦ Bay 15 FTG046(1-2) FTG049(7-8) FTG050(9); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
4b8f7e9d-cc9e-4de5-8bc9-11cec19202d1 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 026 - Pour #26 ¦ Bay 15 FTG047(3-4) FTG048(5-6); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete works
1a6125f7-45e5-41c8-9c3d-541511e70f31 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 027 - Pour #27 ¦ Bay 08 FTG001(1) FTG005(9-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
71e042ed-d981-4395-9e13-4ea5d560e3a9 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 028 - Retaining Wall Pour #28 ¦ (SB-12); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d7688cd8-c6f2-4ff7-91c1-03fc3edef9b8 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 029 - Base Slab Pour #29 ¦ (EB-03); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
765b6912-47e6-455f-82cc-b9f07686baad |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 030 - Base Slab Pour #30 ¦ (EB-04)(EB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
72d8a4e0-48e1-4851-8962-e01be3b7c6e3 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 031 - Base Slab Pour #31 ¦ (EB-06)(EB-07); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
afebda48-1416-492a-9fb8-aaff5ff60054 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 032 - Base Slab Pour #32 ¦ (EB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
b676386a-7e6d-4294-bcfd-2bd8f9d3ebe4 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 033 - Base Slab & Upstand Pour #33 ¦ (SB-13b); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
5e1f1a7c-5670-4a34-9010-d63227cf6eb4 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 035 - Pour #35 ¦ Bay 7 (1,7,8,9,10) Bay 15 & 16 (10,10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
0378cc93-e886-4387-bc50-177aab66db87 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 036 - Base Slab Pour #36 ¦ (SB-14); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
49432aae-4533-492c-b59f-11757af055dc |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 037 - Retaining Wall Pour #37 ¦ (SB-11); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
f806bccb-fa32-4e30-a599-43263a5c9074 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 038 - Retaining Wall Pour #38 ¦ (SB-13)(SB-14); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
679dea34-4bdd-4c79-b19e-d53c9ed201ed |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 041 - Pour #41 ¦ Bay 6 FTG016(1-2) FTG017(3-4) FTG018(5); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
db53cb55-e70b-4d20-a028-63b34d404861 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 042 - Base Slab Pour #42 ¦ (NB-03b) T2; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d254af26-3dfb-4a20-bb26-564df2b659ee |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 043 - Base Slab Pour #43 - (NB-04) T3; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete
df6f721e-3850-482a-98ab-d49ba74a12ea |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 044 - Pour #44 ¦ Bay 6 FTG018(6) FTG019(7-8) FTG020(9-10); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
1dbe2fe4-c1b1-4dcb-9f78-55071af69a20 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 045 - Base Slab Pour #45 ¦ (NB-04) T4; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
05f34c43-53e7-485c-a875-c499f649129c |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 046 - Retaining Wall Pour #46 ¦ (EB-06)(EB-07)(EB-08); Tier 3: RR-SEPD-BESS-ITP-002-03 - FRP works
6e85207d-d181-4502-8915-076c5c5083c5 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 047 - Retaining Wall Pour #47 ¦ (NB-03a) T1; Tier 3: RR-SEPD-BESS-ITP-002-03 - FRP works - Layer
029a60c9-2744-40b5-b778-5dea8b45127e |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 048 - Retaining Wall Pour #48 ¦ (EB-03 to EB-05); Tier 3: RR-SEPD-BESS-ITP-002-03 - FRP works
012dcad6-1cb8-4eb0-8f8a-3db3285fe4e9 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | (10.2) FRP | Lot 051 - Base Slab Pour #51 ¦ (NB-03b)T1/T2 (NB-04)T3/T4 & (SB-10) | (SB-10) | RR-SEPD-BESS-ITP-002-03 - FRP works
13740d3a-918b-4218-9636-cd99f18d86dc |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 052 - Base Slabs Pour #52 ¦ (SB-04)(SB-05); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
2943c3e4-3882-4746-b22b-8ef45e8f2013 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 053 - Pour #53 ¦ Switch Room footings; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
dfc52c63-cfeb-4ae0-8443-b8632359913a |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 057 - Pour #57 ¦ GIS North Footings (F1); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
190414bf-08b9-4027-b54a-24393d717afa |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 058 - Retaining Wall Pour #58 ¦ (SB-09); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
eee0ca94-dbb6-460f-8229-8a7570ef1441 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 059 - Pour #59 ¦ Bay 4 (FTG021) (FTG022); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
5e4728f7-a3c9-4775-a001-0f321a37c642 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 062 - Pour #62 ¦ Bay 3 (1,2,3,4,5); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
1090ba5c-eadc-47ea-aa42-ad141859765a |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 063 - Pour #63 ¦ Bay 3 (6,7,8,9,10) + LV Building footings; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
45d4740b-4897-479b-b3ef-aedcee05c131 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 064 - Pour #64 ¦ Switch Room minor footings; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
115478d7-e066-471c-934c-f130da367af2 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 065 - Pour #65 ¦ Cable Tray Footing; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
783825a8-a178-4286-b301-4e789b2113ef |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 066 - Base Slab Pour #66 ¦ (SB-08); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
444f8bc2-c5e3-4be2-93e4-2cf383e0bc58 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 067 - Pour #67 ¦ Cable Tray Plinths; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
a829286e-70c2-4ca4-be55-dd8b1312e304 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 069 - Transformers Pour #69 ¦ Base Slabs (6.6kV & 33kV Aux); Tier 3: RR-SEPD-BESS-ITP-002-03 - FRP works - Layer
3c7535c9-77c8-4364-af16-6993427b1378 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 070 - Transformers Pour #70 ¦ Plinths (6.6kV & 33kV Aux); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
b48aaf4a-b2fe-4624-96e2-539009a2a051 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 072 - 33kv Transformers Pour #72 ¦ Base Slabs (Bay 14 & 15); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
67db1c0b-3663-4965-abb4-4d72e322505d |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 073 - Base Slab Pour #73 ¦ North Abutment; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
a0c3bffb-8493-4ff1-9d5a-bbfb1130823f |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 075 - Pour #75 ¦ 10x Cable Ladder FTGs + Bay 14 (Bund Wall); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
6bbb8692-2677-4db5-bff2-cc12cc5c28e1 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 083 - Pour #83 ¦ Bay 1; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
93cdb201-015b-4e19-90f2-cab602986052 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 084 - Retaining Wall Pour #84 ¦ (WB-04); Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
43d5999c-4814-4948-868b-e06b9882239f |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 085 - 33kv Transformers Pour #85 & #86 ¦ Bay 8; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
4986e151-a8e1-448a-91d6-7e6439c0a93a |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 087 - Strip Footing Pour #88 ¦ Bay 1 PCS; Tier 3: RR-SEPD-BESS-ITP-002-03 - FRP works - Layer
d3d39d77-9d09-4b10-b107-2ba4d3a5542e |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 088 - Footing Pour #89 ¦ NERs; Tier 3: RR-SEPD-BESS-ITP-002-03 - FRP works
2ccc4aff-3ef9-444a-9455-682e8b8b2ba7 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 093 - North Abutment; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
0884867c-6e18-4571-9d7c-f95527b31b82 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 092 - Bay 6; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
45d7cd91-c831-40bf-ac47-f0a8887248b1 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 094 - Pour # ¦ Bay 5; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
7ba808c0-6b17-407c-b48e-a1c2dc59a6e6 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | Tier 1: (10.2) FRP; Tier 2: Lot 095 - South Abutment; Tier 3: RR-SEPD-BESS-ITP-002-02 - Concrete Works
9a203011-531a-4daa-8ffd-38d08a4d6896 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 001 - Base Slab Pour #01 ¦ (WB-04)(WB-05)(WB-09) | RR-SEPD-BESS-ITP-002-02 - Concrete works
7950fafc-9d14-4f4c-8f44-2feb74405121 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 002 - Base Slab Pour #02 ¦ (WB-06)(WB-10) | RR-SEPD-BESS-ITP-002-02 - Concrete works
361f0a78-e462-4e1a-82a5-c2279e400a3d |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 003 - Base Slab Pour #03 ¦ (WB-11) | RR-SEPD-BESS-ITP-002-02 - Concrete works
09119204-b478-4825-8052-a8c5f6775544 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 004 - Base Slab Pour #04 ¦ (WB-07)(WB-08) | RR-SEPD-BESS-ITP-002-02 - Concrete works
b3b925d2-81fc-41af-9898-e0bddabdce16 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 005 - Base Slab Pour #05 ¦ (NB-01)(NB-02) | RR-SEPD-BESS-ITP-002-02 - Concrete works
324c05ff-21e6-43af-b5da-471605e3d750 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 006 - Base Slab Pour #06 ¦ (NB-05)(NB-06) | RR-SEPD-BESS-ITP-002-02 - Concrete works
2db6a7a8-80b2-43d3-815d-72d12ddd5ece |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 007 - Base Slab Pour #07 ¦ (NB-07)(NB-08a) | RR-SEPD-BESS-ITP-002-02 - Concrete works
8bf41e61-054e-40e3-80ed-96101fde45b5 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 008 - Base Slab Pour #08 ¦ (NB-08b) | RR-SEPD-BESS-ITP-002-02 - Concrete works
a596cac1-c478-467d-993c-a6d2a172f0a5 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 009 - Retaining Wall Pour #09 ¦ (NB-02) | RR-SEPD-BESS-ITP-002-02 - Concrete works
a4e64c52-f35c-439b-ba43-ad38cb8dd789 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 010 - Retaining Wall Pour #10 ¦ (WB-09)(WB-11) | RR-SEPD-BESS-ITP-002-02 - Concrete works
298a3de5-41a5-4e12-96ac-9431afca5b0b |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 011 - Retaining Wall Pour #11 ¦ (NB-01) | RR-SEPD-BESS-ITP-002-02 - Concrete works
a0d87862-b385-4dae-b796-4522dd01107e |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 012 - Retaining Wall Pour #12 ¦ (NB-07) | RR-SEPD-BESS-ITP-002-02 - Concrete works
9e4ceb51-3f8d-4d02-bcb1-aa3ef51c4039 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 013 - Retaining Wall Pour #13 ¦ (WB-10)(NB-05) | RR-SEPD-BESS-ITP-002-02 - Concrete works
ea34685b-d2b0-48e3-9ab3-0de14f2e656a |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 014 - Retaining Wall Pour #14 ¦ (WB-07) | RR-SEPD-BESS-ITP-002-02 - Concrete works
4148a100-16fe-4558-bdc0-c78f00322b2a |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 015 - Retaining Wall Pour #15 ¦ (NB-06)(NB-08a)(NB-08b) | RR-SEPD-BESS-ITP-002-02 - Concrete works
6f7f6f43-1035-44fa-adcf-4b34012e0571 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 016 - Retaining Wall Pour #16 ¦ (WB-05) | RR-SEPD-BESS-ITP-002-02 - Concrete works
7d0b97c9-b29a-499b-88f6-5dba51196261 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 017 - Base Slab Pour #17 ¦ (SB-11)(SB-12)(SB-13a) | RR-SEPD-BESS-ITP-002-02 - Concrete works
5919247c-30c9-4bca-8c70-b90cb21616f4 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 018 - Retaining Wall Pour #18 ¦ (WB-08) | RR-SEPD-BESS-ITP-002-02 - Concrete works
26de9fe1-cd5d-428c-a17c-6f1bd2b211aa |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 019 - Pour #19 ¦ Bay 13: FTG058(6) FTG059(7-8) FTG060(9-10) Bay 14: FTG053(5-6) FTG054(8) FTG055(9-10) | RR-SEPD-BESS-ITP-002-02 - Concrete works
9f311f12-4e4e-48d1-a578-f2266df4e5f0 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 021 - Retaining Wall Pour #21 ¦ (WB-06) | RR-SEPD-BESS-ITP-002-02 - Concrete works
95650c6d-5fb8-4621-9e78-6ddffc2785ed |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 022 - Pour #22 ¦ Bay 14: FTG054(7) ¦ Bay 16: FTG041(1-2) FTG42(3-4) FTG043(5-6) FTG044(7-8) FTG045(9) | RR-SEPD-BESS-ITP-002-02 - Concrete works
d432053e-6ae9-46bf-8b89-647141362435 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 023 - Pour #23 ¦ Bay 8 FTG001(2) FTG002(4) FTG003(5-6) | RR-SEPD-BESS-ITP-002-02 - Concrete works
7dee6254-c897-4d70-b6cd-cfff555d6f34 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 024 - Pour #24 ¦ Bay 8 FTG002(3) FTG004(7-8) | RR-SEPD-BESS-ITP-002-02 - Concrete works
e30ba24c-d9de-4dc2-820d-20e618135c70 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 025 - Pour #25 ¦ Bay 15 FTG046(1-2) FTG049(7-8) FTG050(9) | RR-SEPD-BESS-ITP-002-02 - Concrete works
4b8f7e9d-cc9e-4de5-8bc9-11cec19202d1 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 026 - Pour #26 ¦ Bay 15 FTG047(3-4) FTG048(5-6) | RR-SEPD-BESS-ITP-002-02 - Concrete works
1a6125f7-45e5-41c8-9c3d-541511e70f31 |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 027 - Pour #27 ¦ Bay 08 FTG001(1) FTG005(9-10) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
71e042ed-d981-4395-9e13-4ea5d560e3a9 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 028 - Retaining Wall Pour #28 ¦ (SB-12) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d7688cd8-c6f2-4ff7-91c1-03fc3edef9b8 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 029 - Base Slab Pour #29 ¦ (EB-03) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
765b6912-47e6-455f-82cc-b9f07686baad |  | pass | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 030 - Base Slab Pour #30 ¦ (EB-04)(EB-05) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
72d8a4e0-48e1-4851-8962-e01be3b7c6e3 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 031 - Base Slab Pour #31 ¦ (EB-06)(EB-07) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
afebda48-1416-492a-9fb8-aaff5ff60054 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 032 - Base Slab Pour #32 ¦ (EB-08) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
b676386a-7e6d-4294-bcfd-2bd8f9d3ebe4 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 033 - Base Slab & Upstand Pour #33 ¦ (SB-13b) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
5e1f1a7c-5670-4a34-9010-d63227cf6eb4 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 035 - Pour #35 ¦ Bay 7 (1,7,8,9,10) Bay 15 & 16 (10,10) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
0378cc93-e886-4387-bc50-177aab66db87 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 036 - Base Slab Pour #36 ¦ (SB-14) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
49432aae-4533-492c-b59f-11757af055dc |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 037 - Retaining Wall Pour #37 ¦ (SB-11) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
f806bccb-fa32-4e30-a599-43263a5c9074 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 038 - Retaining Wall Pour #38 ¦ (SB-13)(SB-14) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
679dea34-4bdd-4c79-b19e-d53c9ed201ed |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 041 - Pour #41 ¦ Bay 6 FTG016(1-2) FTG017(3-4) FTG018(5) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
db53cb55-e70b-4d20-a028-63b34d404861 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 042 - Base Slab Pour #42 ¦ (NB-03b) T2 | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
d254af26-3dfb-4a20-bb26-564df2b659ee |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 043 - Base Slab Pour #43 - (NB-04) T3 | RR-SEPD-BESS-ITP-002-02 - Concrete
df6f721e-3850-482a-98ab-d49ba74a12ea |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 044 - Pour #44 ¦ Bay 6 FTG018(6) FTG019(7-8) FTG020(9-10) | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer
1dbe2fe4-c1b1-4dcb-9f78-55071af69a20 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 045 - Base Slab Pour #45 ¦ (NB-04) T4 | RR-SEPD-BESS-ITP-002-02 - Concrete Works
05f34c43-53e7-485c-a875-c499f649129c |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 046 - Retaining Wall Pour #46 ¦ (EB-06)(EB-07)(EB-08) | RR-SEPD-BESS-ITP-002-03 - FRP works
6e85207d-d181-4502-8915-076c5c5083c5 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 047 - Retaining Wall Pour #47 ¦ (NB-03a) T1 | RR-SEPD-BESS-ITP-002-03 - FRP works - Layer
029a60c9-2744-40b5-b778-5dea8b45127e |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 048 - Retaining Wall Pour #48 ¦ (EB-03 to EB-05) | RR-SEPD-BESS-ITP-002-03 - FRP works
012dcad6-1cb8-4eb0-8f8a-3db3285fe4e9 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 051 - Base Slab Pour #51 ¦ (NB-03b)T1/T2 (NB-04)T3/T4 & (SB-10) | (SB-10) | RR-SEPD-BESS-ITP-002-03 - FRP works
13740d3a-918b-4218-9636-cd99f18d86dc |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 052 - Base Slabs Pour #52 ¦ (SB-04)(SB-05) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
2943c3e4-3882-4746-b22b-8ef45e8f2013 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 053 - Pour #53 ¦ Switch Room footings | RR-SEPD-BESS-ITP-002-02 - Concrete Works
dfc52c63-cfeb-4ae0-8443-b8632359913a |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 057 - Pour #57 ¦ GIS North Footings (F1) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
190414bf-08b9-4027-b54a-24393d717afa |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 058 - Retaining Wall Pour #58 ¦ (SB-09) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
eee0ca94-dbb6-460f-8229-8a7570ef1441 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 059 - Pour #59 ¦ Bay 4 (FTG021) (FTG022) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
5e4728f7-a3c9-4775-a001-0f321a37c642 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 062 - Pour #62 ¦ Bay 3 (1,2,3,4,5) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
1090ba5c-eadc-47ea-aa42-ad141859765a |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 063 - Pour #63 ¦ Bay 3 (6,7,8,9,10) + LV Building footings | RR-SEPD-BESS-ITP-002-02 - Concrete Works
45d4740b-4897-479b-b3ef-aedcee05c131 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 064 - Pour #64 ¦ Switch Room minor footings | RR-SEPD-BESS-ITP-002-02 - Concrete Works
115478d7-e066-471c-934c-f130da367af2 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 065 - Pour #65 ¦ Cable Tray Footing | RR-SEPD-BESS-ITP-002-02 - Concrete Works
783825a8-a178-4286-b301-4e789b2113ef |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 066 - Base Slab Pour #66 ¦ (SB-08) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
444f8bc2-c5e3-4be2-93e4-2cf383e0bc58 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 067 - Pour #67 ¦ Cable Tray Plinths | RR-SEPD-BESS-ITP-002-02 - Concrete Works
a829286e-70c2-4ca4-be55-dd8b1312e304 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 069 - Transformers Pour #69 ¦ Base Slabs (6.6kV & 33kV Aux) | RR-SEPD-BESS-ITP-002-03 - FRP works - Layer
3c7535c9-77c8-4364-af16-6993427b1378 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 070 - Transformers Pour #70 ¦ Plinths (6.6kV & 33kV Aux) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
b48aaf4a-b2fe-4624-96e2-539009a2a051 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 072 - 33kv Transformers Pour #72 ¦ Base Slabs (Bay 14 & 15) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
67db1c0b-3663-4965-abb4-4d72e322505d |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 073 - Base Slab Pour #73 ¦ North Abutment | RR-SEPD-BESS-ITP-002-02 - Concrete Works
a0c3bffb-8493-4ff1-9d5a-bbfb1130823f |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 075 - Pour #75 ¦ 10x Cable Ladder FTGs + Bay 14 (Bund Wall) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
6bbb8692-2677-4db5-bff2-cc12cc5c28e1 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 083 - Pour #83 ¦ Bay 1 | RR-SEPD-BESS-ITP-002-02 - Concrete Works
93cdb201-015b-4e19-90f2-cab602986052 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 084 - Retaining Wall Pour #84 ¦ (WB-04) | RR-SEPD-BESS-ITP-002-02 - Concrete Works
43d5999c-4814-4948-868b-e06b9882239f |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 085 - 33kv Transformers Pour #85 & #86 ¦ Bay 8 | RR-SEPD-BESS-ITP-002-02 - Concrete Works
4986e151-a8e1-448a-91d6-7e6439c0a93a |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 087 - Strip Footing Pour #88 ¦ Bay 1 PCS | RR-SEPD-BESS-ITP-002-03 - FRP works - Layer
d3d39d77-9d09-4b10-b107-2ba4d3a5542e |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 088 - Footing Pour #89 ¦ NERs | RR-SEPD-BESS-ITP-002-03 - FRP works
2ccc4aff-3ef9-444a-9455-682e8b8b2ba7 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 093 - North Abutment | RR-SEPD-BESS-ITP-002-02 - Concrete Works
0884867c-6e18-4571-9d7c-f95527b31b82 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 092 - Bay 6 | RR-SEPD-BESS-ITP-002-02 - Concrete Works
45d7cd91-c831-40bf-ac47-f0a8887248b1 |  | work-in-progress | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 094 - Pour # ¦ Bay 5 | RR-SEPD-BESS-ITP-002-02 - Concrete Works
7ba808c0-6b17-407c-b48e-a1c2dc59a6e6 |  | not-started | RR-SEPD-BESS-ITP-002-03 - FRP works | checklist | FALSE | FALSE | 10. ITPs & FICs | (10.2) FRP | Lot 095 - South Abutment | RR-SEPD-BESS-ITP-002-02 - Concrete Works