## Table 1
INSPECTION AND TEST PLAN
Details
ITP Activity: |  |  | RCP installation | [7 empty] | Project: |  |  |  |  | EVA Copper | [7 empty] | Date Lot Opened:
ITP Number: |  |  | EVAMP001-THS- QA-ITP-0004 |  |  |  | Rev. No. |  | A |  | Contract Number: | [12 empty] | Date Lot Closed:
Lot Number: | [10 empty] | Client: |  |  |  |  | Harmony
Location or Area: | [10 empty] | Client Reference: | [12 empty] | JSA/SWMS Ref:
Chainage / Coordinates: | [10 empty] | Contractor / Subcontractor / Supplier: | [12 empty] | SOP Reference:
No. | Inspection / Test Point |  |  | Responsibility |  |  | Method |  | Conformance Criteria |  |  |  | Specification Clause |  | Frequency |  |  | Verification from Thiess / Client (H/W/R/M) | [6 empty] | Records or Comments
[18 empty] | THIESS (Initial) |  |  |  |  | Client (Initial)
1 | Pre-Construction
1 | Drawings supplied most current IFC and transmitted through In Eight |  |  | ENG |  |  | Visual |  | Reviewed drawing register |  |  |  | Reviewed drawing register |  | Prior to works |  |  | HP |  |  |  |  | W
2 | Define RCP ID |  |  | ENG |  |  | Visual |  | Allocate ID for reinforced concrete pipe, define work area |  |  |  | Lot register. EVAMP001- THS-CV-SPE- 0001 EVAMP001- THS-CV-SPE- 0002 |  | Prior to works |  |  | HP |  |  |  |  | W
3 | Lot Register/ WBS submitted and approved |  |  | ENG |  |  | Visual |  | Approved WBS |  |  |  | Approved WBS |  | Prior to works |  |  | WP |  |  |  |  | W
4 | Underlying lot & ITP signed off and conforming |  |  | ENG |  |  | Visual |  | Subgrade prep ITP Signed |  |  |  | Approved QMP. Approved ITP |  | Prior to works |  |  | HP |  |  |  |  | W
5 | Certificate of compliance for RCP Material |  |  | ENG |  |  | Written |  | Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used). |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | Per Pipe |  |  | HP |  |  |  |  | W
6 | Inspect reinforced pipe culverts for damage |  |  | ENG/SV |  |  | Visual |  | Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form. |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | Per pipe |  |  | HP |  |  |  |  | W
2 | Construction
7 | Trench Excavation |  |  | SV/SC |  |  | Visual |  | Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters. Excavations must be kept free from water until work below ground level is adequately set or protected. |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | As required |  |  | HP |  |  |  |  | W
8 | Bedding |  |  | SV |  |  | Visual |  | Culverts shall be bedded as detailed on the Drawings. proposed |  |  |  | EVAMP001- THS-CV-SPE- 0003 clause |  | As required |  |  | HP |  |  |  |  | HP |  | On-site verification sheet and survey
9 | RCP Installation |  |  | SV/SC |  |  | Written/ survey |  | Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm. Inverts shall be smooth and of uniform gradient throughout each culvert length. Tolerances: Vertical level: ± 10mm Horizontal Alignment: ± 25mm |  |  |  | EVAMP001- THS-CV-SPE- 0003 clause 4.17 |  | As required |  |  | HP |  |  |  |  | W
10 | Backfilling of culvert |  |  | ENG/ SV |  |  | Visual |  | Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content. Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/- 2% OMC shall be advised. |  |  |  | EVAMP001- THS-CV-SPE- 0003 clause 2.14 |  | As required |  |  | HP |  |  |  |  | HP |  | On site verification/ NATA Test report
11 | End Treatment – Headwall & Wingwalls (Reinforcement) |  |  | ENG/ SV |  |  | Visual |  | Reinforcement installed as per IFC design drawings. |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | V |  |  | HP |  |  |  |  | W |  | On-site verification sheet
12 | End Treatment – Headwall & Wingwalls (Formwork) |  |  | ENG/SV |  |  | Visual/ Field survey |  | Formwork installed as per IFC design drawings. Tolerances: Variation in cross- sectional Dimensions: + 5mm Variation in overall dimensions: + 10mm Variation in surface level: + 5mm |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | Each inlet/Outlet |  |  | HP |  |  |  |  | W |  | On-site verification sheet
13 | End Treatment – Headwall & Wingwalls (Concrete) |  |  | SC/ SV |  |  | Visual |  | Concrete placed and compacted to specified strength (N40) and slump (max100mm). |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | Each inlet/Outlet |  |  | HP |  |  |  |  | W
14 | Rock Protection |  |  | SC/ SV |  |  | Visual |  | Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings. |  |  |  | EVAMP001- THS-CV-SPE- 0003 |  | Each inlet/Outlet |  |  | HP |  |  |  |  | W
3 | Post Construction
15 | Works completed and update ITP/ Lot Register/ MDR |  |  | ENG |  |  | Visual |  | ITP closed. Approved MDR |  |  |  | - EVAMP001- THS-CV- SPE-0003 - EVA PMP |  | As required |  |  | HP |  |  |  |  | HP
☐ Conformance to Specification | [5 empty] | ☐ Requires Re-Work: (Provide Details): | [15 empty] | ☐ | Non-Conformance |  | NCR No:
Approved by THIESS QA Representative | [6 empty] | Date |  |  | Approved by THIESS Project Manager | [6 empty] | Date |  |  | Approved by Client | [7 empty] | Date
Name (print): | [9 empty] | Name (print): | [9 empty] | Name (print):
Signature: | [9 empty] | Signature: | [9 empty] | Signature:
RESPONSIBILITY |  |  |  |  | METHOD | [6 empty] | VERIFICATION TYPE | [6 empty] | ITP REVISIONS
Symbol |  | Legend |  |  | Symbol |  |  | Legend |  |  |  | Symbol |  | Legend |  |  |  |  | Rev No. |  | Amendment Details |  |  |  |  | Date | Approver
C |  | Client |  |  | W |  |  | Written |  |  |  | HP |  | Hold
SV |  | THIESS Supervisor |  |  | A |  |  | Application |  |  |  | W |  | Witness
Eng |  | THIESS Engineer |  |  | D |  |  | Design |  |  |  | R |  | Review
Surv |  | Surveyor |  |  | S |  |  | Survey Data |  |  |  | M |  | Monitor
SC |  | Subcontractor |  |  | V |  |  | Visual
PM |  | Project Manager |  |  | T |  |  | Test
CM |  | Construction Manager |  |  | C |  |  | Certificate
MC |  | Material Controller |  |  | TA |  |  | Test / Approval
ENV |  | Enviro officer |  |  | M |  |  | Measure
Please transfer information into THIESS Data System ‘Inspection and Test’ Register.