## Table 1
INSPECTION AND TEST PLAN
Details
ITP Activity: |  |  | Unbound Granular Pavements | [9 empty] | Project: |  |  |  |  | EVA Copper | [6 empty] | Date Lot Opened:
ITP Number: |  |  | EVAMP001-THS- |  |  |  | Rev. No. |  |  | 0 |  |  | Contract Number: | [11 empty] | Date Lot Closed:
QA-ITP-000X
Lot Number: | [12 empty] | Client: |  |  |  |  | Harmony
Location or Area: | [12 empty] | Client Reference: | [11 empty] | JSA/ SWMS Ref:
Chainage / Coordinates: | [12 empty] | Contractor / Subcontractor / Supplier: | [11 empty] | SOP Reference:
No. | Inspection / Test Point |  |  | Responsibility |  |  | Method |  |  | Conformance Criteria |  |  |  |  | Specification Clause |  | Frequency |  |  |  | Verification from Thiess / Client (H/ W/ R/ M) |  |  |  |  | Records or Comments
[21 empty] | THIESS (Initial) |  |  |  | Client (Initial)
1 | Pre-Construction
1 | Drawings supplied most current IFC Retrieved from InEight |  |  | ENG |  |  |  | Visual |  |  | Reviewed drawing register |  |  |  | Reviewed drawing register |  | Prior to works |  |  |  | HP |  |  |  | W
2 | Management Plans submitted and approved as per PMP |  |  | ENG |  |  |  | Visual |  |  | Approved Package MP’s |  |  |  | Approved Package MP’s |  | Prior to works |  |  |  | HP |  |  |  | W
3 | Inspection Test Plan (ITP) submitted and approved |  |  | ENG |  |  |  | Visual |  |  | Approved ITP revision |  |  |  | Approved ITP revision |  | Prior to works |  |  |  | HP |  |  |  | W
4 | Lot Register/ WBS submitted and approved |  |  | ENG |  |  |  | Visual |  |  | Approved WBS |  |  |  | Approved WBS |  | Prior to works |  |  |  | WP |  |  |  | W
5 | Pavement material compliance testing |  |  | ENG |  |  |  | Visual |  |  | Test results comply with the details on the drawings or where not specified the specification |  |  |  | EVAMP001-THS- CV-SPE-0002 clauses 2.4.1.1, 3.4 |  | Prior to works |  |  |  | HP |  |  |  | HP
6 | Stockpile locations |  |  | ENG |  |  |  | Visual |  |  | Stockpile locations shown on the drawings or approved by client’s rep |  |  |  | EVAMP001-THS- CV-SPE-0002 clause 3.6 |  | Prior to works |  |  |  | HP |  |  |  | W
7.. | Underlying lot & ITP signed off and conforming |  |  | ENG |  |  |  | Visual |  |  | Subgrade Preparation ITP signed off |  |  |  | Approved QMP |  | Prior to works |  |  |  | HP |  |  |  | W
2 | Construction
8 | Subgrade preparation under pavements |  |  | ENG |  |  |  | Visual/ Field Test |  |  | If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC. |  |  |  | EVAMP001-THS- CV-SPE-0002 clause 4.3 |  | As required |  |  |  | HP |  |  |  | W
9 | Surface level check/ and survey pick-up |  |  | SURV |  |  |  | Survey/ Field Test |  |  | Surface level pick-up submitted to company. |  |  |  | EVAMP001-THS- CV-SPE-0002 clauses 2.4.3 & 4.3 |  | As Required |  |  |  | HP |  |  |  | HP
10 | Proof roll subgrade prior to placement of pavement materials |  |  | ENG |  |  |  | Visual |  |  | Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible |  |  |  | EVAMP001-THS- CV-SPE-0002 clause 4.1 |  | As required |  |  |  | HP |  |  |  | HP
11 | Placement of pavement material layers |  |  | ENG |  |  |  | Visual/ Field Test |  |  | All materials delivered to site shall be accompanied by test certificates. Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings. The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm. Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm. Finished pavement surface level tolerance: Base - 15mm to +25mm Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm Compaction requirements: Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%. Compliance testing frequency as per table in Specification Annexure A clause 5. Road roughness count rate not exceeding 60 counts per kilometre. |  |  |  | EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 & 4.6, Annexure A clauses 3, 4, 5 & 6 |  | — |  |  |  | HP |  |  |  | HP
12 | Surface level check/ and survey pick-up |  |  | SURV |  |  |  | Survey/ Field Test |  |  | Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP. |  |  |  | EVAMP001-THS- CV-SPE-0002 clauses 4.2 & 4.3, Annexure A clause 6 |  | As Required |  |  |  | HP |  |  |  | HP
3 | Post Construction
13 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP |  |  | ENG |  |  |  | Visual |  |  | ITP closed. Approved MDR |  |  |  | - EVAMP001- THS-CV-SPE- 0002 - EVA PMP |  | As Required |  |  |  | HP |  |  |  | HP
☐ Conformance to Specification | [5 empty] | ☐ Requires Re-Work: (Provide Details): | [17 empty] | ☐ Non-Conforman ce NCR No:
Approved by THIESS QA Representative | [6 empty] | Date |  |  |  |  | Approved by THIESS Project Manager | [6 empty] | Date |  |  | Approved by Client | [5 empty] | Date
Name (print): | [11 empty] | Name (print): | [9 empty] | Name (print):
Signature: | [11 empty] | Signature: | [9 empty] | Signature:
RESPONSIBILITY |  |  |  |  | METHOD | [8 empty] | VERIFICATION TYPE | [5 empty] | ITP REVISIONS
Symbol |  | Legend |  |  | Symbol |  |  |  | Legend |  |  |  |  | Symbol |  | Legend |  |  |  | Rev No. |  |  | Amendment Details |  |  | Date | Approver
C |  | Client |  |  | W |  |  |  | Written |  |  |  |  | HP |  | Hold
SV |  | THIESS Supervisor |  |  | A |  |  |  | Application |  |  |  |  | W |  | Witness
Eng |  | THIESS Engineer |  |  | D |  |  |  | Design |  |  |  |  | R |  | Review
Surv |  | Surveyor |  |  | S |  |  |  | Survey Data |  |  |  |  | M |  | Monitor
SC |  | Subcontractor |  |  | V |  |  |  | Visual
PM |  | Project Manager |  |  | T |  |  |  | Test
CM |  | Construction Manager |  |  | C |  |  |  | Certificate
MC |  | Material Controller |  |  | TA |  |  |  | Test / Approval
ENV |  | Enviro officer |  |  | M |  |  |  | Measure
Please transfer information into THIESS Data System ‘Inspection and Test’ Register.