## Table 1
Bechtel Processing Pad – INSPECTION AND TEST PLAN
Details
| ITP Activity: |  | Clear and grubbing | [8 empty] | Project: |  |  |  |  | EVA Copper | [5 empty] | Date Lot Opened:
| ITP Number: |  | EVAMP001-THS- QA-ITP-0011 | [5 empty] | Rev. No. |  | A | Contract Number: | [10 empty] | Date Lot Closed:
| Lot Number: | [10 empty] | Client: |  |  |  |  | Harmony
| Location or Area: |  | Processing Pad | [8 empty] | Client Reference: | [10 empty] | JSA/SWMS Ref:
| Chainage / Coordinates: | [10 empty] | Contractor / Subcontractor / Supplier: | [10 empty] | SOP Reference:
No. |  | Inspection / Test Point |  | Responsibility |  |  |  |  | Method |  | Conformance Criteria |  |  | Specification Clause |  | Frequency |  | Verification from Thiess / Inspector (H/W/R/M) | [6 empty] | Records or Comments
[18 empty] | THIESS (Initial) |  |  |  | Inspector (Initial)
1 |  | Pre-Construction
1 |  | Drawings supplied most current IFC |  | ENG |  |  |  | Visual |  | Reviewed drawing register |  |  | Reviewed drawing register |  |  | Prior to works | HP |  |  |  |  | W
2 |  | Management Plans submitted and approved as per PMP |  | ENG |  |  |  | Visual |  | Approved Package MP’s |  |  | Approved Package MP’s |  |  | Prior to works | HP |  |  |  |  | W
3 |  | Inspection Test Plan (ITP) submitted and approved |  | ENG |  |  |  | Visual |  | Approved ITP revision |  |  | Approved ITP revision |  |  | Prior to works | HP |  |  |  |  | W
4 |  | Lot Register/ WBS submitted and approved |  | ENG |  |  |  | Visual |  | Approved WBS |  |  | Approved WBS |  |  | Prior to works | WP |  |  |  |  | W
5 |  | Erosion and sediment control plan approved |  | ENV |  |  |  | Visual |  | Approved erosion and sediment control plan |  |  | EVAMP001-EVA- 7340-PE-PRM- 0001 |  |  | Prior to works | HP |  |  |  |  | HP
6 |  | Check existing services and dial before you dig |  | ENG |  |  |  | Visual |  | DBYD certificate and EP |  |  | Excavation Permit (EP) Doc no. |  |  | Prior to works | HP |  |  |  |  | W
7 |  | Ground Disturbance Procedure (GDP) obtained |  | ENG |  |  |  | Visual |  | GDP permit with work packs |  |  | EVAMP001-EVA- 7340-PE-PRM- 0001 |  |  | Prior to works | HP |  |  |  |  | HP
8 |  | Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up |  | SURV |  |  |  | Visual |  | Clearing pegs installed at nominal intervals to ensure no over-clearing |  |  | EVAMP001-EVA- 7340-PE-PRM- 0001 to ensure no over-clearing |  |  | Prior to works | HP |  |  |  |  | HP
9 |  | Area of works been pre-cleared for Fauna/ Flora |  | ENV |  |  |  | Visual |  | All areas to be pre-cleared prior to clearing operations. |  |  | EVAMP001-EVA- EN-PLA-0001 |  |  | Prior to works | HP |  |  |  |  | HP
10 |  | Survey of pegs to confirm correct setting out |  | ENV |  |  |  | Visual |  | Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team |  |  | EVAMP001-EVA- EN-PLA-0001 |  |  | Prior to clearing | HP |  |  |  |  | HP
2 |  | Construction
11 |  | Clearing of vegetation and removal to nominated stockpile location |  | ENG |  |  |  | Visual |  | Spotter/ catcher in place during clearing operations Habitat vegetation, threatened species and cultural heritage areas demarcated |  |  | — EVAMP001- EVA-EN-PLA- 1 — EVAMP001- EVA-7340-PE- PRM-1 — C22 of EVAMP001-QVT- PE-PRM-1 |  |  | As required | HP |  |  |  |  | W
12 |  | All Erosion sediment control measures installed prior to construction |  | ENG |  |  |  | Visual |  | All control measures for erosion sediment control need to be implemented after clearing has been completed. |  |  | EVAMP001-EVA- 7340-PE-PRM- 0001 EVAMP001-EVA- EN-PLA-0001 |  |  | After clearing completed | HP |  |  |  |  | HP
13 |  | Inspection of foundation prior to next stage of construction |  | ENG |  |  |  | Field Test |  | Proof roll where required |  |  | EVAMP001-EVA- EN-PLA-0001 |  |  | As required | HP |  |  |  |  | HP
14 |  | Surface level check/ post-strip area survey pick-up |  | SURV |  |  |  | Survey/ Field Test |  | DXF file submitted to Company |  |  | EVAMP001-EVA- 7340-PE-PRM- 0001 |  |  | As required | HP |  |  |  |  | W
3 |  | Post Construction
15 |  | Works completed and update ITP/ Lot Register/ MDR and close out of GDP |  | ENG |  |  |  | Visual |  | GDP permits closed. ITP closed. Approved MDR |  |  | - EVAMP001- EVA-7340-PE- PRM-0001 - EVA PMP |  |  | As required | HP |  |  |  |  | HP
☐ Conformance to Specification | [5 empty] | ☐ Requires Re-Work: (Provide Details): | [14 empty] | ☐ Non-Conformance |  |  | NCR No:
Approved by THIESS QA Representative | [6 empty] | Date |  |  | Approved by THIESS Project Manager | [6 empty] | Date |  | Approved by Client | [7 empty] | Date
Name (print): | [9 empty] | Name (print): | [8 empty] | Name (print):
Signature: | [9 empty] | Signature: | [8 empty] | Signature:
RESPONSIBILITY |  |  |  |  | METHOD | [8 empty] | VERIFICATION TYPE |  |  |  | ITP REVISIONS
Symbol |  | Legend |  |  | Symbol |  |  | Legend | [5 empty] | Symbol | Legend |  |  | Rev No. |  | Amendment Details |  |  |  |  | Date | Approver
C |  | Client |  |  | W |  |  | Written | [5 empty] | HP | Hold
SV |  | THIESS Supervisor |  |  | A |  |  | Application | [5 empty] | W | Witness
Eng |  | THIESS Engineer |  |  | D |  |  | Design | [5 empty] | R | Review
Surv |  | Surveyor |  |  | S |  |  | Survey Data | [5 empty] | M | Monitor
SC |  | Subcontractor |  |  | V |  |  | Visual
PM |  | Project Manager |  |  | T |  |  | Test
CM |  | Construction Manager |  |  | C |  |  | Certificate
MC |  | Material Controller |  |  | TA |  |  | Test / Approval
ENV |  | Enviro officer |  |  | M |  |  | Measure
Please transfer information into THIESS Data System ‘Inspection and Test’ Register.