## Table 1
Bechtel Processing Pad – INSPECTION AND TEST PLAN
Details
ITP Activity: |  |  | Topsoil Stripping | [7 empty] | Project: |  |  |  |  | EVA Copper | [6 empty] | Date Lot Opened:
ITP Number: |  |  | EVAMP001-THS- QA-ITP-0012 |  |  |  | Rev. No. |  | A |  | Contract Number: | [11 empty] | Date Lot Closed:
Lot Number: | [10 empty] | Client: |  |  |  |  | Harmony
Location or Area: |  |  | Processing Pad | [7 empty] | Client Reference: | [11 empty] | JSA/SWMS Ref:
Chainage / Coordinates: | [10 empty] | Contractor / Subcontractor / Supplier: | [11 empty] | SOP Reference:
No. | Inspection / Test Point |  |  | Responsibility |  |  | Method |  | Conformance Criteria |  |  | Specification Clause |  |  | Frequency |  | Verification from Thiess / Inspector (H/W/R/M) | [6 empty] | Records or Comments
[17 empty] | THIESS (Initial) |  |  |  |  | Inspector (Initial)
1 | Pre-Construction
1 | Drawings supplied most current IFC |  |  | ENG |  |  | Visual |  | Reviewed drawing register |  |  | Reviewed drawing register |  |  | Prior to works |  | HP |  |  |  |  | W
2 | Management Plans submitted and approved as per PMP |  |  | ENG |  |  | Visual |  | Approved Package MP’s |  |  | Approved Package MP’s |  |  | Prior to works |  | HP |  |  |  |  | W
3 | Inspection Test Plan (ITP) submitted and approved |  |  | ENG |  |  | Visual |  | Approved ITP revision |  |  | Approved ITP revision |  |  | Prior to works |  | HP |  |  |  |  | W
4 | Lot Register/ WBS submitted and approved |  |  | ENG |  |  | Visual |  | Approved WBS |  |  | Approved WBS |  |  | Prior to works |  | WP |  |  |  |  | W
5 | Check existing services and dial before you dig |  |  | ENG |  |  | Visual |  | DBYD plan |  |  | EVAMP001-EVA- 7340-PE-PRM-0001 |  |  | Prior to works |  | HP |  |  |  |  | HP
6 | Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up |  |  | ENG |  |  | Visual |  | Boundary pegs installed at nominal intervals to ensure no over- stripping |  |  | EVAMP001-EVA- 7340-PE-PRM-0001 |  |  | Prior to works |  | HP |  |  |  |  | HP
2 | Construction
7 | Stripped topsoil load and hauled to nominated stockpile location |  |  | ENG |  |  | Visual |  | Stockpile locations located 40m from watercourses and not exceed 2m in height. Native seeding of topsoil stockpiles as agreed with Company. Topsoil stripping shall be to a depth of 200mm or to the bottom of the grass root zone or as shown on the drawings, whichever is the greater |  |  | — C9 of EVAMP001- QVT-PE-PRM-0001 — EVAMP001-EVA-EN-DCR-0002 — EVAMP001-EVA-EN-PLA-0001 — 107501-EB-00000-27280-001 Rev A — EVAMP001-BEC-3920-CV-SPE-0001 Rev 0 |  |  | As required |  | HP |  |  |  |  | W
8 | Topsoil location, destination and quantity catalogued. |  |  | ENG |  |  | Field Test |  | A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations |  |  | EVAMP001-EVA-EN-PLA-0001 |  |  | As required |  | HP |  |  |  |  | HP
9 | Surface level check/post-strip area and volume survey pick-up |  |  | SURV |  |  | Survey/Field Test |  | DXF file submitted to Company and inventory updated |  |  | EVAMP001-EVA-7340-PE-PRM-0001 |  |  | As required |  | HP |  |  |  |  | W
3 | Post Construction
10 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP |  |  | ENG |  |  | Visual |  | GDP permits closed. ITP closed. Approved MDR |  |  | - EVAMP001- EVA-7340-PE- PRM-0001 - EVA PMP |  |  | As required |  | HP |  |  |  |  | HP
☐ Conformance to Specification | [5 empty] | ☐ Requires Re-Work: (Provide Details): | [14 empty] | ☐ Non-Conformance |  |  | NCR No:
Approved by THIESS QA Representative | [6 empty] | Date |  |  | Approved by THIESS Project Manager | [7 empty] | Date |  | Approved by Client | [6 empty] | Date
Name (print): | [9 empty] | Name (print): | [9 empty] | Name (print):
Signature: | [9 empty] | Signature: | [9 empty] | Signature:
RESPONSIBILITY |  |  |  |  | METHOD | [7 empty] | VERIFICATION TYPE | [5 empty] | ITP REVISIONS
Symbol |  | Legend |  |  | Symbol |  |  | Legend |  |  |  |  | Symbol | Legend |  |  |  |  | Rev No. |  | Amendment Details |  |  |  | Date | Approver
C |  | Client |  |  | W |  |  | Written |  |  |  |  | HP | Hold
SV |  | THIESS Supervisor |  |  | A |  |  | Application |  |  |  |  | W | Witness
Eng |  | THIESS Engineer |  |  | D |  |  | Design |  |  |  |  | R | Review
Surv |  | Surveyor |  |  | S |  |  | Survey Data |  |  |  |  | M | Monitor
SC |  | Subcontractor |  |  | V |  |  | Visual
PM |  | Project Manager |  |  | T |  |  | Test
CM |  | Construction Manager |  |  | C |  |  | Certificate
MC |  | Material Controller |  |  | TA |  |  | Test / Approval
ENV |  | Enviro officer |  |  | M |  |  | Measure
Please transfer information into THIESS Data System ‘Inspection and Test’ Register.