## Sheet1
1 | Drawings supplied most current IFC Retrieved from InEight | ENG | Visual | Reviewed drawing register | Reviewed drawing register | Prior to works | HP | W |  | 1 - Drawings supplied most current IFC Retrieved from InEight | Responsibility - ENG | Method - Visual | Conformance Criteria - Reviewed drawing register | Specification Clause - Reviewed drawing register | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - | 1 - Drawings supplied most current IFC Retrieved from InEight
2 | Management Plans submitted and approved as per PMP | ENG | Visual | Approved Package MP’s | Approved Package MP’s | Prior to works | HP | W |  | 2 - Management Plans submitted and approved as per PMP | Responsibility - ENG | Method - Visual | Conformance Criteria - Approved Package MP’s | Specification Clause - Approved Package MP’s | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - | Responsibility - ENG
3 | Inspection Test Plan (ITP) submitted and approved | ENG | Visual | Approved ITP revision | Approved ITP revision | Prior to works | HP | W |  | 3 - Inspection Test Plan (ITP) submitted and approved | Responsibility - ENG | Method - Visual | Conformance Criteria - Approved ITP revision | Specification Clause - Approved ITP revision | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - | Method - Visual
4 | Lot Register/ WBS submitted and approved | ENG | Visual | Approved WBS | Approved WBS | Prior to works | WP | W |  | 4 - Lot Register/ WBS submitted and approved | Responsibility - ENG | Method - Visual | Conformance Criteria - Approved WBS | Specification Clause - Approved WBS | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - WP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - | Conformance Criteria - Reviewed drawing register
5 | Pavement material compliance testing | ENG | Visual | Test results comply with the details on the drawings or where not specified the specification | EVAMP001-THS- CV-SPE-0002 clauses 2.4.1.1, 3.4 | Prior to works | HP | HP |  | 5 - Pavement material compliance testing | Responsibility - ENG | Method - Visual | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.1.1, 3.4 | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - HP | Records or Comments - | Specification Clause - Reviewed drawing register
6 | Stockpile locations | ENG | Visual | Stockpile locations shown on the drawings or approved by client’s rep | EVAMP001-THS- CV-SPE-0002 clause 3.6 | Prior to works | HP | W |  | 6 - Stockpile locations | Responsibility - ENG | Method - Visual | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep | Specification Clause - EVAMP001-THS- CV-SPE-0002 clause 3.6 | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - | Frequency - Prior to works
7.. | Underlying lot CHAR(AMP) ITP signed off and conforming | ENG | Visual | Subgrade Preparation ITP signed off | Approved QMP | Prior to works | HP | W |  | 7.. - Underlying lot CHAR(AMP) ITP signed off and conforming | Responsibility - ENG | Method - Visual | Conformance Criteria - Subgrade Preparation ITP signed off | Specification Clause - Approved QMP | Frequency - Prior to works | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - | Verification from Thiess / Inspector: THIESS (Initial) - HP
8 | Subgrade preparation under pavements | ENG | Visual/ Field Test | If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC. | EVAMP001-THS- CV-SPE-0002 clause 4.3 | As required | HP | W | On-site verification sheet and survey | 8 - Subgrade preparation under pavements | Responsibility - ENG | Method - Visual/ Field Test | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC. | Specification Clause - EVAMP001-THS- CV-SPE-0002 clause 4.3 | Frequency - As required | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - W | Records or Comments - On-site verification sheet and survey | Verification from Thiess / Inspector: Inspector (Initial) - W
9 | Surface level check/ and survey pick-up | SURV | Survey/ Field Test | Surface level pick-up submitted to company. | EVAMP001-THS- CV-SPE-0002 clauses 2.4.3 CHAR(AMP) 4.3 | As Required | HP | HP |  | 9 - Surface level check/ and survey pick-up | Responsibility - SURV | Method - Survey/ Field Test | Conformance Criteria - Surface level pick-up submitted to company. | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.3 CHAR(AMP) 4.3 | Frequency - As Required | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - HP | Records or Comments - | Records or Comments -
10 | Proof roll subgrade prior to placement of pavement materials | ENG | Visual | Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible | EVAMP001-THS- CV-SPE-0002 clause 4.1 | As required | HP | HP | On site verification/ NATA Test report | 10 - Proof roll subgrade prior to placement of pavement materials | Responsibility - ENG | Method - Visual | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible | Specification Clause - EVAMP001-THS- CV-SPE-0002 clause 4.1 | Frequency - As required | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - HP | Records or Comments - On site verification/ NATA Test report | 2 - Management Plans submitted and approved as per PMP
11 | Placement of pavement material layers | ENG | Visual/ Field Test | All materials delivered to site shall be accompanied by test certificates. Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings. The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm. Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm. Finished pavement surface level tolerance: Base - 15mm to +25mm Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm Compaction requirements: Base CHAR(AMP) Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%. Compliance testing frequency as per table in Specification Annexure A clause 5. Road roughness count rate not exceeding 60 counts per kilometre. | EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 CHAR(AMP) 4.6, Annexure A clauses 3, 4, 5 CHAR(AMP) 6 | — | HP | HP | On-site verification sheet | 11 - Placement of pavement material layers | Responsibility - ENG | Method - Visual/ Field Test | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates. Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings. The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm. Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm. Finished pavement surface level tolerance: Base - 15mm to +25mm Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm Compaction requirements: Base CHAR(AMP) Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%. Compliance testing frequency as per table in Specification Annexure A clause 5. Road roughness count rate not exceeding 60 counts per kilometre. | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 CHAR(AMP) 4.6, Annexure A clauses 3, 4, 5 CHAR(AMP) 6 | Frequency - — | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - HP | Records or Comments - On-site verification sheet | Responsibility - ENG
12 | Surface level check/ and survey pick-up | SURV | Survey/ Field Test | Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP. | EVAMP001-THS- CV-SPE-0002 clauses 4.2 CHAR(AMP) 4.3, Annexure A clause 6 | As Required | HP | HP | On-site verification sheet | 12 - Surface level check/ and survey pick-up | Responsibility - SURV | Method - Survey/ Field Test | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP. | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 4.2 CHAR(AMP) 4.3, Annexure A clause 6 | Frequency - As Required | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - HP | Records or Comments - On-site verification sheet | Method - Visual
13 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP | ENG | Visual | ITP closed. Approved MDR | - EVAMP001- THS-CV-SPE- 0002 - EVA PMP | As Required | HP | HP |  | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Responsibility - ENG | Method - Visual | Conformance Criteria - ITP closed. Approved MDR | Specification Clause - - EVAMP001- THS-CV-SPE- 0002 - EVA PMP | Frequency - As Required | Verification from Thiess / Inspector: THIESS (Initial) - HP | Verification from Thiess / Inspector: Inspector (Initial) - HP | Records or Comments - | Conformance Criteria - Approved Package MP’s
Specification Clause - Approved Package MP’s
Frequency - Prior to works
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - W
Records or Comments -
3 - Inspection Test Plan (ITP) submitted and approved
Responsibility - ENG
Method - Visual
Conformance Criteria - Approved ITP revision
Specification Clause - Approved ITP revision
Frequency - Prior to works
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - W
Records or Comments -
4 - Lot Register/ WBS submitted and approved
Responsibility - ENG
Method - Visual
Conformance Criteria - Approved WBS
Specification Clause - Approved WBS
Frequency - Prior to works
Verification from Thiess / Inspector: THIESS (Initial) - WP
Verification from Thiess / Inspector: Inspector (Initial) - W
Records or Comments -
5 - Pavement material compliance testing
Responsibility - ENG
Method - Visual
Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification
Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.1.1, 3.4
Frequency - Prior to works
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - HP
Records or Comments -
6 - Stockpile locations
Responsibility - ENG
Method - Visual
Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep
Specification Clause - EVAMP001-THS- CV-SPE-0002 clause 3.6
Frequency - Prior to works
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - W
Records or Comments -
7.. - Underlying lot CHAR(AMP) ITP signed off and conforming
Responsibility - ENG
Method - Visual
Conformance Criteria - Subgrade Preparation ITP signed off
Specification Clause - Approved QMP
Frequency - Prior to works
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - W
Records or Comments -
8 - Subgrade preparation under pavements
Responsibility - ENG
Method - Visual/ Field Test
Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
Specification Clause - EVAMP001-THS- CV-SPE-0002 clause 4.3
Frequency - As required
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - W
Records or Comments - On-site verification sheet and survey
9 - Surface level check/ and survey pick-up
Responsibility - SURV
Method - Survey/ Field Test
Conformance Criteria - Surface level pick-up submitted to company.
Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.3 CHAR(AMP) 4.3
Frequency - As Required
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - HP
Records or Comments -
10 - Proof roll subgrade prior to placement of pavement materials
Responsibility - ENG
Method - Visual
Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
Specification Clause - EVAMP001-THS- CV-SPE-0002 clause 4.1
Frequency - As required
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - HP
Records or Comments - On site verification/ NATA Test report
11 - Placement of pavement material layers
Responsibility - ENG
Method - Visual/ Field Test
Conformance Criteria - All materials delivered to site shall be accompanied by test certificates. Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings. The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm. Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm. Finished pavement surface level tolerance: Base - 15mm to +25mm Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm Compaction requirements: Base CHAR(AMP) Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%. Compliance testing frequency as per table in Specification Annexure A clause 5. Road roughness count rate not exceeding 60 counts per kilometre.
Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 CHAR(AMP) 4.6, Annexure A clauses 3, 4, 5 CHAR(AMP) 6
Frequency - —
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - HP
Records or Comments - On-site verification sheet
12 - Surface level check/ and survey pick-up
Responsibility - SURV
Method - Survey/ Field Test
Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 4.2 CHAR(AMP) 4.3, Annexure A clause 6
Frequency - As Required
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - HP
Records or Comments - On-site verification sheet
13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
Responsibility - ENG
Method - Visual
Conformance Criteria - ITP closed. Approved MDR
Specification Clause - - EVAMP001- THS-CV-SPE- 0002 - EVA PMP
Frequency - As Required
Verification from Thiess / Inspector: THIESS (Initial) - HP
Verification from Thiess / Inspector: Inspector (Initial) - HP
Records or Comments -