## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | EVAMP001-THS-QA-ITP-0011 - Bechtel - Clear and Grubbing | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0011 - Bechtel - Clear and Grubbing - RevA
section | Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - WP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | WITNESS POINT
checkpoint | 5 - Erosion and sediment control plan approved
label | Responsibility - ENV
label | Method - Visual
label | Conformance Criteria - Approved erosion and sediment control plan
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Check existing services and dial before you dig
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - DBYD certificate and EP
textbox | Specification Clause - Excavation Permit (EP) Doc no.
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 7 - Ground Disturbance Procedure (GDP) obtained
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permit with work packs
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 8 - Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up
label | Responsibility - SURV
label | Method - Visual
label | Conformance Criteria - Clearing pegs installed at nominal intervals to ensure no over-clearing
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001 to ensure no over-clearing
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 9 - Area of works been pre-cleared for Fauna/ Flora
label | Responsibility - ENV
label | Method - Visual
label | Conformance Criteria - All areas to be pre-cleared prior to clearing operations.
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 10 - Survey of pegs to confirm correct setting out
label | Responsibility - ENV
label | Method - Visual
label | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - Prior to clearing
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
section | Construction
checkpoint | 11 - Clearing of vegetation and removal to nominated stockpile location
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Spotter/ catcher in place during clearing operations
label | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
label | Specification Clause - EVAMP001- EVA-EN-PLA- 1
label | — EVAMP001- EVA-7340-PE- PRM-1
label | — C22 of EVAMP001-QVT- PE-PRM-1
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 12 - All Erosion sediment control measures installed prior to construction
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - All control measures for erosion sediment control need to be implemented after clearing has been completed.
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001, EVAMP001-EVA-EN-PLA-0001
label | Frequency - After clearing completed
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 13 - Inspection of foundation prior to next stage of construction
label | Responsibility - ENG
label | Method - Field Test
label | Conformance Criteria - Proof roll where required
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 14 - Surface level check/ post-strip area survey pick-up
label | Responsibility - SURV
label | Method - Survey/ Field Test
label | Conformance Criteria - DXF file submitted to Company
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Post Construction
checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | — EVA PMP
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0012 - Bechtel - Topsoil Stripping | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0012 - Bechtel - Topsoil Stripping - RevA
section | Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - WP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | WITNESS POINT
checkpoint | 5 - Check existing services and dial before you dig
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - DBYD plan
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Boundary pegs installed at nominal intervals to ensure no over- stripping
label | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
section | Construction
checkpoint | 7 - Stripped topsoil load and hauled to nominated stockpile location
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Stockpile locations located 40m from watercourses and not exceed 2m in height. Native seeding of topsoil stockpiles as agreed with Company. Topsoil stripping shall be to a depth of 200mm or to the bottom of the grass root zone or as shown on the drawings, whichever is the greater
label | Specification Clause - C9 of EVAMP001- QVT-PE-PRM-0001
label | — EVAMP001-EVA-EN-DCR-0002
label | — EVAMP001-EVA-EN-PLA-0001
label | — 107501-EB-00000-27280-001 Rev A
label | — EVAMP001-BEC-3920-CV-SPE-0001 Rev 0
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 8 - Topsoil location, destination and quantity catalogued.
label | Responsibility - ENG
label | Method - Field Test
label | Conformance Criteria - A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations
label | Specification Clause - EVAMP001-EVA-EN-PLA-0001
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 9 - Surface level check/post-strip area and volume survey pick-up
label | Responsibility - SURV
label | Method - Survey/Field Test
label | Conformance Criteria - DXF file submitted to Company and inventory updated
label | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Post Construction
checkpoint | 10 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
label | Specification Clause - - EVAMP001-EVA-7340-PE-PRM-0001
label | — EVA PMP
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0013 - Bechtel - Subgrade | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0013 - Bechtel - Subgrade - RevA
section | Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - W
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | WITNESS POINT
checkpoint | 5 - Check existing services and dial before you dig
label | Responsibility - ENV/ENG
label | Method - Visual
label | Conformance Criteria - Approved erosion and sediment control plan
label | Specification Clause - EVAMP001-EVA- EN-PLA-0001
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Topsoil stripping ITP signed off
label | Specification Clause - Approved QMP
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Construction
checkpoint | 7 - Removal and replacement of unsuitable material
label | Responsibility - SV
label | Method - Visual
label | Conformance Criteria - Where directed by the client’s representative remove and replace unsuitable material and dispose to waste at an approved location or as shown on the drawings.
label | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clauses 3.5.6 Unsuitable Material & 3.5.7 Disposal of Materials
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 8 - CBR values of subgrades under pavements, buildings & structures
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - The materials exposed at subgrade level of cuttings are to have a minimum CBR of 3.
label | If CBR >3:
label | ○ CBR 2 excavate 150 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
label | ○ CBR 1 excavate 250 mm below subgrade level and replace with compacted selected fill (minimum CBR 10)
label | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.9.4.1 Subgrade Preparation for Structures & Pavement
label | Frequency - Not Specified
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 9 - Subgrade preparation under foundations for structures
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - Area to be ripped to 300mm in depth, moisture conditioned and compacted to not less than 100% of the maximum dry density (standard compaction)
label | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clauses 3.9.3 Compaction Standards, 3.9.4.1 Subgrade Preparation for Structures & Pavement
label | Frequency - Normal Level of Testing: 1/500m2
label | ○ 3/visit Reduced Level of Testing: 1/1000m2
label | ○ 3/visit
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 10 - Subgrade preparation under roadways & earthpads
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - Area to be ripped to 150mm in depth, moisture conditioned and compacted to not less than 98% of the maximum dry density (standard compaction).
label | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 Clauses 3.9.3 Compaction Standards, 3.9.4.1 Subgrade Preparation for Structures & Pavement
label | Frequency - Normal Level of Testing: 1/500m2
label | ○ 3/visit Reduced Level of Testing: 1/1000m2
label | ○ 3/visit
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 11 - Proof-roll subgrade surface
label | Responsibility - SV
label | Method - Test
label | Conformance Criteria - All subgrades and foundations shall be proof rolled using a 10,000L water truck loaded to 8 tonnes with dual tyres minimum pressure 600kPa driving at 3- 10km/h. Any areas that show signs of visible movement to be rejected and reworked.
label | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.9.4.1 Subgrade Preparation for Structures & Pavement
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 12 - Surface level check/ and survey pick-up
label | Responsibility - Surv
label | Method - Survey/ Test
label | Conformance Criteria - Vertical Tolerances: General Earthworks +/-25mm
label | ○ Road subgrades, buildings/structures pads -25mm to +0mm Horizontal
label | ○ Tolerances: Road width -0mm to +250mm
label | ○ Trade Tolerances: Road +/-0.25% Pads +/-0.25%
label | Specification Clause - EVAMP001-BEC- 3920-CV-SPE-0001 rev0 Clause 3.11 Construction Tolerance
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
section | Post Construction
checkpoint | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 rev0
label | — EVA PMP
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0015 - Bechtel - Embankment Construction | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0015 - Bechtel - Embankment Construction - RevA
section | Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Define Lot dimensions
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Allocate Lot No to ITP and update Lot register
label | Specification Clause - Lot register. EVAMP001-THS-CV-SPE-0001, EVAMP001-THS-CV-SPE-0002
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - WP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | WITNESS POINT
checkpoint | 4 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Topsoil stripping ITP signed off
label | Specification Clause - Approved QMP. Approved ITP
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Construction
checkpoint | 5 - General Fill Embankment Material Properties
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - Class A:
label | — WPI < 1200
label | — PI > or = 7%
label | — % passing AS 0.075 sieve 15 - 30%
label | Class B:
label | — WPI 1200 to < 2200
label | Class C:
label | — WPI 2200 to 32200
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.1 General Embankment Fill
label | Frequency - 1 test per 5,000m3
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results
holdpoint | HOLD POINT
checkpoint | 6 - Select Fill Embankment Material Properties
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - Select Fill Material:
label | — CBR > OR =15
label | — Max. aggregate size: 40mm
label | — Linear Shrinkage: max. 7.5
label | — Liquid Limit: max. 40
label | — Plasticity Index: 4 to 14
label | — Weighted Plasticity Index: < 560
label | — Swell < OR = 0.5%
label | — Particle size distribution as per Bechtel EW Specification Table 3-6: Select Fill Particle Size Distribution Envelopes
label | Specification Clause - EVAMP001- BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.2 Select Embankment Fill
label | Frequency - Site Won Material: 1 test per 1,000m3
label | ○ Quarry Sourced Material: 1 test per 2,500t
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results
holdpoint | HOLD POINT
checkpoint | 7 - Structural Fill Embankment Material Properties
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - Properties of Coarse components (any component retained on the AS 0.425mm sieve) Type A & B:
label | — 10% fines value (wet): min. 85kN
label | — Wet/dry strength variation: max. 35%
label | — Washington degradation: min. 35
label | — Flakiness index: max. 40%
label | Properties of Fine components (any component passing through the AS 0.425mm sieve) Type A:
label | — Liquid Limit: max. 25%
label | — Plasticity Index: max. 6%
label | — Plasticity Index x % of whole sample passing the AS 0.425mm sieve: max. 150
label | — Linear Shrinkage: max. 8%
label | Properties of Fine components (any component passing through the AS 0.425mm sieve) Type B:
label | — Liquid Limit: max. 35%
label | — Plasticity Index: max. 12%
label | — Plasticity Index x % of whole sample passing the AS 0.425mm sieve: max. 360
label | — Linear Shrinkage: max. 8%
label | Particle size distribution as per Bechtel Specification Table 3-11: Structural Fill Particle Size Distribution Envelopes CBR
label | — Type A: min. 60
label | — Type B: min. 35
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.5 Structural Fill
label | Frequency - Particle size distribution, Liquid Limit, Plasticity Index. Minimum testing frequency: 1 test per 1,000m3, and 1 per work are and 1 per change of material.
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results
holdpoint | HOLD POINT
checkpoint | 8 - Lined Pond Embankment Material Properties
label | Responsibility - ENG
label | Method - Test
label | Conformance Criteria - - % passing 37.5mm sieve > or = 80%
label | — % passing 0.075mm sieve > or = 30%
label | — Maximum particle size 125mm
label | — Plasticity Index > or = 7%
label | — Liquid Limit 20 to 50%
label | — Emerson Class > 3
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.8.2.6 Pond Embankment Fill
label | Frequency - Not specified
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results
holdpoint | HOLD POINT
checkpoint | 9 - Remove & Replace Unsuitable Material (as directed)
label | Responsibility - SV ENG SURV
label | Method - Visual & Survey
label | Conformance Criteria - Where directed by the client’s representative remove and replace unsuitable material and dispose to waste at an approved location or as shown on the drawings prior to placing embankment fill.
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.5.6 Unsuitable Material
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - Survey Records
holdpoint | HOLD POINT
checkpoint | 10 - Subgrade Preparation Under Embankment Fill
label | Responsibility - SV ENG SURV
label | Method - Test & Survey
label | Conformance Criteria - Natural surfaces under embankment fill shall be tyned, moisture conditioned and compacted to a dry density ratio of not less than 98% standard compaction.
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.8.3 Preparation of Natural Ground & 3.10 Testing
label | Frequency - Normal level of testing minimum frequency: 1/500m2 & 3/Visit
label | ○ Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results Survey Records
holdpoint | HOLD POINT
checkpoint | 11 - Embankment Construction, Layer Thickness, Placement & Compaction
label | Responsibility - SV ENG SURV
label | Method - Test & Survey
label | Conformance Criteria - Depths of layers shall not exceed the capability of the proposed plant and in any case shall not exceed 300mm uncompacted.
label | ○ Layers in the top 300 mm below subgrade level for foundations, including the foundation of generators in Independent Power Provider, shall be compacted to not less than 100% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
label | ○ Layers for Earthpads, the top 150mm of Road Embankments, Foundations in the top 300mm below subgrade level, Pond Embankments, and the Crushed Ore Stockpile to be compacted to 98% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
label | ○ Fill material other than that referred to above shall be compacted to a dry density ratio of not less than 95% of the maximum dry density (standard compaction) with moisture content +/- 2% of OMC.
label | ○ Rockfill or mechanical interlock method shall not be used in areas proposed for buildings and other structural works, nor within a zone 600 mm below subgrade level for road embankments. Minimum thickness of uncompacted layers: Greater of 150mm or 1.5 times the max. rock size. Max. thickness of uncompacted layers shall not exceed those nominated in Table 3-14 of the Bechtel EW Spec.
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.9.3
label | ○ Compaction Standards, 3.9.3.1
label | ○ Compaction for Embankment (Compacted Layer method), 3.9.3.2
label | ○ Compaction for Rockfill (Mechanical Interlock Method), 3.9.4.3
label | ○ Compaction and Moisture Content & 3.10 Testing
label | Frequency - Operations >5,000m3:
label | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
label | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
label | Operations 500m3 to 5,000m3:
label | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
label | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
label | Operations <500m3:
label | — Normal level of testing minimum frequency: 1/500m2 & 3/Visit
label | — Reduced level of testing minimum frequency: 1/1,000m2 & 3/visit
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results Survey Records
holdpoint | HOLD POINT
checkpoint | 12 - Subgrade Preparation Under Structural Fill
label | Responsibility - SV ENG SURV
label | Method - Visual & Test & Survey
label | Conformance Criteria - The top 300 mm below subgrade level for foundations shall be compacted to not less than 100% maximum dry density (standard compaction).
label | For subgrades under pavements and buildings / structures, the materials exposed at subgrade level of cuttings are to have a minimum CBR of 8. Should the CBR be less than 8, the following subgrade treatments shall be applied:
label | ○ CBR 2 to 7 – excavate 150 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
label | ○ CBR 1 – excavate 250 mm below subgrade level and replace with compacted selected fill (minimum CBR 10).
label | ○ Proof rolling of the formation which is to receive structural fill and pavement structure shall be witnessed by a civil/geotechnical engineer to ensure that no soft spots remain in the compacted subgrade. Any areas that show signs of visible movement under the rear axle of an on-highway type 10,000L water truck will be rejected. The rear axle of the water truck shall be loaded to at least 8.0 tonnes and fitted with dual tyres. The minimum tyre pressure of the water truck shall be 600 kPa and the testing shall be conducted at a speed in the range of 3-10km/h. Both the Company and the Contractor’s representatives shall walk alongside the testing water truck to observe any surface deformation.
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.9.4.1
label | ○ Subgrade Preparation for Structures and Pavement, 3.9.4.3
label | ○ Compaction and Moisture Content & 3.10 Testing
label | Frequency - Proof roll as required
label | ○ CBR testing frequency not specified
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - NATA Test Results Survey Records, Visual Inspection Record
holdpoint | HOLD POINT
checkpoint | 13 - Structural Fill Construction, Layer Thickness, Placement & Compaction
label | Responsibility - SV ENG SURV
label | Method - Test & Survey
label | Conformance Criteria - Depths of layers shall not exceed the capability of the proposed plant and in any case shall not be less than 75mm or exceed 200mm uncompacted.
label | ○ The top 300 mm below subgrade level for foundations shall be compacted to not less than 100% maximum dry density (standard compaction).
label | Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clauses 3.9.4.2 Layer Thickness for Structural Fills, 3.9.4.3 Compaction and Moisture Content
label | Frequency - In-situ Density, Maximum Dry Density(stan dard compaction) & Density Index Minimum testing frequency: 1 test per 2,500m2 or 1 test per 500m3 distributed evenly through the full depth and area, and 2 per work area, and 1 per change of material
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - NATA Test Results Survey Records
holdpoint | HOLD POINT
checkpoint | 14 - As-built Survey of completed surface
label | Responsibility - ENG SURV
label | Method - Survey
label | Conformance Criteria - Survey to be completed of the finished surface to confirm construction as per the lines and levels shown on the drawings in accordance with the following tolerances:
label | Vertical Tolerances
label | — Road subgrade & building/structure pads: -25 to +0mm
label | — All other earthworks: +/-25mm
label | Horizontal Tolerances
label | — Adjacent Structure: As per the structure
label | — Not adjacent structure (apart from those listed in Section 3.11.1.1 & Section 3.11.1.2 of the spec): -50 to +150mm
label | — Substructure concrete to be placed directly against an excavated vertical surface: -10 to +50mm
label | — Road width: -0 to +250mm
label | — Open channel: -0 to +50mm
label | — Any point on earthworks surface except any of the above: +/-50mm
label | Grade Tolerances
label | — Roads & Pad/embankment: +/-0.25%
label | — Open Channel: +/-0.1%
label | — Specification Clause - EVAMP001-BEC-3920-CV-SPE-0001 Rev0 Clause 3.11 Construction Tolerance
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - Survey report
holdpoint | HOLD POINT
section | Post Construction
checkpoint | 15 - Works completed and updated ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - ITP closed. Approved MDR
label | Specification Clause - EVAMP001
label | — EVA-7340-PE-PRM-1
label | — EVA PMP
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT