## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | EVAMP001-THS-QA-ITP-0004 - RCP installation | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0004 - RCP installation - RevA
section | Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC and transmitted through In Eight
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Define RCP ID
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Allocate ID for reinforced concrete pipe, define work area
label | Specification Clause - Lot register. EVAMP001-THS-CV-SPE-0001, EVAMP001-THS-CV-SPE-0002
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - WP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | WITNESS POINT
checkpoint | 4 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Subgrade prep ITP Signed
label | Specification Clause - Approved QMP. Approved ITP
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 5 - Certificate of compliance for RCP Material
label | Responsibility - ENG
label | Method - Written
label | Conformance Criteria - Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used).
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - Per Pipe
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 6 - Inspect reinforced pipe culverts for damage
label | Responsibility - ENG/SV
label | Method - Visual
label | Conformance Criteria - Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form.
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - Per pipe
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Construction
checkpoint | 7 - Trench Excavation
label | Responsibility - SV/SC
label | Method - Visual
label | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters.
label | ○ Excavations must be kept free from water until work below ground level is adequately set or protected.
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 8 - Bedding
label | Responsibility - SV
label | Method - Visual
label | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. proposed
label | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - On-site verification sheet and survey
holdpoint | HOLD POINT
checkpoint | 9 - RCP Installation
label | Responsibility - SV/SC
label | Method - Written/ survey
label | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm.
label | ○ Inverts shall be smooth and of uniform gradient throughout each culvert length.
label | Tolerances:
label | ○ Vertical level: ± 10mm
label | ○ Horizontal Alignment: ± 25mm
label | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause 4.17
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 10 - Backfilling of culvert
label | Responsibility - ENG/ SV
label | Method - Visual
label | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content.
label | ○ Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/- 2% OMC shall be advised.
label | Specification Clause - EVAMP001-THS-CV-SPE-0003 clause 2.14
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - On site verification/ NATA Test report
holdpoint | HOLD POINT
checkpoint | 11 - End Treatment – Headwall & Wingwalls (Reinforcement)
label | Responsibility - ENG/ SV
label | Method - Visual
label | Conformance Criteria - Reinforcement installed as per IFC design drawings.
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - V
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - On-site verification sheet
holdpoint | HOLD POINT
checkpoint | 12 - End Treatment – Headwall & Wingwalls (Formwork)
label | Responsibility - ENG/SV
label | Method - Visual/ Field survey
label | Conformance Criteria - Formwork installed as per IFC design drawings.
label | ○ Tolerances: Variation in cross- sectional Dimensions: + 5mm Variation in overall dimensions: + 10mm
label | ○ Variation in surface level: + 5mm
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - Each inlet/Outlet
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - On-site verification sheet
holdpoint | HOLD POINT
checkpoint | 13 - End Treatment – Headwall & Wingwalls (Concrete)
label | Responsibility - SC/ SV
label | Method - Visual
label | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm).
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - Each inlet/Outlet
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 14 - Rock Protection
label | Responsibility - SC/ SV
label | Method - Visual
label | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings.
label | Specification Clause - EVAMP001- THS-CV-SPE- 0003
label | Frequency - Each inlet/Outlet
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Post Construction
checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - ITP closed. Approved MDR
label | Specification Clause - EVAMP001-THS-CV-SPE-0003
label | — EVA PMP
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0009 - Unbound Granular Pavements | itp |  |  |  |  | EVAMP001-THS-QA-ITP-0009 - Unbound Granular Pavements - Rev0
section | Pre-Construction
checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Specification Clause - Reviewed drawing register
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Specification Clause - Approved Package MP’s
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Specification Clause - Approved ITP revision
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Approved WBS
label | Specification Clause - Approved WBS
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - WP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | WITNESS POINT
checkpoint | 5 - Pavement material compliance testing
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification
label | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 2.4.1.1, 3.4
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 6 - Stockpile locations
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep
label | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 3.6
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
checkpoint | 7 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Subgrade Preparation ITP signed off
label | Specification Clause - Approved QMP
label | Frequency - Prior to works
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
holdpoint | HOLD POINT
section | Construction
checkpoint | 8 - Subgrade preparation under pavements
label | Responsibility - ENG
label | Method - Visual/ Field Test
label | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material.
label | ○ Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section.
label | ○ Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
label | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 4.3
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - W
label | Records or Comments - On-site verification sheet and survey
holdpoint | HOLD POINT
checkpoint | 9 - Surface level check/ and survey pick-up
label | Responsibility - SURV
label | Method - Survey/ Field Test
label | Conformance Criteria - Surface level pick-up submitted to company.
label | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 2.4.3 & 4.3
label | Frequency - As Required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT
checkpoint | 10 - Proof roll subgrade prior to placement of pavement materials
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
label | Specification Clause - EVAMP001-THS-CV-SPE-0002 clause 4.1
label | Frequency - As required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - On site verification/ NATA Test report
holdpoint | HOLD POINT
checkpoint | 11 - Placement of pavement material layers
label | Responsibility - ENG
label | Method - Visual/ Field Test
label | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates.
label | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings.
label | ○ The deviation from a 3m long straight- edge placed anywhere on the surface of a layer shall not exceed 8mm.
label | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base - 15mm to +30mm.
label | ○ Finished pavement surface level tolerance: Base - 15mm to +25mm
label | ○ Horizontal tolerances: Base, centreline/crown - 150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/- 200mm, change point -100mm to +400mm
label | ○ Compaction requirements:
label | — Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%.
label | — Compliance testing frequency as per table in Specification Annexure A clause 5.
label | — Road roughness count rate not exceeding 60 counts per kilometre.
label | Specification Clause - EVAMP001-THS- CV-SPE-0002 clauses 2.4.2.3, 3.1, 3.2, 4.2, 4.4, 4.5 & 4.6, Annexure A clauses 3, 4, 5 & 6
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - On-site verification sheet
holdpoint | HOLD POINT
checkpoint | 12 - Surface level check/ and survey pick-up
label | Responsibility - SURV
label | Method - Survey/ Field Test
label | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
label | Specification Clause - EVAMP001-THS-CV-SPE-0002 clauses 4.2 & 4.3, Annexure A clause 6
label | Frequency - As Required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
label | Records or Comments - On-site verification sheet
holdpoint | HOLD POINT
section | Post Construction
checkpoint | 13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Method - Visual
label | Conformance Criteria - ITP closed. Approved MDR
label | Specification Clause - EVAMP001-THS-CV-SPE-0002
label | — EVA PMP
label | Frequency - As Required
label | Verification from Thiess / Inspector: THIESS (Initial) - HP
label | Verification from Thiess / Inspector: Inspector (Initial) - HP
holdpoint | HOLD POINT