## Sheet1
1 | Permits | W | Obtain Permits | As required | Document Review | Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place | Permit attached or permit number noted | 1 - Permits | ACTION (Hold, Monitor, Witness) - W | DETAIL - Obtain Permits | FREQUENCY - As required | INSPECTION / TEST METHOD - Document Review | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place | RECORDS - Permit attached or permit number noted | 1 - Permits
2 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | — | Check Drawing Register | 2 - Design | ACTION (Hold, Monitor, Witness) - W | DETAIL - Ensure that Design is approved and Drawings are of the latest revision | FREQUENCY - Prior to commencement | INSPECTION / TEST METHOD - Document Review | CONFORMANCE CRITERIA - — | RECORDS - Check Drawing Register | ACTION (Hold, Monitor, Witness) - W
3 | Previous Lots Completed | W | All previous pavement lots signed off | Prior to commencement | Document Review | Previous ITP must be completed | — | 3 - Previous Lots Completed | ACTION (Hold, Monitor, Witness) - W | DETAIL - All previous pavement lots signed off | FREQUENCY - Prior to commencement | INSPECTION / TEST METHOD - Document Review | CONFORMANCE CRITERIA - Previous ITP must be completed | RECORDS - — | DETAIL - Obtain Permits
4 | Survey Setout | W | Determine chipsealing runs start/stop locations, extent of area to be chipsealed | Prior to commencement | Measure, Inspect | Mark out on site | Chipsealing Dept QA Records | 4 - Survey Setout | ACTION (Hold, Monitor, Witness) - W | DETAIL - Determine chipsealing runs start/stop locations, extent of area to be chipsealed | FREQUENCY - Prior to commencement | INSPECTION / TEST METHOD - Measure, Inspect | CONFORMANCE CRITERIA - Mark out on site | RECORDS - Chipsealing Dept QA Records | FREQUENCY - As required
5 | Material Compliance | H | Bitumen/Emulsion Mix Design approved | Prior to commencement | Submission | Material is approved by a Notice to Supplier being issued | Mix Design | 5 - Material Compliance | ACTION (Hold, Monitor, Witness) - H | DETAIL - Bitumen/Emulsion Mix Design approved | FREQUENCY - Prior to commencement | INSPECTION / TEST METHOD - Submission | CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued | RECORDS - Mix Design | INSPECTION / TEST METHOD - Document Review
6 | Chip grade and application rates | H | Chip grade and application rates determined and submitted for approval | Prior to commencement | Submission | Material is approved by a Notice to Supplier being issued | Mix Design | 6 - Chip grade and application rates | ACTION (Hold, Monitor, Witness) - H | DETAIL - Chip grade and application rates determined and submitted for approval | FREQUENCY - Prior to commencement | INSPECTION / TEST METHOD - Submission | CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued | RECORDS - Mix Design | CONFORMANCE CRITERIA - Ensure all necessary Permit to Works CHAR(AMP) Controlled Checklists are in place
7 | Pavement approval to have Chipsealing commence | H | Subgrade and Basecourse to be at an acceptable standard. Surface to have mosaic surface prepared for bitumen/emulsion application. | Prior to commencement | Review | Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing | Subcontractor QA Records, Pre-seal checklist | 7 - Pavement approval to have Chipsealing commence | ACTION (Hold, Monitor, Witness) - H | DETAIL - Subgrade and Basecourse to be at an acceptable standard. Surface to have mosaic surface prepared for bitumen/emulsion application. | FREQUENCY - Prior to commencement | INSPECTION / TEST METHOD - Review | CONFORMANCE CRITERIA - Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing | RECORDS - Subcontractor QA Records, Pre-seal checklist | RECORDS - Permit attached or permit number noted
8 | Chipsealing new surface | W | Chipsealing team QA Checks | During Construction | Site Measurements | Confirmation of application rates, site QA documentation developed by sealing dept | Subcontractor QA Records, Photos | 8 - Chipsealing new surface | ACTION (Hold, Monitor, Witness) - W | DETAIL - Chipsealing team QA Checks | FREQUENCY - During Construction | INSPECTION / TEST METHOD - Site Measurements | CONFORMANCE CRITERIA - Confirmation of application rates, site QA documentation developed by sealing dept | RECORDS - Subcontractor QA Records, Photos | 2 - Design
9 | Post seal Checks | W | Post sealing review the surface to make sure chip has set. Road Sweeping to be carried out after sealed surface is sound (~48 hours afer sealing) | Post Sealing | Site Measurements | Confirmation of application rates, site QA documentation developed by sealing dept | Photos | 9 - Post seal Checks | ACTION (Hold, Monitor, Witness) - W | DETAIL - Post sealing review the surface to make sure chip has set. Road Sweeping to be carried out after sealed surface is sound (~48 hours afer sealing) | FREQUENCY - Post Sealing | INSPECTION / TEST METHOD - Site Measurements | CONFORMANCE CRITERIA - Confirmation of application rates, site QA documentation developed by sealing dept | RECORDS - Photos | ACTION (Hold, Monitor, Witness) - W
10 | Linemarking | W | Linemarking to be painted per design requirements | Post Sealing | Site Measurements, review | Linemarking is placed per drawings, or as agreed with Engineer | Photos | 10 - Linemarking | ACTION (Hold, Monitor, Witness) - W | DETAIL - Linemarking to be painted per design requirements | FREQUENCY - Post Sealing | INSPECTION / TEST METHOD - Site Measurements, review | CONFORMANCE CRITERIA - Linemarking is placed per drawings, or as agreed with Engineer | RECORDS - Photos | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
11 | As-builts | H | As-builts and QA submitted per contract requirements | At the completion of the Lot of work | Drawings | Uploaded to CONQA | Asbuilt Drawing | 11 - As-builts | ACTION (Hold, Monitor, Witness) - H | DETAIL - As-builts and QA submitted per contract requirements | FREQUENCY - At the completion of the Lot of work | INSPECTION / TEST METHOD - Drawings | CONFORMANCE CRITERIA - Uploaded to CONQA | RECORDS - Asbuilt Drawing | FREQUENCY - Prior to commencement
INSPECTION / TEST METHOD - Document Review
CONFORMANCE CRITERIA - —
RECORDS - Check Drawing Register
3 - Previous Lots Completed
ACTION (Hold, Monitor, Witness) - W
DETAIL - All previous pavement lots signed off
FREQUENCY - Prior to commencement
INSPECTION / TEST METHOD - Document Review
CONFORMANCE CRITERIA - Previous ITP must be completed
RECORDS - —
4 - Survey Setout
ACTION (Hold, Monitor, Witness) - W
DETAIL - Determine chipsealing runs start/stop locations, extent of area to be chipsealed
FREQUENCY - Prior to commencement
INSPECTION / TEST METHOD - Measure, Inspect
CONFORMANCE CRITERIA - Mark out on site
RECORDS - Chipsealing Dept QA Records
5 - Material Compliance
ACTION (Hold, Monitor, Witness) - H
DETAIL - Bitumen/Emulsion Mix Design approved
FREQUENCY - Prior to commencement
INSPECTION / TEST METHOD - Submission
CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued
RECORDS - Mix Design
6 - Chip grade and application rates
ACTION (Hold, Monitor, Witness) - H
DETAIL - Chip grade and application rates determined and submitted for approval
FREQUENCY - Prior to commencement
INSPECTION / TEST METHOD - Submission
CONFORMANCE CRITERIA - Material is approved by a Notice to Supplier being issued
RECORDS - Mix Design
7 - Pavement approval to have Chipsealing commence
ACTION (Hold, Monitor, Witness) - H
DETAIL - Subgrade and Basecourse to be at an acceptable standard. Surface to have mosaic surface prepared for bitumen/emulsion application.
FREQUENCY - Prior to commencement
INSPECTION / TEST METHOD - Review
CONFORMANCE CRITERIA - Delivery temperature, mat thickness before compaction, mix temperature during compaction, compaction testing
RECORDS - Subcontractor QA Records, Pre-seal checklist
8 - Chipsealing new surface
ACTION (Hold, Monitor, Witness) - W
DETAIL - Chipsealing team QA Checks
FREQUENCY - During Construction
INSPECTION / TEST METHOD - Site Measurements
CONFORMANCE CRITERIA - Confirmation of application rates, site QA documentation developed by sealing dept
RECORDS - Subcontractor QA Records, Photos
9 - Post seal Checks
ACTION (Hold, Monitor, Witness) - W
DETAIL - Post sealing review the surface to make sure chip has set. Road Sweeping to be carried out after sealed surface is sound (~48 hours afer sealing)
FREQUENCY - Post Sealing
INSPECTION / TEST METHOD - Site Measurements
CONFORMANCE CRITERIA - Confirmation of application rates, site QA documentation developed by sealing dept
RECORDS - Photos
10 - Linemarking
ACTION (Hold, Monitor, Witness) - W
DETAIL - Linemarking to be painted per design requirements
FREQUENCY - Post Sealing
INSPECTION / TEST METHOD - Site Measurements, review
CONFORMANCE CRITERIA - Linemarking is placed per drawings, or as agreed with Engineer
RECORDS - Photos
11 - As-builts
ACTION (Hold, Monitor, Witness) - H
DETAIL - As-builts and QA submitted per contract requirements
FREQUENCY - At the completion of the Lot of work
INSPECTION / TEST METHOD - Drawings
CONFORMANCE CRITERIA - Uploaded to CONQA
RECORDS - Asbuilt Drawing