## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - CONOC Construction (Dunedin Airport) - Pavement Construction Area 1, 2, 3, 3A, 4 & 5 | itp |  |  |  |  | ITP - CONOC Construction (Dunedin Airport) - Pavement Construction Area 1, 2, 3, 3A, 4 & 5
section | 1.1 - General
checkpoint | 1.1.1 - Contract Management plans, (including ITP)
label | Controlled By : (Position) - Project Manager
label | Accept / Reject Criteria - The Contractor to provide contract management plans as defined in the project specification prior to commencement of works. ITP to be reviewed and updated upon receipt of construction issue drawings/Specification.
label | Frequency Of Inspection Or Test - Prior to physical works
label | Spec. Ref, Procedure Or Method Statement - Project Specification NTC / Email verification approving Contract Management Plans
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - H
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.1 - Site Specific Requirements
checkpoint | 2.1 - Construction Pack (SSSP/CBP)
label | Controlled By : (Position) - SE, FM
label | Accept / Reject Criteria - Construction Pack including Site Specific Safety Plan developed for work area and issued to Engineer in advance of works.
label | Frequency Of Inspection Or Test - Prior to physical works 1 per site
label | Spec. Ref, Procedure Or Method Statement - Downer/Construction Pack
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Service Location
label | Controlled By : (Position) - SE, FM
label | Accept / Reject Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Frequency Of Inspection Or Test - Prior to Excavation 1 per site/work area
label | Spec. Ref, Procedure Or Method Statement - Downer/Excavation Permit
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Internal Permits
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Frequency Of Inspection Or Test - Prior to Excavation as needed
label | Spec. Ref, Procedure Or Method Statement - Downer/Internal Permits
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - External Permits
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Obtain External Permits as required to complete works including but not limited to: Airport Inductions, Close approach, Worksafe Notice etc.
label | Frequency Of Inspection Or Test - Prior to Excavation as needed
label | Spec. Ref, Procedure Or Method Statement - Downer/External Permits
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.1 - Construction
checkpoint | 3.1.1 - Insitu Subgrade Fill Material
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - AP150 - Duncans Quarry (Abbotsford)
label | Frequency Of Inspection Or Test - Annually/Project
label | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Insitu Subgrade Fill Material
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - AP65 - Duncans Quarry (Abbotsford)
label | Frequency Of Inspection Or Test - Annually/Project
label | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Basecourse Aggregates
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - M4-AP40 - Blackhead Quarries
label | Frequency Of Inspection Or Test - Annually/Project
label | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Basecourse Aggregates
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - M4-AP20 - Duncans Quarry (Abbotsford)
label | Frequency Of Inspection Or Test - Annually/Project
label | Spec. Ref, Procedure Or Method Statement - Project Specification/As per NZTA Specifications
checkpoint | 3.1.5 - Geofabric
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Installation of geogrid/geocloth (A29/TX160) when instructed by Engineer. AP65 Compacted in layers not exceeding 200mm.
label | Frequency Of Inspection Or Test - Annually/Project
label | Spec. Ref, Procedure Or Method Statement - NZTA F/1, TNZ M/3 Notes/As per NZTA Specifications
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.2 - Paving
checkpoint | 3.2.1 - Road Asphalt
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 50mm AC14
label | Frequency Of Inspection Or Test - Supplied/approved annually by Engineer to Contract/Prior to AC
label | Spec. Ref, Procedure Or Method Statement - Project Specification TNZ M/10:2020/Approved Mix Design
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Road Asphalt
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | Frequency Of Inspection Or Test - Supplied/approved annually by ETC/Prior to AC
label | Spec. Ref, Procedure Or Method Statement - Project Specification NZTA M32: 2021/Approved Mix Design
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.3 - Pavement Marking
checkpoint | 3.3.1 - Standard Marking
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Standards pavement marking. Paint shall comply with TNZ M7 and shall be on the current Transit New Zealand list of approved paints.
label | Frequency Of Inspection Or Test - Approved once by ETC/Prior to Line Marking
label | Spec. Ref, Procedure Or Method Statement - Project Specification TNZ/LTSA (MOTSAM)/Approved pavement marking quality system
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 - Excavation
checkpoint | 4.1.1 - Site Clearance
label | Controlled By : (Position) - SE, ENG
label | Accept / Reject Criteria - Unless shown otherwise on the drawings or directed by the Engineer, all vegetation, shrubs, trees under 3m in height, fences and foundations, retaining timbers, abandoned pipes and services, etc over the contract length and within the extent of the earthworks shall be removed off site.
label | ○ All waste will be disposed at DIAL approved location.
label | Frequency Of Inspection Or Test - Prior to Excavation/clearance works/per site
label | Spec. Ref, Procedure Or Method Statement - Project Specification/Pre construction walkover inspection DNZ Field Inspection Record
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Excavation
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Excavation carried out as per project extents detailed on construction issue drawings.
label | ○ Level as per subgrade requirements below.
label | Frequency Of Inspection Or Test - Per site specific requirements/as required
label | Spec. Ref, Procedure Or Method Statement - NZTA F1 DNZ Field Inspection Record
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Subgrade
checkpoint | 5.1.1 - Subgrade Suitability Inspection
label | Controlled By : (Position) - SE, ENG
label | Accept / Reject Criteria - The Subgrade must be inspected by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
label | ○ Where Scala testing is deemed unsuitable by Contractor (hardfill or Service Strike Risk etc). Visual inspection by Engineer supersedes foundation testing requirements - Site instruction required.
label | ○ Should material be determined as unsuitable (highly organic, saturated clay pug etc) Contractor to elevate to Engineer who will determine whether the material is unsuitable or not and agree the extent of the unsuitable material with the Contractor.
label | Frequency Of Inspection Or Test - 20m where practical
label | ○ Not required for failed visual inspection areas (ie wet pug, highly organic material)/per site
label | Spec. Ref, Procedure Or Method Statement - NZTA F/1 Scala Report (CBR 5)
label | ○ 3blows per 100mm
label | ○ Visual Inspection
label | ○ DNZ Field Inspection Record
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1.2 - Geofabric installation
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Installation of geogrid/geocloth (A29/TX160) as per design.
label | ○ AP40 compacted in layer not exceeding 100mm, AP65 not exceeding 200mm and AP150 not exceeding 300mm.
label | Frequency Of Inspection Or Test - 10,000m3/Project
label | Spec. Ref, Procedure Or Method Statement - NZTA F/1 TNZ M/3 Notes IANZ Lab Reports (on request)
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.1.3 - Subgrade formation level - Kerbs
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Excavation Min 300mm from design lip level (road tie in) allowing for minimum 120mm M440 foundation for kerbs.
label | Frequency Of Inspection Or Test - Per site specific requirements/Project
label | Spec. Ref, Procedure Or Method Statement - Downer NZTA B/2:2005 DNZ Field Inspection Record
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 6.1 - Area 1
checkpoint | 6.1.1 - Remove top 100mm
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Rip surface and lime treat subbase
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.2 - Subject to Beams Test
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Backfill or Seal
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records and Results
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.3 - Backfill
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - AP40 and stabilise top 200mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1.4 - Surfacing
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | Frequency Of Inspection Or Test - Prior to AC/1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 6.2 - Area 2
checkpoint | 6.2.1 - Remove top 600mm
label | Controlled By : (Position) - SE
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.2 - Geofabric
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - A29 Fabric
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.3 - AP150
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 300mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.4 - Geofabric
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - TX160
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.5 - AP65
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 200mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.6 - AP40
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 100mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2.7 - Surfacing
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 6.3 - Area 3 & 3A
checkpoint | 6.3.1 - Remove existing surface
label | Controlled By : (Position) - SE
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3.2 - Prep to suit existing kerb and drianage
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - AP150
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape and falls
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3.3 - Surfacing
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 50mm AC14
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 6.4 - Area 4
checkpoint | 6.4.1 - Remove top 650mm
label | Controlled By : (Position) - SE
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4.2 - Geofabric
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - A29 Fabric
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4.3 - AP150
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 300mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4.4 - Geofabric
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - TX160
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4.5 - AP65
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 200mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records with measuring tape
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4.6 - AP40
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 100mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4.7 - Surfacing
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 50mm AC14
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 6.5 - Area 5 - Optional
checkpoint | 6.5.1 - Mill top 90mm
label | Controlled By : (Position) - SE
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5.2 - Subject to Beams Test
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Backfill or Seal
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records and Results
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5.3 - Backfill
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - AP40 and stabilise top 200mm
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Photographic records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5.4 - Surfacing
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - 90mm EME2 (Trial Mix)
label | Frequency Of Inspection Or Test - 1 per pavement area
label | Spec. Ref, Procedure Or Method Statement - Project Specification Approved Mix Design
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
section | 7 - Post Construction (Final Inspection and Handover)
checkpoint | 7.1 - Final Completion inspection
label | Controlled By : (Position) - PM, ENG
label | Accept / Reject Criteria - Walk over completed with the Engineer/Engineers Representative to review completed works.
label | ○ Noting any minor omissions, transfer to snag list (NCR if deemed necessary)
label | Frequency Of Inspection Or Test - Each Site (School Zone etc)/Per package of works
label | Spec. Ref, Procedure Or Method Statement - DNZ Field Inspection Record
label | ○ Practical Completion Certificate (Per package of works, ie SP1/SP2)
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Construction Record Compilation
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Frequency Of Inspection Or Test - Post construction/Per package of works
label | Spec. Ref, Procedure Or Method Statement - Records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - Survey Records
label | Controlled By : (Position) - SV
label | Accept / Reject Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Frequency Of Inspection Or Test - Post construction/Per package of works
label | Spec. Ref, Procedure Or Method Statement - Records
label | Records Required - Yes
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 - Asbuilt Drawings
label | Controlled By : (Position) - SE
label | Accept / Reject Criteria - Supplied in accordance with Project specification
label | Frequency Of Inspection Or Test - Post construction/Per package of works
label | Spec. Ref, Procedure Or Method Statement - Records
label | Records Required - YES
label | DOWNER ENGINEER - H
label | SUPERVISOR - R
label | SUB-CON - H
holdpoint | AUTHORITY HOLDPOINT