## Sheet1
3.1 | Material Delivery | Inspect for damage and wear, Confirm items are correct as per drawings and Specifications | - Items are approved as per contract specification or as agreed by the engineer - DCC approved | Photos, delivery docket, MDD results for backfill materials (if required) | On Delivery | Visual | C | PE/QE | 3.1 - Material Delivery | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications | Acceptance Criteria - - Items are approved as per contract specification or as agreed by the engineer - DCC approved | Verifying Document - Photos, delivery docket, MDD results for backfill materials (if required) | Frequency - On Delivery | Inspection Type (Visual, other) - Visual | Inspection: Key - C | Inspection: By (Role Key) - PE/QE | 3.1 - Material Delivery
3.2 | Set out | Set out completed by an approved surveyor marked allignment | Allignment set out matches drawings, 2D data and linework provided or aggreed with the Engineer | Survey marks, photos | Prior to commencement of works | Visual, Instrumental | H | SV/QE/PE/CR | 3.2 - Set out | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment | Acceptance Criteria - Allignment set out matches drawings, 2D data and linework provided or aggreed with the Engineer | Verifying Document - Survey marks, photos | Frequency - Prior to commencement of works | Inspection Type (Visual, other) - Visual, Instrumental | Inspection: Key - H | Inspection: By (Role Key) - SV/QE/PE/CR | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
4.1 | Trench Excavation | - excavate to achieve required depth as per Drawing C4600,C4500 - Floor of trench to be even across width and length | - Allow 100mm for bedding - Allow for minimum cover of 600mm. | Photos | During Installation | Visual | V | SP/QE/PE | 4.1 - Trench Excavation | Inspection Point: Quality Control Activity - - excavate to achieve required depth as per Drawing C4600,C4500 - Floor of trench to be even across width and length | Acceptance Criteria - - Allow 100mm for bedding - Allow for minimum cover of 600mm. | Verifying Document - Photos | Frequency - During Installation | Inspection Type (Visual, other) - Visual | Inspection: Key - V | Inspection: By (Role Key) - SP/QE/PE | Acceptance Criteria - - Items are approved as per contract specification or as agreed by the engineer - DCC approved
4.2 | Foundation | Scala tests on base of trench | minimum of 2 blows per 100mm | test results | During installation, per 20m | Visual, On site test | H | SP/QE | 4.2 - Foundation | Inspection Point: Quality Control Activity - Scala tests on base of trench | Acceptance Criteria - minimum of 2 blows per 100mm | Verifying Document - test results | Frequency - During installation, per 20m | Inspection Type (Visual, other) - Visual, On site test | Inspection: Key - H | Inspection: By (Role Key) - SP/QE | Verifying Document - Photos, delivery docket, MDD results for backfill materials (if required)
4.3 | Install Duct | - Ducting installed and positioned as per design | - Duct not damaged during installation - minimum of 150mm horizontal and vertical clearence from other services or as specified on Drawings C4600, C4500 | Photos, Survey of position for asbuilt, weld records (if required) | During installation | Visual | V | SP/QE | 4.3 - Install Duct | Inspection Point: Quality Control Activity - - Ducting installed and positioned as per design | Acceptance Criteria - - Duct not damaged during installation - minimum of 150mm horizontal and vertical clearence from other services or as specified on Drawings C4600, C4500 | Verifying Document - Photos, Survey of position for asbuilt, weld records (if required) | Frequency - During installation | Inspection Type (Visual, other) - Visual | Inspection: Key - V | Inspection: By (Role Key) - SP/QE | Frequency - On Delivery
4.4 | Embedment zone | Embedment material shall be AP20 or approved by the Engineer in writing | - min 100mm bedding - 100mm overlay | Photos | During Installation | Visual, measurement check | V | SP/QE | 4.4 - Embedment zone | Inspection Point: Quality Control Activity - Embedment material shall be AP20 or approved by the Engineer in writing | Acceptance Criteria - - min 100mm bedding - 100mm overlay | Verifying Document - Photos | Frequency - During Installation | Inspection Type (Visual, other) - Visual, measurement check | Inspection: Key - V | Inspection: By (Role Key) - SP/QE | Inspection Type (Visual, other) - Visual
4.5 | Backfill and Compact | - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at 300mm above duct | 95% MDD in roads, paths, and pavements | Photos, Compaction test results | During Installation, compaction testing per 50m of pipeline | Visual, On Site test | H | SP/QE/PE | 4.5 - Backfill and Compact | Inspection Point: Quality Control Activity - - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at 300mm above duct | Acceptance Criteria - 95% MDD in roads, paths, and pavements | Verifying Document - Photos, Compaction test results | Frequency - During Installation, compaction testing per 50m of pipeline | Inspection Type (Visual, other) - Visual, On Site test | Inspection: Key - H | Inspection: By (Role Key) - SP/QE/PE | Inspection: Key - C
5.1 | As built |  | Engineer Approval | QA records | at completion |  | H | CR/PM | 5.1 - As built | Inspection Point: Quality Control Activity - | Acceptance Criteria - Engineer Approval | Verifying Document - QA records | Frequency - at completion | Inspection Type (Visual, other) - | Inspection: Key - H | Inspection: By (Role Key) - CR/PM | 3.2 - Set out
Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
Acceptance Criteria - Allignment set out matches drawings, 2D data and linework provided or aggreed with the Engineer
Verifying Document - Survey marks, photos
Frequency - Prior to commencement of works
Inspection Type (Visual, other) - Visual, Instrumental
Inspection: Key - H
4.1 - Trench Excavation
Inspection Point: Quality Control Activity - - excavate to achieve required depth as per Drawing C4600,C4500 - Floor of trench to be even across width and length
Acceptance Criteria - - Allow 100mm for bedding - Allow for minimum cover of 600mm.
Verifying Document - Photos
Frequency - During Installation
Inspection Type (Visual, other) - Visual
Inspection: Key - V
4.2 - Foundation
Inspection Point: Quality Control Activity - Scala tests on base of trench
Acceptance Criteria - minimum of 2 blows per 100mm
Verifying Document - test results
Frequency - During installation, per 20m
Inspection Type (Visual, other) - Visual, On site test
Inspection: Key - H
4.3 - Install Duct
Inspection Point: Quality Control Activity - - Ducting installed and positioned as per design
Acceptance Criteria - - Duct not damaged during installation - minimum of 150mm horizontal and vertical clearence from other services or as specified on Drawings C4600, C4500
Verifying Document - Photos, Survey of position for asbuilt, weld records (if required)
Frequency - During installation
Inspection Type (Visual, other) - Visual
Inspection: Key - V
4.4 - Embedment zone
Inspection Point: Quality Control Activity - Embedment material shall be AP20 or approved by the Engineer in writing
Acceptance Criteria - - min 100mm bedding - 100mm overlay
Verifying Document - Photos
Frequency - During Installation
Inspection Type (Visual, other) - Visual, measurement check
Inspection: Key - V
4.5 - Backfill and Compact
Inspection Point: Quality Control Activity - - Backfill in 200mm layers of compacted material - Compaction testing one test every two layers as required - conductive signal strip to be laid at 300mm above duct
Acceptance Criteria - 95% MDD in roads, paths, and pavements
Verifying Document - Photos, Compaction test results
Frequency - During Installation, compaction testing per 50m of pipeline
Inspection Type (Visual, other) - Visual, On Site test
Inspection: Key - H
5.1 - As built
Inspection Point: Quality Control Activity -
Acceptance Criteria - Engineer Approval
Verifying Document - QA records
Frequency - at completion
Inspection Type (Visual, other) -
Inspection: Key - H