## Sheet1
7.1 | Final Completion inspection | PM, ENG | Walk over completed with the Engineer/Engineers Representative to review completed works. Noting any minor omissions, transfer to snag list (NCR if deemed necessary) | Each Site (School Zone etc)/Per package of works | DNZ Field Inspection Record Practical Completion Certificate (Per package of works, ie SP1/SP2) | YES | H | R | H | 7.1 - Final Completion inspection | Controlled By : (Position) - PM, ENG | Accept / Reject Criteria - Walk over completed with the Engineer/Engineers Representative to review completed works. Noting any minor omissions, transfer to snag list (NCR if deemed necessary) | Frequency Of Inspection Or Test - Each Site (School Zone etc)/Per package of works | Spec. Ref, Procedure Or Method Statement - DNZ Field Inspection Record Practical Completion Certificate (Per package of works, ie SP1/SP2) | Records Required - YES | DOWNER ENGINEER - H | SUPERVISOR - R | SUB-CON - H | 7.1 - Final Completion inspection
7.2 | Construction Record Compilation | SE | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Post construction/Per package of works | Records | YES | H | R | H | 7.2 - Construction Record Compilation | Controlled By : (Position) - SE | Accept / Reject Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Frequency Of Inspection Or Test - Post construction/Per package of works | Spec. Ref, Procedure Or Method Statement - Records | Records Required - YES | DOWNER ENGINEER - H | SUPERVISOR - R | SUB-CON - H | Controlled By : (Position) - PM, ENG
Accept / Reject Criteria - Walk over completed with the Engineer/Engineers Representative to review completed works. Noting any minor omissions, transfer to snag list (NCR if deemed necessary)
7.3 | Survey Records | SV | Ensure all items have been surveyed and records are assembled for asbuilting | Post construction/Per package of works | Records | Yes | H | R | H | 7.3 - Survey Records | Controlled By : (Position) - SV | Accept / Reject Criteria - Ensure all items have been surveyed and records are assembled for asbuilting | Frequency Of Inspection Or Test - Post construction/Per package of works | Spec. Ref, Procedure Or Method Statement - Records | Records Required - Yes | DOWNER ENGINEER - H | SUPERVISOR - R | SUB-CON - H | Frequency Of Inspection Or Test - Each Site (School Zone etc)/Per package of works
7.4 | Asbuilt Drawings | SE | Supplied in accordance with Project specification | Post construction/Per package of works | Records | YES | H | R | H | 7.4 - Asbuilt Drawings | Controlled By : (Position) - SE | Accept / Reject Criteria - Supplied in accordance with Project specification | Frequency Of Inspection Or Test - Post construction/Per package of works | Spec. Ref, Procedure Or Method Statement - Records | Records Required - YES | DOWNER ENGINEER - H | SUPERVISOR - R | SUB-CON - H | Spec. Ref, Procedure Or Method Statement - DNZ Field Inspection Record Practical Completion Certificate (Per package of works, ie SP1/SP2)
Records Required - YES
DOWNER ENGINEER - H
SUPERVISOR - R
SUB-CON - H
7.2 - Construction Record Compilation
Controlled By : (Position) - SE
Accept / Reject Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
Frequency Of Inspection Or Test - Post construction/Per package of works
Spec. Ref, Procedure Or Method Statement - Records
Records Required - YES
DOWNER ENGINEER - H
SUPERVISOR - R
SUB-CON - H
7.3 - Survey Records
Controlled By : (Position) - SV
Accept / Reject Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
Frequency Of Inspection Or Test - Post construction/Per package of works
Spec. Ref, Procedure Or Method Statement - Records
Records Required - Yes
DOWNER ENGINEER - H
SUPERVISOR - R
SUB-CON - H
7.4 - Asbuilt Drawings
Controlled By : (Position) - SE
Accept / Reject Criteria - Supplied in accordance with Project specification
Frequency Of Inspection Or Test - Post construction/Per package of works
Spec. Ref, Procedure Or Method Statement - Records
Records Required - YES
DOWNER ENGINEER - H
SUPERVISOR - R
SUB-CON - H