## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP-047-CIV-CPD-Type B FIll - Road | itp |  |  |  | Yes | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | 51c5fee6-4576-467f-8804-773232db449e
checkpoint-group | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-CIV-CPD-Type B Fill - Road (Supply and Install)
label | ITP Description: Type B Fill - Road (Supply and Install)
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV-CPD
label | Revision Number: 1
label | Revision Date: 25/10/2023
label | ITP created by: Matthew Dib
label | ITP approved for use by: Pradeep Talasila
checkpoint-status | 1.1 - Non Dependent
label | Reference - Reference Documents:
label | • IFC Drawings
label | • VicRoads Standard Section 176 (10/9/2008)
label | • VicRoads Standard Section 204 (29/12/2015)
checkpoint-group | 2. Preliminaries
checkpoint-status | 2.1 - Material Supply
label | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
label | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
label | Method - Doc. Review
label | Frequency - Prior to Commencement
label | Category - HP
label | Verifying Documents - NATA Test Certificate
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 3. Pre-construction / Pre-installation Activities
checkpoint-status | 3.1 - Survey Set Out
label | Reference - Design Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | Method - Visual Inspection
label | Frequency - Each lot prior to commencement
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint-status | 3.2 - Pre-Commencement of Fill Works
label | Reference - Section 204.10 (b)
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 4. Construction / Installation Activities
checkpoint-status | 4.1 - Placing of Fill
label | Reference - Section 204.10 (d) (iii)
label | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
label | Method - Monitor
label | Frequency - Each layer
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint-status | 4.2 - Keying of Layers
label | Reference - Section 204.10(d)(i)
label | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
label | Method - Monitor
label | Frequency - Each layer
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint-status | 4.3 - Test Rolling
label | Reference - Section 204.12, 173.03
label | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
label | Method - Measure
label | Frequency - Each layer
label | Category - HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 4.4 - Post Compaction Testing
label | Reference - Section Table 204.131, 204.13, 204.14
label | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | Scale B: Characteristic Density Ratio 98%.
label | Attach: Compaction Test Result:
label | Method - Doc. Review
label | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
label | ○ Placed within 400 mm of top of Type B: Test every second lot of like material and work
label | ○ Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
label | Verifying Documents - NATA Test Certificate
date | Date Completed:
checkpoint-status | 4.5 - Preparation of final surface
label | Reference - Section 204.15, 204.03 (g)
label | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | Method - Measure
label | Frequency - Top layer
label | Verifying Documents - Signed ITP
date | Date Completed:
checkpoint-group | 5. Post-construction / Post-installation Activities
checkpoint-status | 5.1 - Survey Conformance As Built
label | Reference - Section 204.10(h)
label | Acceptance Criteria - The Contractor shall establish a procedure to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
label | Method - Review
label | Frequency - Every 3 layers
label | Verifying Documents - Survey Thickness Conformance
date | Date Completed:
checkpoint-status | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP