## GT01
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-GT01-PIL-001 | PI North - GT1-Pile 01-14 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-13 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-002 | PI North - GT1-Pile 01-12 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-13 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-003 | PI North - GT1-Pile 01-10 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-13 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-004 | PI North - GT1-Pile 01-08 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-13 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-005 | PI North - GT1-Pile 01-06 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-13 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-006 | PI North - GT1-Pile 01-05 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-14 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-007 | PI North - GT1-Pile 01-03 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-14 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-008 | PI North - GT1-Pile 01-01 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-14 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-009 | PI North - GT1-Pile 01-13 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-14 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-010 | PI North - GT1-Pile 01-11 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-14 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-011 | PI North - GT1-Pile 01-09 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-17 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-012 | PI North - GT1-Pile 01-07 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-17 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-013 | PI North - GT1-Pile 01-04 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-17 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-014 | PI North - GT1-Pile 01-02 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-17 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-015 | PI North - GT1-Pile 01-28 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-17 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-016 | PI North - GT1-Pile 01-26 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-17 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-017 | PI North - GT1-Pile 01-24 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-18 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-018 | PI North - GT1-Pile 01-22 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-18 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-019 | PI North - GT1-Pile 01-20 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-18 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-020 | PI North - GT1-Pile 01-18 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-18 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-021 | PI North - GT1-Pile 01-16 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-18 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-022 | PI North - GT1-Pile 01-27 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-19 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-023 | PI North - GT1-Pile 01-25 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-19 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-024 | PI North - GT1-Pile 01-23 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-19 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-025 | PI North - GT1-Pile 01-21 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-19 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-026 | PI North - GT1-Pile 01-19 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-19 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-027 | PI North - GT1-Pile 01-17 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-21 | 2022-12-07 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-028 | PI North - GT1-Pile 01-15 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-21 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-029 | PI North - GT1-Pile 01-42 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-25 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-030 | PI North - GT1-Pile 01-40 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-25 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-031 | PI North - GT1-Pile 01-38 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-27 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-032 | PI North - GT1-Pile 01-36 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-27 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-033 | PI North - GT1-Pile 01-34 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-27 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-034 | PI North - GT1-Pile 01-32 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-27 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-035 | PI North - GT1-Pile 01-30 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-27 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-036 | PI North - GT1-Pile 01-41 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-27 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-037 | PI North - GT1-Pile 01-56 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-28 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-038 | PI North - GT1-Pile 01-39 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-28 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-039 | PI North - GT1-Pile 01-37 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-28 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-040 | PI North - GT1-Pile 01-35 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-28 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-041 | PI North - GT1-Pile 01-33 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-28 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-042 | PI North - GT1-Pile 01-31 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-29 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-043 | PI North - GT1-Pile 01-29 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-29 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-044 | PI North - GT1-Pile 01-55 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-29 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-045 | PI North - GT1-Pile 01-54 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-31 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-046 | PI North - GT1-Pile 01-52 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-31 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-047 | PI North - GT1-Pile 01-50 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-10-31 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-048 | PI North - GT1-Pile 01-48 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-03 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-049 | PI North - GT1-Pile 01-46 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-03 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-050 | PI North - GT1-Pile 01-44 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-03 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-051 | PI North - GT1-Pile 01-53 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-03 | 2022-12-07 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-052 | PI North - GT1-Pile 01-51 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-03 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-053 | PI North - GT1-Pile 01-43 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-04 | 2022-12-07 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-054 | PI North - GT1-Pile 01-45 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-04 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-055 | PI North - GT1-Pile 01-47 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-04 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-056 | PI North - GT1-Pile 01-49 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-04 | 2022-12-06 | Y | Y | Y | NCR-00001 |  | Y |  |  | 2023-01-12 | 2023-01-12
CC0375-GT01-PIL-057 | PI North - Transformer-Pile 02-19 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-058 | PI North - Transformer-Pile 02-20 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-059 | PI North - Transformer-Pile 02-21 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-060 | PI North - Transformer-Pile 02-13 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-061 | PI North - Transformer-Pile 02-14 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-062 | PI North - Transformer-Pile 02-15 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-063 | PI North - Transformer-Pile 02-7 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-064 | PI North - Transformer-Pile 02-8 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-08 | 2022-12-08 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-065 | PI North - Transformer-Pile 02-22 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-066 | PI North - Transformer-Pile 02-23 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-067 | PI North - Transformer-Pile 02-24 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-068 | PI North - Transformer-Pile 02-16 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-069 | PI North - Transformer-Pile 02-17 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-070 | PI North - Transformer-Pile 02-18 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-071 | PI North - Transformer-Pile 02-10 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-072 | PI North - Transformer-Pile 02-11 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-073 | PI North - Transformer-Pile 02-12 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-09 | 2022-12-09 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-074 | PI North - Transformer-Pile 02-09 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-10 | 2022-12-10 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-075 | PI North - Transformer-Pile 02-06 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-16 | 2022-12-16 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-076 | PI North - Transformer-Pile 02-04 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-16 | 2022-12-16 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-077 | PI North - Transformer-Pile 02-02 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-16 | 2022-12-16 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-078 | PI North - Transformer-Pile 02-05 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-10 | 2023-03-10 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-079 | PI North - Transformer-Pile 02-03 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-10 | 2023-03-10 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-080 | PI North - Transformer-Pile 02-01 | CFA Piling | Work Complete | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-10 | 2023-03-10 | N | N | N |  |  |  |  | Pending PIT test
CC0375-GT01-PIL-081 | PI North - GCB & EXC-GT-1-Pile 09-03 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-03-31 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-082 | PI North - GCB & EXC-GT-1-Pile 09-07 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-03-31 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-083 | PI North - GCB & EXC-GT-1-Pile 09-02 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-01 | 2023-04-01 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-084 | PI North - GCB & EXC-GT-1-Pile 09-04 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-01 | 2023-04-01 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-085 | PI North - GCB & EXC-GT-1-Pile 09-06 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-01 | 2023-04-01 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-086 | PI North - GCB & EXC-GT-1-Pile 09-01 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-01 | 2023-04-01 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-087 | PI North - GCB & EXC-GT-1-Pile 09-05 | CFA Piling | Submitted to UGL | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-04 | 2023-04-04 | Y | Y | Y | NCR-00015 |  | Y |  |  | 2023-08-16
CC0375-GT01-PIL-088 | PI North - Exhaust Stack GT1-Pile 10-05 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-16 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-089 | PI North - Exhaust Stack-Pile 10-03 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-16 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-090 | PI North - Exhaust Stack-Pile 10-01 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-16 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-091 | PI North - Exhaust Stack-Pile 10-15 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-16 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-092 | PI North - Exhaust Stack-Pile 10-13 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-16 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-093 | PI North - Exhaust Stack-Pile 10-14 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-094 | PI North - Exhaust Stack-Pile 10-12 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-095 | PI North - Exhaust Stack-Pile 10-25 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-096 | PI North - Exhaust Stack-Pile 10-23 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-097 | PI North - Exhaust Stack-Pile 10-21 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-098 | PI North - Exhaust Stack-Pile 10-02 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-099 | PI North - Exhaust Stack-Pile 10-04 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-22 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0100 | PI North - Exhaust Stack-Pile 10-10 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0101 | PI North - Exhaust Stack-Pile 10-08 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0102 | PI North - Exhaust Stack-Pile 10-06 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0103 | PI North - Exhaust Stack-Pile 10-20 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0104 | PI North - Exhaust Stack-Pile 10-18 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0105 | PI North - Exhaust Stack-Pile 10-16 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0106 | PI North - Exhaust Stack-Pile 10-24 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-23 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0107 | PI North - Exhaust Stack-Pile 10-09 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-24 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0108 | PI North - Exhaust Stack-Pile 10-07 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-24 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0109 | PI North - Exhaust Stack-Pile 10-19 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-24 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0110 | PI North - Exhaust Stack-Pile 10-17 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-24 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0111 | PI North - Exhaust Stack-Pile 10-30 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-24 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0112 | PI North - Exhaust Stack-Pile 10-27 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-24 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0113 | PI North - Exhaust Stack-Pile 10-22 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0114 | PI North - Exhaust Stack-Pile 10-29 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0115 | PI North - Exhaust Stack-Pile 10-11 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0116 | PI North - Exhaust Stack-Pile 10-28 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0117 | PI North - Exhaust Stack-Pile 10-26 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-04 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-08-01 | 2023-08-01
CC0375-GT01-PIL-0118 | PI North - Fin Fan Cooler/Heater GT01-Pile 11-04 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0119 | PI North - Fin Fan Cooler/Heater-Pile 11-03 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0120 | PI North - Fin Fan Cooler/Heater-Pile 11-02 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0121 | PI North - Fin Fan Cooler/Heater-Pile 11-01 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-30 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0122 | PI North - Fin Fan Cooler/Heater-Pile 11-08 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0123 | PI North - Fin Fan Cooler/Heater-Pile 11-07 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0124 | PI North - Fin Fan Cooler/Heater-Pile 11-06 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-PIL-0125 | PI North - Fin Fan Cooler/Heater-Pile 11-05 | CFA Piling | Closed | 2022-10-10 | GT01 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-31 | 2023-06-28 | Y | Y | Y | NCR-00008 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-GT01-FRP-001 | PI North - GT1-Blinding | FRP | Works Complete | 2022-11-10 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2022-11-10 | 2022-11-17 | Y | Y | N
CC0375-GT01-FRP-002 | PI North - GT1-Pile cap | FRP | Works Complete | 2022-11-10 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2022-11-16 | 2023-06-29 | Y | Y | N
CC0375-GT01-FRP-003 | PI North - GT1-GT-1 Superstructure | FRP | Works Complete | 2022-11-10 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-06 | 2023-06-29 | Y | Y | N
CC0375-GT01-FRP-004 | PI North - GT1-Pedestals | FRP | Works Complete | 2022-11-10 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-03-08 | 2023-08-09 | Y | Y | N
CC0375-GT01-FRP-005 | PI North - GT1-Wingslab North-Blinding | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-18 | 2023-08-09 | Y | Y | N
CC0375-GT01-FRP-006 | PI North - GT1-Wingslab North-Foundation | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-18 | 2023-08-09 | Y | N | N
CC0375-GT01-FRP-007 | PI North - GT1-Wingslab North-Plinth/Pedestals | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-21 | 2023-09-08 | Y | N | N
CC0375-GT01-FRP-008 | PI North - GT1-Wingslab South-Blinding | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-01 | 2023-08-09 | Y | N | N
CC0375-GT01-FRP-009 | PI North - GT1-Wingslab South-Foundation | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-01 | 2023-08-09 | Y | N | N
CC0375-GT01-FRP-010 | PI North - Transformer GT1-Blinding | FRP | Works Complete | 2023-09-28 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-28 | 2023-10-04 | Y | N | N
CC0375-GT01-FRP-011 | PI North - Transformer-GSUT-2-Part-1-Pit 07-03 Base | FRP | Works Complete | 2023-10-06 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-10-06 | 2023-10-16 | Y | N | N
CC0375-GT01-FRP-012 | PI North - Transformer-GSUT-2-Part-1-Pit 07-03 Walls | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-013 | PI North - Transformer- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-014 | PI North - Transformer- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-015 | PI North - Circuit Breaker GT01-Blinding | FRP | Works Complete | 2023-04-19 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-19 | 2023-08-12 | Y | N | N
CC0375-GT01-FRP-016 | PI North - Circuit Breaker-Pile Cap/Foundation | FRP | Works Complete | 2023-04-19 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-15 | 2023-08-24 | Y | N | N
CC0375-GT01-FRP-017 | PI North - Circuit Breaker-Pedestals | FRP | Active | 2023-04-19 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-28 |  |  |  | N
CC0375-GT01-FRP-018 | PI North - Exhaust Stack-Blinding | FRP | Works Complete | 2023-04-14 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-14 | 2023-05-30 | Y | N | N
CC0375-GT01-FRP-019 | PI North - Exhaust Stack-Pile Cap | FRP | Works Complete | 2023-04-14 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-15 | 2023-07-03 | Y | N | N
CC0375-GT01-FRP-020 | PI North - Exhaust Stack-Foundation-Plinth-Circle | FRP | Works Complete | 2023-04-14 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-10 | 2023-07-18 | Y | N | N
CC0375-GT01-FRP-021 | PI North - Exhaust Stack-Foundation-Plinth-Part-2 | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-022 | PI North - Exhaust Stack-Foundation-Plinth-Pedestals | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-18 | 2023-07-21 | Y | N | N
CC0375-GT01-FRP-023 | PI North - Exhaust Duct-Blinding | FRP | Works Complete | 2023-07-16 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-17 | 2023-07-17 | Y | N | N
CC0375-GT01-FRP-024 | PI North - Exhaust Duct-Foundation | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-18 | 2023-07-27 | Y | N | N
CC0375-GT01-FRP-025 | PI North - Exhaust Duct-Pedestals | FRP | Works Complete | 2023-07-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-18 | 2023-08-09 | Y | N | N
CC0375-GT01-FRP-026 | PI North - Fuel Gas Heater-Blinding | FRP | Works Complete | 2023-04-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-18 | 2023-08-10 | Y | N | N
CC0375-GT01-FRP-027 | PI North - Fuel Gas Heater-Pile Cap | FRP | Works Complete | 2023-04-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-27 | 2023-08-17 | Y | N | N
CC0375-GT01-FRP-028 | PI North - Fuel Gas Heater-Foundation/Pedestals | FRP | Active | 2023-04-18 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-18 |  |  |  | N
CC0375-GT01-FRP-029 | PI North - Air Intake/Air Duct-Blinding | FRP | Works Complete | 2023-07-08 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-08 | 2023-07-10 | Y | N | N
CC0375-GT01-FRP-030 | PI North - Air Intake/Air Duct-Foundation | FRP | Works Complete | 2023-07-11 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-11 | 2023-08-01 | Y | N | N
CC0375-GT01-FRP-031 | PI North - Air Intake/Air Duct-Pedestals | FRP | Open | 2023-09-11 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N |  | N
CC0375-GT01-FRP-032 | PI North - Air Intake-Blinding-Part-2 | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-033 | PI North - Air Intake-Foundation-Part-2 | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-034 | PI North - Air Intake-Pedestals-Part-2 | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-035 | PI North - Aux Switchroom Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT01-FRP-036 | PI North - Lube Oil Building & Lube Oil Unit- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT01-FRP-037 | PI North - Aux Transformer Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT01-FRP-038 | PI North - Mitsubishi Substation Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT01-FRP-039 | PI North - Rotor Removal Foundation-Blinding | FRP | Works Complete | 2023-09-25 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar | 2023-09-25 | 2023-09-27 | Y | N | N
CC0375-GT01-FRP-040 | PI North - Rotor Removal Foundation-Stage-1 (Trench to blinding level) | FRP | Works Complete | 2023-09-28 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar | 2023-09-28 | 2023-09-29 | Y | N | N
CC0375-GT01-FRP-041 | PI North - Rotor Removal Foundation-Stage-2 Foundation | FRP | Works Complete | 2023-10-03 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar | 2023-10-03 | 2023-10-18 | Y | N | N
CC0375-GT01-FRP-042 | PI North - Rotor Removal Foundation-Grout underneath templates | FRP | Active | 2023-10-19 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar | 2023-10-19 |  | N | N | N
CC0375-GT01-FRP-043 | PI North - SFC Building Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar
CC0375-GT01-FRP-044 | PI North - GT Fuel Oil Drain Pump and Tank Foundation-Blinding/Backblinding | FRP | Active | 2023-08-07 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-07 |  | N | N | N
CC0375-GT01-FRP-045 | PI North - GT Fuel Oil Drain Pump and Tank Foundation-Foundation | FRP | Open | 2023-08-07 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-GT01-FRP-046 | PI North - GT Fuel Oil Drain Pump and Tank Foundation-Plinth | FRP | Open | 2023-08-07 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-GT01-FRP-047 | PI North - GT Fuel Oil Drain Pump and Tank Foundation-Pedestals | FRP | Open | 2023-08-07 | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-GT01-FRP-048 | PI North - SFC Transformer Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT01-FRP-049 | PI North - Prefab Substation Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT01-FRP-050 | PI North - Cooling System Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-051 | PI North - Lube Oil Unit Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT01-FRP-052 | PI North - C02 FF Foundation- | FRP |  |  | GT01 | CC0375-ITP-015 FRP Works (Structures)

## GT02
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-GT02-PIL-001 | PI South - GT2-Pile 03-14 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-07 | 2022-11-07 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-002 | PI South - GT2-Pile 03-12 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-003 | PI South - GT2-Pile 03-10 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-004 | PI South - GT2-Pile 03-08 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-005 | PI South - GT2-Pile 03-06 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-006 | PI South - GT2-Pile 03-04 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-007 | PI South - GT2-Pile 03-02 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-008 | PI South - GT2-Pile 03-28 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-08 | 2022-11-08 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-009 | PI South - GT2-Pile 03-13 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-010 | PI South - GT2-Pile 03-11 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-011 | PI South - GT2-Pile 03-09 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-012 | PI South - GT2-Pile 03-07 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-013 | PI South - GT2-Pile 03-05 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-014 | PI South - GT2-Pile 03-03 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-015 | PI South - GT2-Pile 03-01 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-09 | 2022-11-09 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-016 | PI South - GT2-Pile 03-26 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-10 | 2022-11-10 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-017 | PI South - GT2-Pile 03-24 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-10 | 2022-11-10 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-018 | PI South - GT2-Pile 03-22 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-10 | 2022-11-10 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-019 | PI South - GT2-Pile 03-20 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-10 | 2022-11-10 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-020 | PI South - GT2-Pile 03-18 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-10 | 2022-11-10 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-021 | PI South - GT2-Pile 03-16 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-10 | 2022-11-10 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-022 | PI South - GT2-Pile 03-42 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-023 | PI South - GT2-Pile 03-27 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-024 | PI South - GT2-Pile 03-25 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-025 | PI South - GT2-Pile 03-23 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-026 | PI South - GT2-Pile 03-21 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-027 | PI South - GT2-Pile 03-19 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-028 | PI South - GT2-Pile 03-17 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-24 | 2022-11-24 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-029 | PI South - GT2-Pile 03-15 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-25 | 2022-11-25 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-030 | PI South - GT2-Pile 03-41 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-25 | 2022-11-25 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-031 | PI South - GT2-Pile 03-39 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-25 | 2022-11-25 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-032 | PI South - GT2-Pile 03-37 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-033 | PI South - GT2-Pile 03-56 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-034 | PI South - GT2-Pile 03-40 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-035 | PI South - GT2-Pile 03-35 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-036 | PI South - GT2-Pile 03-33 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-037 | PI South - GT2-Pile 03-31 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-038 | PI South - GT2-Pile 03-29 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-039 | PI South - GT2-Pile 03-55 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-29 | 2022-11-29 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-040 | PI South - GT2-Pile 03-54 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-041 | PI South - GT2-Pile 03-38 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-042 | PI South - GT2-Pile 03-36 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-043 | PI South - GT2-Pile 03-34 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-044 | PI South - GT2-Pile 03-32 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-045 | PI South - GT2-Pile 03-30 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-046 | PI South - GT2-Pile 03-53 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-11-30 | 2022-11-30 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-047 | PI South - GT2-Pile 03-52 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-01 | 2022-12-01 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-048 | PI South - GT2-Pile 03-50 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-01 | 2022-12-01 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-049 | PI South - GT2-Pile 03-48 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-01 | 2022-12-01 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-050 | PI South - GT2-Pile 03-46 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-01 | 2022-12-01 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-051 | PI South - GT2-Pile 03-44 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-01 | 2022-12-01 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-052 | PI South - GT2-Pile 03-51 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-02 | 2022-12-02 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-053 | PI South - GT2-Pile 03-49 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-02 | 2022-12-02 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-054 | PI South - GT2-Pile 03-47 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-02 | 2022-12-02 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-055 | PI South - GT2-Pile 03-45 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-02 | 2022-12-02 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-056 | PI South - GT2-Pile 03-43 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-02 | 2022-12-02 | Y | Y | Y | NCR-00002 |  | Y |  |  | 2023-02-13 | 2023-02-13
CC0375-GT02-PIL-057 | PI South - Transformer-Pile 04-22 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-10 | 2022-12-10 | N | N | N
CC0375-GT02-PIL-058 | PI South - Transformer-Pile 04-23 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-10 | 2022-12-10 | N | N | N
CC0375-GT02-PIL-059 | PI South - Transformer-Pile 04-24 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-10 | 2022-12-10 | N | N | N
CC0375-GT02-PIL-060 | PI South - Transformer-Pile 04-19 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-12 | 2022-12-12 | N | N | N
CC0375-GT02-PIL-061 | PI South - Transformer-Pile 04-20 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-12 | 2022-12-12 | N | N | N
CC0375-GT02-PIL-062 | PI South - Transformer-Pile 04-21 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-12 | 2022-12-12 | N | N | N
CC0375-GT02-PIL-063 | PI South - Transformer-Pile 04-13 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-12 | 2022-12-12 | N | N | N
CC0375-GT02-PIL-064 | PI South - Transformer-Pile 04-14 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-12 | 2022-12-12 | N | N | N
CC0375-GT02-PIL-065 | PI South - Transformer-Pile 04-15 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-13 | 2022-12-13 | N | N | N
CC0375-GT02-PIL-066 | PI South - Transformer-Pile 04-07 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-13 | 2022-12-13 | N | N | N
CC0375-GT02-PIL-067 | PI South - Transformer-Pile 04-08 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-13 | 2022-12-13 | N | N | N
CC0375-GT02-PIL-068 | PI South - Transformer-Pile 04-09 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-13 | 2022-12-13 | N | N | N
CC0375-GT02-PIL-069 | PI South - Transformer-Pile 04-16 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-13 | 2022-12-13 | N | N | N
CC0375-GT02-PIL-070 | PI South - Transformer-Pile 04-17 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-13 | 2022-12-13 | N | N | N
CC0375-GT02-PIL-071 | PI South - Transformer-Pile 04-18 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-072 | PI South - Transformer-Pile 04-10 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-073 | PI South - Transformer-Pile 04-11 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-074 | PI South - Transformer-Pile 04-12 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-075 | PI South - Transformer-Pile 04-05 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-076 | PI South - Transformer-Pile 04-06 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-077 | PI South - Transformer-Pile 04-04 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-078 | PI South - Transformer-Pile 04-02 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-14 | 2022-12-14 | N | N | N
CC0375-GT02-PIL-079 | PI South - Transformer-Pile 04-01 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | N | N | N
CC0375-GT02-PIL-080 | PI South - Transformer-Pile 04-03 | CFA Piling | Works Complete | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | N | N | N
CC0375-GT02-PIL-081 | PI South - GCB & EXC-GT-2-Pile 13-03 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-082 | PI South - GCB & EXC-GT-2-Pile 13-07 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-083 | PI South - GCB & EXC-GT-2-Pile 13-02 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-084 | PI South - GCB & EXC-GT-2-Pile 13-04 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-085 | PI South - GCB & EXC-GT-2-Pile 13-06 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-16 | 2023-05-16 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-086 | PI South - GCB & EXC-GT-2-Pile 13-01 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-087 | PI South - GCB & EXC-GT-2-Pile 13-05 | CFA Piling | Closed | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | N | [5 empty] | 2023-09-14 | 2023-10-09
CC0375-GT02-PIL-088 | PI South - Exhaust Stack-GT-2-Pile 14-05 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-15 | 2023-05-15 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-089 | PI South - Exhaust Stack-GT-2-Pile 14-03 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-15 | 2023-05-15 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-090 | PI South - Exhaust Stack-GT-2-Pile 14-01 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-15 | 2023-05-15 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-091 | PI South - Exhaust Stack-GT-2-Pile 14-29 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-092 | PI South - Exhaust Stack-GT-2-Pile 14-25 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-093 | PI South - Exhaust Stack-GT-2-Pile 14-23 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-094 | PI South - Exhaust Stack-GT-2-Pile 14-21 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-095 | PI South - Exhaust Stack-GT-2-Pile 14-19 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-17 | 2023-05-17 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-096 | PI South - Exhaust Stack-GT-2-Pile 14-17 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-097 | PI South - Exhaust Stack-GT-2-Pile 14-15 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-098 | PI South - Exhaust Stack-GT-2-Pile 14-13 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-099 | PI South - Exhaust Stack-GT-2-Pile 14-11 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0100 | PI South - Exhaust Stack-GT-2-Pile 14-09 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0101 | PI South - Exhaust Stack-GT-2-Pile 14-07 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0102 | PI South - Exhaust Stack-GT-2-Pile 14-27 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-18 | 2023-05-18 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0103 | PI South - Exhaust Stack-GT-2-Pile 14-26 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-19 | 2023-05-19 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0104 | PI South - Exhaust Stack-GT-2-Pile 14-24 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-19 | 2023-05-19 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0105 | PI South - Exhaust Stack-GT-2-Pile 14-22 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-19 | 2023-05-19 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0106 | PI South - Exhaust Stack-GT-2-Pile 14-30 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-23 | 2023-05-23 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0107 | PI South - Exhaust Stack-GT-2-Pile 14-28 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-23 | 2023-05-23 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0108 | PI South - Exhaust Stack-GT-2-Pile 14-20 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-23 | 2023-05-23 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0109 | PI South - Exhaust Stack-GT-2-Pile 14-18 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-23 | 2023-05-23 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0110 | PI South - Exhaust Stack-GT-2-Pile 14-16 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-23 | 2023-05-23 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0111 | PI South - Exhaust Stack-GT-2-Pile 14-14 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-23 | 2023-05-23 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0112 | PI South - Exhaust Stack-GT-2-Pile 14-12 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-24 | 2023-05-24 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0113 | PI South - Exhaust Stack-GT-2-Pile 14-10 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-24 | 2023-05-24 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0114 | PI South - Exhaust Stack-GT-2-Pile 14-08 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-24 | 2023-05-24 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0115 | PI South - Exhaust Stack-GT-2-Pile 14-06 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-24 | 2023-05-24 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0116 | PI South - Exhaust Stack-GT-2-Pile 14-04 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-24 | 2023-05-24 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0117 | PI South - Exhaust Stack-GT-2-Pile 14-02 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-24 | 2023-05-24 | Y | Y | Y | NCR-00014 |  | Y |  |  | 2023-07-28
CC0375-GT02-PIL-0118 | PI South - Fin Fan Cooler/Heater GT2-Pile 15-08 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-12 | 2023-05-12 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0119 | PI South - Fin Fan Cooler/Heater-Pile 15-07 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-12 | 2023-05-12 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0120 | PI South - Fin Fan Cooler/Heater-Pile 15-06 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-12 | 2023-05-12 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0121 | PI South - Fin Fan Cooler/Heater-Pile 15-05 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-12 | 2023-05-12 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0122 | PI South - Fin Fan Cooler/Heater-Pile 15-04 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-13 | 2023-05-13 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0123 | PI South - Fin Fan Cooler/Heater-Pile 15-03 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-13 | 2023-05-13 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0124 | PI South - Fin Fan Cooler/Heater-Pile 15-02 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-13 | 2023-05-13 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-PIL-0125 | PI South - Fin Fan Cooler/Heater-Pile 15-01 | CFA Piling | Submitted to UGL | 2022-10-10 | GT02 | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-15 | 2023-05-15 | Y | Y | N | [5 empty] | 2023-09-21
CC0375-GT02-FRP-001 | PI South - GT2-Blinding | FRP | Works Complete | 2022-12-12 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2022-12-12 | 2022-12-13 | Y | N | N
CC0375-GT02-FRP-002 | PI South - GT2-Pile cap | FRP | Works Complete | 2022-12-12 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-03-27 | 2023-06-14 | Y | N | N
CC0375-GT02-FRP-003 | PI South - GT2-GT-2 Superstructure | FRP | Works Complete | 2022-12-12 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-21 | 2023-07-10 | Y | N | N
CC0375-GT02-FRP-004 | PI South - GT2-Pedestals | FRP | Works Complete | 2022-12-12 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-20 | 2023-05-09 | Y | N | N
CC0375-GT02-FRP-005 | PI South - GT2-Wingslab North-Blinding | FRP | Works Complete | 2023-09-08 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-08 | 2023-09-12 | Y | N | N
CC0375-GT02-FRP-006 | PI South - GT2-Wingslab North-Foundation | FRP | Active | 2023-09-13 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-13 |  | N | N | N
CC0375-GT02-FRP-007 | PI South - GT2-Wingslab North-Plinth | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT02-FRP-008 | PI South - GT2-Wingslab South-Blinding | FRP | Works Complete | 2023-09-08 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-08 | 2023-09-11 | Y | N | N
CC0375-GT02-FRP-009 | PI South - GT2-Wingslab South-Foundation | FRP | Active | 2023-09-13 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-13 |  | N | N | N
CC0375-GT02-FRP-010 | PI South - Transformer GT2- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT02-FRP-011 | PI South - Circuit Breaker-Blinding | FRP | Works Complete | 2023-09-08 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-08 | 2023-09-09 | Y | N | N
CC0375-GT02-FRP-012 | PI South - Circuit Breaker-Pile Cap/Foundation | FRP | Active | 2023-09-14 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-14 |  | N | N | N
CC0375-GT02-FRP-013 | PI South - Circuit Breaker-Pedestals | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT02-FRP-014 | PI South - Exhaust Stack-Blinding | FRP | Works Complete | 2023-06-20 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-21 | 2023-06-21 | Y | N | N
CC0375-GT02-FRP-015 | PI South - Exhaust Stack-Pile Cap | FRP | Works Complete | 2023-06-20 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-22 | 2023-07-28 | Y | N | N
CC0375-GT02-FRP-016 | PI South - Exhaust Stack-Foundation-Plinth-Circle | FRP | Works Complete | 2023-06-20 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-29 | 2023-08-10 | Y | N | N
CC0375-GT02-FRP-017 | PI South - Exhaust Stack-Foundation-Plinth-Part-2 | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT02-FRP-018 | PI South - Exhaust Stack-Foundation-Plinth-Pedestals | FRP | Works Complete | 2023-06-20 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-29 | 2023-08-10 | Y | N | N
CC0375-GT02-FRP-019 | PI South - Exhaust Duct-Blinding | FRP | Works Complete | 2023-06-20 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-24 | 2023-08-24 | Y | N | N
CC0375-GT02-FRP-020 | PI South - Exhaust Duct-Foundation | FRP | Works Complete | 2023-06-20 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-25 | 2023-08-31 | Y | N | N
CC0375-GT02-FRP-021 | PI South - Exhaust Duct-Pedestals | FRP | Works Complete | 2023-09-08 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-08 | 2023-09-13 | Y | N | N
CC0375-GT02-FRP-022 | PI South - Fuel Gas Heater-Blinding | FRP | Works Complete | 2023-09-08 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-08 | 2023-09-12 | Y | N | N
CC0375-GT02-FRP-023 | PI South - Fuel Gas Heater-Foundation | FRP | Works Complete | 2023-09-14 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-14 | 2023-10-16 | Y | N | N
CC0375-GT02-FRP-024 | PI South - Fuel Gas Heater-Pedestals | FRP | Open | 2023-10-17 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-GT02-FRP-025 | PI South - Air Intake/Air Duct-Blinding | FRP | Works Complete | 2023-08-21 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-21 | 2023-08-23 | Y | N | N
CC0375-GT02-FRP-026 | PI South - Air Intake/Air Duct-Foundation | FRP | Works Complete | 2023-08-21 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-08-25 | 2023-09-05 | Y | N | N
CC0375-GT02-FRP-027 | PI South - Air Intake/Air Duct-Pedestals | FRP | Open | 2023-09-13 | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-GT02-FRP-028 | PI South - Air Intake-Blinding-Part-2 | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-029 | PI South - Air Intake-Foundation-Part-2 | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-030 | PI South - Air Intake-Pedestals-Part-2 | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-031 | PI South - Aux Switchroom Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-032 | PI South - Lube Oil Building & Lube Oil Unit- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-033 | PI South - Aux Transformer Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-034 | PI South - Mitsubishi Substation Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-035 | PI South - Rotor Removal Foundation-Blinding | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/YB
CC0375-GT02-FRP-036 | PI South - Rotor Removal Foundation-Stage-1 (Trench to blinding level) | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar
CC0375-GT02-FRP-037 | PI South - Rotor Removal Foundation-Stage-2 Foundation | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar
CC0375-GT02-FRP-038 | PI South - Rotor Removal Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar
CC0375-GT02-FRP-039 | PI South - SFC Building Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts/Yash Bhavsar
CC0375-GT02-FRP-040 | PI South - GT Fuel Oil Drain Pump and Tank Foundation-Blinding/Backblinding | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-041 | PI South - GT Fuel Oil Drain Pump and Tank Foundation-Foundation | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-042 | PI South - GT Fuel Oil Drain Pump and Tank Foundation-Plinth | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-043 | PI South - GT Fuel Oil Drain Pump and Tank Foundation-Pedestals | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-044 | PI South - SFC Transformer Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-045 | PI South - Prefab Substation Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-GT02-FRP-046 | PI South - Cooling System Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT02-FRP-047 | PI South - Lube Oil Unit Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)
CC0375-GT02-FRP-048 | PI South - C02 FF Foundation- | FRP |  |  | GT02 | CC0375-ITP-015 FRP Works (Structures)

## BOP
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-BOP-PIL-001 | Fuel Diesel Tank (South)-Pile 05-09 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-19 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-002 | Fuel Diesel Tank (South)-Pile 05-10 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-19 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-003 | Fuel Diesel Tank (South)-Pile 05-11 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-19 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-004 | Fuel Diesel Tank (South)-Pile 05-08 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-19 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-005 | Fuel Diesel Tank (South)-Pile 05-06 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-19 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-006 | Fuel Diesel Tank (South)-Pile 05-19 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-007 | Fuel Diesel Tank (South)-Pile 05-07 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-008 | Fuel Diesel Tank (South)-Pile 05-05 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2022-12-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-009 | Fuel Diesel Tank (South)-Pile 05-04 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-13 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-010 | Fuel Diesel Tank (South)-Pile 05-18 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-13 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-011 | Fuel Diesel Tank (South)-Pile 05-16 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-13 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-012 | Fuel Diesel Tank (South)-Pile 05-20 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-13 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-013 | Fuel Diesel Tank (South)-Pile 05-12 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-13 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-014 | Fuel Diesel Tank (South)-Pile 05-17 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-17 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-015 | Fuel Diesel Tank (South)-Pile 05-24 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-17 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-016 | Fuel Diesel Tank (South)-Pile 05-15 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-17 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-017 | Fuel Diesel Tank (South)-Pile 05-23 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-018 | Fuel Diesel Tank (South)-Pile 05-13 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-019 | Fuel Diesel Tank (South)-Pile 05-03 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-020 | Fuel Diesel Tank (South)-Pile 05-22 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-24 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-021 | Fuel Diesel Tank (South)-Pile 05-01 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-24 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-022 | Fuel Diesel Tank (South)-Pile 05-21 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-25 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-023 | Fuel Diesel Tank (South)-Pile 05-14 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-01 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-024 | Fuel Diesel Tank (South)-Pile 05-02 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-02 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-025 | Fuel Diesel Tank (North)-Pile 06-07 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-026 | Fuel Diesel Tank (North)-Pile 06-06 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-027 | Fuel Diesel Tank (North)-Pile 06-05 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-20 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-028 | Fuel Diesel Tank (North)-Pile 06-17 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-24 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-029 | Fuel Diesel Tank (North)-Pile 06-04 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-24 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-030 | Fuel Diesel Tank (North)-Pile 06-03 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-24 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-031 | Fuel Diesel Tank (North)-Pile 06-23 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-25 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-032 | Fuel Diesel Tank (North)-Pile 06-16 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-01-25 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-033 | Fuel Diesel Tank (North)-Pile 06-18 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-01 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-034 | Fuel Diesel Tank (North)-Pile 06-15 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-01 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-035 | Fuel Diesel Tank (North)-Pile 06-08 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-02 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-036 | Fuel Diesel Tank (North)-Pile 06-19 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-02 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-037 | Fuel Diesel Tank (North)-Pile 06-09 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-03 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-038 | Fuel Diesel Tank (North)-Pile 06-10 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-03 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-039 | Fuel Diesel Tank (North)-Pile 06-22 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-03 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-040 | Fuel Diesel Tank (North)-Pile 06-24 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-03 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-041 | Fuel Diesel Tank (North)-Pile 06-14 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-03 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-042 | Fuel Diesel Tank (North)-Pile 06-21 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-04 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-043 | Fuel Diesel Tank (North)-Pile 06-20 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-04 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-044 | Fuel Diesel Tank (North)-Pile 06-02 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-04 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-045 | Fuel Diesel Tank (North)-Pile 06-11 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-07 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-046 | Fuel Diesel Tank (North)-Pile 06-13 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-07 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-047 | Fuel Diesel Tank (North)-Pile 06-12 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-08 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-048 | Fuel Diesel Tank (North)-Pile 06-01 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-08 | 2023-03-15 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-03-22 | 2023-03-22
CC0375-BOP-PIL-049 | Demin Tank-Pile 07-7 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-09 | 2023-02-09 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-050 | Demin Tank-Pile 07-3 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-09 | 2023-02-09 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-051 | Demin Tank-Pile 07-5 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-09 | 2023-02-09 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-052 | Demin Tank-Pile 07-6 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-14 | 2023-02-14 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-053 | Demin Tank-Pile 07-4 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-14 | 2023-02-14 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-054 | Demin Tank-Pile 07-15 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-16 | 2023-02-16 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-055 | Demin Tank-Pile 07-17 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-16 | 2023-02-16 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-056 | Demin Tank-Pile 07-16 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-24 | 2023-02-24 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-057 | Demin Tank-Pile 07-14 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-25 | 2023-02-25 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-058 | Demin Tank-Pile 07-02 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-27 | 2023-02-27 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-059 | Demin Tank-Pile 07-01 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-28 | 2023-02-28 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-060 | Demin Tank-Pile 07-21 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-28 | 2023-02-28 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-061 | Demin Tank-Pile 07-10 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-28 | 2023-02-28 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-062 | Demin Tank-Pile 07-22 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-01 | 2023-03-01 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-063 | Demin Tank-Pile 07-13 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-01 | 2023-03-01 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-064 | Demin Tank-Pile 07-11 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-01 | 2023-03-01 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-065 | Demin Tank-Pile 07-12 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-02 | 2023-03-02 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-066 | Demin Tank-Pile 07-24 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-02 | 2023-03-02 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-067 | Demin Tank-Pile 07-20 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-04 | 2023-04-04 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-068 | Demin Tank-Pile 07-23 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-05 | 2023-04-05 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-069 | Demin Tank-Pile 07-19 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-12 | 2023-04-12 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-070 | Demin Tank-Pile 07-18 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-11 | 2023-05-11 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-071 | Demin Tank-Pile 07-08 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-12 | 2023-05-12 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-072 | Demin Tank-Pile 07-09 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-13 | 2023-05-13 | Y | Y | N | N/A |  |  |  |  | 2023-08-22 | 2023-09-19
CC0375-BOP-PIL-073 | Potable Water Tank-Pile 08-12 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-08 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-074 | Potable Water Tank-Pile 08-02 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-08 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-075 | Potable Water Tank-Pile 08-01 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-09 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-076 | Potable Water Tank-Pile 08-03 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-09 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-077 | Potable Water Tank-Pile 08-05 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-09 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-078 | Potable Water Tank-Pile 08-20 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-10 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-079 | Potable Water Tank-Pile 08-14 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-10 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-080 | Potable Water Tank-Pile 08-04 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-10 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-081 | Potable Water Tank-Pile 08-06 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-10 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-082 | Potable Water Tank-Pile 08-11 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-11 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-083 | Potable Water Tank-Pile 08-15 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-14 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-084 | Potable Water Tank-Pile 08-13 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-15 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-085 | Potable Water Tank-Pile 08-16 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-15 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-086 | Potable Water Tank-Pile 08-10 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-15 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-087 | Potable Water Tank-Pile 08-07 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-15 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-088 | Potable Water Tank-Pile 08-21 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-16 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-089 | Potable Water Tank-Pile 08-19 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-16 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-090 | Potable Water Tank-Pile 08-17 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-16 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-091 | Potable Water Tank-Pile 08-22 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-21 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-092 | Potable Water Tank-Pile 08-24 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-21 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-093 | Potable Water Tank-Pile 08-23 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-24 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-094 | Potable Water Tank-Pile 08-09 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-24 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-095 | Potable Water Tank-Pile 08-18 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-25 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-096 | Potable Water Tank-Pile 08-08 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-02-27 | 2023-04-04 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-04-14 | 2023-04-14
CC0375-BOP-PIL-097 | HV Transmission Pole Foundation-Pile 12-09 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-02 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-098 | HV Transmission Pole Foundation-Pile 12-05 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-02 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-099 | HV Transmission Pole Foundation-Pile 12-01 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-02 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0100 | HV Transmission Pole Foundation-Pile 12-02 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-03 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0101 | HV Transmission Pole Foundation-Pile 12-06 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-03 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0102 | HV Transmission Pole Foundation-Pile 12-11 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-03 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0103 | HV Transmission Pole Foundation-Pile 12-07 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-04 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0104 | HV Transmission Pole Foundation-Pile 12-03 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-04 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0105 | HV Transmission Pole Foundation-Pile 12-12 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-04 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0106 | HV Transmission Pole Foundation-Pile 12-10 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-06 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0107 | HV Transmission Pole Foundation-Pile 12-08 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-06 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0108 | HV Transmission Pole Foundation-Pile 12-04 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-06 | 2023-05-10 | Y | Y | Y | NCR-00006 |  | Y |  |  | 2023-08-02 | 2023-08-02
CC0375-BOP-PIL-0109 | HV Gantry Pole Foundation BOP-Pile 16-01 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-08 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0110 | HV Gantry Pole Foundation-Pile 16-03 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-08 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0111 | HV Gantry Pole Foundation-Pile 16-05 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-08 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0112 | HV Gantry Pole Foundation-Pile 16-07 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-08 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0113 | HV Gantry Pole Foundation-Pile 16-02 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-09 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0114 | HV Gantry Pole Foundation-Pile 16-04 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-09 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0115 | HV Gantry Pole Foundation-Pile 16-06 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-09 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0116 | HV Gantry Pole Foundation-Pile 16-08 | CFA Piling | Closed | 2022-10-10 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-03-09 | 2023-05-09 | Y | Y | Y | NCR-00005 |  | Y |  |  | 2023-07-17 | 2023-07-17
CC0375-BOP-PIL-0117 | Fire Water Tank BOP-Pile 17-20 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-04 | 2023-04-04 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0118 | Fire Water Tank-Pile 17-26 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-04 | 2023-04-04 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0119 | Fire Water Tank-Pile 17-18 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-04 | 2023-04-04 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0120 | Fire Water Tank-Pile 17-24 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-05 | 2023-04-05 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0121 | Fire Water Tank-Pile 17-22 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-05 | 2023-04-05 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0122 | Fire Water Tank-Pile 17-28 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-05 | 2023-04-05 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0123 | Fire Water Tank-Pile 17-04 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-05 | 2023-04-05 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0124 | Fire Water Tank-Pile 17-12 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-05 | 2023-04-05 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0125 | Fire Water Tank-Pile 17-19 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-12 | 2023-04-12 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0126 | Fire Water Tank-Pile 17-17 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-12 | 2023-04-12 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0127 | Fire Water Tank-Pile 17-02 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-12 | 2023-04-12 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0128 | Fire Water Tank-Pile 17-21 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-12 | 2023-04-12 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0129 | Fire Water Tank-Pile 17-07 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0130 | Fire Water Tank-Pile 17-05 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0131 | Fire Water Tank-Pile 17-25 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0132 | Fire Water Tank-Pile 17-23 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0133 | Fire Water Tank-Pile 17-10 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0134 | Fire Water Tank-Pile 17-27 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0135 | Fire Water Tank-Pile 17-15 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0136 | Fire Water Tank-Pile 17-13 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-13 | 2023-04-13 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0137 | Fire Water Tank-Pile 17-03 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-14 | 2023-04-14 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0138 | Fire Water Tank-Pile 17-01 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-14 | 2023-04-14 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0139 | Fire Water Tank-Pile 17-08 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-14 | 2023-04-14 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0140 | Fire Water Tank-Pile 17-06 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-14 | 2023-04-14 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0141 | Fire Water Tank-Pile 17-11 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-14 | 2023-04-14 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0142 | Fire Water Tank-Pile 17-09 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-04-14 | 2023-04-14 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0143 | Fire Water Tank-Pile 17-16 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-10 | 2023-05-10 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-PIL-0144 | Fire Water Tank-Pile 17-14 | CFA Piling | Closed | 2023-04-01 | BOP | CC0375-ITP-014 Piles | Yash Bhavsar | 2023-05-11 | 2023-05-11 | Y | Y | Y | NCR-00013 |  | Y |  |  | 2023-07-04 | 2023-10-10
CC0375-BOP-SPL-001 | BOP - Screw Piling OW 30nos & TW 5nos | Screw Piling | Closed | 2023-08-06 | BOP | CC0375-ITP-021 Screw Piling | Jackson Smith | 2023-08-06 | 2023-09-15 | Y | Y | N
CC0375-BOP-FRP-001 | Fuel Diesel Tank (South) BOP-Blinding | FRP | Submitted to UGL | 2023-02-13 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-02-13 | 2023-02-23 | Y | Y | N | [5 empty] | 2023-08-25
CC0375-BOP-FRP-002 | Fuel Diesel Tank (South)-Pile cap | FRP | Submitted to UGL | 2023-02-13 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-03-30 | 2023-05-30 | Y | Y | N | [5 empty] | 2023-08-25
CC0375-BOP-FRP-003 | Fuel Diesel Tank (North)-Blinding | FRP | Submitted to UGL | 2023-02-13 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-02-13 | 2023-02-23 | Y | Y | N | [5 empty] | 2023-08-25
CC0375-BOP-FRP-004 | Fuel Diesel Tank (North)-Pile cap | FRP | Submitted to UGL | 2023-02-13 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-03-30 | 2023-05-30 | Y | Y | N | [5 empty] | 2023-08-25
CC0375-BOP-FRP-005 | Demin Tank BOP-Blinding | FRP | Submitted to UGL | 2023-05-05 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-05-05 | 2023-05-26 | Y | Y | N | [5 empty] | 2023-08-29
CC0375-BOP-FRP-006 | Demin Tank-Pile Cap | FRP | Submitted to UGL | 2023-05-05 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-05-20 | 2023-05-29 | Y | Y | N | [5 empty] | 2023-08-29
CC0375-BOP-FRP-007 | Potable Water Tank BOP-Blinding | FRP | Submitted to UGL | 2023-03-23 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-03-23 | 2023-03-27 | Y | Y | N | [5 empty] | 2023-06-06
CC0375-BOP-FRP-008 | Potable Water Tank-Pile Cap | FRP | Submitted to UGL | 2023-03-23 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-04-12 | 2023-05-17 | Y | Y | N | [5 empty] | 2023-06-06
CC0375-BOP-FRP-009 | HV Transmission Pole Foundation-Blinding | FRP | Works Complete | 2023-04-04 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-04 | 2023-05-04 | Y | N | N
CC0375-BOP-FRP-010 | HV Transmission Pole Foundation-Pile Cap/Foundation | FRP | Works Complete | 2023-04-04 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-05-05 | 2023-07-03 | Y | N | N
CC0375-BOP-FRP-011 | HV Transmission Pole Foundation-Plinth | FRP | Works Complete | 2023-04-04 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-05 | 2023-07-13 | Y | N | N
CC0375-BOP-FRP-012 | BOP - Station Backup Generator Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-013 | BOP - Main LV Switchroom Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-014 | BOP - Unit Transformer Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-015 | BOP - Oily Water Pit Foundation/Interceptor Pit-Blinding |  | Active | 2023-06-02 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-02 |  | N | N | N
CC0375-BOP-FRP-016 | BOP - Oily Water Pit Foundation/Interceptor Pit-Base |  | Open | 2023-06-02 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-BOP-FRP-017 | BOP - Oily Water Pit Foundation/Interceptor Pit-Walls |  | Open | 2023-06-02 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-BOP-FRP-018 | BOP - Plant and Instrument Air Container- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-019 | BOP - Air Receiver Vert Tank Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-020 | BOP - Neutralisation Pit Foundation-Blinding |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-021 | BOP - Neutralisation Pit Foundation-Base |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-022 | BOP - Neutralisation Pit Foundation-Walls |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-023 | BOP - Neutralisation Pit Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-024 | BOP - Demineralised Water Shelter- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-025 | BOP - Demin Equipment Container Unit Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-026 | BOP - Fuel Forwarding Pump Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-027 | BOP - Fuel Oil/Diesel Fuel Unloading Shelter Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-028 | BOP - Fuel Unloading Foundation- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts
CC0375-BOP-FRP-029 | BOP - Fire Water Foundation-Blinding-Part 1 |  | Submitted to UGL | 2023-05-08 | BOP | CC0375-ITP-015 FRP Works (Structures) | Parth Kikaganesh | 2023-05-08 | 2023-05-08 | Y | Y | Y | [5 empty] | 2023-10-14
CC0375-BOP-FRP-030 | BOP - Fire Water Foundation-Blinding-Part-2 |  | Submitted to UGL | 2023-05-08 | BOP | CC0375-ITP-015 FRP Works (Structures) | Parth Kikaganesh | 2023-05-23 | 2023-05-23 | Y | Y | Y | [5 empty] | 2023-10-14
CC0375-BOP-FRP-031 | BOP - Fire Water Foundation-Pile Cap |  | Submitted to UGL | 2023-05-08 | BOP | CC0375-ITP-015 FRP Works (Structures) | Parth Kikaganesh | 2023-08-07 | 2023-08-07 | Y | Y | Y | [5 empty] | 2023-10-14
CC0375-BOP-FRP-032 | BOP - Fire Water Foundation-Plinth |  | Submitted to UGL | 2023-05-08 | BOP | CC0375-ITP-015 FRP Works (Structures) | Parth Kikaganesh | 2023-08-16 | 2023-08-16 | Y | Y | Y | [5 empty] | 2023-10-14
CC0375-BOP-FRP-033 | HV Gantry Foundations and Switchyard equipment foundation BOP-Blinding |  | Works Complete | 2022-03-31 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2022-03-31 | 2023-05-30 | Y | N | N
CC0375-BOP-FRP-034 | HV Gantry Foundations and Switchyard equipment foundation-Pile Cap/Foundation |  | Works Complete | 2022-03-31 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-27 | 2023-04-27 | Y | N | N
CC0375-BOP-FRP-035 | HV Gantry Foundations and Switchyard equipment foundation-Plinth |  | Open | 2022-03-31 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts |  |  | N | N | N
CC0375-BOP-FRP-036 | HV Gantry Foundations and Switchyard equipment foundation-Blinding |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-037 | HV Gantry Foundations and Switchyard equipment foundation-Pile Cap/Foundation |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-038 | HV Gantry Foundations and Switchyard equipment foundation-Blinding |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-039 | HV Gantry Foundations and Switchyard equipment foundation-Pile Cap/Foundation |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-040 | Protection Switch Yard Room BOP- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-041 | BOP-Diesel Tank Bund Area/Slab-Blinding Part-1 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-27 |  | N | N | N
CC0375-BOP-FRP-042 | BOP-Diesel Tank Bund Area/Slab-Blinding Part-2 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-04-28 |  | N | N | N
CC0375-BOP-FRP-043 | BOP-Diesel Tank Bund Area/Slab-Blinding Part-3 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-05-01 |  | N | N | N
CC0375-BOP-FRP-044 | BOP-Diesel Tank Bund Area/Slab-Blinding Part-4 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-29 |  | N | N | N
CC0375-BOP-FRP-045 | BOP-Diesel Tank Bund Area/Slab-Pour-1 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-05-19 |  | N | N | N
CC0375-BOP-FRP-046 | BOP-Diesel Tank Bund Area/Slab-Pour-2 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-06 |  | N | N | N
CC0375-BOP-FRP-047 | BOP-Diesel Tank Bund Area/Slab-Pour-3 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-15 |  | N | N | N
CC0375-BOP-FRP-048 | BOP-Diesel Tank Bund Area/Slab-Pour-4 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-29 |  | N | N | N
CC0375-BOP-FRP-049 | BOP-Diesel Tank Bund Area/Slab-Pour-5 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-30 |  | N | N | N
CC0375-BOP-FRP-050 | BOP-Diesel Tank Bund Area/Slab-Pour 6 |  | Active | 2023-04-27 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-07-06 |  | N | N | N
CC0375-BOP-FRP-051 | BOP-Diesel Tank Bund Area/Slab- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-052 | BOP-Diesel Tank Bund Area/Slab- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-053 | BOP-Diesel Tank Bund Area/Slab- |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-054 | Temp - Ringer crane Foundation-Blinding |  | Closed | 2023-06-06 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-06-06 | 2023-06-06 | Y | Y | N | [5 empty] | 2023-09-07 | 2023-09-13
CC0375-BOP-FRP-055 | Temp - Ringer crane Foundation-Foundation |  | Closed | 2023-06-07 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-06-07 | 2023-06-07 | Y | Y | N | [5 empty] | 2023-09-07 | 2023-09-13
CC0375-BOP-FRP-056 | Temp - Admin Building Pad-Backfilling and Compaction |  | Closed | 2023-05-16 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-05-16 | 2023-05-25 | Y | Y | N | [5 empty] | 2023-09-13 | 2023-10-09
CC0375-BOP-FRP-057 | Temp - Workshop Building Pad-Backfilling and Compaction |  | Closed | 2023-05-16 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts / Yash Bhavsar | 2023-05-16 | 2023-05-25 | Y | Y | N | [5 empty] | 2023-09-13 | 2023-10-09
CC0375-BOP-FRP-058 | Temp 3B Laydown area-Blinding Part-1 |  | Works Complete | 2023-06-05 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-05 | 2023-06-05 | Y | N | N
CC0375-BOP-FRP-059 | Temp 3B Laydown area-Blinding Part-2 |  | Works Complete | 2023-06-05 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-06 | 2023-06-06 | Y | N | N
CC0375-BOP-FRP-060 | Temp 3B Laydown area-Foundation Part-1 |  | Works Complete | 2023-06-05 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-13 | 2023-06-13 | Y | N | N
CC0375-BOP-FRP-061 | Temp 3B Laydown area-Foundation Part-2 |  | Works Complete | 2023-06-05 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-06-14 | 2023-06-14 | Y | N | N
CC0375-BOP-FRP-062 | Temp 3B Laydown area-Blinding Part-3 |  | Works Complete | 2023-09-12 | BOP | CC0375-ITP-015 FRP Works (Structures) | Johan'n Alberts | 2023-09-12 | 2023-09-13 | Y | N | N
CC0375-BOP-FRP-063 | Temp 3B Laydown area-Foundation Part-3 |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-064 | Gas System-Fuel Gas Filters Foundation-North-Blinding |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-065 | Gas System-Fuel Gas Filters Foundation-North-Foundation |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-066 | Gas System-Fuel Gas Filters Foundation-North-Pedestals/Plinth |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-067 | Gas System-Fuel Gas Filters Foundation-South-Blinding |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-068 | Gas System-Fuel Gas Filters Foundation-South-Foundation |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)
CC0375-BOP-FRP-069 | Gas System-Fuel Gas Filters Foundation-South-Pedestals/Plinth |  |  |  | BOP | CC0375-ITP-015 FRP Works (Structures)

## ELE
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-ELE-COND-001 | LV Conduits-01UBZ01 GZ250 to GZ280 | Conduits | Open | 2023-05-08 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-002 | MV Conduits-01UBY01 GZ270 to GZ420 | Conduits | Open | 2023-05-08 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-003 | LV Conduits-01UBZ01 GZ240 to GZ250 | Conduits | Open | 2023-05-08 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-004 | LV Conduits-01UBZ01 GZ280 Turnups | Conduits | Active | 2023-05-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-06-27 |  | N | N | N
CC0375-ELE-COND-005 | LV Conduits-01UBZ01 GZ280 to GZ320 | Conduits | Active | 2023-05-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-16 |  | N | N | N
CC0375-ELE-COND-006 | LV Conduits-01UBZ01 GZ320 Eastern Turnups | Conduits | Active | 2023-05-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-19 |  | N | N | N
CC0375-ELE-COND-007 | LV Conduits-01UBZ01 GZ230 to GZ240 | Conduits | Active | 2023-05-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-18 |  | N | N | N
CC0375-ELE-COND-008 | MV Conduits-02UBY01 GZ270 to GZ420 | Conduits | Active | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-21 |  | N | N | N
CC0375-ELE-COND-009 | LV Conduits-02UBZ01 GZ250 to GZ280 | Conduits | Active | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-06-26 |  | N | N | N
CC0375-ELE-COND-010 | LV Conduits-02UBZ01 GZ240 to GZ250 | Conduits | Active | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-05 |  | N | N | N
CC0375-ELE-COND-011 | LV Conduits-02UBZ01 GZ280 Turnups | Conduits | Active | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-08-15 |  | N | N | N
CC0375-ELE-COND-012 | LV Conduits-02UBZ01 GZ280 to GZ320 | Conduits | Open | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-013 | LV Conduits-02UBZ01 GZ320 Western Turnups | Conduits | Open | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-014 | LV Conduits-02UBZ01 GZ230 to GZ240 | Conduits | Active | 2023-06-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-09-05 |  | N | N | N
CC0375-ELE-COND-015 | MV Conduits-01UBY01 GZ420 to GZ450 & GZ421 Northbound | Conduits | Active | 2023-06-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-06-28 |  | N | N | N
CC0375-ELE-COND-016 | MV Conduits-01UBY01 GZ422 Southbound | Conduits | Active | 2023-06-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-08 |  | N | N | N
CC0375-ELE-COND-017 | MV Conduits-01 SFC Transformer Connections | Conduits | Active | 2023-06-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-03 |  | N | N | N
CC0375-ELE-COND-018 | MV Conduits-01UBY01 GZ440 to GZ450 & Prefab Sub | Conduits | Active | 2023-06-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-25 |  | N | N | N
CC0375-ELE-COND-019 | LV Conduits-01UBZ01 GZ420 Turnups | Conduits | Active | 2023-06-23 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-05 |  | N | N | N
CC0375-ELE-COND-020 | LV Conduits-01UBZ01 GZ230 Southbound | Conduits | Active | 2023-07-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-07-10 |  | N | N | N
CC0375-ELE-COND-021 | LV Conduits-Fire Tank East LV Turnups | Conduits | Active | 2023-07-14 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-15 |  | N | N | N
CC0375-ELE-COND-022 | LV Conduits-Fire Tank West LV Turnups | Conduits | Active | 2023-07-17 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-17 |  | N | N | N
CC0375-ELE-COND-023 | LV Conduits-Fire Tank North LV Turnups | Conduits | Active | 2023-07-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-18 |  | N | N | N
CC0375-ELE-COND-024 | MV Conduits-01 MV Prefab Substation to Step Up Transformer | Conduits | Active | 2023-07-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-07-25 |  | N | N | N
CC0375-ELE-COND-025 | MV Conduits-01UBY01 GZ210 to GZ420 | Conduits | Active | 2023-07-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-08-17 |  | N | N | N
CC0375-ELE-COND-026 | LV Conduits-01LV GCB to EXC | Conduits | Active | 2023-07-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-31 |  | N | N | N
CC0375-ELE-COND-027 | LV Conduits-01UBZ01 GZ410 to GZ420 including Turnups | Conduits | Active | 2023-07-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-05 |  | N | N | N
CC0375-ELE-COND-028 | LV Conduits-01UBZ01 GZ210 to GZ230 | Conduits | Open | 2023-08-08 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-029 | LV Conduits-01UBZ01 GZ210 to GZ410 | Conduits | Active | 2023-08-08 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-09 |  | N | N | N
CC0375-ELE-COND-030 | LV Conduits-02LV GCB to EXC | Conduits | Active | 2023-08-11 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-25 |  | N | N | N
CC0375-ELE-COND-031 | LV Conduits-02UBZ01 GZ230 Southbound | Conduits | Active | 2023-08-11 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-28 |  | N | N | N
CC0375-ELE-COND-032 | MV Conduits-01UBY01 GZ270 West | Conduits | Active | 2023-08-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-15 |  | N | N | N
CC0375-ELE-COND-033 | MV Conduits-02UBY10 GZ411 to 02UBY10 GZ412 SFC transformer | Conduits | Active | 2023-08-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-25 |  | N | N | N
CC0375-ELE-COND-034 | MV Conduits-01UBY01 GZ421 North Turnups | Conduits | Open | 2023-08-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-06-28 |  | N | N | N
CC0375-ELE-COND-035 | MV Conduits-02UBY01 GZ210 to 02UBY01 GZ420 | Conduits | Active | 2023-08-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-03 |  | N | N | N
CC0375-ELE-COND-036 | LV Conduits-02UBZ01 GZ420 Turnups | Conduits | Active | 2023-08-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-30 |  | N | N | N
CC0375-ELE-COND-037 | LV Conduits-90UBZ01 GZ030 to 90UBZ01 GZ040 | Conduits | Works Complete | 2023-08-31 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-01 | 2023-09-05 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000023
CC0375-ELE-COND-038 | LV Conduits-90UBZ01 GZ030 North Turnups | Conduits | Works Complete | 2023-08-31 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-11 | 2023-09-15 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000023
CC0375-ELE-COND-039 | LV Conduits-90UBZ01 GZ030 South Turnups | Conduits | Works Complete | 2023-08-31 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-05 | 2023-09-07 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000023
CC0375-ELE-COND-040 | LV Conduits-90UBZ01 GZ040 North Turnups | Conduits | Works Complete | 2023-08-31 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-07 | 2023-09-15 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000023
CC0375-ELE-COND-041 | LV Conduits-90UBZ01 GZ040 South Turnups | Conduits | Works Complete | 2023-08-31 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-04 | 2023-09-05 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000023
CC0375-ELE-COND-042 | MV Conduits-02UBY01 GZ270 West | Conduits | Open | 2023-09-06 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-043 | LV Conduits-02UBZ01 GZ210 to GZ230 | Conduits | Open | 2023-09-06 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-044 | LV Conduits-01UBZ01 GZ410 Eastern Turnups | Conduits | Active | 2023-09-12 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-18 |  | N | N | N
CC0375-ELE-COND-045 | LV Conduits-02UBZ01 GZ210 to GZ010 (including North and East Turnups) | Conduits | Open | 2023-09-12 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-046 | LV Conduits-90UBZ01 GZ020 to KNSS Existing Conduits | Conduits | Open | 2023-09-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-047 | LV Conduits-90UBZ10 GZ033 (BOP TU1) to 90UBZ10 GZ034 (BOP LVSR) Turnups [LV+CO] | Conduits | Works Complete | 2023-09-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-09 | 2023-10-10 | Y | N | N
CC0375-ELE-COND-048 | LV Conduits-90UBZ10 GZ035 (BOP TU2) to 90UBZ10 GZ036 (BOP LVSR) Turnups [LV+CO] | Conduits | Works Complete | 2023-09-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-10 | 2023-10-12 | Y | N | N
CC0375-ELE-COND-049 | LV Conduits-90UBZ10 GZ037 (BOP TU3) to 90UBZ10 GZ038 (BOP LVSR) Turnups [LV+CO] | Conduits | Works Complete | 2023-09-18 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-10 | 2023-10-12 | Y | N | N
CC0375-ELE-COND-050 | MV Conduits-01UBY01 GZ440 to 90UBY01 GZ260 | Conduits | Active | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-03 |  | N | N | N
CC0375-ELE-COND-051 | MV Conduits-02 MV Prefab Substation to Step Up Transformer | Conduits | Active | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-06 |  | N | N | N
CC0375-ELE-COND-052 | MV Conduits-90UBY01 GZ040 to 90UBY01 GZ260 | Conduits | Works Complete | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-25 | 2023-09-27 | Y | N | N
CC0375-ELE-COND-053 | LV Conduits-01UBZ01 GZ320 Western Turnups | Conduits | Open | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-054 | LV Conduits-01 LV Prefab Substation to Step Up Transformer | Conduits | Active | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-22 |  | N | N | N
CC0375-ELE-COND-055 | LV Conduits-02UBZ01 GZ410 to GZ420 including Turnups | Conduits | Active | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-09 |  | N | N | N
CC0375-ELE-COND-056 | LV Conduits-02UBZ01 GZ410 Eastern Turnups | Conduits | Open | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-057 | LV Conduits-90UBZ10 GZ039 South Turnups | Conduits | Works Complete | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-05 | 2023-10-09 | Y | N | N
CC0375-ELE-COND-058 | LV Conduits-90UBZ10 GZ093 to 90UBZ10 GZ092 Turnups [LV+CO] | Conduits | Active | 2023-09-21 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-12 |  | N | N | N
CC0375-ELE-COND-059 | LV Conduits-01UBZ01 GZ510 West turnups | Conduits | Active | 2023-09-22 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-27 |  | N | N | N
CC0375-ELE-COND-060 | MV Conduits-02UBY01 GZ210 East to Aux Transformer | Conduits | Open | 2023-09-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-061 | LV Conduits-02 LV Lube Oil to Mitsubishi Sub | Conduits | Open | 2023-09-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-062 | LV Conduits-02 LV Air Intake to Aux Transformer | Conduits | Open | 2023-09-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-063 | LV Conduits-02 LV Air Intake to Mitsubishi Sub | Conduits | Open | 2023-09-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-064 | LV Conduits-02UBZ01 GZ210 to GZ410 | Conduits | Open | 2023-09-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-065 | MV Conduits-01 MV 6.6kV Substation to SFC Transformer | Conduits | Active | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-03 |  | N | N | N
CC0375-ELE-COND-066 | MV Conduits-01UBY01 GZ450 to 02UBY01 GZ210 | Conduits | Open | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-09-29 |  | N | N | N
CC0375-ELE-COND-067 | MV Conduits-90UBY01 GZ260 to 01UBY01 GZ340 | Conduits | Open | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-09-11 |  | N | N | N
CC0375-ELE-COND-068 | MV Conduits-01UBY01 GZ421 to GZ422 | Conduits | Open | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-29 |  | N | N | N
CC0375-ELE-COND-069 | LV Conduits-01 LV Prefab Substation to SFC Transformer | Conduits | Active | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-03 |  | N | N | N
CC0375-ELE-COND-070 | LV Conduits-01 LV SFC Transformer Connections | Conduits | Open | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers |  |  | N | N | N
CC0375-ELE-COND-071 | LV Conduits-90UBZ01 GZ262 (Mega Pit) to 90UBZ01GZ270 | Conduits | Works Complete | 2023-10-03 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-04 | 2023-10-17 | Y | N | N
CC0375-ELE-COND-072 | MV Conduits-02UBY01 GZ420 to 450 | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-073 | MV Conduits-02UBY01 450 East Turnups | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-074 | MV Conduits-02 MV Prefab Substation to SFC Transformer | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-075 | LV Conduits-02UBZ01 GZ510 West turnups | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-076 | LV Conduits-02UBZ01 GZ410 Eastern Turnups | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-077 | LV Conduits-02 LV Prefab Substation to Step Up Transformer | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-078 | LV Conduits-02 LV Prefab Substation to SFC Transformer | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-079 | LV Conduits-02 LV SFC Transformer Connections | Conduits | Open | 2023-10-10 | ELE | CC0375-ITP-008 Conduit and Pit Installation |  |  |  | N | N | N
CC0375-ELE-COND-080 | LV Conduits-90UBZ01 GZ270 to 90UBZ01 GZ340 | Conduits | Open | 2023-10-17 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-10-17 |  | N | N | N
CC0375-ELE-COND-081 | LV Conduits-90UBZ01 GZ020 to KNSS Existing Conduits | Conduits | Open | 2023-10-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-082 | LV Conduits-90UBZ01 GZ030 to 90UBZ01 GZ020 & Turnups | Conduits | Open | 2023-10-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-083 | Lighting & GP Conduits-LS90-020 to LS90-010 & LS90-010 East Turnups | Conduits | Open | 2023-10-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-084 | Lighting & GP Conduits-LS90-050 to LS90-040 to LS90-030 & LS90-030 East Turnups | Conduits | Open | 2023-10-24 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-085 | MV Conduits-90UBY01 GZ340 to 90UBZ01 GZ300 | Conduits | Open | 2023-10-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-086 | LV Conduits-90UBZ01 GZ340 to 90UBZ01 GZ330 | Conduits | Open | 2023-10-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-COND-087 | LV Conduits-90UBZ01 GZ330 to 90UBZ01 GZ320 | Conduits | Open | 2023-10-25 | ELE | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-ELE-IPIT-001 | GT01 MV Pit-01UBY01 GZ 270 | Insitu Pit | Submitted to UGL | 2023-05-22 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-22 | 2023-06-13 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-002 | GT01 MV Pit-01UBY01 GZ 421 | Insitu Pit | Works Complete | 2023-05-23 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-23 | 2023-06-13 | Y | N | N
CC0375-ELE-IPIT-003 | GT01 MV Pit-01UBY01 GZ 420 | Insitu Pit | Works Complete | 2023-05-30 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-30 | 2023-06-13 | Y | N | N
CC0375-ELE-IPIT-004 | GT01 LV Pit-01UBZ01 GZ420 | Insitu Pit | Works Complete | 2023-05-30 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-05 | 2023-06-13 | Y | N | N
CC0375-ELE-IPIT-005 | GT01 MV Pit-01UBY01 GZ 450 | Insitu Pit | Works Complete | 2023-06-06 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-06 | 2023-06-25 | Y | N | N
CC0375-ELE-IPIT-006 | GT01 LV Pit-01UBZ01 GZ230 | Insitu Pit | Active | 2023-06-11 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-13 | 2023-07-05 | N | N | N
CC0375-ELE-IPIT-007 | GT01 LV Pit-01UBZ01 GZ240 | Insitu Pit | Works Complete | 2023-06-11 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-13 | 2023-07-05 | Y | N | N
CC0375-ELE-IPIT-008 | GT01 LV Pit-01UBZ01 GZ250 | Insitu Pit | Active | 2023-06-11 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-13 | 2023-05-22 | N | N | N
CC0375-ELE-IPIT-009 | GT01 LV Pit-01UBZ01 GZ280 | Insitu Pit | Submitted to UGL | 2023-06-11 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-13 | 2023-07-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-010 | GT01 LV Pit-01UBZ01 GZ320 | Insitu Pit | Works Complete | 2023-06-11 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-13 | 2023-07-05 | Y | N | N
CC0375-ELE-IPIT-011 | GT01 LV Pit-01UBZ01 GZ210 | Insitu Pit | Submitted to UGL | 2023-07-06 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-07 | 2023-08-02 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-012 | GT01 LV Pit-01UBZ01 GZ410 | Insitu Pit | Submitted to UGL | 2023-07-07 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-10 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-013 | GT01 LV Pit-01UBZ01 GZ010 | Insitu Pit | Submitted to UGL | 2023-07-10 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-13 | 2023-07-31 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-014 | GT01 MV Pit-01UBY01 G Z210 | Insitu Pit | Submitted to UGL | 2023-07-13 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) |  | 2023-07-14 | 2023-08-03 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-015 | GT01 MV Pit-01UBY01 GZ 440 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-016 | GT01 LV Pit-01UBZ01 GZ510 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-017 | GT02 MV Pit-02UBY01 GZ 420 | Insitu Pit | Works Complete | 2023-05-30 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-30 | 2023-06-19 | Y | N | N
CC0375-ELE-IPIT-018 | GT02 MV Pit-02UBY01 GZ 450 | Insitu Pit | Works Complete | 2023-05-30 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-30 | 2023-06-29 | Y | N | N
CC0375-ELE-IPIT-019 | GT02 LV Pit-02UBZ01 GZ250 | Insitu Pit | Works Complete | 2023-06-08 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-09 | 2023-06-20 | Y | N | N
CC0375-ELE-IPIT-020 | GT02 LV Pit-02UBZ01 GZ280 | Insitu Pit | Works Complete | 2023-06-08 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-09 | 2023-06-20 | Y | N | N
CC0375-ELE-IPIT-021 | GT02 LV Pit-02UBZ01 GZ240 | Insitu Pit | Works Complete | 2023-06-09 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-10 | 2023-06-30 | Y | N | N
CC0375-ELE-IPIT-022 | GT02 LV Pit-02UBZ01 GZ420 | Insitu Pit | Works Complete | 2023-06-22 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-23 | 2023-06-30 | Y | N | N
CC0375-ELE-IPIT-023 | GT02 LV Pit-02UBZ01 GZ320 | Insitu Pit | Submitted to UGL | 2023-06-26 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-27 | 2023-07-12 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-024 | GT02 LV Pit-02UBZ01 GZ010 | Insitu Pit | Submitted to UGL | 2023-07-07 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-07 | 2023-07-29 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-025 | GT02 LV Pit-02UBZ01 GZ510 | Insitu Pit | Submitted to UGL | 2023-07-07 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-10 | 2023-08-03 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-026 | GT02 MV Pit-02UBY01 GZ 270 | Insitu Pit | Works Complete | 2023-07-21 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-21 | 2023-08-03 | Y | N | N
CC0375-ELE-IPIT-027 | GT02 MV Pit-02UBY01 GZ 210 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-028 | GT02 MV Pit-02UBY01 GZ 422 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-029 | GT02 LV Pit-02UBZ01 GZ210 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-ELE-IPIT-030 | GT02 LV Pit-02UBZ01 GZ230 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-031 | GT02 LV Pit-02UBZ01 GZ410 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-032 | BOP LV Pit-90UBZ01 GZ330 | Insitu Pit | Submitted to UGL | 2023-06-26 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-28 | 2023-07-18 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-033 | BOP LV Pit-90UBZ01 GZ340 | Insitu Pit | Works Complete | 2023-06-26 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-28 | 2023-07-29 | Y | N | N
CC0375-ELE-IPIT-034 | BOP LV Pit-90UBZ01 GZ320 | Insitu Pit | Submitted to UGL | 2023-06-27 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-28 | 2023-07-20 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-035 | BOP MV Pit-90UBY01 GZ 340 | Insitu Pit | Submitted to UGL | 2023-06-28 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-29 | 2023-07-18 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-036 | BOP LV Pit-90UBZ01 GZ040 | Insitu Pit | Submitted to UGL | 2023-07-06 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-07 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-037 | BOP LV Pit-90UBZ01 GZ110 | Insitu Pit | Submitted to UGL | 2023-07-11 | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-12 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-ELE-IPIT-038 | BOP MV Pit-90UBY01 GZ 010 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-039 | BOP MV Pit-90UBY01 GZ 020 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-040 | BOP MV Pit-90UBY01 GZ 030 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-041 | BOP MV Pit-90UBY01 GZ 040 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-042 | BOP MV Pit-90UBY01 GZ 260 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-043 | BOP MV Pit-90UBY01 GZ 300 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-044 | BOP MV Pit-90UBY01 GZ 910 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-045 | BOP LV Pit-90UBZ01 GZ020 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-046 | BOP LV Pit-90UBZ01 GZ030 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-047 | BOP LV Pit-90UBZ01 GZ039 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-048 | BOP LV Pit-90UBZ01 GZ210 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-049 | BOP LV Pit-90UBZ01 GZ220 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-050 | BOP LV Pit-90UBZ01 GZ230 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-051 | BOP LV Pit-90UBZ01 GZ242 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-052 | BOP LV Pit-90UBZ01 GZ262 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-053 | BOP LV Pit-90UBZ01 GZ270 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-054 | BOP LV Pit-90UBZ01 GZ300 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-ELE-IPIT-055 | BOP LV Pit-90UBZ01 GZ310 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-ELE-IPIT-056 | BOP LV Pit-90UBZ01 GZ350 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-ELE-IPIT-057 | BOP LV Pit-90UBZ01 GZ910 | Insitu Pit |  |  | ELE | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang

## COM
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[8 empty] | 2023-10-18 | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-COM-COND-001 | Comms Conduits-01UCZ01 GZ250 to GZ280 | Conduits | Active | 2023-05-08 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-05-08 | 2023-07-13 | N | N | N
CC0375-COM-COND-002 | Comms Conduits-01UCZ01 GZ240 to GZ250 | Conduits | Active | 2023-05-08 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-05-08 | 2023-07-14 | N | N | N
CC0375-COM-COND-003 | Comms Conduits-01UCZ01 GZ280 Eastern Turnups | Conduits | Active | 2023-05-22 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-05-22 | 2023-07-03 | N | N | N
CC0375-COM-COND-004 | Comms Conduits-01UCZ01 GZ280 to GZ320 | Conduits | Active | 2023-05-29 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-05-29 | 2023-09-13 | N | N | N
CC0375-COM-COND-005 | Comms Conduits-01UCZ01 GZ320 Eastern Turnups | Conduits | Active | 2023-05-29 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-05-29 | 2023-09-19 | N | N | N
CC0375-COM-COND-006 | Comms Conduits-01UCZ01 GZ230 to GZ240 | Conduits | Active | 2023-05-29 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-05-29 | 2023-07-10 | N | N | N
CC0375-COM-COND-007 | Comms Conduits-01UCZ01 GZ220 to GZ230 | Conduits | Active | 2023-06-21 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-06-21 | 2023-08-07 | N | N | N
CC0375-COM-COND-008 | Comms Conduits-01UCZ01 GZ420 Turnups | Conduits | Active | 2023-06-23 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-06-23 | 2023-08-03 | N | N | N
CC0375-COM-COND-009 | Comms Conduits-01UCZ01 GZ240 Southbound | Conduits | Active | 2023-07-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-07-10 | 2023-07-11 | N | N | N
CC0375-COM-COND-010 | Comms Conduits-Fire Tank East Comms Turnups | Conduits | Active | 2023-07-14 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-07-14 | 2023-07-15 | N | N | N
CC0375-COM-COND-011 | Comms Conduits-Fire Tank West Comms Turnups | Conduits | Active | 2023-07-17 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-17 | 2023-07-17 | N | N | N
CC0375-COM-COND-012 | Comms Conduits-Fire Tank North Comms Turnups | Conduits | Active | 2023-07-18 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-18 | 2023-07-18 | N | N | N
CC0375-COM-COND-013 | Comms Conduits-01CO GCB to EXC | Conduits | Active | 2023-07-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-25 | 2023-07-31 | N | N | N
CC0375-COM-COND-014 | Comms Conduits-01UCZ01 GZ410 to GZ420 including Turnups | Conduits | Active | 2023-07-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-07-25 | 2023-09-12 | N | N | N
CC0375-COM-COND-015 | Comms Conduits-02CO GCB to EXC | Conduits | Active | 2023-08-11 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-11 | 2023-08-25 | N | N | N
CC0375-COM-COND-016 | Comms Conduits-02UCZ01 GZ420 Turnups | Conduits | Active | 2023-08-11 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-11 | 2023-08-31 | N | N | N
CC0375-COM-COND-017 | Comms Conduits-02UCZ01 GZ250 to GZ280 | Conduits | Active | 2023-08-11 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-08-11 | 2023-08-18 | N | N | N
CC0375-COM-COND-018 | Comms Conduits-02UCZ01 GZ240 Southbound | Conduits | Active | 2023-08-11 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-11 | 2023-08-31 | N | N | N
CC0375-COM-COND-019 | Comms Conduits-02 CO 02UCZ10 GZ280 Turnups | Conduits | Active | 2023-08-18 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-18 | 2023-08-22 | N | N | N
CC0375-COM-COND-020 | Comms Conduits-02 CO 02UCZ01 GZ230 to 02UCZ01 GZ240 | Conduits | Active | 2023-08-18 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-18 | 2023-09-04 | N | N | N
CC0375-COM-COND-021 | Comms Conduits-02 CO 02UCZ01 GZ240 to UCZ01 GZ250 | Conduits | Active | 2023-08-18 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-18 | 2023-09-01 | N | N | N
CC0375-COM-COND-022 | Comms Conduits-02UCZ01 GZ220 to 02UCZ01 GZ230 | Conduits | Active | 2023-08-24 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-08-24 | 2023-08-24 | N | N | N
CC0375-COM-COND-023 | Comms Conduits-90UCZ01 GZ030 to 90UCZ01 GZ040 | Conduits | Works Complete | 2023-08-31 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-08-31 | 2023-09-18 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000023
CC0375-COM-COND-024 | Comms Conduits-90UCZ01 GZ030 Turnups | Conduits | Works Complete | 2023-08-31 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-08-31 | 2023-09-19 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000024
CC0375-COM-COND-025 | Comms Conduits-90UCZ01 GZ040 Turnups | Conduits | Works Complete | 2023-08-31 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-08-31 | 2023-09-18 | Y | N | Y | 0663-NCR-SYMAL-000022 & 0663-NCR-SYMAL-000025
CC0375-COM-COND-026 | Comms Conduits-01UCZ01 GZ410 Eastern Turnups | Conduits | Active | 2023-09-12 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-12 | 2023-09-19 | N | N | N
CC0375-COM-COND-027 | Comms Conduits-02UCZ01 GZ220 to GZ010 | Conduits | Open | 2023-09-12 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-12 |  | N | N | N
CC0375-COM-COND-028 | Comms Conduits-nm | Conduits | Open | 2023-09-18 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-18 |  | N | N | N
CC0375-COM-COND-029 | Comms Conduits-01UCZ01 GZ420 Eastern Turnups | Conduits | Open | 2023-09-19 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-19 |  | N | N | N
CC0375-COM-COND-030 | Comms Conduits-02UCZ01 GZ420 Eastern Turnups | Conduits | Open | 2023-09-19 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-19 |  | N | N | N
CC0375-COM-COND-031 | Comms Conduits-01 CO Prefab Substation to Step Up Transformer | Conduits | Open | 2023-09-21 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-21 | 2023-09-20 | N | N | N
CC0375-COM-COND-032 | Comms Conduits-01UCZ01 GZ510 West turnups | Conduits | Active | 2023-09-22 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-22 | 2023-09-27 | N | N | N
CC0375-COM-COND-033 | Comms Conduits-02UCZ02 GZ220 to 420 | Conduits | Open | 2023-09-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-25 |  | N | N | N
CC0375-COM-COND-034 | Comms Conduits-02UCZ02 GZ220 South Turnups | Conduits | Open | 2023-09-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-25 |  | N | N | N
CC0375-COM-COND-035 | Comms Conduits-02 CO Lube Oil to Mitsubishi Sub | Conduits | Open | 2023-09-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-25 |  | N | N | N
CC0375-COM-COND-036 | Comms Conduits-02 CO Air Intake to Aux Transformer | Conduits | Open | 2023-09-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-09-25 |  | N | N | N
CC0375-COM-COND-037 | Comms Conduits-01 CO 6.6kV Substation to SFC Transformer | Conduits | Active | 2023-10-03 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-03 | 2023-10-03 | N | N | N
CC0375-COM-COND-038 | Comms Conduits-01 CO SFC Transformer Connections | Conduits | Open | 2023-10-03 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-03 |  | N | N | N
CC0375-COM-COND-039 | Comms Conduits-90UBZ01 GZ262 (Mega Pit) to 90UCZ01 GZ0270 | Conduits | Works Complete | 2023-10-03 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-03 | 2023-10-05 | Y | N | N
CC0375-COM-COND-040 | Comms Conduits-02UCZ01 GZ410 to GZ420 including Turnups | Conduits | Open | 2023-10-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-10-10 | 2023-10-09 | N | N | N
CC0375-COM-COND-041 | Comms Conduits-02 CO Prefab Substation to Step Up Transformer | Conduits | Open | 2023-10-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-10-10 |  | N | N | N
CC0375-COM-COND-042 | Comms Conduits-02UCZ01 GZ510 West turnups | Conduits | Open | 2023-10-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-10 |  | N | N | N
CC0375-COM-COND-043 | Comms Conduits-02UCZ01 GZ410 Eastern Turnups | Conduits | Open | 2023-10-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-10 |  | N | N | N
CC0375-COM-COND-044 | Comms Conduits-02 CO Prefab Substation to SFC Transformer | Conduits | Open | 2023-10-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-10 |  | N | N | N
CC0375-COM-COND-045 | Comms Conduits-02 CO SFC Transformer Connections | Conduits | Open | 2023-10-10 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel | 2023-10-10 |  | N | N | N
CC0375-COM-COND-046 | Comms Conduits-90UCZ01 GZ270 to 90UCZ01 GZ340 | Conduits | Active | 2023-10-17 | COM | CC0375-ITP-008 Conduit and Pit Installation | Ben Summers | 2023-10-17 | 2023-10-17 | N | N | N
CC0375-COM-COND-047 | Comms Conduits-90UCZ10 GZ020 West Turnups | Conduits | Open | 2023-10-24 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-COM-COND-048 | Comms Conduits-90UCZ01 GZ020 to KNSS Existing Conduits | Conduits | Open | 2023-10-24 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-COM-COND-049 | Comms Conduits-90UCZ01 GZ030 East Turnups | Conduits | Open | 2023-10-24 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-COM-COND-050 | Comms Conduits-90UCZ01 GZ340 to 90UCZ01 GZ330 | Conduits | Open | 2023-10-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-COM-COND-051 | Comms Conduits-90UCZ01 GZ330 to 90UCZ01 GZ320 | Conduits | Open | 2023-10-25 | COM | CC0375-ITP-008 Conduit and Pit Installation | Darshak Patel |  |  | N | N | N
CC0375-COM-IPIT-001 | GT01 Comms Pit-01UCZ01 GZ420 | Insitu Pit | Works Complete | 2023-05-25 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-25 | 2023-06-24 | Y | N | N
CC0375-COM-IPIT-002 | GT01 Comms Pit-01UCZ01 GZ230 | Insitu Pit | Submitted to UGL | 2023-06-16 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-16 | 2023-07-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-003 | GT01 Comms Pit-01UCZ01 GZ240 | Insitu Pit | Submitted to UGL | 2023-06-16 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-16 | 2023-07-06 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-004 | GT01 Comms Pit-01UCZ01 GZ250 | Insitu Pit | Submitted to UGL | 2023-06-24 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-26 | 2023-07-06 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-005 | GT01 Comms Pit-01UCZ01 GZ280 | Insitu Pit | Submitted to UGL | 2023-06-29 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-30 | 2023-07-11 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-006 | GT01 Comms Pit-01UCZ01 GZ010 | Insitu Pit | Submitted to UGL | 2023-07-10 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-10 | 2023-07-29 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-007 | GT01 Comms Pit-01UCZ01 GZ220 | Insitu Pit |  | 2023-07-14 | COM | CC0375-ITP-018 Conduit Pits (In-situ) |  | 2023-07-15 | 2023-07-28 | [8 empty] | 2023-08-18
CC0375-COM-IPIT-008 | GT01 Comms Pit-01UCZ01 GZ510 | Insitu Pit | Works Complete | 2023-07-22 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-22 | 2023-08-07 | Y | N | N
CC0375-COM-IPIT-009 | GT01 Comms Pit-01UCZ01 GZ320 | Insitu Pit |  | 2023-07-28 | COM | CC0375-ITP-018 Conduit Pits (In-situ) |  | 2023-07-31
CC0375-COM-IPIT-010 | GT01 Comms Pit-01UCZ01 GZ410 | Insitu Pit | Submitted to UGL | 2023-08-01 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-08-01 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-011 | GT02 Comms Pit-02UCZ01 GZ420 | Insitu Pit | Works Complete | 2023-05-30 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-05-30 | 2023-07-12 | Y | N | N
CC0375-COM-IPIT-012 | GT02 Comms Pit-02UCZ01 GZ510 | Insitu Pit | Submitted to UGL | 2023-07-07 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-07 | 2023-07-29 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-013 | GT02 Comms Pit-02UCZ01 GZ010 | Insitu Pit | Submitted to UGL | 2023-07-10 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-10 | 2023-07-31 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-014 | GT02 Comms Pit-02UCZ01 GZ250 | Insitu Pit |  | 2023-07-17 | COM | CC0375-ITP-018 Conduit Pits (In-situ) |  | 2023-07-18 | 2023-08-05
CC0375-COM-IPIT-015 | GT02 Comms Pit-02UCZ01 GZ280 | Insitu Pit | Submitted to UGL | 2023-07-22 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-22 | 2023-08-07 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-016 | GT02 Comms Pit-02UCZ01 GZ320 | Insitu Pit | Submitted to UGL | 2023-08-03 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-08-04 | 2023-08-11 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-017 | GT02 Comms Pit-02UCZ01 GZ220 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-COM-IPIT-018 | GT02 Comms Pit-02UCZ01 GZ230 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-COM-IPIT-019 | GT02 Comms Pit-02UCZ01 GZ240 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang
CC0375-COM-IPIT-020 | GT02 Comms Pit-02UCZ01 GZ410 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-COM-IPIT-021 | BOP Comms Pit-90UCZ01 GZ330 | Insitu Pit | Works Complete | 2023-06-28 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-29 | 2023-07-18 | Y | N | N
CC0375-COM-IPIT-022 | BOP Comms Pit-90UCZ01 GZ320 | Insitu Pit | Submitted to UGL | 2023-06-29 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-06-30 | 2023-07-29 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-023 | BOP Comms Pit-90UCZ01 GZ110 | Insitu Pit | Submitted to UGL | 2023-07-04 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-10 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-024 | BOP Comms Pit-90UCZ01 GZ340 | Insitu Pit | Submitted to UGL | 2023-07-06 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-07 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-025 | BOP Comms Pit-90UCZ01 GZ040 | Insitu Pit | Submitted to UGL | 2023-07-11 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-07-11 | 2023-08-05 | Y | Y | N | [5 empty] | 2023-08-18
CC0375-COM-IPIT-026 | BOP Comms Pit-90UCZ01 GZ020 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-COM-IPIT-027 | BOP Comms Pit-90UCZ01 GZ030 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-COM-IPIT-028 | BOP Comms Pit-90UCZ01 GZ210 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-COM-IPIT-029 | BOP Comms Pit-90UCZ01 GZ220 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ)
CC0375-COM-IPIT-030 | BOP Comms Pit-90UCZ01 GZ230 | Insitu Pit | Works Complete | 2023-08-26 | COM | CC0375-ITP-018 Conduit Pits (In-situ) |  | 2023-09-05 | 2023-09-06 | Y | N | N
CC0375-COM-IPIT-031 | BOP Comms Pit-90UCZ01 GZ270 | Insitu Pit | Works Complete | 2023-08-11 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-08-12 |  | Y | N | N
CC0375-COM-IPIT-032 | BOP Comms Pit-90UCZ01 GZ300 | Insitu Pit | Works Complete | 2023-08-17 | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang | 2023-08-18 | 2023-08-30 | Y | N | N
CC0375-COM-IPIT-033 | BOP Comms Pit-90UCZ01 GZ310 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ) | Yoon Kang |  |  |  |  | N
CC0375-COM-IPIT-034 | BOP Comms Pit-90UCZ01 GZ350 | Insitu Pit | Works Complete | 2023-08-28 | COM | CC0375-ITP-018 Conduit Pits (In-situ) |  | 2023-09-05 | 2023-09-06 | Y | N | N
CC0376-COM-IPIT-035 | BOP Comms Pit-90UCZ01 GZ910 | Insitu Pit |  |  | COM | CC0375-ITP-018 Conduit Pits (In-situ) | [5 empty] | N
CC0376-COM-IPIT-040 | Start here

## OW
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-OW-PIP-001 | O20-03 to O20-05 | Pipe | Works Complete | 2023-06-08 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | TBC | TBC | N | N | N
CC0375-OW-PIP-002 | O20-02 to O20-03 | Pipe | Works Complete | 2023-06-08 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | TBC | TBC | N | N | Y | NCR-016
CC0375-OW-PIP-003 | O01-11 to O25-01 | Pipe | Works Complete | 2023-06-08 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | TBC | TBC | N | N | N
CC0375-OW-PIP-004 | O25-01 to O02-01, O25-02, O26-01 & O40-01 | Pipe | Active | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-15 |  | N | N | N
CC0375-OW-PIP-005 | O08-02 to O14-01 | Pipe | Open | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-OW-PIP-006 | O14-01 to O15-01 | Pipe | Active | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-10-13 |  | N | N | N
CC0375-OW-PIP-007 | O01-03 to O04-01 | Pipe | Works Complete | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-09-18 | 2023-09-29 | Y | N | N
CC0375-OW-PIP-008 | O04-01 to O30-01 | Pipe | Works Complete | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-09-29 | 2023-10-03 | Y | N | N
CC0375-OW-PIP-009 | O08-05 to O08-06 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-06-23 | 2023-06-28 | Y | N | N
CC0375-OW-PIP-010 | O08-06 to O08-07 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-06-28 | 2023-07-03 | Y | N | Y | NCR-016
CC0375-OW-PIP-011 | O08-07 to O08-08 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-03 | 2023-07-06 | Y | N | Y | NCR-016
CC0375-OW-PIP-012 | O08-08 to O06-01 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-06 | 2023-07-08 | Y | N | Y | NCR-016
CC0375-OW-PIP-013 | O06-01 to O06-02, O09-01, O33-01, O41-01 | Pipe | Active | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-24 |  | N | N | N
CC0375-OW-PIP-014 | O08-06 to O16-02 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-09 | 2023-07-12 | Y | N | N
CC0375-OW-PIP-015 | O08-07 to O31-02 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-08 | 2023-07-08 | Y | N | N
CC0375-OW-PIP-016 | O08-02 to O08-03 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-08-02 | 2023-08-08 | Y | N | N
CC0375-OW-PIP-017 | O08-03 to O08-04 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-08-08 | 2023-08-20 | Y | N | Y | NCR-016
CC0375-OW-PIP-018 | O08-04 to O08-05 | Pipe | Open | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-OW-PIP-019 | O08-04 to O23-01 | Pipe | Works Complete | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-08-22 | 2023-08-27 | Y | N | N
CC0375-OW-PIP-020 | O24-03 to O24-01 | Pipe | Open | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-OW-PIP-021 | O17-01 to O20-02, O20-03 | Pipe | Open | 2023-06-23 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-OW-PIP-022 | O01-03 to O01-04 | Pipe | Works Complete | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-13 | 2023-07-20 | Y | N | N
CC0375-OW-PIP-023 | O01-04 to O08-01 | Pipe | Works Complete | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-20 | 2023-07-25 | Y | N | N
CC0375-OW-PIP-024 | O08-01 to O08-02 | Pipe | Works Complete | 2023-06-07 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-07-25 | 2023-08-01 | Y | N | N
CC0375-OW-PIP-025 | O01-04 to O01-05 | Pipe | Works Complete | 2023-08-15 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-08-18 | 2023-08-22 | Y | N | N
CC0375-OW-PIP-026 | O01-05 to O01-06 | Pipe | Works Complete | 2023-08-15 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-08-25 | 2023-08-29 | Y | N | N
CC0375-OW-PIP-027 | O01-06 to O01-07 | Pipe | Works Complete | 2023-08-25 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) | Austin Slaney | 2023-08-29 | 2023-09-12 | Y | N | N
CC0375-OW-PIP-028 | O01-07 to O07-02 | Pipe | Works Complete | 2023-09-12 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-09-12 | 2023-09-18 | Y | N | N
CC0375-OW-PIP-029 | O01-07 to O01-08 | Pipe | Open | 2023-09-12 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-030 | O01-01 to O01-02 | Pipe | Active | 2023-09-12 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-10-06 |  | N | N | N
CC0375-OW-PIP-031 | O01-02 to O01-03 | Pipe | Works Complete | 2023-09-12 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-10-06 | 2023-10-08 | Y | N | N
CC0375-OW-PIP-032 | O30-01 to O12-01 | Pipe | Works Complete | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-09-28 | 2023-09-30 | Y | N | N
CC0375-OW-PIP-033 | O01-02 to O29-01 | Pipe | Open | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-034 | O14-01 to O14-02 | Pipe | Open | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-035 | O14-02 to O14-03 | Pipe | Open | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-036 | O01-08 to O01-09 | Pipe | Open | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-037 | O01-09 to O01-10 | Pipe | Open | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-038 | O01-10 to O01-11 | Pipe | Open | 2023-09-18 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-039 | O30-01 to O30-02 | Pipe | Open | 2023-10-03 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-09-29 | 2023-10-03 | N | N | N
CC0375-OW-PIP-040 | O30-02 to O30-03 | Pipe | Open | 2023-10-03 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-09-29 | 2023-10-03 | N | N | N
CC0375-OW-PIP-041 | O08-03 to O34-01 | Pipe | Active | 2023-10-03 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-10-10 |  | N | N | N
CC0375-OW-PIP-042 | O19-02 to O19-03 | Pipe | Works Complete | 2023-10-13 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  | 2023-10-13 | 2023-10-16 | Y | N | N
CC0375-OW-PIP-043 | O19-01 to O19-02 | Pipe | Open | 2023-10-13 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-044 | O08-03 to O19-01 | Pipe | Open | 2023-10-13 | OW | CC0375-ITP-004 Oily Water (Pipe Laying) |  |  |  | N | N | N
CC0375-OW-PIP-050 | start here
CC0375-OW-PPIT-001 | Precast Pit-O15-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-25 | 2023-08-10 | Y | N | N
CC0375-OW-PPIT-002 | Precast Pit-O01-03 | Precast Pit | Open | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney |  |  | N | N | N
CC0375-OW-PPIT-003 | Precast Pit-O04-01 | Precast Pit | Open | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney |  |  | N | N | N
CC0375-OW-PPIT-004 | Precast Pit-O30-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-13 | 2023-07-20 | Y | N | N
CC0375-OW-PPIT-005 | Precast Pit-O08-05 | Precast Pit | Active | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-09-27 |  | N | N | N
CC0375-OW-PPIT-006 | Precast Pit-O08-06 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-09-28 | 2023-09-29 | Y | N | N
CC0375-OW-PPIT-007 | Precast Pit-O08-07 | Precast Pit | Open | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-06-21 | 2023-06-28 | N | N | N
CC0375-OW-PPIT-008 | Precast Pit-O08-08 | Precast Pit | Open | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-06-22 | 2023-07-03 | N | N | N
CC0375-OW-PPIT-009 | Precast Pit-O06-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-06-29 | 2023-07-06 | Y | N | N
CC0375-OW-PPIT-010 | Precast Pit-O06-02 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-03 | 2023-07-06 | Y | N | N
CC0375-OW-PPIT-011 | Precast Pit-O16-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-09 | 2023-08-21 | Y | N | N
CC0375-OW-PPIT-012 | Precast Pit-O31-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-26 | 2023-08-21 | Y | N | N
CC0375-OW-PPIT-013 | Precast Pit-O08-03 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-08 | 2023-07-12 | Y | N | N
CC0375-OW-PPIT-014 | Precast Pit-O08-04 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-08 | 2023-07-08 | Y | N | N
CC0375-OW-PPIT-015 | Precast Pit-O23-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-06 | 2023-08-22 | Y | N | N
CC0375-OW-PPIT-016 | Precast Pit-O01-04 | Precast Pit | Active | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-16 |  | N | N | N
CC0375-OW-PPIT-017 | Precast Pit-O08-01 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-22 | 2023-08-24 | Y | N | N
CC0375-OW-PPIT-018 | Precast Pit-O01-05 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-13 | 2023-08-24 | Y | N | N
CC0375-OW-PPIT-019 | Precast Pit-O01-06 | Precast Pit | Works Complete | 2023-06-23 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-22 | 2023-07-24 | Y | N | N
CC0375-OW-PPIT-020 | Precast Pit-O01-07 | Precast Pit | Works Complete | 2023-08-15 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-18 | 2023-08-22 | Y | N | N
CC0375-OW-PPIT-021 | Precast Pit-O01-08 | Precast Pit | Works Complete | 2023-08-15 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-25 | 2023-08-29 | Y | N | N
CC0375-OW-PPIT-022 | Precast Pit-O01-01 | Precast Pit | Works Complete | 2023-08-25 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-29 | 2023-09-18 | Y | N | N
CC0375-OW-PPIT-023 | Precast Pit-O01-02 | Precast Pit | Open | 2023-09-12 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-024 | Precast Pit-O29-01 | Precast Pit | Open | 2023-09-12 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-025 | Precast Pit-O14-02 | Precast Pit | Works Complete | 2023-09-12 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  | 2023-10-06 | 2023-10-08 | Y | N | N
CC0375-OW-PPIT-026 | Precast Pit-O14-03 | Precast Pit | Open | 2023-09-18 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-027 | Precast Pit-O01-09 | Precast Pit | Open | 2023-09-18 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-028 | Precast Pit-O01-10 | Precast Pit | Open | 2023-09-18 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-029 | Precast Pit-O19-01 | Precast Pit | Open | 2023-09-18 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-030 | Precast Pit-O01-10 | Precast Pit | Open | 2023-09-18 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-PPIT-031 | Precast Pit-O19-01 | Precast Pit | Open | 2023-10-13 | OW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-OW-IPIT-001 | Insitu Pit-OW025-1 | Insitu Pit | Works Complete | 2023-06-13 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-06-14 | 2023-06-22 | Y | N | N
CC0375-OW-IPIT-002 | Insitu Pit-OW25-02 | Insitu Pit | Works Complete | 2023-06-30 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-07-01 | 2023-07-11 | Y | N | N
CC0375-OW-IPIT-003 | Insitu Pit-OW01-11 | Insitu Pit | Works Complete | 2023-06-14 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-06-15 | 2023-06-30 | Y | N | N
CC0375-OW-IPIT-004 | Insitu Pit-OW07-02 | Insitu Pit | Works Complete | 2023-07-07 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-07-07 | 2023-07-20 | Y | N | N
CC0375-OW-IPIT-005 | Insitu Pit-OW12-01 | Insitu Pit | Works Complete | 2023-07-23 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-07-23 | 2023-08-07 | Y | N | N
CC0375-OW-IPIT-006 | Insitu Pit-OW24-01 | Insitu Pit | Works Complete | 2023-07-14 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-07-15 | 2023-08-10 | Y | N | N
CC0375-OW-IPIT-007 | Insitu Pit-OW03-01 | Insitu Pit | Active | 2023-09-07 | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures) |  | 2023-09-08 |  | N | N
CC0375-OW-IPIT-008 | Insitu Pit-OW04-02 | Insitu Pit |  |  | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures)
CC0375-OW-IPIT-009 | Insitu Pit-OW04-03 | Insitu Pit |  |  | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures)
CC0375-OW-IPIT-010 | Insitu Pit-OW04-04 | Insitu Pit |  |  | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures)
CC0375-OW-IPIT-011 | Insitu Pit-OW11-01 | Insitu Pit |  |  | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures)
CC0375-OW-IPIT-012 | Insitu Pit-OW30-03 | Insitu Pit |  |  | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures)
CC0375-OW-IPIT-013 | Insitu Pit-OW30-02 | Insitu Pit |  |  | OW | CC0375-ITP-011 Drainage (Cast In-situ Structures)

## SW
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-SW-PIP-001 | A02-06 to A04-01 | Pipe | Works Complete | 2023-02-16 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Josh Fisicaro | 2023-02-17 | 2023-02-18 | Y | N | N
CC0375-SW-PIP-002 | A01-01 to A01-02 | Pipe | Active | 2023-08-28 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Reza Jamshidi | 2023-08-30 |  | N | N | N
CC0375-SW-PIP-003 | A01-02 to A01-03 | Pipe | Active | 2023-08-28 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Reza Jamshidi | 2023-09-05 |  | N | N | N
CC0375-SW-PIP-004 | A10-02 to A10-03 | Pipe | Works Complete | 2023-09-13 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Reza Jamshidi | 2023-09-18 | 2023-09-21 | Y | N | N
CC0375-SW-PIP-005 | A03-01 to A03-02 | Pipe | Complete | 2023-09-13 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Reza Jamshidi | 2023-09-21 | 2023-09-25 | Y | N | N
CC0375-SW-PIP-006 | A03-02 to A03-03 | Pipe | Complete | 2023-09-22 | SW | CC0375-ITP-002 Drainage (Pipe Laying) |  | 2023-09-29 | 2023-09-29 | Y | N | N
CC0375-SW-PIP-007 | A03-03 to A03-04 | Pipe | Active | 2023-09-25 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney | 2023-10-03 |  | N | N | N
CC0375-SW-PIP-008 | A03-05 to A03-06 | Pipe | Open | 2023-10-03 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-009 | A03-06 to A03-07 | Pipe | Open | 2023-10-03 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-010 | A02-05 to A07-01 | Pipe | Open | 2023-10-03 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-011 | A03-01 to A10-04 | Pipe | Open | 2023-10-09 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-012 | A25-05 to A25-04 | Pipe | Open | 2023-10-12 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-013 | A25-04 to A25-03 | Pipe | Open | 2023-10-12 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-014 | A25-03 to A25-02 | Pipe | Open | 2023-10-12 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-015 | A25-02 to A25-01 | Pipe | Open | 2023-10-12 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-016 | A25-01 to A28-01 | Pipe | Open | 2023-10-12 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Austin Slaney |  |  | N | N | N
CC0375-SW-PIP-017 | A01-09 to A01-10 | Pipe | Open | 2023-10-13 | SW | CC0375-ITP-002 Drainage (Pipe Laying) |  |  |  | N | N | N
CC0375-SW-PIP-018 | A01-10 to A01-11 | Pipe | Open | 2023-10-13 | SW | CC0375-ITP-002 Drainage (Pipe Laying) | Reza Jamshidi |  |  | N | N | N
CC0375-SW-PPIT-001 | Precast Pit-A10-02 | Precast Pit | Works Complete | 2023-09-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi | 2023-09-18 | 2023-09-22 | Y | N | N | [5 empty] | 2023-09-23
CC0375-SW-PPIT-002 | Precast Pit-A10-03 | Precast Pit | Works Complete | 2023-09-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi | 2023-09-19 | 2023-09-22 | Y | N | N | [5 empty] | 2023-09-24
CC0375-SW-PPIT-003 | Precast Pit-A03-01 | Precast Pit | Works Complete | 2023-09-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi | 2023-09-21 | 2023-09-25 | Y | N | N
CC0375-SW-PPIT-004 | Precast Pit-A03-02 | Precast Pit | Works Complete | 2023-09-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi | 2023-09-22 | 2023-09-29 | Y | N | N
CC0375-SW-PPIT-005 | Precast Pit-A03-03 | Precast Pit | Works Complete | 2023-09-25 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi | 2023-09-28 | 2023-09-29 | Y | N | N
CC0375-SW-PPIT-006 | Precast Pit-A03-04 | Precast Pit | Active | 2023-09-25 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi | 2023-10-03 |  | N | N | N
CC0375-SW-PPIT-007 | Precast Pit-A03-05 | Precast Pit | Open | 2023-10-03 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi |  |  | N | N | N
CC0375-SW-PPIT-008 | Precast Pit-A03-06 | Precast Pit | Open | 2023-10-03 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi |  |  | N | N | N
CC0375-SW-PPIT-009 | Precast Pit-A03-07 | Precast Pit | Open | 2023-10-03 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi |  |  | N | N | N
CC0375-SW-PPIT-010 | Precast Pit-A02-05 | Precast Pit | Open | 2023-10-03 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi |  |  | N | N | N
CC0375-SW-PPIT-011 | Precast Pit-A07-01 | Precast Pit | Open | 2023-10-03 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Reza Jamshidi |  |  | N | N | N
CC0375-SW-PPIT-012 | Precast Pit-A10-04 | Precast Pit | Open | 2023-10-09 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-013 | Precast Pit-A25-05 | Precast Pit | Open | 2023-10-12 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-014 | Precast Pit-A25-04 | Precast Pit | Open | 2023-10-12 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-015 | Precast Pit-A25-03 | Precast Pit | Open | 2023-10-12 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-016 | Precast Pit-A25-02 | Precast Pit | Open | 2023-10-12 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-017 | Precast Pit-A28-01 | Precast Pit | Open | 2023-10-12 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-018 | Precast Pit-A01-09 | Precast Pit | Open | 2023-10-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-019 | Precast Pit-A01-10 | Precast Pit | Open | 2023-10-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
CC0375-SW-PPIT-020 | Precast Pit-A01-11 | Precast Pit | Open | 2023-10-13 | SW | CC0375-ITP-003 Drainage (Pre-cast Structures) |  |  |  | N | N | N
[10 empty] | N | N | N

## TW
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-TW-PIP-001 | W04-02 to W04-01 | Pipe | Submitted to UGL | 2023-04-03 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-04-03 | 2023-04-06 | Y | Y | N | [5 empty] | 2023-08-30
CC0375-TW-PIP-002 | W04-01 to W02-05 | Pipe | Works Complete | 2023-04-03 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-04-18 | 2023-04-21 | Y | N | N
CC0375-TW-PIP-003 | W02-05 to W02-06 | Pipe | Submitted to UGL | 2023-04-18 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-01 | 2023-05-02 | Y | Y | N | [5 empty] | 2023-08-30
CC0375-TW-PIP-004 | W02-06 to W02-07 | Pipe | Works Complete | 2023-05-02 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-04 | 2023-05-06 | Y | N | N
CC0375-TW-PIP-005 | W02-10 to W02-11 | Pipe | Works Complete | 2023-04-26 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-04-26 | 2023-04-28 | y | N | N
CC0375-TW-PIP-006 | W02-11 to W02-13 | Pipe | Works Complete | 2023-04-26 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-04-27 | 2023-04-28 | y | N | N
CC0375-TW-PIP-007 | W02-13 to W02-15 | Pipe | Works Complete | 2023-04-26 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-04-27 | 2023-04-28 | y | N | N
CC0375-TW-PIP-008 | W02-15 to W02-17 | Pipe | Open | 2023-04-26 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney |  |  |  |  | N
CC0375-TW-PIP-009 | W02-07 to W02-08 | Pipe | Submitted to UGL | 2023-05-05 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-08 | 2023-05-09 | y | N | N | [5 empty] | 2023-09-21
CC0375-TW-PIP-010 | W02-08 to W02-09 | Pipe | Submitted to UGL | 2023-05-05 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-10 | 2023-05-11 | y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PIP-011 | W02-09 to W02-10 | Pipe | Works Complete | 2023-05-05 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-12 | 2023-05-12 | y | N | N
CC0375-TW-PIP-012 | W02-08 to W01-01 | Pipe | Works Complete | 2023-05-05 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-12 | 2023-05-12 | y | N | N
CC0375-TW-PIP-013 | W02-09 to W03-01 | Pipe | Works Complete | 2023-05-05 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-12 | 2023-05-12 | y | N | N
CC0375-TW-PIP-014 | W04-02 to W04-03 | Pipe | Open | 2023-07-12 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-16 | 2023-05-17 |  |  | N
CC0375-TW-PIP-015 | W04-03 to W04-04 | Pipe | Works Complete | 2023-05-16 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-17 | 2023-05-18 | y | N | N
CC0375-TW-PIP-016 | W04-03 to W05-01 | Pipe | Works Complete | 2023-07-12 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-08-23 | 2023-08-23 | y | N | N
CC0375-TW-PIP-017 | W04-04 to W06-01 | Pipe | Works Complete | 2023-07-12 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-09-14 | 2023-09-15 | y | N | N
CC0375-TW-PIP-018 | W04-06 to W04-08 | Pipe | Submitted to UGL | 2023-05-05 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-30 | 2023-05-30 | y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PIP-019 | W04-08 to W04-10 | Pipe | Submitted to UGL | 2023-05-30 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-05-31 | 2023-06-01 | y | Y | N | [5 empty] | 2023-09-21
CC0375-TW-PIP-020 | W04-10 to W04-12 | Pipe | Works Complete | 2023-06-06 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-06-07 | 2023-06-07 | y | N | N
CC0375-TW-PIP-021 | W02-01 to W02-02 | Pipe | Works Complete | 2023-07-18 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-07-25 | 2023-07-26 | y | N | N
CC0375-TW-PIP-022 | W02-02 to W02-03 | Pipe | Works Complete | 2023-07-18 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-07-26 | 2023-08-01 | y | N | N
CC0375-TW-PIP-023 | W02-03 to W02-04 | Pipe | Works Complete | 2023-07-18 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-08-01 | 2023-08-04 | y | N | N
CC0375-TW-PIP-024 | W02-04 to W02-05 | Pipe | Works Complete | 2023-07-18 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-08-04 | 2023-08-12 | y | N | N
CC0375-TW-PIP-025 | W02-17 to W02-18 | Pipe | Active | 2023-07-19 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-07-20 |  | N | N | N
CC0375-TW-PIP-026 | W04-12 to W04-13 | Pipe | Works Complete | 2023-08-22 | TW | CC0375-ITP-005 Trade Waste (Pipe Laying) | Austin Slaney | 2023-08-24 | 2023-08-24 | Y | N | N
CC0375-TW-PIP-030 | start here
CC0375-TW-PPIT-001 | Precast Pit-W04-02 | Precast Pit | Submitted to UGL | 2023-04-03 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Josh Fisicaro | 2023-04-15 | 2023-04-20 | Y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PPIT-002 | Precast Pit-W04-01 | Precast Pit | Submitted to UGL | 2023-04-03 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Josh Fisicaro | 2023-04-15 | 2023-04-20 | Y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PPIT-003 | Precast Pit-W02-05 | Precast Pit | Open | 2023-04-18 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Josh Fisicaro | 1899-12-31 | 1899-12-31 | N | N | N
CC0375-TW-PPIT-004 | Precast Pit-W02-06 | Precast Pit | Submitted to UGL | 2023-04-18 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Josh Fisicaro | 2023-04-25 | 2023-05-10 | Y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PPIT-005 | Precast Pit-W02-07 | Precast Pit | Submitted to UGL | 2023-05-02 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Josh Fisicaro | 2023-05-05 | 2023-05-10 | Y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PPIT-006 | Precast Pit-W02-02 | Precast Pit | Submitted to UGL | 2023-07-18 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-25 | 2023-08-01 | Y | Y | N | [5 empty] | 2023-09-14
CC0375-TW-PPIT-007 | Precast Pit-W02-03 | Precast Pit | Works Complete | 2023-07-18 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-07-28 | 2023-08-07 | Y | N | N
CC0375-TW-PPIT-008 | Precast Pit-W02-04 | Precast Pit | Works Complete | 2023-07-18 | TW | CC0375-ITP-003 Drainage (Pre-cast Structures) | Austin Slaney | 2023-08-02 | 2023-08-17 | Y | N | N
CC0375-TW-IPPIT-001 | Insitu Pit-W02-10 | Insitu Pit | Works Complete | 2023-05-16 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-16 | 2023-05-19 | Y | N | N
CC0375-TW-IPPIT-002 | Insitu Pit-W02-11 | Insitu Pit | Works Complete | 2023-04-26 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-04-26 | 2023-05-16 | Y | N | N
CC0375-TW-IPPIT-003 | Insitu Pit-W02-13 | Insitu Pit | Works Complete | 2023-04-26 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-04-26 | 2023-05-14 | Y | N | N
CC0375-TW-IPPIT-004 | Insitu Pit-W02-15 | Insitu Pit | Works Complete | 2023-04-26 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-04-26 | 2023-05-12 | Y | N | N
CC0375-TW-IPPIT-005 | Insitu Pit-W02-17 | Insitu Pit |  |  | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang
CC0375-TW-IPPIT-006 | Insitu Pit-W02-08 | Insitu Pit | Works Complete | 2023-05-16 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-16 | 2023-06-20 | Y | N | N
CC0375-TW-IPPIT-007 | Insitu Pit-W02-09 | Insitu Pit | Works Complete | 2023-05-16 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-16 | 2023-06-07 | Y | N | N
CC0375-TW-IPPIT-008 | Insitu Pit-W01-01 | Insitu Pit | Works Complete | 2023-06-14 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-06-15 | 2023-06-23 | Y | N | N
CC0375-TW-IPPIT-009 | Insitu Pit-W03-01 | Insitu Pit | Works Complete | 2023-05-22 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-22 | 2023-05-22 | Y | N | N
CC0375-TW-IPPIT-010 | Insitu Pit-W02-18 | Insitu Pit | Works Complete | 2023-06-29 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-06-29 | 2023-07-11 | Y | N | N
CC0375-TW-IPPIT-011 | Insitu Pit-W04-3 | Insitu Pit | Works Complete | 2023-05-19 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-20 | 2023-05-21 | Y | N | N
CC0375-TW-IPPIT-012 | Insitu Pit-W04-4 | Insitu Pit | Works Complete | 2023-05-19 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-19 | 2023-06-01 | Y | N | N
CC0375-TW-IPPIT-013 | Insitu Pit-W04-5 | Insitu Pit | Works Complete |  | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang
CC0375-TW-IPPIT-014 | Insitu Pit-W04-6 | Insitu Pit | Works Complete | 2023-05-30 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-30 | 2023-06-09 | Y | N | N
CC0375-TW-IPPIT-015 | Insitu Pit-W04-8 | Insitu Pit | Works Complete | 2023-05-31 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-31 | 2023-06-09 | Y | N | N
CC0375-TW-IPPIT-016 | Insitu Pit-W04-10 | Insitu Pit | Works Complete | 2023-05-31 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-05-31 | 2023-06-13 | Y | N | N
CC0375-TW-IPPIT-017 | Insitu Pit-W04-12 | Insitu Pit | Works Complete | 2023-06-06 | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang | 2023-06-06 | 2023-06-20 | Y | N | N
CC0375-TW-IPPIT-018 | Insitu Pit-W04-13 | Insitu Pit |  |  | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang
CC0375-TW-IPPIT-019 | Insitu Pit-W05-1 | Insitu Pit |  |  | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang
CC0375-TW-IPPIT-020 | Insitu Pit-W06-1 | Insitu Pit |  |  | TW | CC0375-ITP-011 Drainage (Cast In-situ Structures) | Yoon Kang

## FM
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
[9 empty] | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required
CC0375-FM-PIP-001 | Fire Ring Main-01SGA04AA008 - GT1 Excitation | Pipe | Works Complete | 2023-07-18 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-07-20 | 2023-08-02 | N | N | N
CC0375-FM-PIP-002 | Fire Ring Main-01SGA01BR006 - GT1 Fuel Oil | Pipe | Complete | 2023-07-18 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-07-31 | 2023-08-03 | N | N | N
CC0375-FM-PIP-003 | Fire Ring Main-02SGA04AA008 - GT2 Excitation | Pipe | Complete | 2023-07-18 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-08-16 | 2023-08-23 | N | N | N
CC0375-FM-PIP-004 | Fire Ring Main-02SGA04AA005 - GT2 Fuel Oil | Pipe | Complete | 2023-07-18 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-08-25 | 2023-08-29 | N | N | N
CC0375-FM-PIP-005 | Fire Ring Main-90SGA04AA003 - LV Switch Room | Pipe | Complete | 2023-09-19 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-09-25 | 2023-09-27 | N | N | N
CC0375-FM-PIP-006 | Fire Ring Main-90SGA01AA002 - Switchyard | Pipe | Active | 2023-09-27 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-09-27 | 2023-09-03 | N | N | N
CC0375-FM-PIP-007 | Fire Ring Main-90SGA04AA001 - Control Room | Pipe | Active | 2023-09-29 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi | 2023-09-29 | 2023-09-03 | N | N | N
CC0375-FM-PIP-008 | Fire Ring Main-01SGA01BR004 - GT1 Switchroom Sprinkler | Pipe | Open | 2023-10-04 | FM | CC0375-ITP-019 HDPE Pipe Installation | Reza Jamshidi

## Export (10)
Lot Number | Lot | Discipline | Status | Opened date | Area / System | Inspection Test Plan | Responsible Engineer | Work commenced date | Physical works completed date | All hold points released | Conforming Test Results attached | NCR raised | NCR number | NCR raised date | NCR closed | NCR closed date | Comments | Submitted date | Closed date | Time to Submitted (from Physical Works Complete) Days | Time to Submitted (from Physical Works Complete) | Time to Close (from Physical Works Complete) Days | Time to Close (from Physical Works Complete) | Hold Points Outstanding | Test Results Outstanding | NCRs Outstanding
CC0375-GT01-ETW-001 | Backfill Grid X-Y | Earthworks | Open | 2023-10-18 | GT01 | 0027 - Structural Concrete | Alex Redman | 2023-10-18 | This is guaranteed date) | Y/N | Y/N | Y/N | If applicable | If applicable | If applicable (Y/N) | If applicable | General Lot comments (we used to use this for "NCR outstanding" but can be used for anything | Submitted to client date |  | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required | Should calculate automatically - no value required