## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CTN-ITP-018 - Hydroseed | itp |  |  |  |  | CTN-ITP-018 - Hydroseed
checkpoint | 1.1 - Check for correct documentation
note | Frequency - Prior to commencing any activity
note | Acceptance Criteria - Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – Conflicting documents will be referenced to the hierarchy of documents listed in Section 175.03
note | Reference Documents - Drawings and drawing registers Section 720
note | Inspection / Test Method - Visual inspection
note | Record of conformity - This ITP Signed
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
note | Frequency - Prior to commencing any activity
note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | Reference Documents - OHSMP, EMP, TMS, SWMS, WP
note | Inspection / Test Method - Visual Inspection
note | Record of conformity - This ITP Signed
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | 2.1 - Hydroseed Mix
note | Frequency - Each Lot
note | Acceptance Criteria - Conformance of hydroseed mix with grass seed properties table 720.045
note | Reference Documents - 720.045
note | Inspection / Test Method - Verify
note | Record of conformity - This ITP Signed, Data sheet
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | 2.2 - Hydroseed application
note | Frequency - Each Lot
note | Acceptance Criteria - Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast)
note | Reference Documents - 720.08
note | Inspection / Test Method - Verify
note | Record of conformity - This ITP Signed, Recievable Inspection Checklist
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | 3.1 - Germination
note | Frequency - Each Lot
note | Acceptance Criteria - Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
note | Reference Documents - 720.08
note | Inspection / Test Method - Verify
note | Record of conformity - This ITP Signed
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | 3.2 - Reseeding
note | Frequency - Each Lot
note | Acceptance Criteria - If germination has not been achieved in any grassed area within 8 weeks, then the area(s) shall be reseeded with the specified grass seed mix
note | Reference Documents - 720.08
note | Inspection / Test Method - Verify
note | Record of conformity - This ITP Signed
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | 4.1 - As Built Documentation
note | Frequency - Each Lot
note | Acceptance Criteria - Lot map showing location and area of hydroseed
note | Reference Documents - Drawings and drawing registers Section 720
note | Inspection / Test Method - Verify
note | Record of conformity - Lot Map
note | HP*
note | Responsibility - Site Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Work Completed On:
textbox | Date: