## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_ Saw Cut Production |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_ Saw Cut Production | 04f6332f-9647-4651-ad79-d004c0780ffb
checkpoint-group |  |  | section | Saw Cut Production Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved Saw Cutting List Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Station - Correct Cutting File, as per approved manufacture plan
checkpoint-status |  |  | checkpoint | Station - Cutting lot completed, checked, and as per approved manufacture plan
text | 128da0b7-8b54-5edf-a684-48540377529f |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Packaging & Shipping |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Packaging & Shipping | 09212c60-2e75-43a0-9ba1-20523d54c1c2
checkpoint-group |  |  | section | Internal Fixtures and Fittings Packaging
checkpoint-status |  |  | checkpoint | Toilet: Cistern fixed by using PET fridge tape
checkpoint-status |  |  | checkpoint | Shower: Shower head protected by wrapping it with EPE foam sheet membrane
checkpoint-status |  |  | checkpoint | Cabinets and Doors: All cabinet doors, mirror cabinet doors and drawers fixed using PET fridge tape.
checkpoint-status |  |  | checkpoint | Bathroom: Bathroom door and Shower door will be fixed with PET fridge tape.
checkpoint-status |  |  | checkpoint | Place Desiccant and Hygrometer inside the module.
text | fa7b4715-8e66-598d-897a-792f68fe22cf |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to plumbing
checkpoint-group |  |  | section | External Protective Cover
checkpoint-status |  |  | checkpoint | Use protective film to cover a module completely
checkpoint-status |  |  | checkpoint | Use heat Gun to seal the protective film.
text | 0de7e665-e444-59f1-9588-78a50a9bcd06 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Make sure there are no gaps in the film
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before moving a Module to a Storage area.
checkpoint-group |  |  | section | Lifting and loading
checkpoint-status |  |  | checkpoint | 18-24T Forkhoist will be used to load a module onto a Specialised Transport Vehicle
checkpoint-status |  |  | checkpoint | Tie the module to the Transport Vehicle, using strops or with the equipment attached to the Vehicle
text | e9b7e74f-41c0-5886-b3fd-9c4b41aaeb5d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Make sure the module is correctly sitting on the Transport vehicles
checkpoint-status |  |  | checkpoint | Make sure the Module has been secured with the correct ties
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step.
checkpoint-group |  |  | section | Shipment
checkpoint-status |  |  | checkpoint | A Specialised Transportation Vehicle will be used to transport the module to Site
text | 6c968f51-669d-5e19-b813-90481a756581 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check if the Transport Company meet the approved transport criteria
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before transporting a Module.
checklist-sectioned |  |  | checklist | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE 6A_6B | 0a9acc11-3bdb-4f86-8a68-de4173cfb217
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE 6A_6B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE X 1 @2400MM
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE PATCH X 1 @1470 X 470MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE X 5 @2400MM
checkpoint-status |  |  | checkpoint | GIB 10MM STANDARD X HALF SHEET
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | 12MM PLYWOOD PATCH X 1 @ 1450 X 420MM
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING PATCH
checkpoint-status |  |  | checkpoint | BATTEN & CRADLE
checkpoint-status |  |  | checkpoint | FIRE DOOR FRAMING 140 X 35MM
checkpoint-status |  |  | checkpoint | FIRE DOOR
checkpoint-status |  |  | checkpoint | ARCHITRAVES X 1 LENGTH
checkpoint-status |  |  | checkpoint | SKIRTING X 1 LENGTH
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER DOOR X 1
text | f7863b46-c524-5842-835f-638e68344510 |  | textbox | ITEMS:
text | 385b70b4-82b0-5cfb-9d7a-30815bcdaae4 |  | textbox | ITEMS:
text | f7d81a76-f95f-596b-a45e-9a7e86783bb6 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo Required and Signed off by Team leader
checklist-sectioned |  |  | checklist | EGM_Ver1.0_08.09.23_CEILING & ITEMS IN MODULE PHOTOS/Record Collection/ |  |  |  |  | Yes | EGM_Ver1.0_08.09.23_CEILING & ITEMS IN MODULE PHOTOS/Record Collection/ B | 2447312b-a6c1-4045-a31c-aeb745ab2768
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checklist-sectioned |  |  | checklist | EGM_Ver1.0_29.03.23_Internal - Gib Stopping & Painting Inspection |  |  |  |  | Yes | EGM_Ver1.0_29.03.23_Internal - Gib Stopping & Painting Inspection | 27146822-fb20-4b97-ba82-f8ef467753c4
checkpoint-group |  |  | section | Gib stopping & Painting
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
text | c734fce2-eebf-5842-b69b-03da7d1bcf4a |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping as per approved plans
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | 1st and 2nd Painting
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacture specifications
text | 806aef79-20f3-56b5-b809-c957a5a2b590 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the painting
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE 3A_3B | 28bbf2c6-577a-4259-ba22-43a98b2e510b
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE 3A_3B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE X 4 @2400MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE X 3 @2400MM
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING X 1 @ 3100 X 350 & 2 @ 900 X 350MM
checkpoint-status |  |  | checkpoint | INTERNAL DOOR RH X 1
checkpoint-status |  |  | checkpoint | INTERNAL DOOR LH X 1
checkpoint-status |  |  | checkpoint | ARCHITRAVES X 4 LENGTHS
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER DOOR X 1
text | 3f3f7fdf-df21-563a-a409-303b543965a0 |  | textbox | ITEMS:
text | 8e669a9f-a734-5de1-b331-5115e5299aa1 |  | textbox | ITEMS:
text | cc7a5363-7142-5040-b3b3-c2a7dfd29ade |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo Required and Signed off by Team leader
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Module Assembly | 2f1b3349-e6e2-46b7-a180-271b1cc7cce1
checkpoint-group |  |  | section | Module Assembly Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate floor cassette on the podium
text | 95212685-bc11-5fc3-b015-580913af3a08 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all external walls, internal walls, and ceiling cassette as per Manufacture plan. Support/Prop necessary.
checkpoint-status |  |  | checkpoint | Fire sealant/acoustic installed as per approved plan and manufacturer specification, all edges to wall, floor and ceiling and provide photo. Part of Passive Fire System
text | cca880c0-cea7-5d44-93d4-b10156cd616e |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed floor, ceiling, and walls as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Check and verify all structural fixings as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Hold point: photo required an signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Exterior - Wraps, penetrations, windows/doors and flashings |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Exterior - Wraps, penetrations, windows/doors and flashings | 3729f133-33b3-4037-9f48-eb83be3fe62c
checkpoint-group |  |  | section | Wrap (RAB)
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install balance RAB.
text | 52775008-bffd-5217-aedd-735f5ecdc3dd |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint-status |  |  | checkpoint | Install all penetrations.
text | 65d72017-30dd-5665-b903-f688c5026e1f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Windows and doors
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all windows and doors as per approved plans and manufacture specifications.
text | 942b5810-0a91-50d7-9f22-4e98df6cef7f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Flashings and tapes
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all flashing tapes/Sealants to RAB joints, windows, doors, penetrations, etc., as required.
text | a6d84868-65a8-52ba-af65-b780675359bf |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-status |  |  | checkpoint | Install all flashings: Interstorey, Int/Ext corner, cavity closer.
text | 9f977c0f-9c5c-5a5a-9a0b-3b17fd13713d |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_11.09.23_POST LANDED MODULE PHOTOS/Record Collection/ |  |  |  |  | Yes | EGM_Ver1.0_11.09.23_POST LANDED MODULE PHOTOS/Record Collection/ | 39e0cb99-02d7-4034-a26e-f10eefeb3080
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checklist-sectioned |  |  | checklist | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE 2A_2B | 3fe45528-f1d5-43d5-a772-f5c1f0640700
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE 2A_2B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE X 1 @2400MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE X 3 @2400MM
checkpoint-status |  |  | checkpoint | GIB 10MM STANDARD X HALF SHEET
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING X 1 @ 3100 X 350 & 1 @ 900 X 350MM
checkpoint-status |  |  | checkpoint | INTERNAL DOOR RH X 1
checkpoint-status |  |  | checkpoint | ARCHITRAVES X 2 LENGTHS
checkpoint-status |  |  | checkpoint | SKIRTING X 1 LENGTH
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER DOOR X 1
text | e79ada0c-9f52-51bc-a02d-54a46fc9a739 |  | textbox | ITEMS:
text | 47786738-f3fb-5794-aec9-1310dc8f2475 |  | textbox | ITEMS:
text | 7cd7d844-dd6e-5b94-8d17-8f9bf0a38b70 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo Required and Signed off by Team leader
checklist-sectioned |  |  | checklist | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE 4A_4B | 41954b1a-314f-4176-8eba-32fd42ebfd7c
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE 4A_4B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE X 2 @2400MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE X 5 @2400MM
checkpoint-status |  |  | checkpoint | GIB AQUALINE X HALF SHEET
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING X 1 @ 3100 X 350
checkpoint-status |  |  | checkpoint | INTERNAL DOOR LH X 1
checkpoint-status |  |  | checkpoint | INTERNAL DOOR RH X 1
checkpoint-status |  |  | checkpoint | ARCHITRAVES X 4 LENGTHS
checkpoint-status |  |  | checkpoint | SKIRTING X 1 LENGTH
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER DOOR X 1
text | 839884d1-ffc4-5a88-ac27-82227d596f16 |  | textbox | ITEMS:
text | 1cd89868-5102-5434-a7ae-afc035851266 |  | textbox | ITEMS:
text | b3365327-34f0-516e-9543-1d7276908aef |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo Required and Signed off by Team leader
checklist-sectioned |  |  | checklist | EGM_Ver1.1_28.03.23_Structure - / CE / Ceiling Cassette Inspection |  |  |  |  | Yes | EGM_Ver1.1_28.03.23_Structure - / CE / Ceiling Cassette Inspection | 4e9ed7ff-e3f3-407b-a363-5853cfb62032
checkpoint-group |  |  | section | Structural Framing and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct manufacture plan and provide picture of the respective manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all ceiling framing elements and fixings as per manufacture plan
text | 51a4e3a4-11d8-5359-902c-fdf9240c094f |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | d254c3f1-18e3-59e1-89ec-e59b89c49f77 |  | textbox | Diagonal #1:
text | 0e7d8402-f34e-51c3-aeb6-7170cf133e56 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct manufacture plan and provide picture of the respective manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Manufacture plan
text | 642e0305-917b-5c2d-a20a-ab8bd4af1ac3 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 2nd Layer and fixing as per Manufacture plan
text | 059b8443-aae0-595d-9148-2045b8376974 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Distribution Board |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Distribution Board | 50f14c1d-ca7c-4bde-bd15-3ec250329032
checkpoint-group |  |  | section | Electrical & Mechanical Distribution Board Inspection
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install Distribution Board as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Install all electrical cabling as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Check and verify installed switchgear valves as per plan
checkpoint-status |  |  | checkpoint | All cables are labeled correctly
checkpoint-status |  |  | checkpoint | Ensure all screws are torqued to correct specification
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/Fixing are in good condition without obvious damage
text | 2d4d6496-ff70-5e0f-b4e4-882f48c14e90 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.3_01.06.23_Structure - EW / MW / CW / IW / TW |  |  |  |  | Yes | EGM_Ver1.3_01.06.23_Structure - EW / MW / CW / IW / TW | 5262c3a2-60e9-4274-a998-f5ac745eb8ec
checkpoint-group |  |  | section | Structural Framing and Preline Inspections
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all wall framing elements and fixing as per Manufacture plan
text | 408c1858-f151-52bc-8abb-bd6e23d90919 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 8d739b9d-f048-5b11-91eb-8a13720a715f |  | textbox | Diagonal #1:
text | 2d916044-44d5-5b80-b681-e07f8e95b3aa |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Structural Sheet Bracing
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install bracing and fixing as per Manufacture plan
text | a00d5fb9-a5da-5c76-bbc6-d81b94260693 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | f41a7d68-78ef-54bb-9f47-7674f120a31b |  | textbox | Diagonal #1:
text | 03d6d7ee-2188-5ba5-8ee1-9b2c9a7a4731 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed bracing as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per Manufacture Plan
text | 0a032a47-dd8a-5856-ad57-a529d0f882bf |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Passive Fire Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Passive Fire Module Assembly | 55a070c6-60c0-47a9-aa55-1ff832f5d256
checkpoint-group |  |  | section | Module Assembly
checkpoint-status |  |  | checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint-status |  |  | checkpoint | Install fire dampers, collars and sealants as per manufacturer specifications.
text | db0b461e-2d62-5fd8-8774-449898b75ac0 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire penetration contractor, tags, before going to next step
checkpoint-group |  |  | section | Fire Seal Inspection
checkpoint-status |  |  | checkpoint | Install fire sound and seal to perimeter as per approved plan, manufacturer system specification and provide photos
checkpoint-status |  |  | checkpoint | Check and verify the Fire Sealant installed, as per approved plans
text | 7aff8529-0781-54cb-9b08-962c3ab5f916 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures as per GIB Fire rate system GWTLE 60A
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures as per GIB Fire rate system GBUW 30A
checkpoint-group |  |  | section | Fire Door Inspection
checkpoint-status |  |  | checkpoint | Fire Door install as per approved plan and manufacturer specification and provide photos
text | dcc6d8a2-c2a2-5f2e-a8f6-e260baf1c8aa |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire door contractor, tags, before going to next step
checkpoint-group |  |  | section | Final Passive Fire Inspection
checkpoint-status |  |  | checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-flat |  |  | checklist | EGM_Ver1.0_20.03.23_Final Sign Off |  |  |  |  | Yes | EGM_Ver1.0_20.03.23_Final Sign Off | 592b134f-0c62-4438-9805-48aa6d791ecb
checkpoint-status |  |  | checkpoint | Module Sign off by Licensed Building Practitioner
holdpoint |  |  | signoff | signoff: SIGNED OFF BY LICENSED BUILDING PRACTITIONER
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_Structure/Module Assembly |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_Structure/Module Assembly | 6d2ab827-dfd6-4929-9e15-22c80c5aa8cd
checkpoint-group |  |  | section | Module Assembly Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate floor cassette on the podium
text | 4bbe9ad7-e358-535b-90ca-5703ab8e3677 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all external walls, internal walls, and ceiling cassette as per Manufacture plan. Support/Prop necessary.
checkpoint-status |  |  | checkpoint | Fire sealant/acoustic installed as per approved plan and manufacturer specification, all edges to wall, floor and ceiling and provide photo. Part of Passive Fire System
text | 1c61a089-2cec-5746-a131-0dcff0d4531c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed floor, ceiling, and walls as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Check and verify all structural fixings as per Manufacture plan.
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the bottom plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket is lining up with pre-drilled holes in the top plate, as accepted
checkpoint-status |  |  | checkpoint | Check RothoBlaas bracket in the top & bottom plate pre-drilled hole has NO screw or nail passing through, as accepted
text | 98d523a7-9168-54bb-a8e4-df00347429ef |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required an signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to next step
checkpoint-group |  |  | section | Module Assembly - Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per Manufacture plan
text | 5cf66530-de3b-5642-ac02-4592f52d1664 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per Manufacture plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_20.03.23_Structure - Roof Assembly |  |  |  |  | Yes | EGM_Ver1.0_20.03.23_Structure - Roof Assembly | 7a39963a-d09f-4a56-acfe-52e84104bef9
checkpoint-group |  |  | section | Roof Assembly Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install roof framing/trusses/purlins as per Manufacture plan
text | d84326de-47a9-5d60-a29b-1553af70fb04 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all structural fixings as per Manufacture plan
text | 4774d0f0-a3e8-5e89-9821-9d5c79c8cc9a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify roof framing treatment and grade as per plan
checkpoint-status |  |  | checkpoint | Check and verify bracing as per plan: roof plane braces, fixings and tensioners, roof space braces and fixings
checkpoint-status |  |  | checkpoint | Check and verify roof pitch, overhang and truss/rafter sizes & spacings as per plan
checkpoint-status |  |  | checkpoint | Check and verify roof ply sheet, centres and fixings as per plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_29.03.23_Floor Covering - Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_29.03.23_Floor Covering - Module Assembly | 7e47c6d5-a0c6-4d67-82f3-472d53f80cea
checkpoint-group |  |  | section | Contractor - Floor Covering
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all floor coverings as per approved plans and manufacture specifications.
checkpoint-status |  |  | checkpoint | Install floor protection, completed (as required)
text | 5819c257-1dcf-57f4-a9ef-95a365e77134 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE 1A_1B | 817fbcbc-7ce1-4843-bcd0-469f9b92b550
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE 1A_1B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE X 2 @2400MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE X 4 @2400MM
checkpoint-status |  |  | checkpoint | GIB 10MM STANDARD X HALF SHEET
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | 12MM PLY PATCHES X 1 SHEET
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING X 1 @ 3100 X 350 & 1 @ 900 X 350MM
checkpoint-status |  |  | checkpoint | INTERNAL DOOR LH X 1
checkpoint-status |  |  | checkpoint | ARCHITRAVES X 2 LENGTHS
checkpoint-status |  |  | checkpoint | SKIRTING X 1 LENGTH
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER DOOR X 1
text | 709905d6-0adc-58c1-a06f-fcdd54da4b22 |  | textbox | ITEMS:
text | ebd2f489-0818-5517-a4db-c7b7ef97297a |  | textbox | ITEMS:
text | f7a40915-9fd2-5649-a409-ea49996ee269 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo Required and Signed off by Team leader
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Electrical First Fix Part 2_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Electrical First Fix Part 2_Module Assembly | 8a56df77-4b05-4de9-a05a-4cae471b78f5
checkpoint-group |  |  | section | First Fix Part 2 Electrical and Mechanical
checkpoint-status |  |  | checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all flush boxes as per electrical services plan
text | b544a98d-121e-554f-b219-8610ab17a4e2 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Confirm the fire rated pads of flush boxes have been installed properly
checkpoint-status |  |  | checkpoint | Install all electrical conduit and draw wires as per electrical services plan
text | b0705910-826d-5e83-924d-9ec529126327 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all electrical cablings as per electrical services plan
text | ad23c199-4fa9-565a-902a-2e6ceda70125 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Apply fire sealant around cut-outs if needed
text | f874546c-637c-5745-80ef-07fd6676bd3f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per electrical services plan
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint-status |  |  | checkpoint | Check and verify fire sealants have been applied
holdpoint |  |  | signoff | Hold point: photo required and signed off by Electrical team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_21.04.23_Plumbing & Drainage - Floor Cassette/ Assembly Area |  |  |  |  | Yes | EGM_Ver1.1_21.04.23_Plumbing & Drainage - Floor Cassette/ Assembly Area | 8d252e01-4480-44c8-806b-7e1093481c97
checkpoint-group |  |  | section | Plumbing & Drainage Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install verified pipework as per approved plans and manufacture instructions
text | 9f0e696e-6f31-5bb1-a25f-c2f77a77cc76 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify foul water pipe are gradients compliant
checkpoint-status |  |  | checkpoint | Complete air test to AS/NZS3500
checkpoint-status |  |  | checkpoint | Complete water test to AS/NZS3500
text | 10075ced-bf70-518b-897d-33669fcd7383 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by before going to next step
checkpoint-group |  |  | section | First Fix Plumbing and Drainage
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacture instructions.
text | 8161577e-0c3c-5e24-93dd-6bd3d418b326 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint-status |  |  | checkpoint | After installation of inner wall water pipework, complete water test to 500Kpa for 30mins (Provide Photo)
checkpoint-status |  |  | checkpoint | After plasterboard (GIB) installation, complete pressure test water pipework to 500Kpa for 30mins (Provide Photo)
checkpoint-status |  |  | checkpoint | Hold point: photo required on digital level of all pipes' runs and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checkpoint-group |  |  | section | Plumbing and Drainage Final Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, refer to as per previous EGM_Plumbing & Drainage Inspection- Floor Cassette/ Assembly Area
checkpoint-status |  |  | checkpoint | Station - Pressure test completed Module with mains pressure to 500Kpa Max.
text | 61e2f77e-7e93-50d6-a825-0ae6ed676b06 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | SW pipework flood test, visual check under floor of module for any leaks, provide photos.
checkpoint-status |  |  | checkpoint | Mains Pressure water test all fixtures and fittings for correct operation and visual check for any leakage, (provide photo's as or if required)
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Second fix electrical and mechanical_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Second fix electrical and mechanical_Module Assembly | 9085e8c3-d023-4317-9182-a4fe6996bc25
checkpoint-group |  |  | section | Second fix Electrical & Mechanical
checkpoint-status |  |  | checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Installed distribution board.
text | d9bc9bb3-b1e9-5598-8b2c-7525f6689c14 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all power points and light switches.
checkpoint-status |  |  | checkpoint | Install all lights.
checkpoint-status |  |  | checkpoint | Install heat pumps.
checkpoint-status |  |  | checkpoint | Install heat towel rail.
checkpoint-status |  |  | checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint-status |  |  | checkpoint | Install oven/hob.
checkpoint-status |  |  | checkpoint | Install wall heaters.
checkpoint-status |  |  | checkpoint | Check, by contractor smoke alarm, installed - completed
checkpoint-status |  |  | checkpoint | Check, by contractor sprinkler system, installed - completed
text | 5aaba8d4-e7bd-5b48-889c-ab59bdf7e4ed |  | textbox | Operator Name:
checkpoint-group |  |  | section | Electrical Testing (Inform electrician to carry out the required electrical testing for all above installation)
checkpoint-status |  |  | checkpoint | Electrical Testing-Earth Resistance and Continuity, Insulation Resistance, Polarity and Phase, Correct Circuit connection, etc.
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint-status |  |  | checkpoint | RCD's Test
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_29.03.23_Internal/Doors & Trims/Hardware/Kitchen & Bathroom Joinery - Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_29.03.23_Internal/Doors & Trims/Hardware/Kitchen & Bathroom Joinery - Module Assembly | 9292d484-4359-452d-acbf-bde5444a9f40
checkpoint-group |  |  | section | Internal - Doors & Trims/Hardware/Kitchen & Bathroom Joinery
checkpoint-group |  |  | section | Door and trims
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications
checkpoint-status |  |  | checkpoint | Install all internal doors and trims
text | 5fe64f23-2945-5727-9d86-3a7c5c6bafea |  | textbox | Operator Name:
holdpoint |  |  | signoff | Install all internal doors and trims as per approved plans and manufacture specifications.
checkpoint-status |  |  | checkpoint | Hold point
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Hardware
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Complete all hardware as per approved plans and manufacture specifications.
text | de67112c-72b3-5bae-abcd-7555135ce4f7 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Kitchen and bathroom joinery install
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install kitchen and bathroom joinery as per approved plans and manufacture specifications.
text | 2ba317ca-f0f2-542c-9b56-1fd2da1aae95 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Module Assembly - Penetrations |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Module Assembly - Penetrations | 988f81ff-7056-435c-9690-746e03067bc8
checkpoint-group |  |  | section | Module Assembly - Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per Manufacture plan
text | d1612c79-5b8c-544d-b7e4-1dc3b28ac42b |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per Manufacture plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_29.03.23_Exterior - RAB, Insulation, penetrations, windows/doors & Opening Flashings |  |  |  |  | Yes | EGM_Ver1.1_29.03.23_Exterior - RAB, Insulation, penetrations, windows/doors & Opening Flashings | a1ae29d8-f7cb-408c-85c0-8ddca7c31801
checkpoint-group |  |  | section | Wrap (RAB)
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install balance RAB and install fixings as per manufacturer specification.
checkpoint-status |  |  | checkpoint | Install all RAB joint tapes/Sealants to RAB joints, windows, doors, penetrations, etc., as required.
text | 4092277c-7c4c-5516-9ede-90f2d6a8fadb |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install as per manufacture plan.
checkpoint-status |  |  | checkpoint | Attach Insulation Certificate.
text | eaaf29e0-5294-54a7-b658-599d640dd1e3 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Opening Flashing Tapes & Sill Support
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install opening flashing tapes to Sill, Head, Jamb, window/door etc., as required.
text | 06583829-a36b-553a-87bd-4785db0256b2 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-status |  |  | checkpoint | Install with SS screw fixing all sill supports window/door etc., as required.
text | 13895162-8890-5143-991c-85fbc8f27d1e |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint-status |  |  | checkpoint | Install all penetrations, as required.
text | 78dac05f-8eca-5354-bf4f-fa6a2436a780 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Windows and doors
checkpoint-status |  |  | checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all windows and doors as per approved plans and manufacture specifications.
text | d99f386b-57c1-5df1-bb47-f83e4459aa3d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Smoke Alarm_Sprinkler System |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - Smoke Alarm_Sprinkler System | ab0673d1-82f8-4f2a-9f89-5f646fbe4605
checkpoint-group |  |  | section | Electrical & Mechanical Smoke Alarms/Sprinkler System Inspection
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install smoke alarms as per approved electrical services plan
checkpoint-status |  |  | checkpoint | Install all smoke alarm cabling as per approved electrical services plan
text | fd481e5f-9754-53bc-acb3-a2b98f9aad23 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical Contractor before going to next step
checkpoint-status |  |  | checkpoint | Install sprinkler system as per approved Engineer design plan
text | df543afa-d999-5828-8822-c7f9f348c54d |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.1_29.03.23_Interior Fitout - Module Assembly |  |  |  |  | Yes | EGM_Ver1.1_29.03.23_Interior Fitout - Module Assembly | b853530c-0a16-4427-a688-0dd706a18df7
checkpoint-group |  |  | section | Interior Fit Out Inspection
checkpoint-group |  |  | section | Plumber to confirm first fix plumbing complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Electrician to confirm first fix electrical complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Complete internal wall lines
checkpoint-status |  |  | checkpoint | Complete all internal wall lines as per approved plans and manufacture specifications.
text | 4981a092-a95d-51c0-8f56-1f3331fa37d0 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Postline inspection photos required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Complete all passive fire requirements
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by passive fire contractor
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Mechanical ducts and ventilation
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | False ceiling and bulkheads
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all false ceiling and bulkheads as per approved plans and specifications.
text | 3b1c27d7-847c-5290-a7f1-eb5d9bec2542 |  | textbox | Operator Name:
checkpoint-group |  |  | section | Acoustic floor
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install acoustic floor as per approved plans and manufacture specifications.
checkpoint-status |  |  | checkpoint | Install all batten and cradles and sound proofing as per manufacturers specification
checkpoint-status |  |  | checkpoint | Install Fire fire sealant to perimitter
text | 1a03bb09-d298-53c7-8978-f24e4e162ddf |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Tiling and waterproofing: bathroom laundry Kitchen
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Complete all waterproofing membrane to tile areas as per approved plans and manufacture specifications.
text | 8bb50ce6-2cd0-52f9-b094-2b190c4ccc77 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Plumbing
checkpoint-status |  |  | checkpoint | Plumber to confirm second fix plumbing complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | Electrician to confirm second fix electrical complete
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint |  |  | signoff | Hold point: signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Exterior - Waterproof Membrane |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Exterior - Waterproof Membrane | c0f59730-8707-4a3d-8aa7-7502ecc7c785
checkpoint-group |  |  | section | Internal - Waterproof Membrane
checkpoint-status |  |  | checkpoint | Check and review approved plan & specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Check ply roof substrate prior to application of waterproofing membrane, as accepted
checkpoint-status |  |  | checkpoint | Install waterproofing membrane as per manufacturer specification, provide photo
text | 485bc192-ced1-58e0-ab9b-c402d54c17cc |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by waterproofing membrane applicator
checklist-sectioned |  |  | checklist | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE |  |  |  |  | Yes | EGM_Ver1.0_25.10.23_ ITEMS INCLUDED IN MODULE FOR ONSITE 5A_5B | c2048129-7e1e-465b-9e54-fce21d4b318c
checkpoint-group |  |  | section | ITEMS INCLUDED IN MODULE FOR ONSITE 5A_5B
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE X 1 @2400MM
checkpoint-status |  |  | checkpoint | GIB 16MM FYRELINE PATCH X 1 @1470 X 470MM
checkpoint-status |  |  | checkpoint | GIB 13MM FYRELINE X 5 @2400MM
checkpoint-status |  |  | checkpoint | GIB 10MM STANDARD X HALF SHEET
checkpoint-status |  |  | checkpoint | GIB WEATHERLINE X 1 SHEET
checkpoint-status |  |  | checkpoint | 12MM PLYWOOD PATCH X 1 @ 1450 X 420MM
checkpoint-status |  |  | checkpoint | STRAND-BOARD FLOORING PATCH
checkpoint-status |  |  | checkpoint | BATTEN & CRADLE
checkpoint-status |  |  | checkpoint | FIRE DOOR FRAMING 140 X 35MM
checkpoint-status |  |  | checkpoint | FIRE DOOR
checkpoint-status |  |  | checkpoint | ARCHITRAVES X 1 LENGTH
checkpoint-status |  |  | checkpoint | SKIRTING X 1 LENGTH
checkpoint-status |  |  | checkpoint | DISHWASHER X 1
checkpoint-status |  |  | checkpoint | SHOWER DOOR X 1
text | 0275e9d8-38fc-55ac-9d1d-aca8aaef406f |  | textbox | ITEMS:
text | 754fd6e6-7fda-547b-ad02-243c1c7ed2da |  | textbox | ITEMS:
text | 03526c30-580d-5222-9914-aee8aa4af038 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Photo Required and Signed off by Team leader
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Interior - Waterproof Membrane & Tiling_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Interior - Waterproof Membrane & Tiling_Module Assembly | c957c628-fff5-456e-a0ba-6becdc415bd3
checkpoint-group |  |  | section | Internal - Waterproof Membrane
checkpoint-status |  |  | checkpoint | Check and review approved plan & specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Check substrate wall and floor prior to application of waterproofing membrane, as accepted
checkpoint-status |  |  | checkpoint | Install waterproofing membrane as per manufacturer specification, provide photo
text | 80b82778-1058-5815-9acc-4a554b98c481 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by waterproofing applicator before going to next step
checkpoint-status |  |  | checkpoint | Install tiling and grout to areas as per approved plans
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_RFI_Corrective Action |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_RFI_Corrective Action | ce5067ee-8989-433f-a7ee-46b349dcbe93
checkpoint-group |  |  | section | RFI_CA Reporting
checkpoint-status |  |  | checkpoint | Refer to approved plan & specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Report Issue, description
text | f760fdb2-a29b-505d-afeb-3e9e85a681bd |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team Leader
checkpoint-status |  |  | checkpoint | Outcome & solution implemented
text | c4b3761f-c5e1-545e-97f0-8faa7b4587cd |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team Leader
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Passive Fire - Ceiling_Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Passive Fire - Ceiling_Module Assembly | d2deddeb-37c3-438d-97a3-708ab5b27ba7
checkpoint-group |  |  | section | Passive Fire - Ceiling
checkpoint-status |  |  | checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint-status |  |  | checkpoint | Install fire dampers, collars and sealants as per manufacturer specifications.
text | 4e83ff92-4be1-595a-a2ef-930e69886f18 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures, as per GIB Fire rate system GBUC 60
checkpoint-status |  |  | checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.02.23_Structure - / F / Floor Cassette Inspection |  |  |  |  | Yes | EGM_Ver1.0_22.02.23_Structure - / F / Floor Cassette Inspection | d930b8c2-1602-42a7-9521-a415299f8db7
checkpoint-group |  |  | section | Structural framing and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all floor framing elements and fixings as per Manufacture plan
text | bd5c3926-9713-5441-a5c7-82d2d98bd419 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 486563dd-f918-5a0f-82d5-77cd31fa22b9 |  | textbox | Diagonal #1:
text | 668c2d2e-d010-55dd-927d-137d68121235 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checkpoint-group |  |  | section | Floor sheeting
checkpoint-status |  |  | checkpoint | Check and review correct Manufacture plan and provide picture of the respective Manufacture plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install floor sheeting and fixing as per Manufacture plan
text | 4dadbbd3-e47c-559d-8009-8e5bc9c4f00d |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | d9c22034-602e-545a-ac64-159613bcede1 |  | textbox | Diagonal #1:
text | 2eb9ed88-40ea-5b6e-a341-10edf780fb0a |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify sheet edges in correct locations as per Manufacture plan
checkpoint-status |  |  | checkpoint | Check and verify installed fixings as per Manufacture plan
checkpoint-status |  |  | checkpoint | Hold point: Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | signoff
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_ Pre-Assembly_Pilot Holes |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_ Pre-Assembly_Pilot Holes | dbe22fbf-02e6-4017-806f-439a539703ee
checkpoint-group |  |  | section | Pre-Assembly Inspection Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved template pilot hole manufacture Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per correct template
checkpoint-status |  |  | checkpoint | Station - Pilot Holes, as per specification and tolerance
text | 5f5b444e-ce50-5094-a0bf-8f9b822c046f |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Document/Record Collection |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Document/Record Collection | e90cfab4-1c67-4730-a2f5-28988a59e2d2
checkpoint-group |  |  | section | Document / Attachment / Link / Photo
checkpoint-status |  |  | checkpoint | Records
checklist-sectioned |  |  | checklist | EGM_Ver1.1_17.04.23_ Pre-Assembly_Lining Materials |  |  |  |  | Yes | EGM_Ver1.1_17.04.23_ Pre-Assembly_Lining Materials | eb3037a5-5a55-4230-93de-672456e8a319
checkpoint-group |  |  | section | Pre-Assembly Inspection Inspection
checkpoint-status |  |  | checkpoint | Check and review as per approved Lining Plan Ply & Plasterboard GIB Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Station - Mark up correct, as per approved Manufacture Plan
checkpoint-status |  |  | checkpoint | Station - lining sheet 1 (typically Ply), as per approved Lining Manufacture Plan
checkpoint-status |  |  | checkpoint | Station - lining sheet 2 (typically Gib Plasterboard), as per approved Lining Manufacture Plan
checkpoint-status |  |  | checkpoint | Check nailing pattern - framing as per specification
text | 0f3ce701-b426-5651-ae8a-c2ff40560c1f |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - First Fix |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_ Electrical & Mechanical - First Fix | ece92df0-5fea-407b-a604-f17d4e725c89
checkpoint-group |  |  | section | Electrical & Mechanical Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per fabrication plan
text | 8732dc10-3f0a-58b7-bdf9-df2e34145ebc |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per fabrication plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_P/D - Wall Panels |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_P/D - Wall Panels | f36513de-22a0-4ae2-a7c0-c13eebc26527
checkpoint-group |  |  | section | First fix plumbing and drainage
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacture instructions.
text | 69ddbc47-399b-50c1-9c40-1df106a5f18c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint-status |  |  | checkpoint | Hold point: photo required on digital level of all pipes' runs and signed off by Plumbing team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Plumbing & Drainage - Module Assembly |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Plumbing & Drainage - Module Assembly | f6806ea1-ba88-42dc-806f-c8f195c2e486
checkpoint-group |  |  | section | Plumbing and Drainage Inspection - Module Assembly
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install pipes as per approved plumbing and drainage services Plan
checkpoint-status |  |  | checkpoint | Install connections as per approved plumbing and drainage services Plan
checkpoint-status |  |  | checkpoint | Station - Pressure test wingback as per AS/NZS 3500, provide photo
checkpoint-status |  |  | checkpoint | Station - Pressure test after plasterboard install, as per AS/NZS 3500, provide photo
text | a9b56933-1f65-581a-addb-b95a9f659b64 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | SW pipework flood test, provide photo
checkpoint-status |  |  | checkpoint | Hot and Cold Water test for 30mins at 1550KPa as per AS/NZS 3500
checkpoint-status |  |  | checkpoint | Hold point: photo required of pressure gauge and signed off by Plumbing team leader before going to next step
checkpoint-status |  |  | checkpoint | Pressure gauge will be kept until second fix
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | EGM_Ver1.0_22.03.23_Structure ITP |  |  |  |  | Yes | EGM_Ver1.0_22.03.23_Structure ITP | fe9a2f0a-c18d-465b-b100-66c047e81483
checkpoint-group |  |  | section | 1 - ITP Review and Approval Inspection
checkpoint-status |  |  | checkpoint | ITP reviewed, approved and attached
checkpoint-group |  |  | section | 2 - Preparation
checkpoint-status |  |  | checkpoint | Drawings review and approval
checkpoint-status |  |  | checkpoint | Project specification review and approval
checkpoint-status |  |  | checkpoint | Equipment calibration
checkpoint-status |  |  | checkpoint | Personnel certifications & Licenses
checkpoint-status |  |  | checkpoint | Staff training
checkpoint-status |  |  | checkpoint | Manufacture record and inspection report template
checkpoint-group |  |  | section | 3 - Material Management
checkpoint-status |  |  | checkpoint | Material list review and approval
checkpoint-status |  |  | checkpoint | Incoming material check
checkpoint-status |  |  | checkpoint | Material storage
checkpoint-status |  |  | checkpoint | Material Handling and traceability
checkpoint-group |  |  | section | 4 - Manufacture
checkpoint-status |  |  | checkpoint | 4.1 - Floor Cassette
boolean | 2a26da6e-13bb-51a5-8484-925f609c403d |  | tickbox | Structural Framing & Fixings
boolean | b731aa58-a10f-555e-9689-d0f1f4c77dc6 |  | tickbox | Floor sheeting
checkpoint-status |  |  | checkpoint | 4.2 - External Wall / Marriage Wall / Intertenancy Wall
boolean | 267b8c83-2d20-5dcf-b6ae-8e8e446b5cf6 |  | tickbox | Structural Framing & Fixings
boolean | 71c515f4-b5a3-59f9-b31c-0df090a2f2c7 |  | tickbox | Structural Sheet Bracing
boolean | 78180ae1-f7fa-5e1f-a1d1-1d9391203e14 |  | tickbox | Fire Lining 1st Layer
boolean | d10156a7-ac9e-59d1-8c90-23f4d79bc825 |  | tickbox | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | 4.3 - Internal wall
boolean | d7fa36db-43fb-585d-b8ae-a42edcf8330a |  | tickbox | Structural Framing & Fixings
boolean | df5fa7ce-78ae-5e71-b8f4-977a42ed3981 |  | tickbox | Standard/Single Layer Gib board
checkpoint-status |  |  | checkpoint | 4.4 - Ceiling cassette
boolean | fe45908c-812c-571c-9646-1c5bb52b566e |  | tickbox | Structural Framing & Fixings
boolean | 38b251f8-a947-5db6-8fb5-780cc134e6bb |  | tickbox | Structural Sheet Bracing as required
boolean | 4fde2ddd-c906-5d4e-a46c-6d0eb5426a22 |  | tickbox | Fire Lining 1st Layer
boolean | ad1dcbe8-fb1d-516b-8c98-7aa2f1087075 |  | tickbox | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | 4.5 - Module Assembly
boolean | 663dd67f-c585-530a-9326-7fb5e04cba24 |  | tickbox | Module Assembly
boolean | 3c2277ec-368f-57c2-84c4-144aceabeb72 |  | tickbox | Structural Fixing & Services as per manufacture plan
checkpoint-status |  |  | checkpoint | 4.6 - Roof Assembly
boolean | 9069f637-9323-5300-a20c-eabddec7d620 |  | tickbox | Roof Assembly
boolean | e7d0e863-4ed0-5897-a735-f4a93930d3c3 |  | tickbox | Structural framing/trusses and Fixing