## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) |  |  |  |  | Yes | ITP - R - Apartment Pre Cast Floor Structure and Concrete Pour (per level/area) | d300b0f8-6c48-4179-bc21-29136dd0e10b
checkpoint-group | Pre Commencement
checkpoint-status | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
button | Confirm construction method | Double T's, Rib & Infill, Post Tensioned, Other
text | Other details:
checkpoint-status | Propping/Falseworks Confirmed and Accepted. Evidence required.
button | Propping layout confirmed as "issued for construction" | Yes, N/A
button | Floor area cleared for propping to be erected | Yes, N/A
checkpoint-group | Floor Construction
checkpoint-status | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
checkpoint-status | Hogging of panels within design tolerances. Installed in accordance with suppliers recommendations.
checkpoint-status | Adequate identification, cast date and verification of inspection marked on precast element.
checkpoint-status | Pre-cast elements inspected upon delivery and accepted for lifting.
checkpoint-status | Floor structure elements landed as per layout
checkpoint-status | If Rib and Infill, Ryman SOP followed where applicable. (Reference the document name / version)
checkpoint-status | Reinforcing laid as per specification
checkpoint-status | Service penetrations present as per specification
checkpoint-status | Engineer inspection completed and approved for pour
button | Note remedial work needed | None, Minor, Major
holdpoint | Raise remedial as required.
checkpoint-status | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group | Post Tensioned Floor Construction
checkpoint-status | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
checkpoint-status | Stressing access correct
checkpoint-status | Tensioning strands quantity, length, and size correct.
checkpoint-status | Tendons quantity, size, and spacing correct
checkpoint-status | Tendon profiles (highs and lows and edges) correct
checkpoint-status | Antiburst are located at the correct position on the tendon
checkpoint-status | Grout Tubes height above concrete surface, quantity, and location correct
checkpoint-status | Pans and pan trimmers, anchorages, antiburst
checkpoint-status | Reinforcing laid as per specification
checkpoint-status | Service penetrations present as per specification
checkpoint-status | Engineer inspection completed and approved for pour
button | Note remedial work needed | None, Minor, Major
holdpoint | Raise remedial as required.
checkpoint-status | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group | Pre Pour Planning
checkpoint-status | Concrete pour planning completed with subcontractor
text | Date of pour
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
checkpoint-status | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group | Pour
checkpoint-status | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
checkpoint-status | Request to pour received and approved
button | Reinforcing meets specification | Yes, Reworked, N/A
button | Service penetrations present and correct | Yes, Reworked, N/A
button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | Couplers present and correct | Yes, Reworked, N/A
button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status | Engineer Inspection conducted and passed
button | Note remedial work needed | None, Minor, Major
holdpoint | Raise remedial as required.
checkpoint-status | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-group | Post Pour (Post Tensioned Floor Only)
checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint | Initial Tension applied (limits ie MPA)
checkpoint | Final Tension applied (limits ie MPA)
checkpoint | Cutting of strands and sealing of pockets completed
checkpoint | Grouting completed as per specification and tubes clear
checkpoint | Engineer Inspection conducted and passed
button | Note remedial work needed | None, Minor, Major
holdpoint | Raise remedial as required.
checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checklist-sectioned | ITP - R - Apartment Pre & Post Line (per area/grid/Location) |  |  |  |  | Yes | ITP - R - Apartment Pre & Post Line (per area/grid/Location) | bac19c72-52e0-4f5e-b215-ab6cb258bc45
checkpoint-group | Pre-Line
checkpoint-status | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
checkpoint-status | Pre-line completed
checkpoint-status | Framing system installation completed and acceptable
checkpoint-status | Nogs Installed and comply
checkpoint-status | Electrical First Fix completed and acceptable
checkpoint-status | Plumbing First Fix completed and acceptable
checkpoint-status | Insulation installation completed and acceptable
checkpoint-status | Security, Comms and Data First Fix completed and acceptable
checkpoint-status | HVAC First Fix completed and acceptable
checkpoint-status | Fire Security First Fix completed and acceptable
checkpoint-status | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable
checkpoint-status | Kitchen extract First Fix completed and acceptable
holdpoint | Passive fire installation completed and acceptable (relevant installation documents uploaded)
checkpoint-status | Suspended ceiling grids installation completed and acceptable
checkpoint-status | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | Note remedial work needed | None, Minor, Major
holdpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | Note remedial work needed | None, Minor, Major
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group | Post-Line GIB
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
checkpoint-status | GIB installation correct, screw types, pattern, etc..
checkpoint-status | Fire rated GIB installed
checkpoint-status | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status | Ceilings and Walls: Consider bracing, adhesive/sealant & lining layer(s) requirements (including fire stopping between layers)
checkpoint-status | Ceilings and Walls: Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status | Ceilings and Walls: Correct fixing pattern/sealant (including fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | Note remedial work needed | None, Minor, Major
holdpoint | Raise remedial as required.
checkpoint-group | Balustrade Testing
checkpoint-status | PASS to confirm work has started.
checkpoint-status | PASS to confirm expectations have been set for all contractors.
checkpoint-status | Balustrade Anchor Bolt Pull Testing
label | Test results to be uploaded
checkpoint-status | Balustrade Lateral Load Testing
label | Test results to be uploaded
checkpoint-status | Consultant Inspections Completed and Passed
button | Note remedial work needed | None, Minor, Major
holdpoint | Raise remedial as required.
checkpoint-status | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
text | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)