## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 74f3eb4f-9a6e-431f-b72c-b26cf2679d63 |  | checklist | V52 Firebarrier. Date: |  |  |  |  | Yes | QA - V52 Firebarrier | 174e9b78-1bd3-424b-9132-9b53a25416ac
checkpoint-status | 49f4ec61-7df7-4e81-b206-a3dc29ca2c0b |  | checkpoint | Location/Gridline details entered
text | 5b026adf-f622-5118-9c14-ca54659243e4 |  | textbox | Location/Gridline:
checkpoint-status | b2afc647-e720-4915-beb8-4dffe7d5d360 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | bf07c1ac-f23b-4e4d-ba4c-073fa3653d80 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 1f3cefa3-dc4c-4aa9-8e5b-48848c38499c |  | checkpoint | Compress and fit off rockwool strips to required compression depth for any other product allowance
checkpoint-status | 1c54bdad-d75c-4f80-8b58-01eb26c608b4 |  | checkpoint | 3mm thick Intusil applied evenly to one side only
checkpoint-status | 541ee6c5-846d-4b3d-8828-15930f8bf913 |  | checkpoint | Check full coverage is achieved
checklist-flat | edb2a550-4f01-4fda-b3ba-ed99a62d8f8f |  | checklist | Firefly wall + ceilings / All gap sizes |  |  |  |  | Yes | QA - Firefly wall + ceilings / All gap sizes | dcb04f4c-69ed-4f46-8dc9-ffab9939f0f7
checkpoint-status | 5a36e053-c96f-421f-a529-048382b81859 |  | checkpoint | Location/Gridline details entered
text | dc176d5c-8b8c-5832-89e7-579156afd444 |  | textbox | Location/Gridline:
checkpoint-status | ca5d4605-7bbe-411b-b12f-b2f4f28e124d |  | checkpoint | Location of Firefly install is watertight
checkpoint-status | 1a3b3e35-219b-4736-974f-5b1c78de3c70 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 2075ec0a-9153-41e7-8f6c-13453b117840 |  | checkpoint | Smooth substrate
checkpoint-status | 5fb48466-6e45-4093-aed4-80926d9bf2a7 |  | checkpoint | Substrate appropriately fire rated
checkpoint-status | d4b6d14c-4a91-4ad1-a895-a7c684ee6bca |  | checkpoint | No services to penetrate Firefly
checkpoint-status | d1814917-4a7e-45c9-9ccf-3b5bdebd066b |  | checkpoint | Detail correct â€“ IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 0ae720c4-f12a-42e8-bb20-b7e8979c37f8 |  | checkpoint | 100mm flap to be protruding beyond the steel pressure bar
checkpoint-status | 44f2d87b-be63-435c-80b2-fa921b5e43b5 |  | checkpoint | Screw bolt fixings installed at correct intervals
checkpoint-status | a060bd64-12fd-4f92-b65d-c7003739bc65 |  | checkpoint | Joins/intersections lapped and stapled as per manufacturers specifications
checkpoint-status | adbd114d-ad58-4196-806d-539e66ce59d6 |  | checkpoint | Final check to ensure a compliant fire cell has been created
checklist-flat | 09d4caef-3260-4eba-bd66-e3bfe4a7eeb7 |  | checklist | SF 6"+. Date: |  |  |  |  | Yes | QA - SF 6inch+ Wall Joints | a30cdfdb-9940-4fe9-b3de-57df69034c04
checkpoint-status | a2c509df-371b-4ec2-9676-c78fc1d1e604 |  | checkpoint | Location/Gridline details entered
text | a5879a62-26c2-525d-8051-af312be92bc1 |  | textbox | Location/Gridline:
checkpoint-status | e89928ef-5ef8-41c6-8b5b-7e8957ee6e95 |  | checkpoint | Materials checked
checkpoint-status | 9fbbb7dc-8a3d-42fe-a214-401ed093d168 |  | checkpoint | Smooth substrate
checkpoint-status | 7d8fff1d-aff2-49d8-946a-2205a7b0eb9a |  | checkpoint | Flashing installed (if required)
checkpoint-status | e45d490d-1344-4f4c-968f-a43f4a68db64 |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 9cdf4950-3511-4de3-b076-7221fb289de2 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 86fdb6c7-dfa6-4516-a03b-6f82d00a9da7 |  | checkpoint | EPDM (or secondary seal) installation well sealed with movement allowed
checkpoint-status | 2c91a335-b713-4d9a-b512-2c6027707bec |  | checkpoint | EPDM Boot at base formed correctly and tested for fall
checkpoint-status | 19ad088a-711a-40fe-bfd6-f2b0c0131780 |  | checkpoint | Turnbars installed correctly, right angle / centres
checkpoint-status | bacb57a6-b912-47ea-81c6-4d7fe26015e4 |  | checkpoint | Centre mullions securely installed
checkpoint-status | 98d30107-35f0-4ca3-b3d2-1233d0440cce |  | checkpoint | Primary gasket fitted correct pressed in fully
checklist-flat | 44f9a1b8-0f2f-4323-979f-89fd522700a2 |  | checklist | QA - SSRZW 400+ Floor to wall joint |  |  |  |  | Yes | QA - SSRZW 400+ Floor to wall joint | a0e40a25-0fe0-4da0-b2d5-1a81c797a26e
checkpoint-status | d324db66-d08e-4cff-91cd-e1a28af75c22 |  | checkpoint | Location/Gridline details entered
text | e5db09e3-0a1b-5090-8a3d-99bbcdd2ea98 |  | textbox | Location/Gridline:
checkpoint-status | 072d61c3-55d2-4aa2-a498-0976cada9136 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 8e60c3df-9952-40a6-8ebc-5318f101cad2 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 0f839a5a-1e37-4829-9dcb-7e4a7a55f40c |  | checkpoint | Floor Rebates correct depth / width
checkpoint-status | 86202000-c900-4e7e-93d4-188d55703471 |  | checkpoint | Solid Substraight on hinge side to fix too
checkpoint-status | 22d2b53d-72c3-4df8-9065-5778f55d210f |  | checkpoint | FFL height confirmed
checkpoint-status | d7faf3dc-ca7c-493e-a815-2e132f0260a1 |  | checkpoint | Packers / grout installed with retainers fixed securely
checkpoint-status | b26ca1d4-7609-4fa5-a341-9d7a8dd8640e |  | checkpoint | Hinge set to height and fixed off securely
checkpoint-status | 572c165a-5c9b-40c6-acf8-7b9f045cf33c |  | checkpoint | Centre plate installed and checked for correct alignment with outside retainer
checkpoint-status | 8c8e9e6d-22ce-4b91-8060-7c1a5dc03971 |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 79fcf4af-1981-49e1-af5d-41f340087f73 |  | checkpoint | Clean of installed product
checklist-flat | 82ba2639-f924-41c1-a73f-ea436565b45f |  | checklist | QA - CSX Expandiseal |  |  |  |  | Yes | QA - CSX Expandiseal | 4ec62e4e-68c8-40d2-8453-d2ed5f023976
checkpoint-no-status | 4c7e1dcd-a490-469c-8524-40103add0948 |  | checkpoint | Location/Gridline
text | 77ff907a-ab2b-5d66-b663-1972147f9cb6 |  | textbox | Location/Gridline details
checkpoint-status | 9e60e9d3-4c27-4934-9ee1-9c32c5b485ce |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | c6ef8702-7e15-4f21-a450-81ae98242cf0 |  | checkpoint | Substrate checked to be smooth and flat
checkpoint-status | 86ae73bb-5f6d-4d76-a8a7-7542b7bcb035 |  | checkpoint | check blockouts in wall are the correct width/depth
checkpoint-status | a61ef142-bf84-4e2d-8e58-01d318926864 |  | checkpoint | Correct width / depth of product supplied
checkpoint-status | 44fc5053-2f5a-4455-b38d-249637802663 |  | checkpoint | Detail correct i.e Gap size, Parallel and straight, surrounding products / substrates as per details
checkpoint-status | 43a3f171-926c-4612-827c-2a46e50caca2 |  | checkpoint | Masking / temporary cover required and setup
checkpoint-status | 3c6a1a20-cf96-4466-bbfb-a38c8f9c96b2 |  | checkpoint | Epoxy applied to substraight
checkpoint-status | c35820b8-7589-4204-b9e2-5adff17fd69b |  | checkpoint | CSX fit into place at the correct depth
checkpoint-status | c2026960-fd29-47d6-bf55-70330a067f7f |  | checkpoint | Epoxy butt joins accordingly
checkpoint-status | 7885fd79-50f8-4fad-939d-ff81e0175d86 |  | checkpoint | Continue until all lengths are completed
checkpoint-status | 56da4f8e-0169-4dc6-b875-d3def81b1781 |  | checkpoint | Final clean up, removal of masking tape / temporary covers and inspection of joint and surrounding areas
checklist-flat | fc5064ba-0d18-4d6e-8e9d-4e6f6de8630e |  | checklist | FWF-400. Date: |  |  |  |  | Yes | QA - FWF-400 | 65d66ef7-048e-4836-9594-8addef314b74
checkpoint-status | 62565dd9-2b8b-43b9-8626-b76221074394 |  | checkpoint | Location/Gridline details entered
text | 49497f22-98cf-509e-b1c0-a84ae65ef959 |  | textbox | Location/Gridline:
checkpoint-status | 5f96beb0-dfe9-40a6-94cd-d8919f385d54 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 14bfc0cd-f983-4aea-82f7-e455c8620a32 |  | checkpoint | Smooth parallel substrate
checkpoint-status | ebde2743-9393-46e5-ae5a-2c0915af513f |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | d007ff44-c7af-455f-8faf-ef2829705ce9 |  | checkpoint | Solid substrate behind plasterboard to fix into
checkpoint-status | 0b48d45b-722e-43c8-87e3-2f6cfec2f60c |  | checkpoint | Retainers fixed securely
checkpoint-status | 94a3374b-3907-4178-89be-50f96d47fd81 |  | checkpoint | Gasket installed and is flush - no lumps or un evenness
checkpoint-status | 1e7a284d-8184-4a60-bc60-2733f8d6c1ff |  | checkpoint | Clean of installed finished product
checklist-flat | 1d0e474a-03e9-467a-8791-2c3d567d9a20 |  | checklist | SRJ. Date: |  |  |  |  | Yes | QA - SRJ | 9ef4772b-5459-493e-9984-4fabd5eb098f
checkpoint-status | 33409ef5-46eb-4329-a76a-61cd986c3f2b |  | checkpoint | Location/Gridline details entered
text | d7701b27-80f7-57b6-87e3-542ab7ae0d42 |  | textbox | Location/Gridline:
checkpoint-status | 99a87ccf-dabd-42e2-8b65-a0002bf94c7c |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | fdff2a85-e703-4cfd-859a-9286a4b69057 |  | checkpoint | Smooth substrate
checkpoint-status | 154a3423-8348-4c63-a5ed-db879affa658 |  | checkpoint | Correct upstand angle
checkpoint-status | c87f3c8d-b2c9-4f34-9c8e-728cadbbc023 |  | checkpoint | Flashing or Torch On installed
checkpoint-status | 98aadee3-b4b2-48cc-94a7-c6ecfe460f7e |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | f3a19130-ff09-43e9-8026-f33b321ee596 |  | checkpoint | Fall to Vertical/Drain acceptable
checkpoint-status | b137d926-8499-49a4-8480-e472272ff4f9 |  | checkpoint | Drain placements correct (if required)
checkpoint-status | c17a9a8f-0a1e-452b-a1f8-4c6b74192cef |  | checkpoint | Correct Sealant used (Black Jack or Seal N Flex in conjunction with butyl tape)
checkpoint-status | 8c0bc053-dcff-49d0-beae-9857a5db6804 |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | 0f08d23f-47be-424e-a5fb-fb73c1470e33 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | a0d9ed0c-9c95-46c0-b05b-022e55084b8d |  | checkpoint | Fall / watertest complete and archived
checkpoint-status | 76192280-438e-47de-b4e8-a82c3b5b9258 |  | checkpoint | Roof cap installed with turn bars ready to tighten
checkpoint-status | d409f06a-7f95-42a9-9a7d-1299f0d307e4 |  | checkpoint | Turnbars installed correctly, right angle / centers
checkpoint-status | 036b79ad-3cee-42aa-8034-b1b8458cfff6 |  | checkpoint | Soakers installed with sealant underneath
checkpoint-status | 3e8db612-b509-4b49-932c-9c0537a8381f |  | checkpoint | End caps and transitions installed
checkpoint-status | 618276bc-65a7-4e76-98bc-5396e35c92f7 |  | checkpoint | Sealant applied to roof cap upstand top edge
checklist-flat | f680d599-f552-423f-b098-9fb20b97dd6d |  | checklist | QA - Insulation wall + ceiling |  |  |  |  | Yes | QA - Insulation wall + ceiling | 3c51c78d-471a-419b-98c2-d68d4d85bb0d
checkpoint-status | 3a851f23-967d-4405-8b36-326d692891fb |  | checkpoint | Location/Gridline details entered
text | 434569c2-358a-5ab6-80b8-b3e8133871e1 |  | textbox | Location/Gridline:
checkpoint-status | 45fe88e7-e84b-47f9-805c-cf7178c46fd0 |  | checkpoint | Location where insulation is to be installed is watertight
checkpoint-status | 667ec0bd-4db9-4436-a19b-9f2fc947f5ee |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 877fbb8d-19df-4a1f-9438-b3c28a07fad8 |  | checkpoint | Smooth substrate
checkpoint-status | ebf05819-f67b-4cc0-b0ba-3d2e3ca73437 |  | checkpoint | Insulation is the correct R value
checkpoint-status | a1f917d7-d4cf-4616-b814-52375696fc3d |  | checkpoint | Sufficient fixing proved
checkpoint-status | 927c5a59-f65f-4d22-bfe3-511ba5b1ea98 |  | checkpoint | Insulation firmly fixed and support straps installed if required
checklist-flat | d5288fb2-888f-4b80-8b22-d4c53a4d7510 |  | checklist | QA - XLS + XLP All sizes |  |  |  |  | Yes | QA - XLS + XLP All sizes | ac67724e-2ca7-4392-b332-0fc0095b407f
checkpoint-status | 67feed72-896e-448c-a6c4-32901b754fd7 |  | checkpoint | Location/Gridline details entered
text | 10d8507e-9f65-5837-94eb-6efb80ae8b1f |  | textbox | Location/Gridline:
checkpoint-status | 555f3c35-c249-41d6-8faa-694cdb04b678 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 9c78c922-d57e-4931-8b84-cf149b370b71 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 742c4722-f857-49cf-815e-bfdd94dbeb78 |  | checkpoint | Rebates correct depth / width
checkpoint-status | e4e4cfc6-0879-4b49-9e8e-df6df12d4b5a |  | checkpoint | E.P.D.M installed and well sealed
checkpoint-status | 8e795c5f-2bb7-477b-bc13-185c30d9247a |  | checkpoint | Boot at bottom of joint formed correctly
checkpoint-status | d53bdc1b-7567-46b8-89f7-08eab19b0d10 |  | checkpoint | Hinge and plate side of joint installed plumb and securely
checkpoint-status | bc65d61e-89fa-45c0-b459-576802de6fca |  | checkpoint | Wall retainer on opposite side installed to solid substrate securely and parallel to hinge side
checkpoint-status | 279bd5cd-02c4-4f0f-9402-f6a1f1121b01 |  | checkpoint | Cardboard removed from magnet and sash weight checked to be operating correctly
checkpoint-status | bfe15124-f8f1-4982-8efa-7c26a2f37352 |  | checkpoint | Close panel carefully to magnets and re check for parallel
checkpoint-status | 4f288329-d539-45e2-8f7e-60f7915d8f20 |  | checkpoint | Clean of installed finished product
checklist-flat | 6e6229e8-d2f2-453c-b2e7-4dd3f1ad422d |  | checklist | FCF+FWF-100/200. Date: |  |  |  |  | Yes | QA - FCF+FWF-100/200 | ef1da245-4734-45d0-a7ab-ea98337c8f30
checkpoint-status | 9c7f238c-4c35-461f-9e44-84fc401fe69f |  | checkpoint | Location/Gridline details entered
text | 40dfa8d8-e22f-57b3-b8f3-a551b2571887 |  | textbox | Location/Gridline:
checkpoint-status | 6cdb9d26-c427-4851-adef-3ab23ad89ec4 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 5ef86bb4-3311-4bcf-baa2-bf45159160e1 |  | checkpoint | Smooth parallel substrate
checkpoint-status | eca7266b-07d1-463c-b7b5-106c6c1b439c |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | 8c165c50-0e31-407d-9d76-5edb61b05975 |  | checkpoint | Solid substrate behind plasterboard to fix into
checkpoint-status | 3d18035d-cfb4-480b-be08-f3e9c647ff6a |  | checkpoint | Retainers fixed securely
checkpoint-status | ca50eb80-45e0-425e-a588-9aebf24e7d63 |  | checkpoint | Gasket installed and is flush - no lumps or un evenness
checkpoint-status | 52853f4e-ae7c-4fc7-baad-19d00d433ad5 |  | checkpoint | Clean of installed finished product
checklist-flat | e779471f-3fd7-4d8b-ad4b-b91a599b1bbb |  | checklist | GTWC 200/300. Date: |  |  |  |  | Yes | QA - GTWC 200/300 | 35840e2a-ddb1-4b23-8f89-8bc94c3a2458
checkpoint-status | f2bfd4d8-8909-49ef-ae03-63b17797fe8a |  | checkpoint | Location/Gridline details entered
text | 40795963-f817-57b9-bbc3-2d39e0ab7198 |  | textbox | Location/Gridline:
checkpoint-status | 7f0cd130-63f1-44a1-8211-53fdd1516aa4 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 8b25871c-484f-49bd-ae06-4bb607bed710 |  | checkpoint | Smooth parallel substrate
checkpoint-status | ab379279-cda6-4e3a-958d-6de5569ef545 |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | 1954310c-9eee-4f19-b6e0-30265dc90129 |  | checkpoint | Plasterboard cut back to correct Setout
checkpoint-status | d980265e-f6fb-4b59-8053-db4ea66b04a3 |  | checkpoint | Solid substrate to fix into
checkpoint-status | b5748a88-8f61-4707-bae1-5e7949076cc5 |  | checkpoint | Retainers fixed securely
checkpoint-status | d1906ac5-0d64-4907-9d96-5ac3b068264b |  | checkpoint | Centre plate fixed securely
checkpoint-status | 1ddfe1c6-af07-42dc-9ac5-ded451b3db1a |  | checkpoint | Infill plate D/S in place evenly
checkpoint-status | 1e2d568c-ce48-44c5-9878-d30412bc7730 |  | checkpoint | Gasket installed and is flush - no lumps or un evenness
checkpoint-status | 3f3ff7ba-4ee0-4cc5-a8f6-a908ed4e63fc |  | checkpoint | Clean of installed finished product
checklist-flat | ef72b0b1-d6f3-4ee0-a312-f80335627994 |  | checklist | QA - L.A.F / L.A.F.C 4"+ Wall Joints |  |  |  |  | Yes | QA - L.A.F / L.A.F.C 4"+ Wall Joints | 1b714494-cf16-4750-8dbb-e2866f6eed68
checkpoint-status | 654fdb5d-c634-4c9e-95e7-ccac7839f703 |  | checkpoint | Location/Gridline details entered
text | b91a9d11-c997-5ff0-bd49-6719722f29e2 |  | textbox | Location/Gridline:
checkpoint-status | 8a9e56ba-756e-4b94-aa6e-5b5a070c07e8 |  | checkpoint | Materials checked
checkpoint-status | f5350afb-5c7d-481e-b10f-24a5d564059b |  | checkpoint | Smooth substrate
checkpoint-status | ba1706f6-df95-4277-b989-ad8cb13aa8a7 |  | checkpoint | Rebate in gib correct width and depth
checkpoint-status | 63d9945b-c972-47ab-9091-b8aa5d748424 |  | checkpoint | Detail correct â€“ IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 2417fd28-fddd-441f-907f-f14425b85a3f |  | checkpoint | Sufficient continuous fixing has been provided
checkpoint-status | 9a7820b2-1b6e-497d-85e6-d1ced70c180f |  | checkpoint | Retainers cut to length and fixed off accordingly
checkpoint-status | 7400df54-69b7-4584-91c7-f370e6ac452a |  | checkpoint | Shock cord installed
checkpoint-status | 79978b75-7b23-48db-8229-9dece1b0e6ff |  | checkpoint | Plates cut to length and S hooks installed on the back
checkpoint-status | 83f3ddb0-1081-4e8b-b6f2-ea6a2132bd21 |  | checkpoint | Velcro pads line up on retainers and back of plates
checkpoint-status | 6749296f-6636-4137-b7f1-97fbad7f9cbd |  | checkpoint | S hooks on back of plate connected to bungee and plates pressed back firmly
checkpoint-status | 989bf94d-d600-4e7f-b1ac-5d278b9d95b2 |  | checkpoint | Clean of installed finished product
checklist-flat | 7021cd16-d1c8-41a2-80d5-994e0149e07f |  | checklist | QA - SSRZ 400+ Floor to floor joint |  |  |  |  | Yes | QA - SSRZ 400+ Floor to floor joint | f831e476-5042-49f8-aad6-e9a0908e12c7
checkpoint-status | 8b40ef59-e7e9-4a6d-a790-1678b1bfcc35 |  | checkpoint | Location/Gridline details entered
text | 98057dd8-e75a-5dec-a950-292c74cb6893 |  | textbox | Location/Gridline:
checkpoint-status | e2bdb4f3-9956-4beb-a991-32ed0b2f7c10 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | df24533d-3b62-44b5-8b5a-b3b720e846b0 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 1896d753-b14f-4a74-9c40-2ed66416c89b |  | checkpoint | Floor Rebates correct depth / width
checkpoint-status | 21a5b98a-012f-48f1-ae2b-78423370e38e |  | checkpoint | FFL height confirmed
checkpoint-status | bb6ce51c-1347-4dae-9fdc-fe7e72fcce5b |  | checkpoint | Packers / grout installed with retainers fix securely
checkpoint-status | 79753124-bf88-4680-b94f-a01b2ad45c01 |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | 10335b86-da68-4676-9830-da7bd67e49c2 |  | checkpoint | Centre plate installed and checked for correct alignment with outside retainers
checkpoint-status | 96b53a12-b0b5-4a53-8c9c-6e74b8756bb4 |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 7583f8e1-816b-4c36-a730-7a364f5351ba |  | checkpoint | Clean of installed finish product
checklist-flat | fa779ee1-e661-4b30-b6c8-65adc37821a5 |  | checklist | SSRZW. Date: |  |  |  |  | Yes | QA - SSRZW | 4c7d8195-1a74-451a-8952-b22d35fc775b
checkpoint-status | 7cac0883-af4f-44aa-8dcc-93e0ecb10b8a |  | checkpoint | Location/Gridline details entered
text | d89293f5-b83c-5c13-b0ff-338fb01c3a2e |  | textbox | Location/Gridline:
checkpoint-status | 192d979a-aced-4c88-bd44-334a543b2a65 |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 42dc31b5-543d-409f-a6e9-7f6392826869 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 90dce189-09de-40d2-9f5e-07290a56a950 |  | checkpoint | Rebates correct depth / width
checkpoint-status | c79071f2-cc4e-4887-8437-88880b9c6214 |  | checkpoint | FFL height confirmed
checkpoint-status | 1f8fde2f-7a6b-4d6b-a27e-98d6f837132d |  | checkpoint | Packer / grout installed with retainers fix securely to floor
checkpoint-status | cbb600a3-9c05-4041-a7b2-2287de0b5abb |  | checkpoint | Wall retainers installed to solid substrate securely
checkpoint-status | 5ed499bf-7f8a-4f90-b9bb-31754be26597 |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | 15be64ce-5a00-4a17-969f-0b4ea80111d6 |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 2c086104-c8f3-4b2b-abdb-68b974ed6cd7 |  | checkpoint | Clean finished product installed
checklist-flat | 94b98ed3-3b59-4eab-8e0d-0b6679d4584a |  | checklist | QA - FCF+FWF-1"/6" Internal wall + ceiling |  |  |  |  | Yes | QA - FCF+FWF-1"/6" Internal wall + ceiling | b8d0b7f3-56b7-49a6-aa9b-2508b1e18ad5
checkpoint-status | cef6f3cc-cbc4-4cbb-958a-967ef8549b2c |  | checkpoint | Location/Gridline details entered
text | dd15f636-92b2-5903-a799-0fe1e1eb0f5c |  | textbox | Location/Gridline:
checkpoint-status | 00e5539d-6afc-43b3-8112-006fcbdf463c |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | 4be6fa8c-e25d-46c7-b6fd-4665de7f0219 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 3715a0f5-5edf-4167-8027-c4ecf50c6ed2 |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | 8fd2b4b7-c1c9-4308-a71e-837acff5eb74 |  | checkpoint | Solid Substraight behind plasterboard to fix into
checkpoint-status | 43e344d3-c2b0-4e02-b01b-70578cbd9b91 |  | checkpoint | Retainers fixed securely
checkpoint-status | c78e3cf7-0e49-4cae-a036-a52d404df3b0 |  | checkpoint | Gasket installed and is flush )no lumps or un evenness
checkpoint-status | 2efff9bf-d522-4455-990e-e3f1a1af569f |  | checkpoint | Clean of installed finished product
checklist-flat | db098782-2c38-47e2-ba48-7fc7e457ce30 |  | checklist | SF 2" - 6". Date: |  |  |  |  | Yes | QA - SF 2-6inch Wall Joints | a2fe4eb5-f86e-4794-93b2-89682189351c
checkpoint-status | 171ca86a-5e73-44a4-91d7-ba66654826c4 |  | checkpoint | Location/Gridline details entered
text | 89347ec5-6a3f-52b2-b994-9808381846f5 |  | textbox | Location/Gridline:
checkpoint-status | 6cc7cb47-5c1c-4dc1-9d7e-c35628c2a60e |  | checkpoint | Materials checked
checkpoint-status | aac02d7f-cc92-41d5-8b38-63d5c26f971b |  | checkpoint | Smooth substrate
checkpoint-status | 308d8018-6837-44ed-bba1-fe2455b3a362 |  | checkpoint | Flashing installed (if required)
checkpoint-status | d1c75489-bc69-4989-80c5-6c3fda354224 |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | c8d5c890-6f66-4d2a-beac-c77897eeddd9 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 4dfe526a-6723-4c47-9d6e-a593f1099e59 |  | checkpoint | EPDM (or secondary seal) installation well sealed with movement allowed
checkpoint-status | b0fd897e-5bc0-4832-8be7-a4e6d973bdd9 |  | checkpoint | EPDM Boot at base formed correctly and tested for fall
checkpoint-status | 2e339ca6-b6f6-4f5b-a51c-46bb04645bbb |  | checkpoint | Primary gasket fitted correct pressed in fully
checklist-flat | 0b67444e-8afa-4c36-bbd1-b1524e15116c |  | checklist | QA - FCF+FWF-8" + Internal wall / ceiling |  |  |  |  | Yes | QA - FCF+FWF-8" + Internal wall / ceiling | d7135ebe-95f6-4b69-ba6b-fafa777af418
checkpoint-status | 49c3340f-106b-4fc2-a164-c284cf8e08ab |  | checkpoint | Location/Gridline details entered
text | 1e92ee9b-346d-505f-b454-2cffbf04e15e |  | textbox | Location/Gridline:
checkpoint-status | e3f8c3cb-ce42-4299-ac22-ed7d322a0ba3 |  | checkpoint | Materials Checked and correct quantity for gridline
checkpoint-status | c429c530-8d08-433b-a5c2-87757c3c5378 |  | checkpoint | Smooth parallel substrate
checkpoint-status | 821a493e-87ce-4683-ac91-55fe54cdf8a6 |  | checkpoint | Plaster / paint at correct stage for installation (IE not after painting is complete)
checkpoint-status | e2ce5df9-c412-45e8-bd9f-955119d1eea6 |  | checkpoint | Plasterboard cut back to correct Setout
checkpoint-status | 9dc6b370-6ad0-49c0-a4e6-e4918a092cbc |  | checkpoint | Solid Substraight to fix into
checkpoint-status | 1aa3c406-fa44-47bb-a5ba-05f24143cf8d |  | checkpoint | Retainers fixed securely
checkpoint-status | f53efd0a-a55d-4ec8-aee4-b630e20320e1 |  | checkpoint | Turnbars and centre mullion installed securely and at correct spacings
checkpoint-status | 56b911a4-704f-4128-a892-70a372689a76 |  | checkpoint | Gasket installed and is flush )no lumps or un evenness
checkpoint-status | 3ce98ee2-7617-481a-ba38-99086024e105 |  | checkpoint | Clean of installed finished product
checklist-flat | 9ccacc2b-c19e-45cc-a334-54ff5712aa88 |  | checklist | Acrovyn. Date: |  |  |  |  | Yes | QA - Acrovyn Wall Protection | 65214e6c-450d-4193-b2e6-7da86992ffc3
checkpoint-status | 42869fb3-ec03-44fb-a0be-3325fef48f35 |  | checkpoint | Location/Gridline details entered
text | 447aee0e-8862-5cfa-88d1-54daeaa23b78 |  | textbox | Location/Gridline:
checkpoint-status | c63f0c55-8fda-48a2-982f-cce2b3e308dd |  | checkpoint | Materials checked
checkpoint-status | 916cb04f-714a-455c-8c89-186d41cfd8c2 |  | checkpoint | Clean and straight smooth substrate
checkpoint-status | 39a887bf-22e4-450d-9bf9-f59939fdc7e1 |  | checkpoint | Floor / skirting level correct minimal variance
checkpoint-status | 5cf62ac3-941a-449f-9949-fdf1cfa1037a |  | checkpoint | Wall sheet height correct and confirmed
checkpoint-status | f59d0187-2424-4911-8711-3ec8eebc3288 |  | checkpoint | Adhesive applied
checkpoint-status | e898bd46-79f9-4dd7-a6b3-b05047577722 |  | checkpoint | Sheets rolled
checkpoint-status | aa7dcde4-7f39-4c40-bbed-8ef76430299c |  | checkpoint | Sheets cleaned
checkpoint-status | a12841a4-7dd6-45f1-ae10-fe8584ef9b90 |  | checkpoint | Silicone applied
checkpoint-status | 7819f5fd-20d1-4174-b586-dababd38920c |  | checkpoint | Final Photos
checklist-flat | bcaaf28d-9378-46e0-a1a7-8a94d5928c7f |  | checklist | SRJW. Date: |  |  |  |  | Yes | QA - SRJW | 6a34cb42-d8e6-4c55-a4ff-2f1e7c53706b
checkpoint-status | 6d15d58e-ec92-40ec-b95b-d83b2154b6c1 |  | checkpoint | Location/Gridline details entered
text | 762ece2e-9e1b-52f3-8819-f596e8e1bc1a |  | textbox | Location/Gridline:
checkpoint-status | 5d4336b1-cf3e-4b07-8174-1d0498e1a7ad |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 20e99d8f-334a-4427-9066-f1ff68724ed0 |  | checkpoint | Smooth substrate
checkpoint-status | 7529cb50-b7e4-4f52-bab6-0b9c0841c0c2 |  | checkpoint | Correct upstand angle
checkpoint-status | 7556885d-38fd-4d10-b1e3-8875098dfa3e |  | checkpoint | Flashing or Torch On installed
checkpoint-status | f4d8339b-cfdb-4a54-a8c4-117b2a53d9ad |  | checkpoint | Detail correct i.e. Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 3c23b0ac-900c-4fc2-ba03-be2281924fdf |  | checkpoint | Fall to Vertical/Drain acceptable
checkpoint-status | 40bf9b3f-5c65-49d4-a445-00073ae6e4cc |  | checkpoint | Drain placements correct (if required)
checkpoint-status | 5bf8ace9-86e7-4ea7-a918-509d6cab109b |  | checkpoint | Correct Sealant used (Black Jack or Seal N Flex in conjunction with butyl tape)
checkpoint-status | c1cb4543-e5a4-4de4-bc4e-840d20283ff2 |  | checkpoint | EPDM installation well sealed with movement allowed and terminations / transitions complete
checkpoint-status | 4245ec22-194c-453a-9706-26930d64c6e5 |  | checkpoint | Retainer fixing to substrate secure and watertight
checkpoint-status | 0af2d5ad-b629-4f7f-ab47-1e03e93ee2cd |  | checkpoint | Fall / water test complete and archived
checkpoint-status | c714fd17-5e4f-4028-80e6-a9e5e7f8475f |  | checkpoint | Roof cap installed with turn bars ready to tighten
checkpoint-status | 9f6ae710-2dea-4487-9774-3ea9c44e8ea8 |  | checkpoint | Turnbars installed correctly, right angle / centres
checkpoint-status | 11102cab-232c-44f4-93fa-2969870ad050 |  | checkpoint | Soakers installed with sealant underneath
checkpoint-status | f92c816e-4b93-4ad2-ae26-81278b824b67 |  | checkpoint | End caps and transitions installed
checkpoint-status | 32f57a65-15b5-4b0e-95ad-1f353e6ab824 |  | checkpoint | Sealant applied to roof cap upstand top edge
checklist-flat | 1e1c3182-373c-411d-86be-ee03de81eeb4 |  | checklist | QA - L.A.S / L.A.S.C 4" + Wall Joints |  |  |  |  | Yes | QA - L.A.S / L.A.S.C 4" + Wall Joints | 539190f2-ed2d-4b31-ac2a-e8f32bafba22
checkpoint-status | d9dc28dc-da04-4003-8981-962142d24f83 |  | checkpoint | Location/Gridline details entered
text | 07eb41aa-e07a-59c6-b243-5a170366d89c |  | textbox | Location/Gridline:
checkpoint-status | 374b9d3c-b180-4e9a-89f5-32a0a8b02f60 |  | checkpoint | Materials checked
checkpoint-status | ad9c04c0-7a2b-4219-80be-b6fb7a9eff47 |  | checkpoint | Smooth substrate
checkpoint-status | 448b2cc9-fbad-4a2d-ae7f-e27b33752168 |  | checkpoint | Walls finish stopped and painted
checkpoint-status | 8ac60f73-0090-4258-a266-7f31c2425255 |  | checkpoint | Detail correct â€“ IE Gap size, parallel and straight, surrounding products / substrates correct
checkpoint-status | 0cd3f570-176e-4c02-bc3e-a31245a5433f |  | checkpoint | Sufficient continuous fixing has been provided
checkpoint-status | b9919f26-d402-4aae-b5dd-00de321fb4bb |  | checkpoint | Retainers cut to length and fixed off accordingly
checkpoint-status | 988a6ee9-a019-446b-9948-4d8570555832 |  | checkpoint | Shock cord installed
checkpoint-status | 155b5881-0f92-4fa0-b2fe-37e3d6c27311 |  | checkpoint | Plates cut to length and S hooks installed on the back
checkpoint-status | 8db52900-2e43-4281-884e-45cff3c0dc63 |  | checkpoint | Velcro pads line up on retainers and back of plates
checkpoint-status | a72c76f6-061b-4671-bc54-0f3c339258db |  | checkpoint | S hooks on back of pate connected to bungee and plates pressed back firmly
checkpoint-status | 6923cd4f-daa9-46ac-bf39-035a8b19cc34 |  | checkpoint | Clean of installed finished product
checklist-flat | eb868630-c9d2-449e-8694-383adefc9b9c |  | checklist | SSRZ. Date: |  |  |  |  | Yes | QA - SSRZ | a110492f-a8b8-4200-af8d-b66ddd3e5668
checkpoint-status | 19a3310a-ec53-4fde-a44c-afc72f9160f8 |  | checkpoint | Location/Gridline details entered
text | 747d74e0-cf1c-57bf-82b2-28b91f4853a7 |  | textbox | Location/Gridline:
checkpoint-status | 5ea0c47a-a1fd-4a10-ba58-2c2627cf37af |  | checkpoint | Materials checked and correct quantity for gridline
checkpoint-status | 50c48f95-cbaa-40c3-a543-a4baaeec568e |  | checkpoint | Smooth parallel substrate
checkpoint-status | 4d9cccde-0ac4-4cbe-b9bd-0afaf198f0b2 |  | checkpoint | Rebates correct depth / width
checkpoint-status | 7a3a9429-d29e-4d31-992e-0d9efdd51b27 |  | checkpoint | FFL height confirmed
checkpoint-status | e6c055a6-b147-4b9f-acef-1b11bec584ab |  | checkpoint | Packer / grout installed with retainers fix securely
checkpoint-status | 2fa2421e-4178-4b47-b019-bd5becc642df |  | checkpoint | Turnbars installed with centre plate securely
checkpoint-status | dfbe647e-7637-43a1-9134-207a9c91532f |  | checkpoint | Sealant applied to retainer edge
checkpoint-status | 14b4b0b7-6d0d-4552-bad4-482aa93858b9 |  | checkpoint | Clean finished product installed