## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a841648e-e155-4245-ae76-575fcac4ad1f |  | checklist | QA - Base Set Out Checklist |  |  |  |  | Yes | QA - Base Set Out | 066222fa-13cb-4d4c-bc46-4871096e7aaa
checkpoint-status | 2a789262-deb8-4ee6-ab14-acb3f2173991 |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 144d20c0-ec31-4140-a31d-56a99473f698 |  | checkpoint | Set out points and Datum to be established by surveyor
checkpoint-status | b41edaf8-208b-4878-bb5e-c5f9fd1d5781 |  | checkpoint | Obtain written confirmation from surveyor
checkpoint-status | fd0bb3a2-9a83-4ee5-a8e9-7eba95fbc3ab |  | checkpoint | Send Report to client
checklist-flat |  |  | checklist | Stairs Checklist |  |  |  |  | Yes | QA - Stairs | 2c87be40-9a37-49ee-bfc2-e1df8b3220d7
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
checkpoint-status |  |  | checkpoint | Stair Units as per Plan
checkpoint-status |  |  | checkpoint | Post / Beam Connections
checkpoint-status |  |  | checkpoint | Bracing Connections
checkpoint-status |  |  | checkpoint | Stringer have enough fixing to framing with solid packer(s)
checkpoint-status |  |  | checkpoint | Verticals Plumb
checkpoint-status |  |  | checkpoint | Aligned and secured
checkpoint-status |  |  | checkpoint | 5mm gap between GIB each side of stairs
checkpoint-status |  |  | checkpoint | Top landing height to RL
checkpoint-status |  |  | checkpoint | Parallel with framing
checkpoint-status |  |  | checkpoint | Stair installation complete
checkpoint-status |  |  | checkpoint | Stair Installation report sent through to client
checklist-flat |  |  | checklist | QA - Wall Framing Checks |  |  |  |  | Yes | QA - Wall Framing Checks | 3c1fe1d9-1ca2-423f-aad8-5e4ae36be2d6
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
text | 5aab873a-136b-57b9-ad86-0d2958215095 |  | textbox | Drawing no. and revision
checkpoint-status |  |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status |  |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status |  |  | checkpoint | Fixings and hold down bolts checked and correct
checkpoint-status |  |  | checkpoint | All openings (doors / windows etc) checked, correct and approved
boolean | 8262d66c-ad6b-5aee-8246-635f0c17a4b3 |  | tickbox | Deflection heads type installed and correct
checkpoint-status |  |  | checkpoint | Wall type checked (straight and plumb) and within tolerance
checkpoint-status |  |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
boolean | d9074eda-1638-538e-b0b5-73e3f91dc891 |  | tickbox | All other nogs checked and approved
checkpoint-status |  |  | checkpoint | Moisture reading checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | All wall framing checks completed & Inspections carried out
boolean | c2128dc1-0d5a-5d0b-8f5b-d8e3d338e562 |  | tickbox | Relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Send Report to Client
checklist-flat |  |  | checklist | QA - CD Plywood |  |  |  |  | Yes | QA - CD Plywood | 5aa3e89f-72c0-4fea-ade5-dc3d9d374ed1
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Joists in correct height
checkpoint-status |  |  | checkpoint | Plywood thickness / treatment correct
checkpoint-status |  |  | checkpoint | Correct fixings being used – screws / nails
checkpoint-status |  |  | checkpoint | Fixings are installed at correct centres (perimeter – 150mm max / intermediate -300mm max)
checkpoint-status |  |  | checkpoint | Plywood pattern installed correctly
checkpoint-status |  |  | checkpoint | Send report to client
checklist-flat |  |  | checklist | QA - Blockwork |  |  |  |  | Yes | QA - Blockwork | 606da453-29f8-4b20-9ffa-a59de8d8cce8
checkpoint-status |  |  | checkpoint | All relevant drawings and revisions numbers checked and attached
checkpoint-status |  |  | checkpoint | Correct block type, colour and grade
checkpoint-status |  |  | checkpoint | Scaffold is stable and correctly installed
checkpoint-status |  |  | checkpoint | Correct steel size, tied and placed
checkpoint-status |  |  | checkpoint | Washouts clean and clear of mortar
checkpoint-status |  |  | checkpoint | Block lintels correct steel type and position
checkpoint-status |  |  | checkpoint | Mortar - quantities and correct consistency
checkpoint-status |  |  | checkpoint | Block filled correct Mpa and additives if specified
checkpoint-status |  |  | checkpoint | Delivery dockets (attached)
checkpoint-status |  |  | checkpoint | Work area left clean and tidy
checkpoint-status |  |  | checkpoint | Joints uniform and clean
checkpoint-status |  |  | checkpoint | Sent report to client
checklist-flat | fa8bbb71-7dc8-4b66-863e-a53b54e6ee43 |  | checklist | Door |  |  |  |  | Yes | QA - Doors | 8448d36b-084f-4116-81cd-bf01c6a19878
checkpoint-status | 50ae36cb-918c-44a5-bbc2-196beec1d209 |  | checkpoint | Installer details input
checkpoint-status | 24f6ba02-a751-4757-aed3-07347777ce68 |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status | 9397bc3d-3d06-4d93-8555-525e8377b9c3 |  | checkpoint | Door opening checked and correct
checkpoint-status | b10cda3e-443b-43c4-90a3-7fe08b4a3969 |  | checkpoint | Direction of door correct
checkpoint-status | 1a3615ae-175c-41f7-a2e7-3c577a391269 |  | checkpoint | Number of screws and hardware location correct
checkpoint-status | 045ad3dd-e5a0-40ac-ae72-e9c2bda6fe50 |  | checkpoint | Door hinges installed in place with correct screws
checkpoint-status | 2f40daae-fa96-48e2-a278-ccda6425a82b |  | checkpoint | Floor clearance correct
checkpoint-status | 9c9d11de-833d-41ef-a428-f220c69a19e9 |  | checkpoint | Undercoat on door surface
checkpoint-status | a0e7e54b-b4fc-4792-a919-910fcce162a1 |  | checkpoint | Fireseal around door installed as per spec
checkpoint-status | 8acefef0-653b-4624-a1c3-02480725f666 |  | checkpoint | Door is fully operational after installation
checkpoint-status | c68675b0-ecb6-407e-9975-fcf6472495de |  | checkpoint | Door jambs are plumn and level
checkpoint-status | 61102063-5bd6-4651-bf0e-9ab8bcaa9d7e |  | checkpoint | Door gap around door leaf within tolerance
checkpoint-status | 80ae7c7f-fd63-41a2-babc-5780cc5a71a8 |  | checkpoint | Door report sent through to client
checklist-flat |  |  | checklist | QA - Pre-nailed Trusses |  |  |  |  | Yes | QA - Pre-nailed Trusses | 9201586a-9acb-432b-88c0-0494652496ba
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached.
checkpoint-status |  |  | checkpoint | Timber free from visible defects.
checkpoint-status |  |  | checkpoint | Timber size / treatment correct.
checkpoint-status |  |  | checkpoint | All supporting structure fully braced, plumb and stable.
checkpoint-status |  |  | checkpoint | All top plates that support trusses are level and straight.
checkpoint-status |  |  | checkpoint | Rise and pitch of roof as per drawing specifications.
checkpoint-status |  |  | checkpoint | Positions, plumbness, spacing and orientation of main trusses checked.
checkpoint-status |  |  | checkpoint | Battens/purlins size and spacing is correct
checkpoint-status |  |  | checkpoint | All nailing/joints properly done with correct nail type.
checkpoint-status |  |  | checkpoint | Sufficient bracings installed to prevent movement.
checkpoint-status |  |  | checkpoint | Acceptable roof trusses final alignment or gradient.
checkpoint-status |  |  | checkpoint | Send report to client
checklist-flat | 966b7476-9eb7-498c-94af-009870c68568 |  | checklist | Villaboard Install |  |  |  |  | Yes | QA - Villaboard Install | 9ccac707-e870-49a5-a0fd-55e75491dcba
checkpoint-status | 6239867b-4ecc-46dc-bf86-dce511e536d3 |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | a870d562-4407-464c-8ec8-beba57cafcbd |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | ff4ea2e0-3f68-4762-b863-d96d47566d6e |  | checkpoint | All lining completed, checked and approved as per specification
checkpoint-status | 7f217a23-5c57-4f79-9c49-76a681a268d7 |  | checkpoint | Correct stopping product and applied correctly to Villaboard walls to L4 finish
checkpoint-status | d2751379-361c-421f-b53e-ae5b2c30d34c |  | checkpoint | Adequate drying time between applications & no visible bubbling
checkpoint-status | 029c00e2-8739-4487-83f4-0dc6c665125e |  | checkpoint | All sanding completed as required
checkpoint-status | 1e17f728-bfd1-4264-8611-1546701c8b74 |  | checkpoint | Soffit Framing and Villaboard completed correctly within specified tolerance, checked and approved
checkpoint-status | d03a0f5e-1093-4af2-b720-98dab792d1b9 |  | checkpoint | Villaboard report sent through to client
checklist-flat | c5545b62-adc5-4d54-a159-7304b5d62b24 |  | checklist | Ceiling Grid Checklist |  |  |  |  | Yes | QA - Ceiling Grid | a3788834-92e8-401e-b580-1282a4e501c3
checkpoint-status | 48a19672-b293-4807-85ce-0f24bf658b5f |  | checkpoint | Latest consented drawings available, checked and referenced
checkpoint-status | 97e65b14-0223-4766-8893-3b2b2ebeeb69 |  | checkpoint | Substrate correct (nogging installed if required)
checkpoint-status | 138eca96-9343-4476-b4b1-737d40036078 |  | checkpoint | Ceiling Grid installed level and to correct heights
checkpoint-status | 4880a2c5-894b-40d2-96d2-11784ea9d250 |  | checkpoint | Correct fixings and number of fixings
checkpoint-status | 46b2b392-7ae5-4544-9da6-8d14f31a024b |  | checkpoint | Member centres correct
checkpoint-status | 508a4c37-d2ab-4f10-be72-8908ebfb5076 |  | checkpoint | Correct Clips installed
checkpoint-status | 6cc5673b-948b-4367-a528-c2c3d43d8af6 |  | checkpoint | Earth strap installed
checkpoint-status | 99498bab-3296-4ccf-8e86-f97e13b62272 |  | checkpoint | Hatches openings trimmed out and installed
checkpoint-status | 0ab30eea-3f90-43e0-9a84-f5f23ff02d77 |  | checkpoint | Ceiling Grid completed correctly, checked & reviewed - as per specification
checkpoint-status | 017b79a6-5742-4975-bf5a-012a60da26b8 |  | checkpoint | Area left clean & tidy
checkpoint-status | dd4e1252-2d7c-47fb-9a3d-d5e6a5e96730 |  | checkpoint | Ceiling Grid report sent through to client
checklist-flat |  |  | checklist | QA - Timber Joist |  |  |  |  | Yes | QA - Timber Joist | d5896b91-7b11-4d89-bd08-dee0e88cc496
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Barriers in correct height
checkpoint-status |  |  | checkpoint | Timber size / treatment correct
checkpoint-status |  |  | checkpoint | Joists are installed at correct centres (400mm max)
checkpoint-status |  |  | checkpoint | Solid timber blockings are installed at correct centres (600mm max)
checkpoint-status |  |  | checkpoint | Correct fixings being used – joist hangers / nailon plates / nails / bolts / washers
checkpoint-status |  |  | checkpoint | Send report to client
checklist-flat |  |  | checklist | QA - Timber Barriers |  |  |  |  | Yes | QA - Timber Barriers | ed2ea236-b880-4b43-8039-fa2202e058be
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Piles in correct location
checkpoint-status |  |  | checkpoint | Timber size / treatment correct
checkpoint-status |  |  | checkpoint | Barriers / notches / holes (100mm max)
checkpoint-status |  |  | checkpoint | Correct fixings being used – brace straps / bolts / washers
checkpoint-status |  |  | checkpoint | Send report to client
checklist-sectioned | 23d077e4-7271-4988-bef3-4d7c277d0f8a |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pour | f83131e7-404a-4cd5-834c-92c0431d1bc7
checkpoint-group | df4cade4-644d-4cb6-9752-f71d7f156859 |  | section | Pour Details
checkpoint-status | 9b8a82b3-6f1d-4c1e-ae02-4d47b9a834a9 |  | checkpoint | Pour details entered
text | 228a87c2-c4fc-528b-b148-3367e32e6a9a |  | textbox | Area to be poured (grid lines, location):
text | 5278331b-f876-56b0-85a3-4f9d2523931f |  | textbox | Drawing numbers and revisions
text | 19ca0f3c-08f4-567f-b8cd-17309dbb4f9d |  | textbox | Date of pour
checkpoint-group | 246a43ae-7357-488f-a2e4-463daca0f66f |  | section | Formwork and embedded items
checkpoint-status | 34ed4b21-b2be-4ac1-b184-3ac4e79ba423 |  | checkpoint | Grids and RLs clearly marked for reference
checkpoint-status | 61905e2c-0473-4694-ac3c-7558a936315a |  | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
checkpoint-status | ef39c091-3f3e-4ef7-849f-41b7a5b5d180 |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status | 0a49f692-f700-4c0d-a47a-c55573db8a61 |  | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
boolean | a9d46929-2553-504b-89ee-ea45651168f6 |  | tickbox | Hold down bolts checked and correct
boolean | c4b20aca-f494-507f-96cc-5b8fc468a3a6 |  | tickbox | Precast panel starters checked and correct
checkpoint-status | fcd662d3-12a4-4337-8051-fe61a08d853d |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | efc13c0b-7170-48ab-b46f-9ff59f5dcae7 |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
checkpoint-status | 5624e7c6-9103-472f-b8fc-18ee5b10f73d |  | checkpoint | Any control joints / stop ends installed accurately and correctly braced
checkpoint-status | 83af4a1a-d94b-4c9b-a120-cd29f7977336 |  | checkpoint | DPM & Connection to other waterproofing completed
checkpoint-status | bd517ae6-a1dc-40bd-95dc-35e34f907ed0 |  | checkpoint | Any additional formwork photos and observations
checkpoint-status | 32b2f5e8-6222-4cb5-90cd-dbbc8498d23a |  | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
checkpoint-status | cacb6b94-fb04-4c99-a20b-578889895330 |  | checkpoint | Concrete ordered - correct mix and strength
text | c3b1317d-0675-5bdc-aa34-9d48fe0a420b |  | textbox | Mix
text | 90d654b6-13b4-542d-aef5-d614ff03b318 |  | textbox | Strength:
text | 1af2a3c5-1784-5877-8dce-7411582b80f8 |  | textbox | Summary of Proposed cement mix date and revision checked:
text | ba0a9a35-7c96-53b5-a723-22111870db39 |  | textbox | Structrual services specifications number and revision checked:
checkpoint-status | f8c51566-8dc7-4f6c-a029-fcf6e0c52929 |  | checkpoint | Slump test/Spread test (only applicable for special mix)
checkpoint-group | 3bb14464-1db2-4ff6-8e62-82bd7b3c9872 |  | section | Placement Method
checkpoint-status | df416dea-2706-4be6-a677-f6ac6161bf3d |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 0728475c-9ce0-509e-82b8-999e2610e96d |  | textbox | Who is placing the concrete
checkpoint-status | 3588b4ef-300f-4e91-a241-5ceaac8a2b8a |  | checkpoint | Height and falls checked / confirmed before placement
checkpoint-status | 729f57b3-0f92-4754-b3dd-afc38289e172 |  | checkpoint | Cover correct to specification
checkpoint-status | 9e29c331-0aff-4152-a158-39d82f97d5b9 |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
boolean | 5e74aef3-cfbc-5431-a8c3-4326f5b12008 |  | tickbox | All concrete dockets attached
checkpoint-status | a578d2f7-5cd7-49bd-ab9b-1c61e2813b57 |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-status | 5d9b8c07-01a8-4125-ae26-3de5809c5699 |  | checkpoint | Heights and falls checked / confirmed after placement
checkpoint-status | 88e5e337-c4c0-445e-9b65-faeeae31d236 |  | checkpoint | Any curing compound applied correctly
checkpoint-status | f350ca97-55f7-4e54-8748-8eba97a339a5 |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status | 4e41cbd5-2a55-4329-8247-aa41b525a966 |  | checkpoint | Area left clean and tidy
checkpoint-group | 3747f9de-59e4-4013-9c1c-801413e24739 |  | section | Post Pour Checks / Signoff
checkpoint-status | 0ea2d8e3-fe67-4139-9306-2f8289155a15 |  | checkpoint | Any remedial work completed
checkpoint-status | 8dda0684-8f10-4073-8d0c-f2436754203a |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
checkpoint-status | 42a0ba64-df64-4a58-b333-444359a90c29 |  | checkpoint | Report sent through to client