## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a841648e-e155-4245-ae76-575fcac4ad1f |  | checklist | QA - Base Set Out Checklist |  |  |  |  | Yes | QA - Base Set Out Checklist | 19a3af6b-571f-44ac-8817-e3ea0d58dbc4
checkpoint-status | 2a789262-deb8-4ee6-ab14-acb3f2173991 |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 144d20c0-ec31-4140-a31d-56a99473f698 |  | checkpoint | Set out points and Datum to be established by surveyor
checkpoint-status | b41edaf8-208b-4878-bb5e-c5f9fd1d5781 |  | checkpoint | Obtain written confirmation from surveyor
checkpoint-status | fd0bb3a2-9a83-4ee5-a8e9-7eba95fbc3ab |  | checkpoint | Send Report to client
checklist-flat | 2dc772e3-f8a2-40bc-ae25-1f0e32937a07 |  | checklist | GIB Lining |  |  |  |  | Yes | GIB Lining | 222b8828-45c7-44b2-997b-115a029f1531
checkpoint-status | 9fd0eeea-01a3-4f99-82dc-ab12ab5aa8d7 |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 2272a0be-2d68-4156-9a17-adc2fb45e459 |  | checkpoint | Area ready for GIB install
checkpoint-status | e5b864fc-0f23-4733-a923-ccd0ecd2b567 |  | checkpoint | Insulation installed
checkpoint-status | 7aa46461-3f38-411b-b593-0358b52de006 |  | checkpoint | General photos, comments and observations during install
checkpoint-status | adbf1d5b-dbb7-48f3-9bde-2fc35f8709bf |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status | fd676076-01b2-4643-925e-08062a26c5ef |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status | db368c12-fac9-425f-8612-60cf52b3890e |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 89d10454-7595-4845-8868-a3a439a8f3c2 |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status | 6a81160f-3a7a-4e36-883b-7441d5bfe6ea |  | checkpoint | GIB Lining report sent through to client
checklist-flat | d53f08f4-4aad-4fdc-af51-c18af63b186f |  | checklist | Villaboard |  |  |  |  | Yes | Villaboard Checklist | 4ce4fb8e-ce51-424d-b35e-511f4222f3c3
checkpoint-status | 3856fc07-569d-459e-b0a3-05911f8d2ec5 |  | checkpoint | Framing set out (ie;stud and nog spacing)
checkpoint-status | 806babef-4a65-4362-b360-1ec60f5ba852 |  | checkpoint | Gib Lining base are secured and flush with each other with no protruding fixings.
checkpoint-status | ba256ed8-7b9e-4d78-9599-9a22ad679a28 |  | checkpoint | Gap between Villaboard edges/joints are at 1-2mm maximum
checkpoint-status | de42766f-3d79-4b06-8e2e-e68599cc9b05 |  | checkpoint | 6mm gap between floor and bottom edge of sheet. 6mm gap between ceiling and top of sheet.
checkpoint-status | 2665285d-5d9d-4c26-ad15-afc739aef4c0 |  | checkpoint | Villaboard must be installed dry.
checkpoint-status | 7b1f6135-d8db-462b-9c66-1232b42fed7e |  | checkpoint | Correct fixings used and installed at correct centres.
checkpoint-status | d8f65752-16ad-4132-81f8-471ac4d399c2 |  | checkpoint | Villaboard report sent through to client.
checklist-flat | 94b5a846-932a-451f-ae50-db446232bc7a |  | checklist | QA - Speedwall |  |  |  |  | Yes | QA - Speedwall | 6760bf3b-0c64-4eae-89c0-9d38fc54c25b
checkpoint-status | 1f73fb39-3aec-4617-b752-e0b148dadafd |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | d58f555b-1c79-4457-a728-c39464e27c5f |  | checkpoint | Area ready for Speedwall install
checkpoint-status | 0205df2a-ac44-4cd8-ab69-a9085e2e8cc8 |  | checkpoint | General photos, comments and observations during install
checkpoint-status | 3140302d-8776-4419-a65f-2f9c96940875 |  | checkpoint | Bottom track correctly installed (size, location and fixings)
checkpoint-status | 606620e0-459d-4e5e-a3f6-9c8a14be1dc9 |  | checkpoint | Top track correctly installed (size, location and fixings)
checkpoint-status | 5e593327-a707-4add-b964-38cd00879d5b |  | checkpoint | 30mm minimum gap at head
checkpoint-status | b0baf590-5c89-4400-a4e3-076a9e94e2e9 |  | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
checkpoint-status | 58e1c117-e198-4c1f-a456-3f865e76dd25 |  | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
checkpoint-status | 85926975-6557-4739-95bb-1fd9fd03f524 |  | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
checkpoint-status | 045ac816-256e-4f23-9cc3-5846ed51189f |  | checkpoint | Fire sealant installed correctly and photographed
checkpoint-status | b1cecd3c-518d-4426-89cf-e9e425ce19b5 |  | checkpoint | All joints sealed correctly as per specification
checkpoint-status | 4c18cdbe-3801-4dbb-afc9-c14ee19cf3d6 |  | checkpoint | Speedwall installed straight and level
checkpoint-status | c7f83f2b-2d31-41d7-ba70-aa2042dea3e3 |  | checkpoint | Openings installed for services as per drawings
checkpoint-status | 999aed05-8633-4392-852e-b23f0ad6fba6 |  | checkpoint | Speedwall completed within specified tolerance, checked and approved
checkpoint-status | d91e6b9a-b394-45bf-8677-eab2136db213 |  | checkpoint | Speedwall report sent through to client
checklist-flat | eed73ee6-7c2b-490c-807e-a86cbc4a6c34 |  | checklist | GIB Weatherline |  |  |  |  | Yes | GIB Weatherline | 67a6ebfe-5432-4954-b00d-05cd2d7b4c15
checkpoint-status | d595fe6f-47aa-4495-8cd9-60358bad0c04 |  | checkpoint | All relevant drawings and revision numbers checked and attached / commented.
checkpoint-status | fb6af9a2-c3a2-4b04-b6b7-54b10c0782b7 |  | checkpoint | Substrate accepted and approval given to start lining.
checkpoint-status | 4e7c829a-a2b0-4422-bceb-3df340b1d59d |  | checkpoint | Correct fixings used and installed at correct centres.
checkpoint-status | 3853ca57-c18f-45e9-ae17-7d9c22a1f66a |  | checkpoint | Panels overhang the bottom plate on a concrete slab by 15mm minimum as per Gib Weatherline installation manual.
checkpoint-status | 55acccc5-9386-4d19-9619-c965f96c803b |  | checkpoint | Correct tape installed over vertical / horizontal joints, corners and openings in accordance with Gib Weatherline installation manual.
checkpoint-status | c304f8a1-56f8-4a8b-93ce-99bc0f4d4415 |  | checkpoint | General photos, comments and observations during installation.
checkpoint-status | c9a1643b-a50c-4187-a80b-b1e450582a04 |  | checkpoint | All lining completed correctly within a specified tolerance, checked and approved.
checkpoint-status | 8d2c44f1-cac6-41fe-8903-2f66c1c20a4f |  | checkpoint | Gib lining report sent to client
holdpoint | a33b7cd7-b6b8-4e27-b8a4-839ca797d6b4 |  | signoff | ( RAISE REMEDIAL / REQUEST FOR SIGNOFF)
checklist-sectioned | 0302df29-196e-4d5c-8dfd-7661398ad6d2 |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pour Checklist | 915f2944-109c-4ec5-a0ee-7dbeb2daef2a
checkpoint-group | 785c119a-8646-4755-885d-a9221d1ec567 |  | section | Pour Details
checkpoint-status | d0a5ed3a-3987-4688-8879-7a9c0b4bc7e9 |  | checkpoint | Pour details entered
text | 37f857ef-3dd0-5166-8709-f1cf9543ae38 |  | textbox | Area to be poured (grid lines, location):
text | 06b900b6-b774-5547-a11b-6b2d30f4915a |  | textbox | Drawing numbers and revisions
text | 1564f102-3cdd-5e10-8d8b-577e42aea616 |  | textbox | Date of pour
checkpoint-group | 7546f043-f70c-46fb-a27b-c493ccfcd6dd |  | section | Formwork and embedded items
checkpoint-status | 5fee0f71-081a-46ae-8d16-11a5e7ae7f3c |  | checkpoint | Grids and RLs clearly marked for reference
checkpoint-status | a0c33cba-eb3b-481a-bbc2-dc4d302601e3 |  | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
checkpoint-status | 8e8d2f55-5d81-4951-b0db-38e962abacaa |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status | 0b304067-cadc-47e1-9eda-ab046af39a8d |  | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
boolean | 10ea8be6-a80e-50b5-ab28-3eb53010671b |  | tickbox | Hold down bolts checked and correct
boolean | 69677464-67f2-5a49-bfb4-ecade3cc7e6d |  | tickbox | Precast panel starters checked and correct
checkpoint-status | a851613b-74bd-468d-95ed-bf741dcf5486 |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | dfd9ce6c-c71e-4dae-bf4e-f0d03a0b2ea9 |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
checkpoint-status | a9704117-5b09-4819-9bf7-3ac04c401f83 |  | checkpoint | Any control joints / stop ends installed accurately and correctly braced
checkpoint-status | 3ab06c6a-72ab-4d21-9b9c-a0b6135cd442 |  | checkpoint | DPM & Connection to other waterproofing completed
checkpoint-status | 104e6668-f6ad-40df-a229-ff6a95be562f |  | checkpoint | Any additional formwork photos and observations
checkpoint-status | 945e04ff-41c6-4277-bbc4-ede548c28bbc |  | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
checkpoint-status | ca4c07e5-b032-404a-9945-cee471ac65be |  | checkpoint | Concrete ordered - correct mix and strength
text | 408300b7-8e3c-56bc-b70e-161405bd12ba |  | textbox | Mix
text | 29976237-77cb-507f-a97c-9b5e1980a418 |  | textbox | Strength:
text | 970972bf-faa0-527f-93bb-063e946a5051 |  | textbox | Summary of Proposed cement mix date and revision checked:
text | fabdf027-04ec-5879-a8ad-d5b1346cdc93 |  | textbox | Structrual services specifications number and revision checked:
checkpoint-group | c8f60f6a-7e51-4f9a-bfc2-3e8f313978b9 |  | section | Placement Method
checkpoint-status | 9a167a7a-7da1-4614-9174-c6ef186e6b62 |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | c2514e5f-2935-5338-9161-4c3d71c518cd |  | textbox | Who is placing the concrete
checkpoint-status | 77610116-ce73-46fe-a988-687179221ca3 |  | checkpoint | Height and falls checked / confirmed before placement
checkpoint-status | 68911439-3859-4459-a23e-ad7beef1b0bc |  | checkpoint | Cover correct to specification
checkpoint-status | 28cb1f50-6de4-49f5-a370-0023c0e307e6 |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
boolean | 2d121f55-b47c-52ff-b0b2-d0d268d7549c |  | tickbox | All concrete dockets attached
checkpoint-status | 4e114a16-1665-4fa1-b3de-b57ec45d6688 |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-status | e5f248e8-f97d-4cfc-83e1-ea490932a7b9 |  | checkpoint | Heights and falls checked / confirmed after placement
checkpoint-status | bcedd0a4-ee5c-43d5-ad44-a986b33c6808 |  | checkpoint | Any curing compound applied correctly
checkpoint-status | 3886a49a-2243-4286-864f-a613970d711c |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status | 356e7aaa-38b3-4245-8559-985a9803fc8f |  | checkpoint | Area left clean and tidy
checkpoint-group | 802b7464-e53c-4e6f-b262-fe883bc76329 |  | section | Post Pour Checks / Signoff
checkpoint-status | 89f681ce-5d83-459d-9a05-799302e54c0b |  | checkpoint | Any remedial work completed
checkpoint-status | bead8982-14d2-485d-ae05-f6bf2380feb2 |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
checkpoint-status | 59181f95-8203-44a9-ab16-8cbc120de4ee |  | checkpoint | Report sent through to client
checklist-flat | 08df6555-c518-4d8b-92a6-d14d4ea09e50 |  | checklist | Ecoply Sheet Fixing |  |  |  |  | Yes | Ecoply Sheet Fixing Checklist | c831c686-c34d-4812-97c8-2f6a8ecdf299
checkpoint-status | b0c5e562-c2b8-469c-933a-b68b50ca70b6 |  | checkpoint | Ecoply pre cladding/RAB board to be kept dry and under cover
checkpoint-status | ee177e0a-d213-4efd-ba85-5267c7691afc |  | checkpoint | Ecoply Pre-cladding/RAB board installed in accordance with Ecoply barrier installation manual
checkpoint-status | f8a9e64c-5d2b-44d4-bb40-90932f4420e6 |  | checkpoint | Tape installed over Ecoply pre-cladding/RaB board vertical joints, corners and openings in accordance with Ecoply Barrier installation manual
checkpoint-status | b9d0fa8a-00b9-4e1e-9010-5d51c56dc8a3 |  | checkpoint | uPVC horizontal flashing used at all horizontal joints
checkpoint-status | ac88fb81-fa96-4523-8e63-1962bcb5c22e |  | checkpoint | Fixings: Type - Stainless Steel/Galv correct spacing
text | 522d4cca-9047-5c38-abca-55e4fd5cbd64 |  | textbox | size
checkpoint-status | 1b69cecc-4696-4b90-9814-c4a9454214e1 |  | checkpoint | The panels overhang the bottom plate on a concrete slab by a maximum of 40mm as per installation manual
checkpoint-status | 72701328-a0c4-4f19-94f1-b2c41f240742 |  | checkpoint | Penetrations through Ecoply pre-cladding/Rab board sealed properly using flexible flashing tape as per E2/AS1
checkpoint-status | 1901648b-1801-4add-8a89-9a0233e8efeb |  | checkpoint | Fix Watergate Plus underlay with printed side facing the exterior and run horizontally.
checkpoint-status | e0c03340-7f8b-431e-955d-8aac1c0c7e23 |  | checkpoint | Fix securely to the frame, with staples at 300 mm centres horizontally and vertically
checkpoint-status | 8452d28c-826c-4545-8481-736479879df1 |  | checkpoint | Minimum of 150mm lap is required at joins.
checkpoint-status | eabc2c5e-55fc-40a9-9b16-c3e76113d01c |  | checkpoint | All vertical laps must be made over studs.
checkpoint-status | d020fc2e-06d1-4e30-a398-e06d644dab02 |  | checkpoint | Repair small damages, if any.
checkpoint-status | e39d9b1c-f866-4c0f-975a-97a0b6c14180 |  | checkpoint | Report sent to client
checklist-flat | 90977b8f-e6f1-4c46-a1a9-eb1ba71be7ad |  | checklist | Wall Framing Checks |  |  |  |  | Yes | Wall Framing Checks Checklist | d037f5da-42c7-4a8e-8357-dc3c14f2e5b6
checkpoint-status | 3e506f75-1653-4ec4-8d3c-39cafbd488d9 |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status | bb293dd3-b2c3-40e9-b8cf-962c12845ce4 |  | checkpoint | Drawing no. and revision
checkpoint-status | 03499694-427e-42f8-9ef1-bab3c9d73149 |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status | 37a02d95-5d71-4c73-8b0d-8786c56a9299 |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status | c7feff73-e92d-4a7d-b297-4eec336ab205 |  | checkpoint | Fixings and hold down bolts checked and correct
checkpoint-status | 1638992f-b76d-45d6-8909-6d99a24ca3a8 |  | checkpoint | All openings (doors / windows etc) checked, correct and approved
checkpoint-status | 6cf26a86-cdf9-4e43-85ea-d0e57c5c0867 |  | checkpoint | Deflection heads type installed and correct
checkpoint-status | c616ea29-bd50-438a-a7b8-1b65bc90a84f |  | checkpoint | Wall type checked (straight and plumb) and within tolerance
checkpoint-status | 1e6e2077-7302-4dd6-8a5c-fb731ca2de23 |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
checkpoint-status | 7cf0047b-6049-4c01-8334-83da1c81402f |  | checkpoint | All other nogs checked and approved
checkpoint-status | 053bffdb-8422-426a-8078-79e8e5b4e1de |  | checkpoint | Moisture reading checked, recorded and acceptable
checkpoint-status | c585cb27-6adc-4a71-a44d-697149642ccc |  | checkpoint | All wall framing checks completed & Inspections carried out
checkpoint-status | df8a3779-304e-45f0-a005-8dc4a84b0b9c |  | checkpoint | Relevant inspections completed and attached
checkpoint-status | 9219c05b-441d-4dbe-950d-fe6e93dcff6c |  | checkpoint | Report sent to client
checklist-flat | 43c61897-8599-4d3d-a834-56d2677d3883 |  | checklist | Vaproshield Installation Checklist |  |  |  |  | Yes | Vaproshield Installation Checklist | e35d2d79-e9db-4880-b0a6-828a1114261e
checkpoint-status | b645b6bb-e743-49a3-9f7b-c44f43a1b580 |  | checkpoint | Wrapshield rolls stored upright
checkpoint-status | 6f4a3ad0-42d9-4195-bcc7-77884aacbc78 |  | checkpoint | RAB clean, free of contaminations and dry to touch
checkpoint-status | 6d9084b4-fd94-4002-abc9-48d5b8f33fb2 |  | checkpoint | Lower courses lapped under the upper courses with a minimum 80mm lap joints
checkpoint-status | 32c5a4eb-b4f5-4b95-a49c-6113f720dfd9 |  | checkpoint | 150mm lap joint at internal and external corners
checkpoint-status | 03e43949-6200-4869-a0bd-7174367f15f0 |  | checkpoint | All service penetrations covered with liquid flashing
checkpoint-status | 8bc4d5c1-c2c1-4bed-add6-019e28570abb |  | checkpoint | 25 mm liquid flashing to all steel and concrete connections
checkpoint-status | 48514255-b5b7-49ca-847b-515b29c882ef |  | checkpoint | All penetrations and damage to Vaproshield repaired