## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-Track & Civil-Track Removal & Construction
ITP Description: |  | Track Removal & Construction
Document Number (in Teambinder): |  | N/A
Discipline (e.g. CIV/STR/RAIL: |  | Track & Civil
Revision Number: |  | 2
Revision Date: |  | 2022-11-14
ITP created by: |  | Jake Argentaro
ITP approved for use by: |  | Jihad Chahda
Special Notes to ConQA Team : |  | ITP for Robinsons Road Track Removal & Construction
Inspection & Test Plan - Track Removal & Construction
|  |  | Document No.: | N/A |  |  |  |  | Revision: | 2
[9 empty] | Date: | 2022-11-14
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.01 | Non Dependent | Robinsons Road Track & Civil IFC Drawing Set MRP-DPK-072-00-CPW-0060 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.02 | Non Dependent | NIST-2654 Ballast | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.03 | Non Dependent | NIST-2651 Sleepers and Fastenings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.04 | Non Dependent | NIST-2650 Rail | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.05 | Non Dependent | NIST-2630 Track Construction | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.06 | Non Dependent | NIST-2706 Track Geometry | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.07 | Non Dependent | NIST-2659 Earthworks and Drainage | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.08 | Non Dependent | NIST-2618 Track Design | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.09 | Non Dependent | NIFO-2650.5 Aluminothermic Weld Record | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.1 | Non Dependent | NIFO-2690.3 Certificate of Track for Operation | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.11 | Non Dependent | NIST-2703 Inspection and Assessment: Rail and Rail Joints (External) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.12 | Non Dependent | NIST-2704 Inspection and Assessment: Rail (Internal) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries
2.01 | Obtain and submit Material Certificate of Compliance for Track Materials; -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits -Wleding Crucibles | IFC Drawing(s) Track Constrction Site Mudmap Bill of Materials | Units to be free from damage, total and types of units for full set validated No signs of discoloration. Attach: Manufactuer Cetificates of Compliance. Welding materials shall comply with specification NIST‐2650 Rev3 Section 9 and AS1085.20 "Railway Track Material: Welding of Steel Rail. | Review Document | Once | HP | Site/Project Engineer | ConQA Hold Point Release
2.02 | Submit Welding Procedure/welding qualification welders Record | NIST-2650 Rail AS 1085.20 Welding Rail Steels | Qualified personnel & welding accordance with manufacturers specs. | Review Document | Once | HP | Site/Project Engineer | ConQA Hold Point Release
2.03 | Inspect supplied items upon delivery | Bill of Materials | No damage or debris on components Validate total number and type of components matches drawing Attach: Photos on site; -Track Rail -Track Sleepers -Track Jewellery -Geofabric -Ballast Matting -Ballast 60mm Aggregate -Welding Kits -Welding Crucibles | Visual Measure | Per delivery | IP | Site/Project Engineer | Material Inspection Report
2.04 | Confirm extent of track removal required for civil works | IFC Drawing(s) Track Constrction Site Mudmap | Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site Pre-removal survey of existing track alignment | Visual Measure | Once | IP | Site/Project Engineer | This ITP
3 | Construction / Installation Activities
3.01 | Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction | IFC Drawing(s) Track Constrction Site Mudmap | Track structure to be removed to the designated limits as identified. Visual confirmation of removal on site | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.02 | Earthworks completed and site handed over from Civil Contractor | NIST-2659 Earthworks and Drainage | Confirmation of completion of underlying ITP(s) Underlying ITP reference:________________ | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.03 | Installation of Ballast Shock Matt | IFC Drawing(s) NIST-2654 Ballast | Ensure all area of bridge deck is covered with ballast shock matt and matt fastened together with approved tape Attach Site Photo: -Installed Ballast Matt | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.04 | Installlation of Bottom Ballast | NIST-2654 Ballast | Overal Minimum 300mm bottom ballast depth Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate Bottom Ballast to be left 20mm below final design level Tolerance: Under sleeper -0mm/+25mm. Attach Site Photo: -Installed Bottom Ballast Layer | Visual Measure | Once | IP | Track Surveyor Track Supervisor Site/Project Engineer | This ITP
3.05 | Laying of Sleepers | NIST-2651 Sleepers and Fastenings | Sleepers square at nominal 685mm +/-25mm for open track Sleepers square at nominal 600mm +/-25mm through level crossing Attach Site Photo: -Laid Sleepers -Sleeper Spacing Measurement | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.06 | Rail & Fastening Installation | NIST-2650 Rail NIST-2651 Sleepers and Fastenings | All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed Serviceable used rail shall be tested in accordance to NIST-2650 Rev 3 Section 6.3 and NIST-2704: - Running rails in main lines shall be ultrasonically tested for internal defects, using rail flaw detection apparatus Attached to rail bound or hi-rail plant in accordance to NIST-2650 Section 6.1.1; - Manual ultrasonic testing shall be carried out within 30 days of completion of all new alumina-thermic and flash-butt welds on passenger lines in accordance to NIST-2650 Section 6.1.2 and AS1085.20 Appendix F4. New Rail lengths installed to be as per approved Robinsons Road Rail Weld Plan Rails to be painted with Mirrortoned paint within areas of temporary roadway Gauge of track to be checked upon installation of fastenings Gauge +4mm/-3mm Gauge Variation over 2m 4mm Attach Site Photo: -Laid rail -Rail joint to exisiting weld measurement -Rail joint between sleeper bay measurements | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.07 | Track Tamping | NIST-2630 Track Construction NIST-2706 Track Geometry | Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm); Line (10m Chord) +/-5mm Twist (3.5m Chord) +/-5mm Twist 10m (Chord) +/-10mm Cant +/-5mm Top (10m Chord) +/-5mm Alignment +/-20mm Survey measurment of RL of top of rail head A minimum horizontal clearance of 3.0m from track centreline to structure. Attach; -Tamping Geometry Recording -Survey RL measuring sheet Attach Site Photos: -Tamping Activity -Structual Offset Measurement | Visual Measure | Once | HP | Track Surveyor Track Supervisor Site/Project Engineer | This ITP
3.08 | Regualting and Ballast Profile | NIST-2630 Track Construction NIST-2706 Track Geometry NIST-2654 Rev 2 Section 7 | Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter, to minimum depth of 300mm below underside of sleeper nominally. No Ballast to be on top surface of sleepers or aorund rail Fastenings Attach Site Photos: -Ballast Shoulder Measurement -Rubber Panels free of ballast materials | Visual Measure | Once | IP | Track Supervisor Site/Project Engineer | This ITP
3.09 | Aluminothermic Welding | NIST-2650 Rail NIFO-2650.5 Aluminothermic Weld Record NIST-2650 Rail Use, Laying and Adjustment | Welds to be lined and finished to alignment standard Tolerance: Gauge Face +1.0/-0.5mm Running Face +0.6/-0.0mm Welds shall be: - A minimum of 65mm between rail end to be welded and edge of first bolt hole. - Welds must be located at least: ‐3m from a bridge abutment, ‐3m from a level crossing, clear (at least 5 sleepers) of change in track stiffness , ‐3m from any other weld, ‐3m from a rail end at a joint, ‐+/‐ 50mm from centre of bay between sleepers. - The weld identification number (Record Sheet No.) must be legibly marked with white paint on the rail web, near the weld. Free welds must be painted black on the web prior to applying the weld identification number; welder identification (initials), weld number, year shall be clearly marked. Verify Aluminothermic welding carried out in accordance with AS1085.20 Aluminothermic Weld Return Form to be completed Attach: - Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6). Attach Site Photos: -Welding Aligning -Welding Process | Visual Measure | Each Weld | IP | Track Welder Track Supervisor Site/Project Engineer | This ITP NIFO-2650.5 Aluminothermic Weld Record
3.1 | Track Stressing | NIST-2650 Rail NIFO-2650.5 Aluminothermic Weld Record NIST-2650 Rail Use, Laying and Adjustment | Stressing Rail in line with V/Line Rail Welding Process Ensure Stressing only performed between rail temperatures; >10 and <38 degrees Complete track stressing in 330m module or otherwise as noted on approved track stressing plan Reference Marks recorded pre and post tensing of rail, creep monument recordings to be undertaken prior-to and following rail cutting in accordance to NIST‐2708 Rev2 Section 6 and Appendix A. Aluminothermic Weld Return Form to be completed Attach: - Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6). Attach Site Photos: -Stressing Activity -Before/After Reference Mark Measurments | Visual Measure | Each Restress module | IP | Track Welder Track Supervisor Site/Project Engineer | This ITP NIFO-2650.5 Aluminothermic Weld Record
3.11 | Weld Ultrasonic Testing | NIST-2650 Rail NIFO-2650.5 Aluminothermic Weld Record NIST-2703 Inspection and Assessment Rail and Rail Joints (External) NIST-2704 Inspection and Assessment Rail (Internal) | Ultrasonic testing to be carried out in accordance with NIST-2650 Rail - Testing Procedure: Olympus Epoch 650 Ultrasonic Flaw Detector or approved equivalent. The cross section of the area of the head and web shall be completely scanned; • The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2. • Welds shall be scanned to both directions. No classified internal defects found Final weld geometry to be assessed Tolerance: Gauge Face +1.0/-0.5mm Running Face +0.6/-0.0mm Aluminothermic Weld Return Form to be completed Attach -Aluminothermic Weld Return Form - Aluminothermic Weld Test Report Attach Site Photos: -Welding Aligning -Welding Process | Visual Measure Test | Each Weld | HP | Weld Tester Track Supervisor Site/Project Engineer | This ITP Ultrasonic Inspection Report
3.12 | Installation of Epiflex | IFC Drawing(s) NIST-2650 Rail | Install Epiflex rubber stripping along length of rail to be located within temporary roadway Insure all fastening clips are properly secured with applicator and geofabric is laid over sleepers/ballast in areas to be asphalted Attach Site Photo: -Epiflex -Geofabric | Visual Measure Test | Once | HP | Track Supervisor Site/Project Engineer | This ITP
3.13 | Installation of Guard Rail & Guard Rail Nose | IFC Drawing(s) NIST-2650 Rail | Install guard rail and guard rail nose as per IFC design Guardrail to be installed with alternating fastening pattern Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion Attach Site Photo: -Guard rail isntalled -Guard rail nose installed | Visual Measure Test | Once | HP | Track Supervisor Site/Project Engineer | This ITP
4 | Post-construction / Post-installation Activities
4.01 | As-built Survey | IFC Drawing(s) | Survey activities undertaken to validate correct construction Attach: -Survey Report -Engineering Asset From | Survey Document Review | Once | IP | Track Surveyor Site/Project Engineer | This ITP
4.02 | Track Certification | NIFO-2690.3 Certificate of Track for Operation | Attach : -Track Geometry Conformance Certificate -Track System and Component Attach Site Photos: -Before/After Photo of worksite | Visual Measure Doument Reivew | Once when all occupation works complete | HP | Track Certifier Site/Project Engineer | ConQA Hold Point Release
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /