## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-Track & Civil-Track Removal & Construction | itp |  |  |  |  | ITP-Track & Civil-Track Removal & Construction Rev 2
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-Track & Civil-Track Removal & Construction
note | ITP Description: Track Removal & Construction
note | Document Number (in Teambinder): N/A
note | Discipline (e.g. CIV/STR/RAIL): Track & Civil
note | Revision Number: 2
note | Revision Date: 14/11/2022
note | ITP created by: Jake Argentaro
note | ITP approved for use by: Jihad Chahda
note | 1.01 Non Dependent
note | Reference: Robinsons Road Track & Civil IFC Drawing Set MRP-DPK-072-00-CPW-0060
note | 1.02 Non Dependent
note | Reference: NIST-2654 Ballast
note | 1.03 Non Dependent
note | Reference: NIST-2651 Sleepers and Fastenings
note | 1.04 Non Dependent
note | Reference: NIST-2650 Rail
note | 1.05 Non Dependent
note | Reference: NIST-2630 Track Construction
note | 1.06 Non Dependent
note | Reference: NIST-2706 Track Geometry
note | 1.07 Non Dependent
note | Reference: NIST-2659 Earthworks and Drainage
note | 1.08 Non Dependent
note | Reference: NIST-2618 Track Design
note | 1.09 Non Dependent
note | Reference: NIFO-2650.5 Aluminothermic Weld Record
note | 1.10 Non Dependent
note | Reference: NIFO-2690.3 Certificate of Track for Operation
note | 1.11 Non Dependent
note | Reference: NIST-2703 Inspection and Assessment: Rail and Rail Joints (External)
note | 1.12 Non Dependent
note | Reference: NIST-2704 Inspection and Assessment: Rail (Internal)
section | Preliminaries
checkpoint | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials: Track Rail, Track Sleepers, Track Jewellery, Geofabric, Ballast Matting, Ballast 60mm Aggregate, Welding Kits, Welding Crucibles
note | REFERENCE: IFC Drawing(s)
note | Track Constrction Site Mudmap
note | Bill of Materials
note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration.
note | Attach: Manufactuer Cetificates of Compliance.
note | Welding materials shall comply with specification NIST‐2650 Rev3 Section 9 and AS1085.20 "Railway Track Material: Welding of Steel Rail.
note | METHOD: Review Document
note | FREQUENCY: Once
note | CATEGORY: HP
note | RESPONSIBILITY: Site/Project Engineer
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.02 Submit Welding Procedure/welding qualification welders Record
note | REFERENCE: NIST-2650 Rail AS 1085.20 Welding Rail Steels
note | ACCEPTANCE CRITERIA: Qualified personnel & welding accordance with manufacturers specs.
note | METHOD: Review Document
note | FREQUENCY: Once
note | CATEGORY: HP
note | RESPONSIBILITY: Site/Project Engineer
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.03 Inspect supplied items upon delivery
note | REFERENCE: Bill of Materials
note | ACCEPTANCE CRITERIA: No damage or debris on components
note | Validate total number and type of components matches drawing
note | Attach: Photos on site;
note | – Track Rail
note | – Track Sleepers
note | – Track Jewellery
note | – Geofabric
note | – Ballast Matting
note | – Ballast 60mm Aggregate
note | – Welding Kits
note | – Welding Crucibles
note | METHOD: Visual, Measure
note | FREQUENCY: Per delivery
note | CATEGORY: IP
note | RESPONSIBILITY: Site/Project Engineer
note | VERIFYING DOCUMENTS: Material Inspection Report
textbox | Date Completed:
checkpoint | 2.04 Confirm extent of track removal required for civil works
note | REFERENCE: IFC Drawing(s)
note | Track Constrction Site Mudmap
note | ACCEPTANCE CRITERIA: Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
note | Pre-removal survey of existing track alignment
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction / Installation Activities
checkpoint | 3.01 Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
note | REFERENCE: IFC Drawing(s)
note | Track Constrction Site Mudmap
note | ACCEPTANCE CRITERIA: Track structure to be removed to the designated limits as identified.
note | Visual confirmation of removal on site
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.02 Earthworks completed and site handed over from Civil Contractor
note | REFERENCE: NIST-2659 Earthworks and Drainage
note | ACCEPTANCE CRITERIA: Confirmation of completion of underlying ITP(s)
textbox | Underlying ITP reference:
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.03 Installation of Ballast Shock Matt
note | REFERENCE: IFC Drawing(s)
note | NIST-2654 Ballast
note | ACCEPTANCE CRITERIA: Ensure all area of bridge deck is covered with ballast shock matt and matt fastened together with approved tape
note | Attach Site Photo:
note | – Installed Ballast Matt
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.04 Installlation of Bottom Ballast
note | REFERENCE: NIST-2654 Ballast
note | ACCEPTANCE CRITERIA: Overal Minimum 300mm bottom ballast depth
note | Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
note | Bottom Ballast to be left 20mm below final design level
note | Tolerance:
note | Under sleeper -0mm/+25mm.
note | Attach Site Photo:
note | – Installed Bottom Ballast Layer
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.05 Laying of Sleepers
note | REFERENCE: NIST-2651 Sleepers and Fastenings
note | ACCEPTANCE CRITERIA: Sleepers square at nominal 685mm +/-25mm for open track
note | Sleepers square at nominal 600mm +/-25mm through level crossing
note | Attach Site Photo:
note | – Laid Sleepers
note | – Sleeper Spacing Measurement
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.06 Rail & Fastening Installation
note | REFERENCE: NIST-2650 Rail
note | NIST-2651 Sleepers and Fastenings
note | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
note | Serviceable used rail shall be tested in accordance to NIST-2650 Rev 3 Section 6.3 and NIST-2704:
note | – Running rails in main lines shall be ultrasonically tested for internal defects, using rail flaw detection apparatus Attached to rail bound or hi-rail plant in accordance to NIST-2650 Section 6.1.1;
note | – Manual ultrasonic testing shall be carried out within 30 days of completion of all new alumina-thermic and flash-butt welds on passenger lines in accordance to NIST-2650 Section 6.1.2 and AS1085.20 Appendix F4.
note | New Rail lengths installed to be as per approved Robinsons Road Rail Weld Plan
note | Rails to be painted with Mirrortoned paint within areas of temporary roadway
note | Gauge of track to be checked upon installation of fastenings
note | Gauge +4mm/-3mm
note | Gauge Variation over 2m 4mm
note | Attach Site Photo:
note | – Laid rail
note | – Rail joint to exisiting weld measurement
note | – Rail joint between sleeper bay measurements
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.07 Track Tamping
note | REFERENCE: NIST-2630 Track Construction
note | NIST-2706 Track Geometry
note | ACCEPTANCE CRITERIA: Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm);
note | Line (10m Chord) +/-5mm
note | Twist (3.5m Chord) +/-5mm
note | Twist 10m (Chord) +/-10mm
note | Cant +/-5mm
note | Top (10m Chord) +/-5mm
note | Alignment +/-20mm
note | Survey measurment of RL of top of rail head
note | A minimum horizontal clearance of 3.0m from track centreline to structure.
note | Attach;
note | – Tamping Geometry Recording
note | – Survey RL measuring sheet
note | Attach Site Photos:
note | – Tamping Activity
note | – Structual Offset Measurement
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: HP
note | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.08 Regualting and Ballast Profile
note | REFERENCE: NIST-2630 Track Construction
note | NIST-2706 Track Geometry
note | NIST-2654 Rev 2 Section 7
note | ACCEPTANCE CRITERIA: Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter, to minimum depth of 300mm below underside of sleeper nominally.
note | No Ballast to be on top surface of sleepers or aorund rail Fastenings
note | Attach Site Photos:
note | – Ballast Shoulder Measurement
note | – Rubber Panels free of ballast materials
note | METHOD: Visual, Measure
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 3.09 Aluminothermic Welding
note | REFERENCE: NIST-2650 Rail
note | NIFO-2650.5 Aluminothermic Weld Record
note | NIST-2650 Rail Use, Laying and Adjustment
note | ACCEPTANCE CRITERIA: Welds to be lined and finished to alignment standard
note | Tolerance:
note | Gauge Face +1.0/-0.5mm
note | Running Face +0.6/-0.0mm
note | Welds shall be:
note | – A minimum of 65mm between rail end to be welded and edge of first bolt hole.
note | – Welds must be located at least: ‐3m from a bridge abutment, ‐3m from a level crossing, clear (at least 5 sleepers) of change in track stiffness , ‐3m from any other weld, ‐3m from a rail end at a joint, ‐+/‐ 50mm from centre of bay between sleepers.
note | – The weld identification number (Record Sheet No.) must be legibly marked with white paint on the rail web, near the weld. Free welds must be painted black on the web prior to applying the weld identification number; welder identification (initials), weld number, year shall be clearly marked.
note | Verify Aluminothermic welding carried out in accordance with AS1085.20
note | Aluminothermic Weld Return Form to be completed
note | Attach:
note | – Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6).
note | Attach Site Photos:
note | – Welding Aligning
note | – Welding Process
note | METHOD: Visual, Measure
note | FREQUENCY: Each Weld
note | CATEGORY: IP
note | RESPONSIBILITY: Track Welder, Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP, NIFO-2650.5 Aluminothermic Weld Record
textbox | Date Completed:
checkpoint | 3.10 Track Stressing
note | REFERENCE: NIST-2650 Rail
note | NIFO-2650.5 Aluminothermic Weld Record
note | NIST-2650 Rail Use, Laying and Adjustment
note | ACCEPTANCE CRITERIA: Stressing Rail in line with V/Line Rail Welding Process
note | Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
note | Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
note | Reference Marks recorded pre and post tensing of rail, creep monument recordings to be undertaken prior-to and following rail cutting in accordance to NIST‐2708 Rev2 Section 6 and Appendix A.
note | Aluminothermic Weld Return Form to be completed
note | Attach:
note | – Aluminothermic Weld Record Sheet (NIFO-2650.5) or Flash-butt Weld Record Sheet (NIFO-2650.6).
note | Attach Site Photos:
note | – Stressing Activity
note | – Before/After Reference Mark Measurments
note | METHOD: Visual, Measure
note | FREQUENCY: Each Restress module
note | CATEGORY: IP
note | RESPONSIBILITY: Track Welder, Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP, NIFO-2650.5 Aluminothermic Weld Record
textbox | Date Completed:
checkpoint | 3.11 Weld Ultrasonic Testing
note | REFERENCE: NIST-2650 Rail
note | NIFO-2650.5 Aluminothermic Weld Record
note | NIST-2703 Inspection and Assessment Rail and Rail Joints (External)
note | NIST-2704 Inspection and Assessment Rail (Internal)
note | ACCEPTANCE CRITERIA: Ultrasonic testing to be carried out in accordance with NIST-2650 Rail
note | – Testing Procedure: Olympus Epoch 650 Ultrasonic Flaw Detector or approved equivalent.
note | The cross section of the area of the head and web shall be completely scanned;
note | • The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
note | • Welds shall be scanned to both directions.
note | No classified internal defects found
note | Final weld geometry to be assessed
note | Tolerance:
note | Gauge Face +1.0/-0.5mm
note | Running Face +0.6/-0.0mm
note | Aluminothermic Weld Return Form to be completed
note | Attach
note | – Aluminothermic Weld Return Form
note | – Aluminothermic Weld Test Report
note | Attach Site Photos:
note | – Welding Aligning
note | – Welding Process
note | METHOD: Visual, Measure, Test
note | FREQUENCY: Each Weld
note | CATEGORY: HP
note | RESPONSIBILITY: Weld Tester, Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP, Ultrasonic Inspection Report
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.12 Installation of Epiflex
note | REFERENCE: IFC Drawing(s)
note | NIST-2650 Rail
note | ACCEPTANCE CRITERIA: Install Epiflex rubber stripping along length of rail to be located within temporary roadway
note | Insure all fastening clips are properly secured with applicator and geofabric is laid over sleepers/ballast in areas to be asphalted
note | Attach Site Photo:
note | – Epiflex
note | – Geofabric
note | METHOD: Visual, Measure, Test
note | FREQUENCY: Once
note | CATEGORY: HP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.13 Installation of Guard Rail & Guard Rail Nose
note | REFERENCE: IFC Drawing(s)
note | NIST-2650 Rail
note | ACCEPTANCE CRITERIA: Install guard rail and guard rail nose as per IFC design
note | Guardrail to be installed with alternating fastening pattern
note | Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
note | Attach Site Photo:
note | – Guard rail installed
note | – Guard rail nose installed
note | METHOD: Visual, Measure, Test
note | FREQUENCY: Once
note | CATEGORY: HP
note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
section | Post-construction / Post-installation Activities
checkpoint | 4.01 As-built Survey
note | REFERENCE: IFC Drawing(s)
note | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
note | Attach: Survey Report, Engineering Asset From
note | METHOD: Survey, Document Review
note | FREQUENCY: Once
note | CATEGORY: IP
note | RESPONSIBILITY: Track Surveyor, Site/Project Engineer
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.02 Track Certification
note | REFERENCE: NIFO-2690.3 Certificate of Track for Operation
note | ACCEPTANCE CRITERIA: Attach :
note | – Track Geometry Conformance Certificate
note | – Track System and Component
note | Attach Site Photos:
note | – Before/After Photo of worksite
note | METHOD: Visual, Measure, Doument Reivew
note | FREQUENCY: Once when all occupation works complete
note | CATEGORY: HP
note | RESPONSIBILITY: Track Certifier, Site/Project Engineer
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP