## ITP-01
INSPECTION AND TEST PLAN
Inspection & Test Plan Description:
Downer
ITP for Shop fabrication - Homai pedestrian bridge- Span 6
Downer- Homai pedestrian bridge |  |  |  |  | Location: | Hamilton | [7 empty] | ITP Doc No: | ITP-001-39028- Span 6
Customer: |  | Downer |  |  | Customer Job Reference: | 746-24-847-AC | [7 empty] | Revision: | D
Prepared by: |  | Regan Hose |  |  | PFS Job Reference | 39028
Date: |  | 2024-11-01 |  |  | Review by: | Bashir Heidarian
[5 empty] | Date: | 2024-11-01
| Construction Category |  | CC3 | Service Category | SC2 |  | Fabrication Category | FC1 |  |  | Weld Category | SP |  | Tolerance | Class 2
Seq | Task/ QA Activity |  | Specification Standard | Acceptance Criteria |  | Certify Doc / Ref |  | PFS Engineering | Sign | C | Subcontracted scope | Sign | C | Downer | sign | C | Remark
Engineering
1 | Inspection and Test Plan Reviewed and Approved by Customer |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. |  | IFC DWGs |  | PM/PE | Initial: Sign: | S |  |  |  | Downer | Initial: Sign: | H
2 | Shop Drawing approval |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form |  | Shop Drawing Check form |  | PM/PE | Initial: Sign: | S |  |  |  | Downer | Initial: Sign: | H
3 | Submit Inspection personel competencies |  | Project Structure Specification C07 Rev. 01 | Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4 |  | NDT qualification |  | PM/PE | Initial: Sign: | S |  |  |  | Downer | Initial: Sign: | H
4 | Welding Procedures - Structural |  | AS/NZS 1554.1:2014 Category SP | Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified. |  | Welding Procedures HERA/CSWIP Stamp |  | PM/PE | Initial: Sign: | S | SQA | Initial: Sign: | RA
5 | Welder Qualifications - Structural |  | AS/NZS 1554.1:2014, ISO 9606-1:2017 | A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out. No welder shall carry out work for which he is not certified. |  | WQT by Authorised Person (Welding Supervisor) |  | PM/PE | Initial: Sign: | S | SQA | Initial: Sign: | RA
6 | Submit the required documents to Client for review |  | Project Structure Specification C07 Rev. 01 | Following shall be submitted to the Engineer for review before fabrication is commenced: 1-Quality Management Plan 2- IMS Manual 3- SFC Certificate 4-ISO 9001 Certificate |  | Quality certificates Quality Plan |  | PM/PE | Initial: Sign: | S |  |  |  | Downer | Initial: Sign: | R
Procurement
7 | Procurement of materials in line with IFC drawings and Technical Specification |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | Materials match that specified in Project IFC drawings and Technical Specification. Structural steel Material shall be sourced from suppliers certified by ACRS Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories) |  | Supplier Material Certificate |  | PM/PE | Initial: Sign: | RA/S |  |  |  | Downer | Initial: Sign: | H
8 | Procurement of Welding consumable to match Weld procedure and parent materials. |  | AS/NZS 1554.1 | Welding consumables and gas match what is specified on the appropriate welding procedures. |  | Supplier Material Certificate PFS Welding Procedures |  | PM/PE | Initial: Sign: | RA
9 | Material inspection upon receiving (By supplier/sub-contractor/ Free issue material) |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs. |  | IFC DWGs |  | Team Leader | Initial: Sign: | H
Steel structure Fabrication
10 | Manufacturing Work Pack Issued to Production Manager |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet |  |  |  | Production Manager | Initial: Sign: | RA
11 | Cutting the structural steel |  | Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0039 | Dimensional survey of fabricated item's against IFC drawings. Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10 |  | IFC DWGs |  | Team Leader | Initial: Sign: | D
12 | Holing |  | Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0040 | Dimensional survey of fabricated item's against IFC drawings. Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10 |  | IFC DWGs |  | Team Leader | Initial: Sign: | D
13 | Identification and traceability for main items |  | Project Structure Specification C07 Rev. 01 IFC structure DWG AS/NZS 5131 | Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like. |  | IFC DWGs |  | PM/PE | Initial: Sign: | H
14 | Manufacture of steel structure Tack welded only |  | IFC DWGs | Manufacture completed as per IFC Fabrication drawings. All tack welding shall be performed in accordance with PFS weld procedure. Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. |  | IFC DWGs |  | Team Leader | Initial: Sign: | D
15 | Pre Weld Dimensional Check (Tack Check) |  | IFC Drawings | Dimensional survey of fabricated item's against IFC drawings. Measured dimensions shall be within stated tolerances unless noted otherwise. Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10 Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure |  | IFC DWGs |  | Team Leader | Initial: Sign: | D
16 | Welding |  | AS/NZS 1554.1 AS/NZS 9606.1 | All welding shall be performed in accordance with PFS weld procedures Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register. |  | Welding Procedure and Welder Qualification |  | Team Leader | Initial: Sign: | V
17 | Post Weld Dimensional Check |  | IFC DWGs | Dimensional survey of fabricated item's against IFC drawings. Measured dimensions shall be within stated tolerances unless noted otherwise. Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10 Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure |  | IFC DWGs & Workshop Pack. |  | Team Leader | Initial: Sign: | D
18 | Weld Visual Scanning (PFS Internal Check) |  | IFC Drawing | 100% of all welds shall be subject to visual scanning |  | PFS NDT Register |  | Team Leader | Initial: Sign: | V
19 | NDT inspection |  | Project Structure Specification C07 Rev. 01 | NDE shall include as a minimum: 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects. |  | Stamped NDT report |  | PM/PE | Initial: Sign: | RA | NDT subcontractor | Initial: Sign: | S
20 | Protective Coatings Preparation |  | Project Structure Specification C07 Rev. 01 | Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter. All sharp edges are ground to a smooth 2 mm radius. |  | N/A |  | Team Leader | Initial: Sign: | V
21 | Fabrication NCR (if any) |  | Project Structure Specification C07 Rev. 01 | All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval |  | - |  | PM/PE | Initial: Sign: | S |  |  |  | Downer | Initial: Sign: | RA
Shop Assembly - Pannels, Handrails and Balustrades
22 | Inspection the free issue pannel uppon receipt at PFS work shop |  | Pannel DWGs | Check pannel to make sure the quantity and/or dimension are based on approved DWGs. |  | Pannel DWGs |  | Team Leader | Initial: Sign: | V
23 | Panels Pre-assembly |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | After painting, Client supplied pannels for decking and balastrades to be assembled. Handrails need to be assembled in the shop |  | IFC DWGs |  | Team Leader | Initial: Sign: | V/D
24 | Dimension check |  | IFC DWG | Compliance with IFC DWGs |  | - |  | Team Leader | Initial: Sign: | D
25 | Visual inspection of Fasteners (Free issue) |  | IFC Drawing | All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length) |  | IFC Drawing |  | Team Leader | Initial: Sign: | V
26 | Snug tightening of conposite component fixings |  | Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified. |  | - |  | Team Leader | Initial: Sign: | V
27 | Final Inspection |  | IFC Drawings, AS/NZS 1554.1:2014 Category SP | Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings. >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated. |  | IFC DWGs |  | PM/PE | Initial: Sign: | RA
Quality Review
28 | Compile, review and submit documentation |  | Project Structure Specification C07 Rev. 01 IFC structure DWG | Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report |  | PFS Manufactures Data Report |  | PM/PE | Initial: Sign: | RA |  |  |  | Downer | Initial: Sign: | RA
PFS Revision Record: 39028-ITP-001-39028- Span 6 RevD
| Approved by [Engineer/Client] |  |  | Name: |  | Date: |  | Sign:
| Issued for Construction |  |  | Name: |  | Date: |  | Sign:
Comments/Notes: