## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-016 Shop fabrication - Span 2 | itp |  |  |  |  | DN1212-ITP-016 Shop fabrication - Span 2 RevD
section | Engineering
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
label | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Submit Inspection personel competencies
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
label | Certify Doc / Ref - NDT qualification
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 5 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
label | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 6 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
label | 1 - Quality Management Plan
label | 2 - IMS Manual
label | 3 - SFC Certificate
label | 4 - ISO 9001 Certificate
label | Certify Doc / Ref - Quality certificates, Quality Plan
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - R
section | Procurement
checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA/S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
section | Steel structure Fabrication
checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
label | PFS Engineering - Production Manager
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 11 - Cutting the structural steel
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 12 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 13 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Manufacture of steel structure - Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
label | ○ All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 16 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 17 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NDT Register
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 19 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NDE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Subcontracted scope - NDT subcontractor
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - S
checkpoint | 20 - Protective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 21 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | Shop Assembly - Pannels, Handrails and Balustrades
checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
label | Specification Standard - Pannel DWGs
label | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
label | Certify Doc / Ref - Pannel DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 23 - Panels Pre-assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
label | ○ Handrails need to be assembled in the shop
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V/D
checkpoint | 24 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 25 - Visual inspection of Fasteners (Free issue)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 26 - Snug tightening of conposite component fixings
label | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 27 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
section | Quality Review
checkpoint | 28 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client]:
textbox | Issued for Construction:
holdpoint | Sign:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-017 Shop fabrication - Span 3 | itp |  |  |  |  | DN1212-ITP-017 Shop fabrication - Span 3 RevD
section | Engineering
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Submit Inspection personel competencies
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
label | Certify Doc / Ref - NDT qualification
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures, HERA/CSWIP Stamp
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 5 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
label | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 6 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
label | 1 - Quality Management Plan
label | 2 - IMS Manual
label | 3 - SFC Certificate
label | 4 - ISO 9001 Certificate
label | Certify Doc / Ref - Quality certificates, Quality Plan
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - R
section | Procurement
checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA/S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
section | Steel structure Fabrication
checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
label | PFS Engineering - Production Manager
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 11 - Cutting the structural steel
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 12 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 13 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Manufacture of steel structure - Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
label | ○ All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 16 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 17 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NDT Register
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 19 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NDE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Subcontracted scope - NDT subcontractor
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - S
checkpoint | 20 - Protective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 21 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | Shop Assembly - Pannels, Handrails and Balustrades
checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
label | Specification Standard - Pannel DWGs
label | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
label | Certify Doc / Ref - Pannel DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 23 - Panels Pre-assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
label | ○ Handrails need to be assembled in the shop
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V/D
checkpoint | 24 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 25 - Visual inspection of Fasteners (Free issue)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 26 - Snug tightening of conposite component fixings
label | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 27 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
section | Quality Review
checkpoint | 28 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client]:
textbox | Issued for Construction:
holdpoint | Sign:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-018 Shop fabrication - Span 4 | itp |  |  |  |  | DN1212-ITP-018 Shop fabrication - Span 4 RevD
section | Engineering
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
label | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Submit Inspection personel competencies
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
label | Certify Doc / Ref - NDT qualification
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 5 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
label | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 6 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
label | 1 - Quality Management Plan
label | 2 - IMS Manual
label | 3 - SFC Certificate
label | 4 - ISO 9001 Certificate
label | Certify Doc / Ref - Quality certificates, Quality Plan
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - R
section | Procurement
checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA/S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
section | Steel structure Fabrication
checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
label | PFS Engineering - Production Manager
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 11 - Cutting the structural steel
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 12 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 13 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Manufacture of steel structure - Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
label | ○ All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 16 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 17 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NDT Register
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 19 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NDE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Subcontracted scope - NDT subcontractor
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - S
checkpoint | 20 - Protective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 21 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | Shop Assembly - Pannels, Handrails and Balustrades
checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
label | Specification Standard - Pannel DWGs
label | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
label | Certify Doc / Ref - Pannel DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 23 - Panels Pre-assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
label | ○ Handrails need to be assembled in the shop
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V/D
checkpoint | 24 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 25 - Visual inspection of Fasteners (Free issue)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 26 - Snug tightening of conposite component fixings
label | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 27 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
section | Quality Review
checkpoint | 28 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client]:
textbox | Issued for Construction:
holdpoint | Sign:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-019 Shop fabrication - Span 5 | itp |  |  |  |  | DN1212-ITP-019 Shop fabrication - Span 5 RevD
section | Engineering
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
label | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Submit Inspection personel competencies
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
label | Certify Doc / Ref - NDT qualification
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 5 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
label | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 6 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
label | 1 - Quality Management Plan
label | 2 - IMS Manual
label | 3 - SFC Certificate
label | 4 - ISO 9001 Certificate
label | Certify Doc / Ref - Quality certificates, Quality Plan
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - R
section | Procurement
checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA/S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
section | Steel structure Fabrication
checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
label | PFS Engineering - Production Manager
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 11 - Cutting the structural steel
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 12 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 13 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Manufacture of steel structure - Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
label | ○ All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 16 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 17 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NDT Register
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 19 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NDE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Subcontracted scope - NDT subcontractor
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - S
checkpoint | 20 - Protective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 21 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | Shop Assembly - Pannels, Handrails and Balustrades
checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
label | Specification Standard - Pannel DWGs
label | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
label | Certify Doc / Ref - Pannel DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 23 - Panels Pre-assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
label | ○ Handrails need to be assembled in the shop
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V/D
checkpoint | 24 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 25 - Visual inspection of Fasteners (Free issue)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 26 - Snug tightening of conposite component fixings
label | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 27 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
section | Quality Review
checkpoint | 28 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client]:
textbox | Issued for Construction:
holdpoint | Sign:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1212-ITP-020 Shop fabrication - Span 6 | itp |  |  |  |  | DN1212-ITP-020 Shop fabrication - Span 6 RevD
section | Engineering
checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Shop Drawing approval
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
label | Certify Doc / Ref - Shop Drawing Check form
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
label | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Submit Inspection personel competencies
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
label | Certify Doc / Ref - NDT qualification
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Welding Procedures - Structural
label | Specification Standard - AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 5 - Welder Qualifications - Structural
label | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
label | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
label | ○ No welder shall carry out work for which he is not certified.
label | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Subcontracted scope - SQA
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - RA
checkpoint | 6 - Submit the required documents to Client for review
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
label | 1 - Quality Management Plan
label | 2 - IMS Manual
label | 3 - SFC Certificate
label | 4 - ISO 9001 Certificate
label | Certify Doc / Ref - Quality certificates, Quality Plan
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - R
section | Procurement
checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
label | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
label | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
label | Certify Doc / Ref - Supplier Material Certificate
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA/S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
label | Specification Standard - AS/NZS 1554.1
label | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
label | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
section | Steel structure Fabrication
checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
label | PFS Engineering - Production Manager
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
checkpoint | 11 - Cutting the structural steel
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 12 - Holing
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 13 - Identification and traceability for main items
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
label | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Manufacture of steel structure - Tack welded only
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
label | ○ All tack welding shall be performed in accordance with PFS weld procedure.
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
label | Specification Standard - IFC Drawings
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 16 - Welding
label | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
label | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
label | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
label | Certify Doc / Ref - Welding Procedure and Welder Qualification
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 17 - Post Weld Dimensional Check
label | Specification Standard - IFC DWGs
label | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
label | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
label | ○ Project specification clause C0702.1.3
label | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
label | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
label | Certify Doc / Ref - IFC DWGs & Workshop Pack.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
label | Certify Doc / Ref - PFS NDT Register
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 19 - NDT inspection
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - NDE shall include as a minimum:
label | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
label | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
label | Certify Doc / Ref - Stamped NDT report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Subcontracted scope - NDT subcontractor
textbox | Subcontracted scope: Sign - Initial: Sign:
label | Subcontracted scope: C - S
checkpoint | 20 - Protective Coatings Preparation
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
label | ○ All sharp edges are ground to a smooth 2 mm radius.
label | Certify Doc / Ref - N/A
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 21 - Fabrication NCR (if any)
label | Specification Standard - Project Structure Specification C07 Rev. 01
label | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - S
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | Shop Assembly - Pannels, Handrails and Balustrades
checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
label | Specification Standard - Pannel DWGs
label | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
label | Certify Doc / Ref - Pannel DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 23 - Panels Pre-assembly
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
label | ○ Handrails need to be assembled in the shop
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V/D
checkpoint | 24 - Dimension check
label | Specification Standard - IFC DWG
label | Acceptance Criteria - Compliance with IFC DWGs
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - D
checkpoint | 25 - Visual inspection of Fasteners (Free issue)
label | Specification Standard - IFC Drawing
label | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
label | Certify Doc / Ref - IFC Drawing
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 26 - Snug tightening of conposite component fixings
label | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
label | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
label | PFS Engineering - Team Leader
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - V
checkpoint | 27 - Final Inspection
label | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
label | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
label | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
label | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
label | Certify Doc / Ref - IFC DWGs
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
section | Quality Review
checkpoint | 28 - Compile, review and submit documentation
label | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
label | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
label | Certify Doc / Ref - PFS Manufactures Data Report
label | PFS Engineering - PM/PE
textbox | PFS Engineering: Sign - Initial: Sign:
label | PFS Engineering: C - RA
label | Downer - Downer
textbox | Downer: Sign - Initial: Sign:
label | Downer: C - RA
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
textbox | Approved by [Engineer/Client]:
textbox | Issued for Construction:
holdpoint | Sign:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature