## Table 1
Aconex Document Number: |  | TEA-QA-ITP-00001 |  |  | Date: | 2024-07-26
ITP Number: |  | TEA-QA-ITP-00001 |  |  | Revision: | 01
PROJECT NAME: |  | New Sydney Fish Markets |  |  | ZONE:
SUBCONTRACTOR: |  | Teammembers Project Pty Ltd |  |  | LEVEL:
BUILDER: |  | Multiplex Constructions Pty Ltd |  |  | ROOM:
SCOPE: |  | Supply and Installation of Ceramic Tiles |  |  | LOT:
ITP Prepared by: |  | Alex Chong |  | ITP Reviewed and Approved by: |  | Philip Chong
Company/Role |  | Teammembers Project Pty Ltd/ Project Manager |  | Company/Role: |  | Teammembers Project Pty Ltd - Director
Date: |  | 2024-01-22 |  | Date: |  | 2024-01-22
Signature: |  | #VALUE! |  | Signature: |  | #VALUE!
Project Drawings/Documents |  |  |  | Relevant Standards
Drawing Number |  | Drawing Title |  | Standard Number |  | Standard Title
|  |  |  | AS 3958.1-2007 |  | Ceramic tiles - Guide to the installation of ceramic tiles
Ref | Inspection Item | Verification | Acceptance Criteria |  | TM Site Supervisor |  | MPX Engineer | Note/Commnt
1 | Material Delivery: Teammembers site supervisor to confirm all tiling materials are correct as per approved samples and are free from damage upon delivery to site and record received material. | Inspection Point | All materials are free from damage upon delivery to the correct areas and match the approved samples. Tile batch numbers to match TMM to document |  | JI Kang Site Supervisor Date |  | Name Date Sign
H-1 | Substrate Inspection - Wall and Floor: Acceptance of substrate including structural elements, such as movement joints. | Hold Point | Wall Linings: Surface flat, walls plumb, no protrusions, screw heads filled, external corners trimmed and square, internal corners filled and square. Ceiling linings: Installed, sanded, painted. Floor: Acceptance of substrate including structural elements, such as movement joints. Membrane testing completed by others and confirmed that screed installation can commence. Prior to commencement of screed beds, ensure taped barrier to amenities by waterproofer is intact to avoid access by other trades prior to screed commencement. If breached, advise MPX representative prior to commencement for go ahead. |  | Ji Kang Site Supervisor Date |  | Name Date Sign
2 | Sand and Cement Screeding: • Screed beds - Tiled Wet Areas | Inspection Point | Screed beds: Screed to be mixed and installed as per approved samples manufacturer data sheet. Screed mixed by machine ratio 1:4. Grey cement - washed sand conventional screed and Efflock additive 100ml per single drum mix. Ensure water / cement 1:1 slurry applied to whole floor area and screed applied wet on wet. Mesh will be used when screed thickness is greater than 50mm. Screed separation from perimeter walls: Not required unless wall is concrete or brick than 10mm ableflex will be used. Expansion Joint: Joints to be formed full depth threough screed. Internal joints 6mm wide by ableflex/equivalent. Full revmove prior to sealant application. Floorwastes: Protect floorwastes with sponges to remove risk of screed debris from entering the drain. Falls ratio: Laser check all start heights from starting height of Door entry FFL, perimeter and to floorwastes. Falls ratios in showers to be between 1:60 to 1:80, outside showers between 1:80 to 1:100 as per AS3958.1-2007. Check that levels to WC flush pipes and to basin heights comply with FFLs nominated within AR finishes plan. |  | JI Kang Site Supervisor Date |  | Name Date Sign
W-1 | Floor Tiling Set-out: Setup start and set-out points to Tiling demonstrating layouts, minimum cuts, etc... | Witness Point | Setout chalkline to floor surface, eliminate small tile cuts to nib walls where in exposed locations. Full tile to start from door entry, minimum 1/2 cut tiles to exposed walls. |  | Ji Kang Site Supervisor Date |  | Name Date Sign
3 | Floor Tile Installation: • Floor tiling • Expansion joints • Floor protection | Inspection Point | Floor tiling: Allow 2mm nominal joint spacing, tile to tile lippage max 1.00mm, 6mm expansion joints to carry to wall tiling, cross cut tiles permitted to maintain falls ratios to floorwastes, ensure 4 to 6mm gaps to all perimeter walls, door frames and to floorwastes as per AS3958.1-2007. Expansion joints: Expansion joints to be 6mm and filled with backing rod and approved silicone. Expansion joints to be installed at locations as per BVN drawing Floor protection: Cover floor with white 3mm plastic with joints taped to protect floor tiles from wall tiling operation. |  | JI Kang Site Supervisor Date |  | Name Date Sign
W-2 | Wall Tiling Set-out: Setup start and set-out points to Tiling demonstrating layouts, minimum cuts, etc… | Witness Point | Highest point of floor perimeter and lowest point to be identified to determine extent of tile cut to the base of the wall. Allow to maintain 4-6mm gap to floor perimeter and to determine cut height to ceiling. |  | Ji Kang Site Supervisor Date |  | Name Date Sign
4 | Wall Tile Installation: • Wall tiling • Penetrations to wall tiling | Inspection Point | Wall tiling: Wall joints to align with floor tiles, tile to tile lippage max 1.00mm, expansion joints 6mm. Ensure 4-6mm gaps to all perimeter walls, internal corners and door frames as per AS3958.1-2007. Tiling to be plumb and square. Ensure even to gauge tiling to curved walls. Penetrations to wall tiling: Ensure cuts to pipe penetrations are even and tight and checked with cover flange of specified tapware, towel dispensers. |  | JI Kang Site Supervisor Date |  | Name Date Sign
5 | Grouting Wall / Floor Tiles: • Grouting generally epoxy and non epoxy (48 hours minimum after completion of wall tiling) • After exoxy grouting (before clean / after clean) | Inspection Point | Grouting generally epoxy and non epoxy: All temporary protection removed, spacers removed, and grout joints cleaned and free from foreign contaminants. Floors and walls to be cleaned with damp sponges prior to grout application. Internal corners to be free from grout and debris. Grouting to be completed as per manufacturer data sheet Fugalite Eco/Fugabella Colour as per approved sample. After exoxy grouting: All tiled surfaces to be cleaned from residue within 24 hours of installation. |  | Ji Kang Site Supervisor Date |  | Name Date Sign
W-3 | Grout Completion / Clean Up | Witness Point | Ensure tiling surfaces are clean, wall and floor grout joints are aligned, and there are no chipped or cracked tiles. If defects are identified, defects are to be repaired to ensure the above are achieved. |  | JI Kang Site Supervisor Date |  | N/A
6 | Floor Protection: Installing floor protection to floor tiling | Inspection Point | After final inspection, cover floor with white 3mm plastic coreflute with joints taped to protect floor tiles from ensuing tradeworks. Make allowance for Toilet pan installation and partitions. |  | Ji Kang Site Supervisor Date |  | Name Date Sign
Completion Items
Ref | Completion Item | Description |  |  | TM Site Supervisor
1 | NCR (if applicable) | All NCRs closed and/or actioned as agreed with the Managing contractor. |  |  | JI Kang Date
2 | RFI (if applicable) | All RFI's closed. |  |  | JI Kang Date
3 | Check and compile lot records | All completion documents are attached. |  |  | JI Kang Date
Comments:
By signing the below, I declare all items in this Inspection and Test Plan have been Completed and to the required standard.
Teammembers Site Supervisor |  | Multiplex Engineer
JI Kang Site Supervisor Date |  | Name Date Signature
Appendix
Samples
Aconex Document Number |  | Sample Title
TEA-FO-SMP-10001 | TEA-FO-SMP-10001 | TIL-01a- White Matt Tile | TIL-01a White Matt Tile (SKU NT22-1335WP)
TEA-FO-SMP-10002 | TEA-FO-SMP-10002 | TIL-01b Naval Matt Tile | TIL-01b Naval Matt Tile (SKU NT22-1349WP)
TEA-FO-SMP-10003 | TEA-FO-SMP-10003 | TIL-01c Terracotta Matt Tile | TIL-01c Terracotta Matt Tile (SKU NT22-1335WP)
TEA-FO-SMP-10006 | TEA-FO-SMP-10004 | TIL-04 - Aria Deep Taupe Matt Amenity | TIL-02 (i.e. TIL-21) Promenade Stair Terracotta Tile
TEA-FO-SMP-11005 | TEA-FO-SMP-10005 | TIL-03 White Gloss Tile (BASICS) | TIL-03 White Gloss Tile (BASICS)
TEA-FO-SMP-11010 | TEA-FO-SMP-10006 | Efflock - Tiles | TIL-04 Cool Grey Matt Tile (CORE)
TEA-FO-SMP-11011 | TEA-FO-SMP-10006 | External Tile Trim | TIL-04 Cool Grey Matt Tile (CORE)
TEA-FO-SMP-11012 | TEA-FO-SMP-10006 | Silicone - Tiles | TIL-22 Lift Floor Small Black Aggregate
TEA-FO-SMP-11013 | TEA-FO-SMP-10006 | Epoxy Grout - Tiles | TIL-22 Lift Floor Small Black Aggregate
TEA-FO-SMP-11014 | TEA-FO-SMP-10006 | Kerakoll Bioflex S1 Zero | TIL-22 Lift Floor Small Black Aggregate

## ITP
INSPECTION AND TEST PLAN
Aconex Document Number: |  | TEA-QA-ITP-00001 |  | Date: |  | 2024-11-11
ITP Number: |  | TEA-QA-ITP-00001 |  | Revision: |  | 1
Project Name: |  | John Hunter Health and Innovation Precinct |  | Zone:
Subcontractor: |  | Teammembers Project Pty Ltd |  | Level:
Builder |  | Multiplex Constructions Pty Ltd |  | Room:
Scope: |  | Supply and Installation of Ceramic Tiles and Engineered Screed |  | LOT:
ITP Prepared by: |  | Daniel Yu |  | ITP Reviewed and Approved by: |  | Philip Chong
Company / Role: |  | Teammembers Project Pty Ltd / Operatioins Manager |  | Company / Role: |  | Teammembers Project Pty Ltd / Director
Date: |  | 2024-11-11 |  | Date: |  | 2024-11-11
Signature: | [5 empty] | #VALUE!
Project Drawings / Documents |  |  |  | Relevant Standards
Drawing Number |  | Drawing Title |  | Standard Number |  | Standard Title
|  |  |  | AS 3958.1 - 2007 |  | Ceramic Tiles - Guide to the installation of ceramic tiles
Ref | Inspection Item | Verification | Acceptance Criteria |  | TMP Supervisor | Note/Comment
1 | Material Delivery: TMP site supervisor to confirm all tiling materials are correct as per approved samples and are free from damage upon delivery to site and record received material. | Inspection Point Record | All materials are free from damage upon delivery to the correct areas and match the approved samples. Tile batch numbers to match TMM to document |  | Bol Ajak Site Supervisor Date
H-1 | Substrate Inspection - Wall and Floor: Acceptance of substrate including structural elements, such as movement joints. | MPX Hold Point | Wall Linings: Surface flat, walls plumb, no protrusions, screw heads filled, external corners trimmed and square, internal corners filled and square. Ceiling linings: Installed, sanded, painted. Floor: Acceptance of substrate including structural elements, such as movement joints. Membrane testing completed by others and confirmed that screed installation can commence. Prior to commencement of screed beds, ensure taped barrier to amenities by waterproofer is intact to avoid access by other trades prior to screed commencement. If breached, advise MPX representative prior to commencement for go ahead. |  | Bol Ajak Site Supervisor Date
2.1 | Sand and Cement Screeding: • Conventional Screed Beds | Inspection Point | Conventional Screed beds: Screed to be mixed and installed as per approved samples manufacturer data sheet. Screed mixed by machine ratio 1:4. Grey cement : washed sand. Ensure water / cement 1:1 slurry applied to whole floor area and screed applied wet on wet. Mesh will be used when screed thickness is greater than 50mm. Screed separation from perimeter walls: Not required unless wall is concrete or brick then 10mm ableflex will be used. Expansion Joint: Joints to be cut into the screed. Internal joints 6mm wide by ableflex/equivalent. Full remove prior to sealant application. Floorwastes: Protect floorwastes with sponges to remove risk of screed debris from entering the drain. Falls ratio: Laser check all start heights from starting height of Door entry FFL, perimeter and to floorwastes. Falls as per BVN docs. BVN to follow Standards. |  | Bol Ajak Site Supervisor Date
2.2 | Sand and Cement Screeding: • Engineered Screed Beds | Inspection Point | Engineered Screed beds: Screed to be mixed and installed as per approved samples manufacturer data sheet. Screed mixed by machine ratio 1:6. Kerecem : Riversand / Washed sand 50/50 mix. Ensure water / cement 1:1 slurry applied to whole floor area and screed applied wet on wet. Mesh will be used when screed thickness is greater than 50mm. Efflock additive 100ml per single drum mix to be added when screeding outdoor areas |  | Bol Ajak Site Supervisor Date
W-1 | Floor Tiling Set-out: Setup start and set-out points to Tiling demonstrating layouts, minimum cuts, etc... | Witness Point | Setout chalkline to floor surface. Tile set out as per architectural drawings. |  | Bol Ajak Site Supervisor Date
3 | Floor Tile Installation: • Floor tiling • Expansion joints • Floor protection | Inspection Point | Floor tiling: Allow 3mm nominal joint spacing, tile to tile lippage max 1.00mm, cross cut tiles permitted to maintain falls ratios to floorwastes, ensure 4 to 6mm gaps to all perimeter walls, door frames and to floorwastes as per AS3958.1-2007. 10mm depth perimeter joints as per MPX handbook. Note, if this does not match BVN set out drawings MPX is to be notified. Expansion joints: Expansion joints to be 6mm and filled with backing rod and approved silicone. Expansion joints to be installed at locations as per BVN drawing. Full-depth cuts to the screed, extending to the substrate, will be made at all expansion joint locations. Floor protection: Cover floor with white 3mm plastic with joints taped to protect floor tiles from wall tiling operation. Glue as per approved sample form |  | Bol Ajak Site Supervisor Date
W-2 | Wall Tiling Set-out: Setup start and set-out points to Tiling demonstrating layouts, minimum cuts, etc… | Witness Point | Highest point of floor perimeter and lowest point to be identified to determine extent of tile cut to the base of the wall. Allow to maintain 4-6mm gap to floor perimeter and to determine cut height to ceiling. Note, if this does not match BVN set out drawings MPX is to be notified |  | Bol Ajak Site Supervisor Date
4 | Wall Tile Installation: • Wall tiling • Penetrations to wall tiling | Inspection Point | Wall tiling: Wall tile setout as per architectural drawings, tile to tile lippage max 1.00mm. Ensure 4-6mm gaps to all perimeter walls, internal corners and door frames as per AS3958.1-2007. Tiling to be plumb and square. Penetrations to wall tiling: Ensure cuts to pipe penetrations are even and tight and checked with cover flange of specified tapware, towel dispensers. |  | Bol Ajak Site Supervisor Date
5 | Grouting Wall / Floor Tiles: • Grouting generally epoxy and non epoxy (48 hours minimum after completion of wall tiling) • After exoxy grouting (before clean / after clean) | Inspection Point | Grouting generally epoxy and non epoxy: All temporary protection removed, spacers removed, and grout joints cleaned and free from foreign contaminants. Floors and walls to be cleaned with damp sponges prior to grout application. Internal corners to be free from grout and debris. Grouting to be completed as per manufacturer data sheet. Grouting to be per approved sample and sample form. |  | Bol Ajak Site Supervisor Date
W-3 | Grout Completion / Clean Up | MPX Hold Point | Ensure tiling surfaces are clean, wall and floor grout joints are aligned, and there are no chipped or cracked tiles. If defects are identified, defects are to be repaired to ensure the above are achieved. |  | Bol Ajak Site Supervisor Date
6 | Floor Protection: Installing floor protection to floor tiling | Inspection Point | After final inspection, cover floor with white 3mm plastic coreflute with joints taped to protect floor tiles from ensuing tradeworks. |  | Bol Ajak Site Supervisor Date
Completion Itmes
Ref | Completion Item |  | Description |  | TM Site Supervisor
1 | NCR (if applicable) |  | All NCRs closed and/or actioned as agreed with the Managing contractor. |  | Bol Ajak Date
2 | RFI (if applicable) |  | All RFI's closed. |  | Bol Ajak Date
3 | Check and compile lot records |  | All completion documents are attached. |  | Bol Ajak Date
Additional Notes
By signing the below, I declare all items in this Inspection and Test Plan has been completed and to the required standard.
Teammembers Site Supervisor
Bol Ajak Site Supervisor Date
Appendix
Samples
|  |  | Aconex Document Number | Sample Title
|  |  | TEA-FO-SMP-10001 | TIL-01a- White Matt Tile
|  |  | TEA-FO-SMP-10002 | TIL-01b Naval Matt Tile
|  |  | TEA-FO-SMP-10003 | TIL-01c Terracotta Matt Tile
|  |  | TEA-FO-SMP-10006 | TIL-04 - Aria Deep Taupe Matt Amenity
|  |  | TEA-FO-SMP-10005 | TIL-03 White Gloss Tile (BASICS)
|  |  | TEA-FO-SMP-10010 | Efflock - Tiles
|  |  | TEA-FO-SMP-10011 | External Tile Trim
|  |  | TEA-FO-SMP-10012 | Silicone - Tiles
|  |  | TEA-FO-SMP-10013 | Epoxy Grout - Tiles
|  |  | TEA-FO-SMP-10014 | Kerakoll Bioflex S1 Zero