## Sheet1
1 | Inspection and Test Plan Reviewed and Approved by Customer | Project Structure Specification C0702 Rev. 01 IFC structure DWG | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. | IFC DWGs | PM/PE | Initial: Sign: | S | Downer | Initial: Sign: | H | 1 - Inspection and Test Plan Reviewed and Approved by Customer | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. | Certify Doc / Ref - IFC DWGs | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - S | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - H | 1 - Inspection and Test Plan Reviewed and Approved by Customer
2 | Submit the required documents to Client for review | Project Structure Specification C0702 Rev. 01 | Site installation methodology shall be submitted to the Engineer for review | Erection Sequence Methodology | PM/PE | Initial: Sign: | S | Downer | Initial: Sign: | R | 2 - Submit the required documents to Client for review | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Site installation methodology shall be submitted to the Engineer for review | Certify Doc / Ref - Erection Sequence Methodology | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - S | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
3 | Installation Procurement - Cast in items | Project Structure Specification C0702 Rev. 01 IFC structure DWG | Confirm Procurement and delivery of all Cast in Items: i.shear keys. ii. uplift restraints and associated nuts iii. plate washers. iv. Maccaloy bars (ETA 06/01/25) and couplers with denso tape. v. Reidbar and couplers + touch up protective coating. vi. Nylon washers and rubber sleeves. vii. Temporary bearing components. | IFC DWG PFS: 39028-3202-000-FABRC PFS: 39028-3201-000-FABRC Mill Certs Compliance Documentation | PM/PE | Initial: Sign: | V |  |  |  | 3 - Installation Procurement - Cast in items | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Confirm Procurement and delivery of all Cast in Items: i.shear keys. ii. uplift restraints and associated nuts iii. plate washers. iv. Maccaloy bars (ETA 06/01/25) and couplers with denso tape. v. Reidbar and couplers + touch up protective coating. vi. Nylon washers and rubber sleeves. vii. Temporary bearing components. | Certify Doc / Ref - IFC DWG PFS: 39028-3202-000-FABRC PFS: 39028-3201-000-FABRC Mill Certs Compliance Documentation | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
4 | Inspection upon receipt at site | Project Structure Specification C0702 Rev. 01 IFC structure DWG | The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | IFC DWG | PM/PE | Initial: Sign: | V | Downer | Initial: Sign: | R | 4 - Inspection upon receipt at site | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport | Certify Doc / Ref - IFC DWG | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Certify Doc / Ref - IFC DWGs
5 | Inspection upon receipt at site - Cast in Items. | Project Structure Specification C0702 Rev. 01 IFC structure DWG | The material receipt at site need to be visually inspected for quantity, make sure no damage occurred during transport. All related documents have been received. | IFC DWG | PM/PE | Initial: Sign: | V | Downer | Initial: Sign: | R | 5 - Inspection upon receipt at site - Cast in Items. | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity, make sure no damage occurred during transport. All related documents have been received. | Certify Doc / Ref - IFC DWG | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | PFS Engineering - PM/PE
6 | Preparation work- prior to Span Lifting for All Spans | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Make sure survey has been done and center marks on the framework as a reference have been provided by Downer Installation of 100x100 EA as a lifting aid on temporary structure Span unloaded from truck and placed on Dunnage on ground prior to rigging adjustment Attaching the tag lines to Spans to prevent rotation during installation | Lift plan | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 6 - Preparation work- prior to Span Lifting for All Spans | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Make sure survey has been done and center marks on the framework as a reference have been provided by Downer Installation of 100x100 EA as a lifting aid on temporary structure Span unloaded from truck and placed on Dunnage on ground prior to rigging adjustment Attaching the tag lines to Spans to prevent rotation during installation | Certify Doc / Ref - Lift plan | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | PFS Engineering: Sign - Initial: Sign:
7 | Confirm all Manufacture documentation has been completed for Span #2 | Project Structure Specification C0702 Rev. 01 | Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | QA Documentation | PM/PE | Initial: Sign: | V |  |  |  | 7 - Confirm all Manufacture documentation has been completed for Span #2 | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | Certify Doc / Ref - QA Documentation | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | PFS Engineering: C - S
8 | Installation of Span#2 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Verify that the structural component is securely rigged according to the rigging plan To lift Span #2 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure Chain block will be connected to the West end to adjust level. when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Lift plan | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 8 - Installation of Span#2 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Verify that the structural component is securely rigged according to the rigging plan To lift Span #2 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure Chain block will be connected to the West end to adjust level. when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Certify Doc / Ref - Lift plan | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Subcontracted scope -
9 | Macalloy Bars installation for Span #2 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | To keep Macalloy bar aligned, a coupler to be tightened to extend the Macalloy bar and Tempory nut will be added to the rod on the Span 2 high end. The nuts will be tightened to hold the Macalloy bars in correct position. | IFC Drawing | Site project Manager | Initial: Sign: | H |  |  |  | 9 - Macalloy Bars installation for Span #2 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - To keep Macalloy bar aligned, a coupler to be tightened to extend the Macalloy bar and Tempory nut will be added to the rod on the Span 2 high end. The nuts will be tightened to hold the Macalloy bars in correct position. | Certify Doc / Ref - IFC Drawing | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Subcontracted scope: Sign -
10 | Confirm all Manufacture documentation has been completed for Span #3 | Project Structure Specification C0702 Rev. 01 | Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | QA Documentation | PM/PE | Initial: Sign: | V | Downer | Initial: Sign: | R | 10 - Confirm all Manufacture documentation has been completed for Span #3 | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | Certify Doc / Ref - QA Documentation | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Subcontracted scope: C -
11 | Installation of Span#3 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Verify that the structural component is securely rigged according to the lift plan To lift Span #3 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Lift plan | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 11 - Installation of Span#3 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #3 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Certify Doc / Ref - Lift plan | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Downer - Downer
12 | Shear Keys, Hold Down Bolt and Reidbars Installation for Span #3 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Shear keys, Hold Down bolts and Reidbars Drawing | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 12 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #3 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Downer: Sign - Initial: Sign:
13 | Confirm all Manufacture documentation has been completed for Span #4 | Project Structure Specification C0702 Rev. 01 | Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | QA Documentation | PM/PE | Initial: Sign: | V |  |  |  | 13 - Confirm all Manufacture documentation has been completed for Span #4 | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | Certify Doc / Ref - QA Documentation | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Downer: C - H
14 | Installation of Span#4 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Verify that the structural component is securely rigged according to the lift plan To lift Span #4 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Lift plan | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 14 - Installation of Span#4 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #4 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Certify Doc / Ref - Lift plan | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | 2 - Submit the required documents to Client for review
15 | Shear Keys, Hold Down Bolt and Reidbars Installation for Span #4 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Shear keys, Hold Down bolts and Reidbars Drawing | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 15 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #4 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Specification Standard - Project Structure Specification C0702 Rev. 01
16 | Confirm all Manufacture documentation has been completed for Span #5 | Project Structure Specification C0702 Rev. 01 | Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | QA Documentation | PM/PE | Initial: Sign: | V |  |  |  | 16 - Confirm all Manufacture documentation has been completed for Span #5 | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | Certify Doc / Ref - QA Documentation | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Acceptance Criteria - Site installation methodology shall be submitted to the Engineer for review
17 | Installation of Span#5 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Verify that the structural component is securely rigged according to the lift plan To lift Span #5 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Lift plan | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 17 - Installation of Span#5 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #5 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Certify Doc / Ref - Lift plan | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Certify Doc / Ref - Erection Sequence Methodology
18 | Shear Keys, Hold Down Bolt and Reidbars Installation for Span #5 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Shear keys, Hold Down bolts and Reidbars Drawing | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 18 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #5 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | PFS Engineering - PM/PE
19 | Confirm all Manufacture documentation has been completed for Span #6 | Project Structure Specification C0702 Rev. 01 | Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | QA Documentation | PM/PE | Initial: Sign: | V |  |  |  | 19 - Confirm all Manufacture documentation has been completed for Span #6 | Specification Standard - Project Structure Specification C0702 Rev. 01 | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off. | Certify Doc / Ref - QA Documentation | PFS Engineering - PM/PE | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | PFS Engineering: Sign - Initial: Sign:
20 | Installation of Span#6 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Verify that the structural component is securely rigged according to the lift plan To lift Span #6 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Lift plan | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 20 - Installation of Span#6 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #6 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | Certify Doc / Ref - Lift plan | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | PFS Engineering: C - S
21 | Shear Keys, Hold Down Bolt and Reidbars Installation for Span #6 | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Temporary Bearing installation under lower end Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Shear keys, Hold Down bolts and Reidbars Drawing | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | R | 21 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #6 | Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Temporary Bearing installation under lower end Nuts on Reidbar to be snug tightened to help minimal lateral movement. | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - R | Subcontracted scope -
22 | Dimensional survey By Downer | Site installation methodology IFC Drawings | Conduct a thorough dimensinal survay inspection to confirm that the component is correctly positioned and secured based on IFC Drawing. Measured dimensions shall be within stated tolerances unless noted otherwise. Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10 Record the lifting operation in the project log, including any deviations or required adjustments to be made. | Marked up and Signed IFC DWGs | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | H | 22 - Dimensional survey By Downer | Specification Standard - Site installation methodology IFC Drawings | Acceptance Criteria - Conduct a thorough dimensinal survay inspection to confirm that the component is correctly positioned and secured based on IFC Drawing. Measured dimensions shall be within stated tolerances unless noted otherwise. Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10 Record the lifting operation in the project log, including any deviations or required adjustments to be made. | Certify Doc / Ref - Marked up and Signed IFC DWGs | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - H | Subcontracted scope: Sign -
23 | Remove Reid bar tension. | Site installation methodology IFC Drawings | Lossen Reidbars to match IFC drawing detail at all peirs before any headstock pours. | IFC DWGs | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | H | 23 - Remove Reid bar tension. | Specification Standard - Site installation methodology IFC Drawings | Acceptance Criteria - Lossen Reidbars to match IFC drawing detail at all peirs before any headstock pours. | Certify Doc / Ref - IFC DWGs | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - H | Subcontracted scope: C -
24 | Reid bar touch up painting (if required) |  | Any coatings damage to Reidbars touched up as per paint specification, Coatings to comply with note 1.2 on drawing ST-3202. | Project Paint Specification | Site project Manager | Initial: Sign: | V | Downer | Initial: Sign: | V | 24 - Reid bar touch up painting (if required) | Specification Standard - | Acceptance Criteria - Any coatings damage to Reidbars touched up as per paint specification, Coatings to comply with note 1.2 on drawing ST-3202. | Certify Doc / Ref - Project Paint Specification | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - V | Downer - Downer
25 | Hold Down Bolts tightening | Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Remove additional nuts, tape (masking and double sided) used for alignment. Apply rubber sleeves to the exposed threads. Reinstall oversized washers, apply instulating washers and tighten nuts down to achive a 1mm gap between washer and nut, lock nut to be installed as per detail C CHAR(AMP) Section 5 on ST-3202, Detail D on ST-3200. | Bolt Tightening report | Site project Manager | Initial: Sign: | H |  |  |  | 25 - Hold Down Bolts tightening | Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - Remove additional nuts, tape (masking and double sided) used for alignment. Apply rubber sleeves to the exposed threads. Reinstall oversized washers, apply instulating washers and tighten nuts down to achive a 1mm gap between washer and nut, lock nut to be installed as per detail C CHAR(AMP) Section 5 on ST-3202, Detail D on ST-3200. | Certify Doc / Ref - Bolt Tightening report | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Downer: Sign - Initial: Sign:
26 | Macalloy Bolts tightening | Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | to Undo the coupler, remove temporary alignment nut, install the rubber sleeves to the exposed rod, install the washers, nuts and snug tighten the nuts (as there are compressible components in contanc area) | Bolt Tightening report | Site project Manager | Initial: Sign: | H |  |  |  | 26 - Macalloy Bolts tightening | Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - to Undo the coupler, remove temporary alignment nut, install the rubber sleeves to the exposed rod, install the washers, nuts and snug tighten the nuts (as there are compressible components in contanc area) | Certify Doc / Ref - Bolt Tightening report | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Downer: C - R
27 | Temporary restraints removal | Site installation methodology IFC Drawings | All temporary restraints to the temporary shoring to be removed All positioning Jigs and screws applied to PTFE on Shear Keys to be removed | - | Team Leader | Initial: Sign: | V |  |  |  | 27 - Temporary restraints removal | Specification Standard - Site installation methodology IFC Drawings | Acceptance Criteria - All temporary restraints to the temporary shoring to be removed All positioning Jigs and screws applied to PTFE on Shear Keys to be removed | Certify Doc / Ref - - | PFS Engineering - Team Leader | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - V | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | 3 - Installation Procurement - Cast in items
28 | Installation of Granor Bearing | Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | The Temporary Bearing to be removed and Granor Bearing to be installed in the position the Bolts need to be snug tightened to the girders (top) and screws need to be snug tightened into the base plate. The keeper plates' bolts (M20) for uplift restraint to be tightened (full Tensioned). | Bolt Tightening report | Site project Manager | Initial: Sign: | H |  |  |  | 28 - Installation of Granor Bearing | Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - The Temporary Bearing to be removed and Granor Bearing to be installed in the position the Bolts need to be snug tightened to the girders (top) and screws need to be snug tightened into the base plate. The keeper plates' bolts (M20) for uplift restraint to be tightened (full Tensioned). | Certify Doc / Ref - Bolt Tightening report | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
29 | Installation of remaining Decking panels and wall panels | Site installation methodology IFC Drawings | Carefully position the Decking and wall panels in the conjunction area according to the approved drawings. | IFC DWGs | Team Leader | Initial: Sign: | D |  |  |  | 29 - Installation of remaining Decking panels and wall panels | Specification Standard - Site installation methodology IFC Drawings | Acceptance Criteria - Carefully position the Decking and wall panels in the conjunction area according to the approved drawings. | Certify Doc / Ref - IFC DWGs | PFS Engineering - Team Leader | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - D | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Acceptance Criteria - Confirm Procurement and delivery of all Cast in Items: i.shear keys. ii. uplift restraints and associated nuts iii. plate washers. iv. Maccaloy bars (ETA 06/01/25) and couplers with denso tape. v. Reidbar and couplers + touch up protective coating. vi. Nylon washers and rubber sleeves. vii. Temporary bearing components.
30 | Snug tightening of Decking panels and wall panels | Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Fasteners of Decking and wall panels to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified. | Bolt Tightening report | Site project Manager | Initial: Sign: | H |  |  |  | 30 - Snug tightening of Decking panels and wall panels | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - Fasteners of Decking and wall panels to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified. | Certify Doc / Ref - Bolt Tightening report | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | Certify Doc / Ref - IFC DWG PFS: 39028-3202-000-FABRC PFS: 39028-3201-000-FABRC Mill Certs Compliance Documentation
31 | Installation of remaining handrails between the spans | Site installation methodology IFC Drawings | Carefully position the handrails in the conjunction area according to the approved drawings. | IFC DWGs | Team Leader | Initial: Sign: | D |  |  |  | 31 - Installation of remaining handrails between the spans | Specification Standard - Site installation methodology IFC Drawings | Acceptance Criteria - Carefully position the handrails in the conjunction area according to the approved drawings. | Certify Doc / Ref - IFC DWGs | PFS Engineering - Team Leader | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - D | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | PFS Engineering - PM/PE
32 | Snug tightening of Conduti Brackets | Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Fasteners of handrails to be inspected for snug tight condition with addition of Loctite or Locknut to prevent loosening and marked with coloured paint pen to confirm fixing condtion has been checked and verified. Note: The connections for the EA's spanning the pier movement joints shall be hand tightened, Ref CAN 063. | Bolt Tightening report | Site project Manager | Initial: Sign: | H |  |  |  | 32 - Snug tightening of Conduti Brackets | Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Acceptance Criteria - Fasteners of handrails to be inspected for snug tight condition with addition of Loctite or Locknut to prevent loosening and marked with coloured paint pen to confirm fixing condtion has been checked and verified. Note: The connections for the EA's spanning the pier movement joints shall be hand tightened, Ref CAN 063. | Certify Doc / Ref - Bolt Tightening report | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | PFS Engineering: Sign - Initial: Sign:
33 | Installation of Expansion plates | Site installation methodology IFC Drawings | The expansion plates to be installed between Span 1 and 2 and between span 6 and 7 | IFC DWGs | Team Leader | Initial: Sign: | D |  |  |  | 33 - Installation of Expansion plates | Specification Standard - Site installation methodology IFC Drawings | Acceptance Criteria - The expansion plates to be installed between Span 1 and 2 and between span 6 and 7 | Certify Doc / Ref - IFC DWGs | PFS Engineering - Team Leader | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - D | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - | Downer: Sign - | Downer: C - | PFS Engineering: C - V
34 | Inspection to identify any damage to painted surfaceses requiring touchup |  | Inspect paint for any required repair and touch up of paint works (bolted connections and any damage paint to steelwork). Repair method proposed shall be approved by the independent coating inspector. Areas repaired shall be reinspected by the coating applicator and independent inspector. | Note 1.2, Drawing ST-3202 | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | H | 34 - Inspection to identify any damage to painted surfaceses requiring touchup | Specification Standard - | Acceptance Criteria - Inspect paint for any required repair and touch up of paint works (bolted connections and any damage paint to steelwork). Repair method proposed shall be approved by the independent coating inspector. Areas repaired shall be reinspected by the coating applicator and independent inspector. | Certify Doc / Ref - Note 1.2, Drawing ST-3202 | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - H | Subcontracted scope -
35 | Site Installation and Sign-off. | Erection sequence methodology (EMS) IFC Drawings | Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been completely installed. Inspection of erected steelwork in accordance with AS/NZS 5131 Section 13.11 as per specification C0702.1.10. Inspections shall cover all relevant items listed in clause 13.11.1. Inspections shall be documented in inspection reports as per clause 13.11.3 of AS/NZS5131, and included in the QA documentation. Inspections shall be conducted by competent personnel. Evidence of experience or qualifications for nominated individual(s) shall be provided for review. An example of qualification of competent personnel is a relevant trade qualification and over 10 years experience in structural steel erection. Following inspection on site, should any modification or repairs be required a written procedure shall be submitted to the Engineer prior to any work proceeding as per C0702.3. | IFC DWGs | Site project Manager | Initial: Sign: | H | Downer | Initial: Sign: | H | 35 - Site Installation and Sign-off. | Specification Standard - Erection sequence methodology (EMS) IFC Drawings | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been completely installed. Inspection of erected steelwork in accordance with AS/NZS 5131 Section 13.11 as per specification C0702.1.10. Inspections shall cover all relevant items listed in clause 13.11.1. Inspections shall be documented in inspection reports as per clause 13.11.3 of AS/NZS5131, and included in the QA documentation. Inspections shall be conducted by competent personnel. Evidence of experience or qualifications for nominated individual(s) shall be provided for review. An example of qualification of competent personnel is a relevant trade qualification and over 10 years experience in structural steel erection. Following inspection on site, should any modification or repairs be required a written procedure shall be submitted to the Engineer prior to any work proceeding as per C0702.3. | Certify Doc / Ref - IFC DWGs | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - H | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - H | Subcontracted scope: Sign -
36 | Compile, review and submit documentation | Project Structure Specification C07 Rev. 01 IFC structure DWG | Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | PFS Manufactures Data Report | Site project Manager | Initial: Sign: | S | Downer | Initial: Sign: | RA | 36 - Compile, review and submit documentation | Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report | Certify Doc / Ref - PFS Manufactures Data Report | PFS Engineering - Site project Manager | PFS Engineering: Sign - Initial: Sign: | PFS Engineering: C - S | Subcontracted scope - | Subcontracted scope: Sign - | Subcontracted scope: C - | Downer - Downer | Downer: Sign - Initial: Sign: | Downer: C - RA | Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
4 - Inspection upon receipt at site
Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
Certify Doc / Ref - IFC DWG
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
5 - Inspection upon receipt at site - Cast in Items.
Specification Standard - Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - The material receipt at site need to be visually inspected for quantity, make sure no damage occurred during transport. All related documents have been received.
Certify Doc / Ref - IFC DWG
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
6 - Preparation work- prior to Span Lifting for All Spans
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Make sure survey has been done and center marks on the framework as a reference have been provided by Downer Installation of 100x100 EA as a lifting aid on temporary structure Span unloaded from truck and placed on Dunnage on ground prior to rigging adjustment Attaching the tag lines to Spans to prevent rotation during installation
Certify Doc / Ref - Lift plan
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
7 - Confirm all Manufacture documentation has been completed for Span #2
Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
Certify Doc / Ref - QA Documentation
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
8 - Installation of Span#2
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Verify that the structural component is securely rigged according to the rigging plan To lift Span #2 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure Chain block will be connected to the West end to adjust level. when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
Certify Doc / Ref - Lift plan
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
9 - Macalloy Bars installation for Span #2
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - To keep Macalloy bar aligned, a coupler to be tightened to extend the Macalloy bar and Tempory nut will be added to the rod on the Span 2 high end. The nuts will be tightened to hold the Macalloy bars in correct position.
Certify Doc / Ref - IFC Drawing
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
10 - Confirm all Manufacture documentation has been completed for Span #3
Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
Certify Doc / Ref - QA Documentation
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
11 - Installation of Span#3
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #3 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
Certify Doc / Ref - Lift plan
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
12 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #3
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement.
Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
13 - Confirm all Manufacture documentation has been completed for Span #4
Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
Certify Doc / Ref - QA Documentation
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
14 - Installation of Span#4
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #4 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
Certify Doc / Ref - Lift plan
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
15 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #4
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement.
Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
16 - Confirm all Manufacture documentation has been completed for Span #5
Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
Certify Doc / Ref - QA Documentation
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
17 - Installation of Span#5
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #5 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
Certify Doc / Ref - Lift plan
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
18 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #5
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement.
Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
19 - Confirm all Manufacture documentation has been completed for Span #6
Specification Standard - Project Structure Specification C0702 Rev. 01
Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
Certify Doc / Ref - QA Documentation
PFS Engineering - PM/PE
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
20 - Installation of Span#6
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan To lift Span #6 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
Certify Doc / Ref - Lift plan
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
21 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #6
Specification Standard - Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG
Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Temporary Bearing installation under lower end Nuts on Reidbar to be snug tightened to help minimal lateral movement.
Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - R
22 - Dimensional survey By Downer
Specification Standard - Site installation methodology IFC Drawings
Acceptance Criteria - Conduct a thorough dimensinal survay inspection to confirm that the component is correctly positioned and secured based on IFC Drawing. Measured dimensions shall be within stated tolerances unless noted otherwise. Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10 Record the lifting operation in the project log, including any deviations or required adjustments to be made.
Certify Doc / Ref - Marked up and Signed IFC DWGs
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - H
23 - Remove Reid bar tension.
Specification Standard - Site installation methodology IFC Drawings
Acceptance Criteria - Lossen Reidbars to match IFC drawing detail at all peirs before any headstock pours.
Certify Doc / Ref - IFC DWGs
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - H
24 - Reid bar touch up painting (if required)
Specification Standard -
Acceptance Criteria - Any coatings damage to Reidbars touched up as per paint specification, Coatings to comply with note 1.2 on drawing ST-3202.
Certify Doc / Ref - Project Paint Specification
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - V
25 - Hold Down Bolts tightening
Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - Remove additional nuts, tape (masking and double sided) used for alignment. Apply rubber sleeves to the exposed threads. Reinstall oversized washers, apply instulating washers and tighten nuts down to achive a 1mm gap between washer and nut, lock nut to be installed as per detail C CHAR(AMP) Section 5 on ST-3202, Detail D on ST-3200.
Certify Doc / Ref - Bolt Tightening report
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
26 - Macalloy Bolts tightening
Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - to Undo the coupler, remove temporary alignment nut, install the rubber sleeves to the exposed rod, install the washers, nuts and snug tighten the nuts (as there are compressible components in contanc area)
Certify Doc / Ref - Bolt Tightening report
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
27 - Temporary restraints removal
Specification Standard - Site installation methodology IFC Drawings
Acceptance Criteria - All temporary restraints to the temporary shoring to be removed All positioning Jigs and screws applied to PTFE on Shear Keys to be removed
Certify Doc / Ref - -
PFS Engineering - Team Leader
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - V
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
28 - Installation of Granor Bearing
Specification Standard - Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - The Temporary Bearing to be removed and Granor Bearing to be installed in the position the Bolts need to be snug tightened to the girders (top) and screws need to be snug tightened into the base plate. The keeper plates' bolts (M20) for uplift restraint to be tightened (full Tensioned).
Certify Doc / Ref - Bolt Tightening report
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
29 - Installation of remaining Decking panels and wall panels
Specification Standard - Site installation methodology IFC Drawings
Acceptance Criteria - Carefully position the Decking and wall panels in the conjunction area according to the approved drawings.
Certify Doc / Ref - IFC DWGs
PFS Engineering - Team Leader
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - D
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
30 - Snug tightening of Decking panels and wall panels
Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - Fasteners of Decking and wall panels to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
Certify Doc / Ref - Bolt Tightening report
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
31 - Installation of remaining handrails between the spans
Specification Standard - Site installation methodology IFC Drawings
Acceptance Criteria - Carefully position the handrails in the conjunction area according to the approved drawings.
Certify Doc / Ref - IFC DWGs
PFS Engineering - Team Leader
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - D
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
32 - Snug tightening of Conduti Brackets
Specification Standard - Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038
Acceptance Criteria - Fasteners of handrails to be inspected for snug tight condition with addition of Loctite or Locknut to prevent loosening and marked with coloured paint pen to confirm fixing condtion has been checked and verified. Note: The connections for the EA's spanning the pier movement joints shall be hand tightened, Ref CAN 063.
Certify Doc / Ref - Bolt Tightening report
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
33 - Installation of Expansion plates
Specification Standard - Site installation methodology IFC Drawings
Acceptance Criteria - The expansion plates to be installed between Span 1 and 2 and between span 6 and 7
Certify Doc / Ref - IFC DWGs
PFS Engineering - Team Leader
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - D
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer -
Downer: Sign -
Downer: C -
34 - Inspection to identify any damage to painted surfaceses requiring touchup
Specification Standard -
Acceptance Criteria - Inspect paint for any required repair and touch up of paint works (bolted connections and any damage paint to steelwork). Repair method proposed shall be approved by the independent coating inspector. Areas repaired shall be reinspected by the coating applicator and independent inspector.
Certify Doc / Ref - Note 1.2, Drawing ST-3202
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - H
35 - Site Installation and Sign-off.
Specification Standard - Erection sequence methodology (EMS) IFC Drawings
Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been completely installed. Inspection of erected steelwork in accordance with AS/NZS 5131 Section 13.11 as per specification C0702.1.10. Inspections shall cover all relevant items listed in clause 13.11.1. Inspections shall be documented in inspection reports as per clause 13.11.3 of AS/NZS5131, and included in the QA documentation. Inspections shall be conducted by competent personnel. Evidence of experience or qualifications for nominated individual(s) shall be provided for review. An example of qualification of competent personnel is a relevant trade qualification and over 10 years experience in structural steel erection. Following inspection on site, should any modification or repairs be required a written procedure shall be submitted to the Engineer prior to any work proceeding as per C0702.3.
Certify Doc / Ref - IFC DWGs
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - H
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - H
36 - Compile, review and submit documentation
Specification Standard - Project Structure Specification C07 Rev. 01 IFC structure DWG
Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
Certify Doc / Ref - PFS Manufactures Data Report
PFS Engineering - Site project Manager
PFS Engineering: Sign - Initial: Sign:
PFS Engineering: C - S
Subcontracted scope -
Subcontracted scope: Sign -
Subcontracted scope: C -
Downer - Downer
Downer: Sign - Initial: Sign:
Downer: C - RA