## Sheet1
1 | QAE | Lot Identification | IFC Drawings Lot Register | ITP | N/A | Location of works identified in accordance with the project drawings and specification. | Lot Register | H | H | W | 1 - Lot Identification | Resp. - QAE | References - IFC Drawings Lot Register | Test Method - ITP | Test Freq. - N/A | Acceptance Criteria - Location of works identified in accordance with the project drawings and specification. | Evidence Form - Lot Register | CQA - H | McCosker Representative - H | GRC Representative - W | 1 - Lot Identification
2 | MNR | Identification of any services and structure | Technical Specification Section 2.3, Section 3.5.3 | Review | N/A | The contractor shall identify any services within the work area and shall erect and maintain temporary barriers and boarding’s etc to protect the services and structure during construction. | Inspect / ITP | R | R | W | 2 - Identification of any services and structure | Resp. - MNR | References - Technical Specification Section 2.3, Section 3.5.3 | Test Method - Review | Test Freq. - N/A | Acceptance Criteria - The contractor shall identify any services within the work area and shall erect and maintain temporary barriers and boarding’s etc to protect the services and structure during construction. | Evidence Form - Inspect / ITP | CQA - R | McCosker Representative - R | GRC Representative - W | Resp. - QAE
3 | MNR | Spoil Stockpile area | Technical Specification- Section 3.5.1 | Visual | N/A | Unsuitable, surplus material, Contaminated excavated material and legacy waste shall be spoiled to locations directed by the Superintendent with all waste material sent offsite to be documented and tracked as required by state regulations. | Inspect / ITP | S | R | R | 3 - Spoil Stockpile area | Resp. - MNR | References - Technical Specification- Section 3.5.1 | Test Method - Visual | Test Freq. - N/A | Acceptance Criteria - Unsuitable, surplus material, Contaminated excavated material and legacy waste shall be spoiled to locations directed by the Superintendent with all waste material sent offsite to be documented and tracked as required by state regulations. | Evidence Form - Inspect / ITP | CQA - S | McCosker Representative - R | GRC Representative - R | References - IFC Drawings Lot Register
4 | MNR | Ground Stability | Specifications Section:3.5.3 | Visual | N/A | The stability of the ground to be excavated shall be confirmed prior to construction commencing. All work methods shall be carried out to the satisfaction of the Superintendent. | Inspect / ITP | S | W | W | 4 - Ground Stability | Resp. - MNR | References - Specifications Section:3.5.3 | Test Method - Visual | Test Freq. - N/A | Acceptance Criteria - The stability of the ground to be excavated shall be confirmed prior to construction commencing. All work methods shall be carried out to the satisfaction of the Superintendent. | Evidence Form - Inspect / ITP | CQA - S | McCosker Representative - W | GRC Representative - W | Test Method - ITP
5 | SUP | Excavation | Specifications Section:3.5.2 IFC Drawings | Visual | N/A | Any loose soft spots or loose materials shall be excavated and spoiled to the approved stockpile area. The floors and sides of excavations shall be trimmed to the lines, levels, grades and batters shown on the Drawings and within the tolerances specified. | Inspect / ITP | S | W | W | 5 - Excavation | Resp. - SUP | References - Specifications Section:3.5.2 IFC Drawings | Test Method - Visual | Test Freq. - N/A | Acceptance Criteria - Any loose soft spots or loose materials shall be excavated and spoiled to the approved stockpile area. The floors and sides of excavations shall be trimmed to the lines, levels, grades and batters shown on the Drawings and within the tolerances specified. | Evidence Form - Inspect / ITP | CQA - S | McCosker Representative - W | GRC Representative - W | Test Freq. - N/A
6 | Sup | Dewatering of Excavation | Technical Specification- Section 3.4 and 3.5.4 | Review | N/A | Excavations shall always be drained. If, during excavation, natural ground water is encountered, the Contractor shall immediately notify the Superintendent and shall ensure that relevant water quality sampling and testing is undertaken to demonstrate suitability of this release. If required, de-watering shall be carried out in a safe and efficient manner and in accordance with the Site licence requirements and approved management plans. The point of surface water release will be to existing receptors or to a site determined by the principal. | Inspect / ITP | S | W | W | 6 - Dewatering of Excavation | Resp. - Sup | References - Technical Specification- Section 3.4 and 3.5.4 | Test Method - Review | Test Freq. - N/A | Acceptance Criteria - Excavations shall always be drained. If, during excavation, natural ground water is encountered, the Contractor shall immediately notify the Superintendent and shall ensure that relevant water quality sampling and testing is undertaken to demonstrate suitability of this release. If required, de-watering shall be carried out in a safe and efficient manner and in accordance with the Site licence requirements and approved management plans. The point of surface water release will be to existing receptors or to a site determined by the principal. | Evidence Form - Inspect / ITP | CQA - S | McCosker Representative - W | GRC Representative - W | Acceptance Criteria - Location of works identified in accordance with the project drawings and specification.
7 | QAE | Lot Close Out | ITP / Lot Register | Review | N/A | Lot close out, Material Compliance Checked, NCR’s Closed. | Lot Register | R | R | R | 7 - Lot Close Out | Resp. - QAE | References - ITP / Lot Register | Test Method - Review | Test Freq. - N/A | Acceptance Criteria - Lot close out, Material Compliance Checked, NCR’s Closed. | Evidence Form - Lot Register | CQA - R | McCosker Representative - R | GRC Representative - R | Evidence Form - Lot Register
CQA - H
McCosker Representative - H
GRC Representative - W
2 - Identification of any services and structure
Resp. - MNR
References - Technical Specification Section 2.3, Section 3.5.3
Test Method - Review
Test Freq. - N/A
Acceptance Criteria - The contractor shall identify any services within the work area and shall erect and maintain temporary barriers and boarding’s etc to protect the services and structure during construction.
Evidence Form - Inspect / ITP
CQA - R
McCosker Representative - R
GRC Representative - W
3 - Spoil Stockpile area
Resp. - MNR
References - Technical Specification- Section 3.5.1
Test Method - Visual
Test Freq. - N/A
Acceptance Criteria - Unsuitable, surplus material, Contaminated excavated material and legacy waste shall be spoiled to locations directed by the Superintendent with all waste material sent offsite to be documented and tracked as required by state regulations.
Evidence Form - Inspect / ITP
CQA - S
McCosker Representative - R
GRC Representative - R
4 - Ground Stability
Resp. - MNR
References - Specifications Section:3.5.3
Test Method - Visual
Test Freq. - N/A
Acceptance Criteria - The stability of the ground to be excavated shall be confirmed prior to construction commencing. All work methods shall be carried out to the satisfaction of the Superintendent.
Evidence Form - Inspect / ITP
CQA - S
McCosker Representative - W
GRC Representative - W
5 - Excavation
Resp. - SUP
References - Specifications Section:3.5.2 IFC Drawings
Test Method - Visual
Test Freq. - N/A
Acceptance Criteria - Any loose soft spots or loose materials shall be excavated and spoiled to the approved stockpile area. The floors and sides of excavations shall be trimmed to the lines, levels, grades and batters shown on the Drawings and within the tolerances specified.
Evidence Form - Inspect / ITP
CQA - S
McCosker Representative - W
GRC Representative - W
6 - Dewatering of Excavation
Resp. - Sup
References - Technical Specification- Section 3.4 and 3.5.4
Test Method - Review
Test Freq. - N/A
Acceptance Criteria - Excavations shall always be drained. If, during excavation, natural ground water is encountered, the Contractor shall immediately notify the Superintendent and shall ensure that relevant water quality sampling and testing is undertaken to demonstrate suitability of this release. If required, de-watering shall be carried out in a safe and efficient manner and in accordance with the Site licence requirements and approved management plans. The point of surface water release will be to existing receptors or to a site determined by the principal.
Evidence Form - Inspect / ITP
CQA - S
McCosker Representative - W
GRC Representative - W
7 - Lot Close Out
Resp. - QAE
References - ITP / Lot Register
Test Method - Review
Test Freq. - N/A
Acceptance Criteria - Lot close out, Material Compliance Checked, NCR’s Closed.
Evidence Form - Lot Register
CQA - R
McCosker Representative - R
GRC Representative - R