## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Tasman District Council Culvert Renewals |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 6698xx |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Alliance |  |  |  |  | B | Report by Breach | CM | Construction Manager
Contract Number: | [5 empty] | C | Check | CR | Cust. Representative
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Tasman District Council Culvert Renewals, all work areas |  |  |  |  | I | Inspection | PM | Project Manager
Discipline: | Civil Construction |  |  |  |  | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | [5 empty] | O | Operation | QE | Quality Engineer
[6 empty] | R | Review | QM | QA Manager
Drawings: | [5 empty] | S | Subcontractor | SP | Supervisor
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Tyler Peppin |  | Date: | 2023-08-12 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1 | Service Locates |  | Services located by Chorus and Delta prior to wokrs commencing | Photos | Once for each work location | Verification |  | Downer
2 | Temporary Traffic Management | Temporary Traffic Management to be set up on site prior to any works commencing | Temporary Traffic Management set up by qualified STMS according to approved plans | Approved TM Plan | Daily | Verification |  | Downer
3 | Culvert Bedding | Scalas to be done on subgrade | If scala test results lower than 3, add 100mm of compacted AP65 | Photos, Field testing document | One lot of tests for each work location | Hold Point |  | Downer
4 | AP65 Backfill | Clegg testing to be done on backfill | Clegg Impact Value to be greater than 25 | Photos, Field testing document | Every 150mm lift | Hold Point |  | Downer
5 | AP40 Backfill | Clegg testing to be done on backfill | Clegg Impact Value to be greater than 35 | Photos, Field testing document | Every 150mm lift | Hold Point |  | Downer
6 | Pavement Strength | Clegg testing to be done on Pavement | Clegg Impact Value to be greater than 35 | Photos, Field testing document | One lot of tests for each work location | Hold Point |  | Downer
7 | Alignment | 3 metre straight edge | Maximum 10mm | Visual | One lot of tests for each work location | Verification |  | Downer

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: