## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp |  |  |  |  | DG-QA-TP018 Inspection and Test Plan (ITP) | 45f2bc5c-246a-49b0-923f-48e53609874b
section | 1. Receiving Inspection
checkpoint | 1.1 - Service Locates
label | Acceptance Criteria - Services located by Chorus and Delta prior to wokrs commencing
label | Verifying Document - Photos
label | Frequency - Once for each work location
label | Inspection Type (Visual, other) - Verification
label | Inspection: By (Role Key) - Downer
checkpoint | 1.2 - Temporary Traffic Management
label | Inspection Point: Quality Control Activity - Temporary Traffic Management to be set up on site prior to any works commencing
label | Acceptance Criteria - Temporary Traffic Management set up by qualified STMS according to approved plans
label | Verifying Document - Approved TM Plan
label | Frequency - Daily
label | Inspection Type (Visual, other) - Verification
label | Inspection: By (Role Key) - Downer
checkpoint | 1.3 - Culvert Bedding
label | Inspection Point: Quality Control Activity - Scalas to be done on subgrade
label | Acceptance Criteria - If scala test results lower than 3, add 100mm of compacted AP65
label | Verifying Document - Photos, Field testing document
label | Frequency - One lot of tests for each work location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - AP65 Backfill
label | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | Acceptance Criteria - Clegg Impact Value to be greater than 25
label | Verifying Document - Photos, Field testing document
label | Frequency - Every 150mm lift
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - AP40 Backfill
label | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | Verifying Document - Photos, Field testing document
label | Frequency - Every 150mm lift
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Pavement Strength
label | Inspection Point: Quality Control Activity - Clegg testing to be done on Pavement
label | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | Verifying Document - Photos, Field testing document
label | Frequency - One lot of tests for each work location
label | Inspection Type (Visual, other) - Hold Point
label | Inspection: By (Role Key) - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Alignment
label | Inspection Point: Quality Control Activity - 3 metre straight edge
label | Acceptance Criteria - Maximum 10mm
label | Verifying Document - Visual
label | Frequency - One lot of tests for each work location
label | Inspection Type (Visual, other) - Verification
label | Inspection: By (Role Key) - Downer