## sheet 1
ConQA Team Notes:
Document Title: |  | FHC-ITP-030 - DDA Compliant Hand Railing (Supply & Installation)
ITP Description: |  | DDA Compliant Hand Railing (Supply & Installation)
Discipline (e.g. CIV/STR/RAIL:
Revision Number: |  | 00
Revision Date: |  | 4.09.02025
ITP created by: |  | Mike Freeman
ITP approved for use by:
Special Notes to ConQA Team :
Inspection & Test Plan - DDA Compliant Hand Railing (Supply & Installation)
|  |  | Document No.: | ITP-030 |  |  |  |  | Revision: | 00
|  |  | Specification: | AS1428.1 - Design for Access & Mobility, General Requirements (2021) |  |  |  |  | Date: | 4.09.02025
|  |  | Other Referenced Documentation: | AS1428.2 - Design for Access & Mobility, Enhanced Requirements (1992)
AS4100 - Steel Structures (2020)
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Preliminaries
1.1 | Railing Components - Proprietary System | IFC Drawings Manufacturer's Drawings & Installation Recommendations Fulton Hogan Quality Management Plan | Where applicable, product to be selected based on the following criteria: i. Certified or nominated as compliant to AS1428.1 ii. Able to be erected with top of hand rail between 865mm (min.) & 1000mm (max.) iii. Extend beyond landings with rounded end or closed loop by 300mm (min.) iv. Able to withstand the load conditions (where specified) v. Have a protective coating that aligns with the atmosphere it will be erected in Details of the nominated proprietary system to be submitted for review to the Superintendent. Enter: Teambinder Material Approval number [free text box] | Document Review | Each component | IP | PE/SE/SPE | This ITP
1.2 | Railing Components - Fabricated System | IFC Drawings Fulton Hogan Quality Management Plan | Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but is not limited to: i. Certificate of Compliance ii. Completed ITP iii. Weld Procedure Specifications iv. Weld Procedure Qualifications v. Welder Qualifications vi. Material Certificates and traceability vii. Quality Assurance check sheets viii. Welding Consumable batch certificates ix. Coating certificate(s) x. Non-destructive Testing (NDT) Reports xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel Collate: Structural Steel Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) | Document Review | Each component | IP | PE/SE/SPE | This ITP
1 | Preliminaries (Continued)
1.3 | Fixing Detail | IFC Drawings Manufacturer's Drawings & Installation Recommendations | Fixing detail to be either positive connection via cast-in ferrules or similar. Changes to the approved Drawings shall be accompanied with a PE Certificate. Enter: Teambinder Approval number [free text box] or Attach: PE Certificate of Compliance | Document Review | Each component | IP | PE/SE/SPE | This ITP
2 | Pre-installation Activities
2.1 | IFC Drawings | Fulton Hogan Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
2.2 | Materials Inspection Checklist | IFC Drawings Fulton Hogan Quality Management Plan | General inspection of railing components for defects including cracks, handling and storage damage & distortion. Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each component | IP | SE/PE/SPE | This ITP
3 | Installation Activities
3.1 | Bearing / Mounting Surface Preparation | Manufacturer's Drawings & Installation Recommendations | As a minimum, ensure that the bearing surface is clean and free from loose particles and laitance. | Visual | Each post location | IP | SE/PE/SPE | This ITP
3.2 | Railing Handling | Manufacturer's Drawings & Installation Recommendations | The method of handling and erection of the railing shall ensure that the components are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings. | Visual | Each component | IP | SE/PE/SPE | This ITP
3.3 | Railing Erection | Manufacturer's Drawings & Installation Recommendations AS4100, Clause 15.2 AS4100, Clause 15.3 | Place raill component into position, ensuring that it is plumb, level, square and within tolerances shown on the IFC drawings or Manufacturer's Drawings and installation recommendations. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely. Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia | Measure Visual | Each component | IP | SE/PE/SPE | This ITP
3 | Installation Activities (Continued)
3.4 | Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S) | IFC Drawings Manufacturer's Drawings & Installation Recommendations AS4100, Clause 14.3.3.1 | Place bolts, washers and nuts as detailed on the drawings. At least 1 no. washer shall be used underneath the rotating part unless this is not part of the hand rail system. Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread pitch and any thread run-off beyond the nut. Note: No maximum projection length is stated in the Australian Standards. | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP
4 | Post-installation Activities
4.1 | Inspection of Coating | IFC Drawings Manufacturer's Drawings & Installation Recommendations | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure. | Visual | Each component | IP | SE/PE/SPE | This ITP
4.2 | As-built Survey | IFC Drawings Manufacturer's Drawings & Installation Recommendations Fulton Hogan Quality Management Plan | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: i. Top railing height = 865mm (min.) &1000mm (max.) ii. Rounded end o closed loop = extend beyond landings 300mm (min.) Attach: Survey As-builts / Survey Report / Photos | Document Review | Each component | IP | Surveyor SE/PE/SPE | This ITP
4.3 | Non-conformance Report (NCR) Closure | Fulton Hogan Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /