## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
b68fa053-63b4-4ecb-9753-4feb74b44a79 | checklist | ITP - Rock Fill - Sassafras Rev0 | itp | ITP - Rock Fill - Sassafras
134160b1-017f-480f-8c50-f89d28b37ff1 | section | 1 - Preliminaries and Submissions
ca703c6f-0893-4968-9f29-bd35d62f4748 | checkpoint | 1.1 - Check for correct documentation
0d74b5c6-1621-5d08-be0a-034aecfaabfb | note | FREQUENCY: Before commencement of activity
626ab84f-ff58-53c1-b025-4fe92a04df91 | note | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
ab3dc480-fd20-5e57-aa29-c6250aa978a6 | note | REFERENCE DOCUMENTS: Drawings
aa4d2fb7-468f-502a-b0ec-5da0727f0e44 | note | INSPECTION/TEST METHOD: Current revision of drawing
816ac3f8-e259-59b9-b13a-4f0f3586943c | note | CONFORMANCE RECORD: Current revision of drawing
27fe8dea-2154-5106-bf78-d8d501b5829f | note | *HP
d57f9535-0269-5f34-ab11-f1c791d9256b | note | RESPONSIBILITY: Fulton Hogan
e45e4e3c-21cb-5137-b7c7-2190b9fa6284 | date | Date Completed:
529b009d-f028-4546-b6c4-0fa2fc9f529b | checkpoint | 1.2 - Ensure Safety, Traffic, Quality & Environmental management measures are in place
ff6f5fb0-f0a6-5efc-a325-396dcff92da3 | note | FREQUENCY: Prior to commencement of activity.
7273cea8-63ba-5d61-8f83-503658155f0a | note | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
8d6c00cb-bdeb-5440-9439-9c40e73a5efb | note | REFERENCE DOCUMENTS: PSP, TMP, EMP
12aaab1e-399e-5927-a21a-6a14ef920a00 | note | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
64e5304f-f764-55ea-987e-4ff6bd07c7ac | note | CONFORMANCE RECORD: Inspection
95d56037-851c-5cf6-8406-adc7a820ef9f | note | HP
66190dfd-373c-53b5-a079-25f3732cab6b | note | RESPONSIBILITY: Fulton Hogan/Client
ceb62acb-3edc-5bcd-ae07-9bbb1d736d21 | date | Date Completed:
44096daf-9a18-4e17-a53d-6768ea8d46da | signoff | AUTHORITY HOLDPOINT
908af7e8-0d70-4c26-b6fd-2c68a09fa03c | checkpoint | 1.3 - Stockpiling
bb1adbbd-04a6-5236-bd91-0eaf6eb841a8 | note | FREQUENCY: Prior to removing material
1ac8f0d3-776d-5947-becc-0a02194398dd | note | ACCEPTANCE CRITERIA: Confirmation of stockpile location approved by superintendent.
597f7a1d-7841-5a48-8f93-228dc8250d13 | note | REFERENCE DOCUMENTS: FH Scope document, EMP
b57c60b1-99da-5a37-8bf4-822af74b190f | note | INSPECTION/TEST METHOD: Approval
a34e5c1a-453c-5136-825a-0d2bd6b4ca86 | note | CONFORMANCE RECORD: ITP
ea687d6b-d15c-5175-8f7a-4ae304569446 | note | WP
ef351593-33d1-5c19-8e6a-f0e62e52c359 | note | RESPONSIBILITY: Client/ Fulton Hogan
94ba1864-3bea-5204-9c1d-80f835fafbde | date | Date Completed:
5f217546-6a4d-45cb-92cc-d6b84e9ac6ee | checkpoint | 1.4 - Identification of services
8873f132-abc8-5c9b-a965-504fcfb3fe63 | note | FREQUENCY: Prior to commencement
7655256e-3c85-5a47-8c32-6509388dcff5 | note | ACCEPTANCE CRITERIA: Any existence of underground services to be located and proven
e268859c-b371-52c3-ba04-55ab26c89593 | note | REFERENCE DOCUMENTS: BYDA Section 100.8
06d7ebbe-8b5c-5ad1-8abe-529c74e6fe93 | note | INSPECTION/TEST METHOD: Inspection
5eab4cc4-6151-542f-ab90-2eeaaf5ca063 | note | CONFORMANCE RECORD: ITP
db56e8a4-8611-53e6-9e85-e4361317d47a | note | HP
938b8843-969f-59b7-abad-3224a06acc55 | note | RESPONSIBILITY: Fulton Hogan
fba998e3-c462-585c-bfbf-7e00311621a8 | date | Date Completed:
09bb826c-aef6-4827-b16b-a3e09206991b | signoff | AUTHORITY HOLDPOINT
7314d267-e555-4b4a-a4a5-84936a881390 | checkpoint | 1.5 - Project management Plan Completed
bb5b6e31-cc41-55ab-b497-c446e8b77e5c | note | FREQUENCY: Prior to commencement
a8f4282a-19d9-52e3-815a-9b1de4632186 | note | ACCEPTANCE CRITERIA: PMP Completed
c691274b-5e24-55df-b7f1-e33aba715cd4 | note | REFERENCE DOCUMENTS: PMP checklist completed
5637211a-a6f2-54c2-bb78-79245f755926 | note | INSPECTION/TEST METHOD: Inspection
60e3cda9-af9a-5bbd-a568-7d64936c94e3 | note | CONFORMANCE RECORD: ITP
59585d91-7957-517c-9105-1a2e1c273e2b | note | HP
dd31ff56-e8fe-5809-87eb-6ed763e2b470 | note | RESPONSIBILITY: Fulton Hogan/Client
54659d37-78e8-5ed6-95fb-7c1d38da0ff6 | date | Date Completed:
9bfd35ab-b74d-45a3-a8ff-ee0145d497d3 | signoff | AUTHORITY HOLDPOINT
851eccad-918f-45e3-bbc0-f5d22b78dc38 | checkpoint | 1.6 - Site set out
c9ff69e5-2f73-5a2c-b60e-a353f7afa6ab | note | FREQUENCY: Prior to commencement
73469628-bc81-5ce7-9526-fb33f22ec4df | note | ACCEPTANCE CRITERIA: Site inspection
24e27e70-973a-52cf-975b-16f4a0f8f317 | note | REFERENCE DOCUMENTS: Drawings
3dd3215d-afd8-5d16-8bea-0ba8ba1d05dd | note | INSPECTION/TEST METHOD: Site inspection
112b601f-e227-5b48-bc19-b0f1363cbf93 | note | CONFORMANCE RECORD: ITP
7389d168-1fee-5558-97c8-18204f3733fe | note | HP
e99d1e0d-d4eb-57f4-995f-b8cf55450d02 | note | RESPONSIBILITY: Client/ Fulton Hogan
7012fd4a-2a70-53cf-ac07-7b7bcb51ad2a | date | Date Completed:
e32d2643-e922-47c6-b7c8-5ca606aa59b9 | signoff | AUTHORITY HOLDPOINT
42a8e970-4e9b-4ff4-b89f-447bc6f9d9a4 | checkpoint | 1.7 - Ground breaking
93eb5d19-9545-5a26-bcc8-8aa339f44e7c | note | FREQUENCY: Prior to excavation
d9bafd7f-a6e5-5033-952e-1b2cf16d7266 | note | ACCEPTANCE CRITERIA: Works to be reviewed and agreed by Superintendent
cb9ef008-b930-5594-8072-ba647af3f2f6 | note | REFERENCE DOCUMENTS: Hold Point release for Commenceme nt of Works Letter
3bed9f96-17bf-58fa-b935-2b5b35ab8681 | note | INSPECTION/TEST METHOD: Inspection
374c68d3-204a-5ed2-9afe-daa49ec5762a | note | CONFORMANCE RECORD: ITP
b772aaab-cb4a-5b90-b21d-2bf020f70742 | note | HP
625cac75-12cb-5f65-b4bf-04666e5200b0 | note | RESPONSIBILITY: Client
22dfdb54-0614-55b0-b4fb-d816f4b08498 | date | Date Completed:
6c9cd492-4e8a-4af0-a845-82f1b3da0732 | signoff | AUTHORITY HOLDPOINT
cc48366a-f3cc-4322-b447-a3161e836f4a | checkpoint | 1.9 - Environmental controls
c2077251-6c8f-566c-82ae-bb95f932a7a4 | note | FREQUENCY: Prior to commencement
674d098d-1ab7-5b80-b47d-a19c6fa0778b | note | ACCEPTANCE CRITERIA: Environmental controls installed and maintained as per EMP
6b6ff728-c0cd-5858-8501-18c6032815ec | note | REFERENCE DOCUMENTS: EMP
916b8611-fef2-59fa-8fb0-5311657fcaf3 | note | INSPECTION/TEST METHOD: Inspection
721d6e37-1af3-55bd-a740-293ade7a4034 | note | CONFORMANCE RECORD: ITP
db0df8dc-5a4d-5e76-9a86-53dc1e6add61 | note | HP*
5d1eb350-819b-56a7-894b-d7f78a06a842 | note | RESPONSIBILITY: Fulton Hogan
5b8c1955-f2cf-57cc-a1f5-6cc53e655bce | date | Date Completed:
fc2790f2-f0f9-4330-86ce-174551b9cb62 | section | 2 - Drainage/Rock Fill/Type A select fill
29df2cf3-0737-413c-94a0-f3ca34728992 | checkpoint | 2.01 - Control of water through site
9fa9f479-c033-5caf-9a69-01be3a93f2c6 | note | FREQUENCY: Prior to excavation of toe
9c248d09-1b3e-5ba4-bf70-f63528348478 | note | ACCEPTANCE CRITERIA: Diversion to be agreed by Superintendent
b99ceddc-2bd7-5af5-85e1-aa270e53cc9b | note | REFERENCE DOCUMENTS: Environmental Management plan
d8aba333-9486-53f3-923c-487d1ecb00ae | note | INSPECTION/TEST METHOD: Site inspection
9d4647f0-4db8-5bf1-a40a-a99e5c9bbcdb | note | CONFORMANCE RECORD: ITP
37db38cd-ee5d-5a44-a987-20c5b19caabd | note | IP
b71a492e-9572-536f-8b99-6b81bb00a9d7 | note | RESPONSIBILITY: Client and Fulton Hogan
7a8beaeb-8658-5e4e-aa5e-d20c452e1786 | date | Date Completed:
2d14b8c2-f7cf-457b-94c2-6cdff8d731c9 | checkpoint | 2.02 - Rock Fill Material
2a03ff3a-1446-523f-ba23-704e7aeb9e7c | note | FREQUENCY: Prior to placement
71eaf7dd-b43d-5e3b-8a35-2fb59c4baa7c | note | ACCEPTANCE CRITERIA: Rock fill to be suitable and size and approved
40c8eabd-baea-5566-966d-803d4c62f1d8 | note | REFERENCE DOCUMENTS: Drawings
3a186b99-ede1-56d9-9e91-1a795ecbb8fc | note | INSPECTION/TEST METHOD: Inspection
26f5244d-f5ce-510e-95b8-87696faba52c | note | CONFORMANCE RECORD: ITP
420b0ea8-e6fb-5559-bb89-141e8f642036 | note | WP
5f678cd2-eca9-5e9d-9755-5ad8615a44bd | note | RESPONSIBILITY: Fulton Hogan/Client
ea2f4475-cabb-5f91-b4ce-baf8db0b4087 | date | Date Completed:
80c3d2de-90cc-4a6f-8d48-ed81aa3fe538 | checkpoint | 2.03 - Site Benching/ Staging
9a956921-d02c-579a-91da-c66ed5791d50 | note | FREQUENCY: Prior to commencement
033f4370-3e57-545c-aae5-59048c8d125c | note | ACCEPTANCE CRITERIA: Site benching confirmed with site supervisor
3cf2c8e8-628c-5140-bbf2-9162d29961c1 | note | ○ Meets the bench sloping of 1:1
6eb9f436-5def-5496-bdf5-f3e81f405efe | note | ○ Rock needs to be installed in stages to ensure that the structure will not be compromise in flood
3edb7e3e-f6de-53f2-86e2-a11e32b0a768 | note | REFERENCE DOCUMENTS: Drawings
0c0c77ca-4fed-5460-bb84-418f38de4f08 | note | INSPECTION/TEST METHOD: Inspection
0f0e3404-bcfb-5837-af17-203d5acb8621 | note | CONFORMANCE RECORD: ITP
d2a27597-de28-5c2b-bb63-1e4bbd2d1958 | note | IP
b1e94d66-2dbf-5f5e-a98e-2f64f49c4d4c | note | RESPONSIBILITY: Fulton Hogan
1398078f-d9ae-5b79-8420-45f73935cef2 | date | Date Completed:
6a5c18c5-0b15-4464-b01b-f4089dc0a3fb | checkpoint | 2.04 - Base of Excavation
a39f829e-cbe3-5a5c-8764-03b44592fcf4 | note | FREQUENCY: Post benching access
7ce8cf6c-c982-5664-b6a1-6a4c838b945d | note | ACCEPTANCE CRITERIA: Geotextile layer at excavated surface and on top of rock
45669920-1b23-5286-b03c-48ad33f09e21 | note | REFERENCE DOCUMENTS: Section 200.10
76708ec2-d461-57dc-babe-d21eb159891b | note | INSPECTION/TEST METHOD: Inspection
f79b8323-57c9-5f3e-b5e0-31b826e710b2 | note | CONFORMANCE RECORD: ITP
131c8dc5-e623-5907-8c08-9eb1d0181c54 | note | HP*
7aeea46f-3e48-5cff-bab3-36121ab21041 | note | RESPONSIBILITY: Fulton Hogan
484a5913-ab76-5921-be4f-317b681bda7b | date | Date Completed:
e9cf6e5f-07a5-4e1b-96a9-e47b410e4a88 | checkpoint | 2.05 - Base for Toe rock and machine
dd5dc8c8-0615-5a7b-94ea-f8929a790d3b | note | FREQUENCY: Once ramp and benching is completed
5383676d-af5f-5857-aeb5-b098a7f2f50c | note | ACCEPTANCE CRITERIA: Solid base visually confirmed
19c43cd9-9b52-5e0a-8ec5-ea5842ccc202 | note | REFERENCE DOCUMENTS: N/A
daa2df95-cb8d-529b-91f2-038a06f2b0f0 | note | INSPECTION/TEST METHOD: Inspection
c0b53987-fe42-5cea-8c25-b293fddfcffa | note | CONFORMANCE RECORD: ITP
c5c65e1f-94df-53e1-b348-0d6903e1046b | note | HP*
42eb14ee-cd30-52ae-a30b-37a4570e2940 | note | RESPONSIBILITY: DTP
239a2a23-4224-5a9a-adcf-52605123053a | date | Date Completed:
a405bf4f-4ab4-41d7-a33b-cbaaece5f654 | checkpoint | 2.06 - Base Rock Placement
061719c1-404c-5e72-9eb3-59b448e46379 | note | FREQUENCY: During the placement of the toe rock
b7af33ed-14d9-5476-9a9c-25bfaff624b9 | note | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 500mm
f753f487-b49b-5cee-aed3-dff4c6ab2944 | note | REFERENCE DOCUMENTS: N/A
6af7cbb6-c4af-5fcf-b5fe-41c009576b0c | note | INSPECTION/TEST METHOD: Inspection
ddf7bb8a-7dd2-5ba2-ab29-75c81bb00325 | note | CONFORMANCE RECORD: ITP
d819e679-3f49-5a39-98de-ab5f3b3856d1 | note | IP
37a6945e-77d1-52d5-9535-6fad056a842a | note | RESPONSIBILITY: Client/ Fulton Hogan
06769718-f400-538b-8686-b078d3f2c782 | date | Date Completed:
a43a0086-b9dd-4b1a-a951-25295578157c | checkpoint | 2.07 - Treatment for works between the bridge abutment
0e2d9a21-edf2-5bf9-ac33-70d5a030c6df | note | FREQUENCY: At the completion of the rockwork
6a85d129-d8a7-5bed-b54d-270729b9ab8f | note | ACCEPTANCE CRITERIA: Agreement on the scope to repair above the rock beaching
0f3b5c3b-3946-55eb-bf4a-785e288bcf6a | note | REFERENCE DOCUMENTS: Drawings
7e079d4b-1a9d-5d7c-95c9-e7319e825a70 | note | INSPECTION/TEST METHOD: Inspection
cf58cf84-bdd0-54eb-9c49-3caf57643b17 | note | CONFORMANCE RECORD: ITP
6770474f-e6d2-5d2d-ad57-d80d473f792c | note | Hold Point
21fbef68-d8b6-5ecf-84e3-a784b3acad23 | note | RESPONSIBILITY: Client
b54a753c-f831-582a-9c6b-bb657ee0a09a | date | Date Completed:
988073e9-a96e-441e-b9d4-50099cdc07e0 | checkpoint | 2.08 - Demobilisation
651a584e-b3b9-5154-b3d7-3da7a79e10b9 | note | FREQUENCY: At the completion of works
d2afdb97-e2e6-50cf-aafd-0e5dbd3ca4c1 | note | ACCEPTANCE CRITERIA: Stockpiles and temporary works are removed.
da156bdc-b22a-5c7f-8612-1d5544161a5a | note | ○ Minor defects are agreed with client
84f7e13a-b5cb-556e-a093-34da4411550d | note | REFERENCE DOCUMENTS: NA
1f8c4e4e-8a4a-5a5c-9779-3399fdd4103d | note | INSPECTION/TEST METHOD: Inspection
396cae90-9c52-54a6-ad07-ea189c2d61d2 | note | CONFORMANCE RECORD: ITP
373115ee-3721-58d5-bfec-47ddd28a4ab0 | note | Hold Point
f56bf5e5-9b95-50ab-9e4e-40be72cedd55 | note | RESPONSIBILITY: Client
52d313a5-abe9-58ad-9bc7-a2e1a2e22f7e | date | Date Completed:
119618ec-febe-47c9-9b6d-273b864ca7fc | section | Classed Crushed Rock Backfill
9d555fd1-ae0d-47a2-ac57-0453331a4550 | checkpoint | 3 - Proof Roll
19d5f74d-0dcc-53ee-9c9a-e18539a419ee | note | FREQUENCY: After placing material
43feea8f-3558-59de-8caf-3dddb3fa376c | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
478e1cf2-4086-58c3-bc0a-e96cfde8beac | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv) Cl. 173
40950f15-9206-5767-8ef5-3f7bf280fb4d | note | INSPECTION/TEST METHOD: Inspection
a9d80a50-dfbf-5d72-9a26-9f3e195cce5e | note | CONFORMANCE RECORD: ITP
233ac523-1994-5b86-a3a8-a9ee3f93d71b | note | Hold Point*
4e33da07-c590-548d-9be9-ecf8bb7a103e | note | RESPONSIBILITY: DTP/ Fulton Hogan
e3f4fa98-b6be-541d-a66d-3712021e97af | date | Date Completed:
6a31214e-de47-47ad-b5ed-3d21f82ed882 | checkpoint | 3.1 - Lot Size
63dba1a0-301e-56cc-b296-964feef61ec2 | note | FREQUENCY: Check prior to placing material
6f6a7f83-5fb4-526a-b7f9-5615983cbb72 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
05228301-5026-5e0f-b5d0-8a2bc776a79d | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
29282ce5-c9f8-5512-a209-1b589e142981 | note | INSPECTION/TEST METHOD: Inspection
581ccf14-be1c-5610-b258-3fa36c062819 | note | CONFORMANCE RECORD: ITP
8b2224d4-3947-5d16-a158-bdf83f2c0ffe | note | IP
3f00b793-e1ec-56e4-9b7c-57677f93dab9 | note | RESPONSIBILITY: Fulton Hogan
5f437810-c457-5bd2-8bfc-df178c065f45 | date | Date Completed:
b8da9e72-201c-49db-aed7-cb5025fef50d | checkpoint | Final Inspection
3ec89e1f-6671-5ed9-803a-e54f2b1e5173 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
61d5eb9d-cce2-525a-8b32-ffc31b2415b9 | textbox | Print Name:
2642e95c-a897-5212-b43c-be8fc18aa098 | textbox | Position:
7c74b5a2-e40e-52ee-be4d-825e711de0c3 | date | Date:
f2ecb5e9-fd0b-4148-b297-33bd5b4abf82 | checklist | ITP-001 - Clearing & Grubbing Rev0 | itp | ITP-001 - Clearing & Grubbing
9980f71e-9976-4a92-8b90-cc5b5d97eede | section | 1 - Preliminary Works
a497681d-1bf0-4f6f-92e0-92e8d1588032 | checkpoint | 1.1 - Check current drawings are used on site for works
1d6ef922-4ceb-5f16-91bd-7b5a276e05ab | note | FREQUENCY: Prior to commencing any activity
07e248e5-5d65-550b-a788-4aa2b3881b8d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a0d02c80-711c-564f-b911-5640076a74db | note | — using the correct and complete set of drawings
b64ebc48-283f-5a8f-abec-7b74397a48b9 | note | — all drawings are the latest revision
fc022823-f831-5d98-b5a2-4e9a5041c5a8 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7634c2a5-dcdd-5712-b8d1-4def3e052f9f | note | INSPECTION/TEST METHOD: Visual inspection
4c28f015-93a5-553d-987e-89838da767d6 | note | RECORD OF CONFORMITY: This ITP signed
c59ced34-74a7-5810-ae97-d3087a4e1172 | note | HP*
6ec0b837-ee09-5866-a310-5c56aa7fcb53 | note | RESPONSIBILITY: Site Engineer / Site Foreman
676f984b-3346-5e8e-8179-34263a38b0a0 | date | Date Completed:
b5e9c195-6f0d-4c6e-ade0-f838b2a23535 | checkpoint | 1.2 - Implementation of all measures and controls
9861b0a8-4ef1-50a4-b261-446e4b8d090b | note | FREQUENCY: Prior to commencing any activity
b036a13e-23dd-53b5-9cc3-dae661223062 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
5bda4457-1a4a-5298-9789-93d2ef305446 | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
b0a6d9e4-6c53-59e4-be83-b0339a135730 | note | INSPECTION/TEST METHOD: Visual Inspection
f939ab37-716c-55ae-afce-01bbeaf19add | note | RECORD OF CONFORMITY: This ITP signed
25ed3d4d-1f10-5915-b91e-b1b78be475fd | note | HP*
b80f85ea-4a6b-579a-8d57-fd48d8d2c286 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a221c162-1c09-59da-a041-a4cb33723335 | date | Date Completed:
a52989d4-d64d-4f2a-9d7b-1ed2def536d9 | checkpoint | 1.3 - Excavation Permit issued
30f548cd-3335-59ba-94ec-1d1a5f7f8f41 | note | FREQUENCY: Prior to Commencing
90cc8b4f-96f6-5d4d-b735-6c54c87c457a | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
80eff5f2-45a8-52f5-af13-589826c8832a | note | REFERENCE DOCUMENTS: Excavation Permit
c1c26634-d5c2-5a93-8ac5-fd921faf2098 | note | INSPECTION/TEST METHOD: Document review
733c0cb4-c86e-5ba8-8675-dba40712b742 | note | RECORD OF CONFORMITY: Excavation Permit #
4c5484a7-f9f8-5109-9026-b5ab6814fc69 | note | IP
c3071b9d-758b-59ea-859e-d6587d2f96b8 | note | RESPONSIBILITY: Site Engineer
e2951107-1c8c-5138-9841-2c5f33f9ba13 | date | Date Completed:
d0e83212-62d2-466d-8234-6e88f422bdbd | checkpoint | 1.4 - Permit to distrurb flora & fauna
467e00a3-6237-5bfc-b741-9c34e6609668 | note | FREQUENCY: Prior to commencing clearing
cd79d3a6-4201-5b9a-a2ee-356ab3d1acd1 | note | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
19fea2ed-ba87-5376-a568-bc0f6fe2e368 | note | REFERENCE DOCUMENTS: Condition Plans endorsement
0491112f-699a-5585-bf44-73242d0eaeaf | note | INSPECTION/TEST METHOD: Visual Inspection
d6f64f10-5974-51f3-b219-9b972f037f98 | note | RECORD OF CONFORMITY: This ITP Signed off
faf1c1bf-d3d7-5cd3-a190-4643ad802e75 | note | IP
2503e137-5f62-5b54-b7e9-6d8377b01e36 | note | RESPONSIBILITY: Project Engineer
17f5ac8a-5ec9-5dcb-987b-a5334915cd91 | date | Date Completed:
6c43d27e-e3ca-464a-9a2d-6114b00da328 | section | 2 - Clear & Grub
1c182d2f-5679-4e88-8f22-400d39df7b65 | checkpoint | 2.1 - Define work area
2e73da49-9426-52cb-93ed-aa6b2c505973 | note | FREQUENCY: Prior to commencing clearing
e92b5fb9-8513-573b-9fcb-30abb1b61811 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
33a12042-c8d8-5fc3-96b0-a59708f26c45 | note | REFERENCE DOCUMENTS: 201.1
2804786b-f011-5f0d-ac71-6573282831b5 | note | INSPECTION/TEST METHOD: Inspect
07db47ef-0aaf-5915-b873-74cd08893e6d | note | RECORD OF CONFORMITY: This ITP Signed off
4a8a9022-1509-5ed7-8217-bed2c1abcaab | note | HP
10595648-d6d2-59aa-89c5-75a3e94cb8db | note | RESPONSIBILITY: Project Engineer/ Superintendent
ee272105-00c0-5083-b883-40fc5ab80e08 | date | Date Completed:
055d7620-aac1-4c12-97e6-93cd6dc59d89 | signoff | AUTHORITY HOLDPOINT
1bed45c8-4e61-4bb3-8d22-96f5984369fa | checkpoint | 2.2 - Cultural Heritage and Areas of Significance
484ba7a7-5936-55ac-a8d6-f0c04e2afbc2 | note | FREQUENCY: Prior to commencing clearing
f27d9bea-7e86-5a05-bc51-8592673df0c2 | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
dc1dd18b-6627-58db-8f6a-43ae0b2e0e4a | note | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
a081146d-ff35-586e-89c3-fba14bbfe7ac | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
eacb088e-81c1-54de-8432-3abbb7a08188 | note | REFERENCE DOCUMENTS: CHMP
f157523f-1fec-5499-a48e-22b1235d035b | note | INSPECTION/TEST METHOD: Inspect
e14349a1-5dc9-5720-bbbd-30f9fcdbf001 | note | RECORD OF CONFORMITY: This ITP Signed off
50446792-3d13-5702-9b78-f21f928c43d4 | note | HP
2e1c58a7-2346-5bc2-859b-411520e94bd1 | note | RESPONSIBILITY: Project Engineer/ Superintendent
b02cc604-0953-50fe-b854-0e3d5281d7d9 | date | Date Completed:
588a2a84-38b7-48b9-8876-41a8a4eaa1cc | signoff | AUTHORITY HOLDPOINT
58080dc6-4f3e-4d55-a772-06210f5c9888 | checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
45999cd6-14a2-54d5-a919-249a96303a09 | note | FREQUENCY: Prior to commencing clearing
4385cd25-ad8c-59e8-a859-7fc03a41a293 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
bbea25ff-e771-54cc-a809-59981b74a0ea | note | REFERENCE DOCUMENTS: Drawings, CEMP, Tree Management Plan 176.I1
8d2bd515-0f6e-58c9-a7c9-1c6bd427c957 | note | INSPECTION/TEST METHOD: Visual Inspection
c459dd20-1680-57e7-a06b-b1ca804a47ae | note | RECORD OF CONFORMITY: This ITP Signed off
aa64844d-7bf4-5fc3-b484-1362136259ab | note | HP
6bb15217-1c5b-5664-ad5f-1caeb4addbf4 | note | RESPONSIBILITY: Project Engineer/ Superintendent
91c7e964-4e32-5957-9d25-d80eaba2d5e6 | date | Date Completed:
ed1b1974-4c1c-42de-b263-d0c808b536a0 | signoff | AUTHORITY HOLDPOINT
7840ff5c-3edc-4f25-b30f-a212d59f9f61 | checkpoint | 2.4 - Felling of Trees
d5a4b68e-89aa-5cd4-82a1-f0903940f10c | note | FREQUENCY: Prior to commencing clearing
ed3afbe1-f029-5cda-a397-f501551420af | note | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
75be0371-000e-565a-887e-61ef6159a45f | note | REFERENCE DOCUMENTS: 201.04
75c75d34-c2cd-5cf8-adb2-31c4f087f80f | note | INSPECTION/TEST METHOD: Visual Inspection
ea120c1b-9b59-5dff-90c4-7b24b2deea76 | note | RECORD OF CONFORMITY: This ITP Signed off
6cade948-8fd7-529c-acd2-c5d4e8fd583f | note | IP
4e1fb97b-89b4-51b2-8702-897453598269 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8150d7b4-95fb-58ad-a3b3-35ae65b63127 | date | Date Completed:
4dbc7eff-9872-4619-9ab8-586d364f4a8d | checkpoint | 2.5 - Backfill holes
97a183d2-a06e-54c4-b0f4-a683efc79d07 | note | FREQUENCY: After clearing
ccfd1f7b-976f-5fc9-b0f7-783c09870f45 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
5e5496d9-caa8-529d-bfe9-b59d265df91c | note | REFERENCE DOCUMENTS: 201.05
0153a85d-7edc-522b-a3db-6cf6e59f5b39 | note | INSPECTION/TEST METHOD: Visual Inspection
fd0ef581-62f2-5837-a2be-83f54141edc3 | note | RECORD OF CONFORMITY: This ITP Signed off
0fce539a-ec37-52e3-98f0-feecf8bf11e3 | note | IP
d8307edf-159c-574b-8416-d3af9a7e4d5e | note | RESPONSIBILITY: Site Engineer / Site Foreman
f81ee003-595e-5c64-ab16-af47156a6f74 | date | Date Completed:
9b7bfd32-5c7d-49e8-a9eb-615c81366977 | checkpoint | 2.6 - Dispose of Trees and vegetation
238361fb-61f7-53df-ac76-42fbf59f4651 | note | FREQUENCY: After clearing
43232224-7ba0-5dae-b7e6-2d2c5f1dc9d8 | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
f93a1851-a42c-5794-8158-9b0e512a0721 | note | ○ Noxious weeds shall not be mulched.
2581193c-d376-5842-9fc9-3aac6c5bb42e | note | REFERENCE DOCUMENTS: 201.07
65198238-035f-5e6c-81e6-69aa9fe4eab5 | note | INSPECTION/TEST METHOD: Visual Inspection
6e44da94-0cbe-5ce8-9628-b8709dbb5398 | note | RECORD OF CONFORMITY: This ITP Signed off
139c8738-cca0-5135-b60a-9716c334f594 | note | IP
4e985b2f-4f03-5e34-aa03-cc93781c8ba1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
43a6a1be-7d50-514d-b6ee-2ae511788930 | date | Date Completed:
e9d151c6-a2a3-40ba-84cb-0c7fd567652b | checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
2e1bca18-3203-5ba4-8808-b1e2c217b3f4 | note | FREQUENCY: After clearing
b17d7cf7-f3e0-5d35-adfc-dfc81116589a | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
b7766bdf-66d3-5157-a33d-265b233b8ae6 | note | REFERENCE DOCUMENTS: 201.07
8093d3ea-9edb-509f-b613-771d96715154 | note | INSPECTION/TEST METHOD: Visual Inspection
0d73e174-2a6f-5841-beac-66ec8edbeca1 | note | RECORD OF CONFORMITY: This ITP Signed off
bf77447e-0e15-5436-afbb-e763c93b1f5a | note | IP
42d84147-014d-5e5a-9018-cb210271fc2d | note | RESPONSIBILITY: Site Engineer / Site Foreman
6c889e35-2e05-568e-ab8c-a63409ac1dbb | date | Date Completed:
012f784d-5d2f-4055-aa2a-93c1e757a6e8 | checkpoint | 2.8 - Stripping of topsoil
6a81510e-6e18-5eb4-81d1-8e07673a43bf | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
388eddee-884e-54cb-bd0e-d183ca4521c1 | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation. Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
4ec161be-0073-5893-91df-e7970b95b3d9 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
aadd95b9-28a2-51d6-b803-c1601233d0e5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
5a3d9766-b7ad-5034-9806-8a9b10b6f9e0 | note | INSPECTION/TEST METHOD: Visual Inspection
61b19b08-3a18-5796-b2c6-ebafca35152a | note | RECORD OF CONFORMITY: This ITP Signed off
39aa1289-79fa-50dd-8e8e-85e120a02262 | note | IP
0b86576c-dfc5-5464-b549-9fd25e212012 | note | RESPONSIBILITY: Site Engineer / Site Foreman
4cd10f5e-e67c-5140-8419-01901dcc3efa | date | Date Completed:
07593bbd-6fc1-49b6-bf2f-dcd817209109 | checkpoint | 2.9 - Removal of abandoned services
2be33be3-ee54-5e46-bc93-84832563cf54 | note | FREQUENCY: Prior to commencing works
c4bf6c01-8c02-5c77-a401-924aac6e8c3a | note | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
311d1025-a010-58b8-8401-673768516ee9 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
7a685304-d276-55e4-b274-d16dacc23896 | note | INSPECTION/TEST METHOD: Visual Inspection
f0931f7f-1bc4-5f89-8c7c-c0fa9a4e6a39 | note | RECORD OF CONFORMITY: This ITP Signed off
80ce3b00-456e-5393-a061-bc2c6f0a9a63 | note | IP
f6d5b670-b31a-52f8-ae65-802ae89c9468 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f22e5555-3a76-5a0a-a7ee-1d630b711814 | date | Date Completed:
d56aa692-cbb7-4fc0-baef-4258d9f0d2fb | checkpoint | 2.10 - Clearing of Trees and Vegetation
2b29cfa7-89ef-52a9-b37c-f1214a72333a | note | FREQUENCY: During clearin works
598dbc32-a646-5395-8857-86303702c82e | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
3678ab55-2d93-5246-a46a-8b05068691a3 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
f082b302-8f1c-55fc-9538-99b6d6854269 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
6c752e5b-d26f-5825-a907-5caf79cd16e3 | note | INSPECTION/TEST METHOD: Visual Inspection
4540837d-a1e6-52d8-bdd5-3504aeae8700 | note | RECORD OF CONFORMITY: This ITP Signed off
c6fc20d4-97b6-5447-b58a-940ca4b254a9 | note | IP
a25d118a-1c8e-56f6-a2cb-0a50fd3f97e1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
d946aa76-1de3-53f8-bb32-d13980c92b79 | date | Date Completed:
8410895d-85ef-49a9-bae3-51f9352ea9e0 | checkpoint | 2.11 - Grubbing of vegetation
778cace2-a272-5741-88e0-e310286f4bfb | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
492fe2f8-6eac-5222-a1c6-39492fef328c | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
284fddbc-5be3-588d-b15e-c8a739069504 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
372f5af0-fec9-5d48-bfb2-48b88c506cf9 | note | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
96ab0370-f32d-511e-867e-03b6e15342fb | note | INSPECTION/TEST METHOD: Visual Inspection
87df9be4-cc3f-5a03-bb4c-1fb687c14c1d | note | RECORD OF CONFORMITY: This ITP Signed off
be0be81c-9dc4-59ec-99ef-fb08d9987fa6 | note | IP
e2f45d62-dd43-5c74-8f05-545675045b4d | note | RESPONSIBILITY: Site Engineer / Site Foreman
b08016e8-440c-5e92-aae2-e4be3c3bedce | date | Date Completed:
2669a66b-ef74-4640-9709-50411c9432f9 | checkpoint | Final Inspection
8191cd7a-459c-5292-8572-bb6c2fa9f2d3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
03fd025c-2560-5648-bd5d-c63e01333818 | textbox | Print Name:
c253771c-5176-5835-9150-d4112e285674 | textbox | Position:
6a973bc8-6462-5e3a-b6e3-e30d51b82f81 | date | Date:
22ff58d9-984e-4c0d-96da-88946fcd886e | checklist | ITP-002 - Construction of Underground Stormwater Drainage Rev1 | itp | ITP-002 - Construction of Underground Stormwater Drainage
a0723274-48fa-4845-8a13-50a9eaa63bbf | section | 1 - Preliminary Works
e91657bf-946f-41bf-876d-dc8633ac4c39 | checkpoint | 1.1 - Check for correct documentation
594c9a33-3bd1-5933-a985-93c36711fdcd | note | FREQUENCY: Prior to commencing any activity
4a1cf308-922a-5936-970f-3b8cd7b7c7c1 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
477360f5-c784-567c-a6a8-091f3f3312ed | note | — using the correct and complete set of drawings
7adf56e7-214f-5769-8873-d492eec0da9e | note | — all drawings are the latest revision
5d183aae-f645-51e9-af7c-a6446735735c | note | REFERENCE DOCUMENTS: Drawings and drawing registers
88fd727d-3b1a-516a-8790-85219e83c707 | note | INSPECTION/TEST METHOD: Visual inspection
0a470195-5819-5fef-8b99-a7ac15fd7649 | note | RECORD OF CONFORMITY: This ITP signed off
0431ee64-dca1-5f03-abfa-8fcb9bef3c71 | note | HP*
9c6a1238-f6d7-5c8d-a3ee-90422942fc1e | note | RESPONSIBILITY: Project Engineer / Site Foreman
2f304c66-645e-5f01-9fc8-471198e2c425 | date | Date Completed:
64a0c1de-a3bc-484b-aad8-915510635e96 | checkpoint | 1.2 - Implementation of all measures and controls
a8e5481d-e635-5842-9ddd-ae8c2b8b053a | note | FREQUENCY: Prior to commencing any activity
25892a6f-d1c6-5700-8ac0-5cbd8635150b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
69aa903f-c22d-5c92-96da-7dbb6f0b7dc3 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
b1b2061e-3cd0-5925-bcb0-21d28b46fcb2 | note | INSPECTION/TEST METHOD: Visual Inspection
3a9c419e-e294-58bd-aa4f-b86e7a3b0709 | note | RECORD OF CONFORMITY: This ITP signed off
25cac1fe-2aa9-5d8f-91da-86292b8bf1e7 | note | HP*
d5902b02-8ef1-56fb-ac3b-7fd90c75a7b6 | note | RESPONSIBILITY: Project Engineer / Site Foreman
e381e0f0-93ff-527c-89ca-d1b39e93771e | date | Date Completed:
450c20de-575c-4843-909e-e50cf6be09b7 | checkpoint | 1.3 - Precast Materials Inspection
7349ad79-faaa-5d07-8fba-00ab44afefd9 | note | FREQUENCY: Each Delivery
ebae7b37-dee3-57f1-820e-1f567300c247 | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
cfd45caf-a221-58dc-9e8b-150a2872f029 | note | REFERENCE DOCUMENTS: 701.04b
d7b5ff05-0702-5ebe-b4b8-bb99cf0354e1 | note | INSPECTION/TEST METHOD: Visual Inspection
7c43644a-38d9-5178-8b5b-0fcf06239227 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
ed3eeca3-503b-501d-8d85-aafe10daeac2 | note | IP
2d282a2a-03d6-51d6-8a41-def08d714c7c | note | RESPONSIBILITY: Project Engineer
0c79ee8c-5580-5491-b428-e8a8afc3363e | date | Date Completed:
19cefb15-922b-442e-9bb4-a9fb302fb68e | checkpoint | 1.4 - Precast Pipe Compliance
1836ba13-3644-5b06-950d-ad69dd1afaf1 | note | FREQUENCY: Prior to Commencing
5762c1ca-3d15-546e-bca4-847e60b4fcd2 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
94e93112-da2f-5152-a31d-ae23d61d9716 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
d2a77d9c-5619-5f5d-9d48-ed6b5bb358b3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619
c24b9c41-8b1d-53e4-a3fa-22bfc898cca7 | note | ○ Cl. 701.04(a)
6740e442-68e7-56c1-b410-ea4fdb69bb03 | note | ○ Cl. 701.04(b)(i)
fdc38602-d049-5185-9df5-a7e8dc86130f | note | ○ Cl. 705.04(d)
28898f34-0969-58f2-939c-f61d58126444 | note | ○ Cl. 705.11
a7145138-9a82-553b-a7c3-e368668254ab | note | ○ AS4058
5aa2bcfc-f6e9-5221-8e90-0865cab84d2a | note | ○ AS4680
ebc86804-4d8d-5d2e-84e8-a133c17dbdd1 | note | INSPECTION/TEST METHOD: Document review & Site inspection
f90515aa-7518-535c-921d-ed485ed161d2 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
e42fec1e-d485-5462-9b31-0be066ec49c6 | note | IP
29fc029e-8aa1-5a6e-a70d-c8d9758cb44a | note | RESPONSIBILITY: Project Engineer
548c0391-3a64-56bb-adc7-016172f8fb68 | date | Date Completed:
eb4dab69-46e3-48a8-b79a-3626412c91d3 | checkpoint | 1.5 - Bedding material classification
b22ede31-84a7-504c-9d39-60120c53a492 | note | FREQUENCY: Prior to start
8624ecc0-b490-5f4d-bfa2-c1c13bfe4146 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
b4739100-36d1-5caa-8909-1c5ba159077f | note | ○ 100% passing 19mm sieve.
990269b4-256f-55ed-a59c-b38a1b36d598 | note | ○ 5%-40% passing 0.075mm.
ba3737d3-9f63-517e-984a-49a75f9af06d | note | ○ PI = 20 max.
9591bfe7-c8f9-5095-b136-9d7f370238ef | note | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
48b67678-0324-5417-a276-3973234fb88b | note | INSPECTION/TEST METHOD: Verify
fef1eebd-c8bc-5549-91f4-6d154f74fcbc | note | RECORD OF CONFORMITY: Test Reports from supplier
bc1924f2-9069-59ac-bb0f-5e4609fbbd4d | note | TP
5f66d629-b838-51be-9066-c036ba552341 | note | RESPONSIBILITY: Project Engineer
b46db094-e7d4-5a3e-b757-82ce88f85314 | date | Date Completed:
2c38e453-528c-47c4-b4dc-78b5e57d3825 | checkpoint | 1.6 - Backfill material Classification
faeba227-7cea-5f7b-96a9-fa861cf22f1a | note | FREQUENCY: Prior to start
21046c36-1586-5b60-b95f-e03c5aea3601 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
0e3a2201-f6ea-5b9c-9665-834ede41d5bf | note | ○ 100% passing 37.5mm sieve.
32ff55fe-346c-53d7-aa74-f5563a0d0df9 | note | ○ 5%-40% passing 0.075mm sieve.
5304b8ac-55a0-55f3-a77b-175df95c2829 | note | ○ PI = 20 max.
00fc9c85-d10f-505e-9bcf-947d7e25c99f | note | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
4fcd55d3-850f-5e0a-bf37-f7bf56cd8dc8 | note | INSPECTION/TEST METHOD: Verify
05d360ab-a4c3-5472-9380-7ae336c2a73e | note | RECORD OF CONFORMITY: Test Reports from supplier
4b88280c-22ea-5721-9d1d-1bad1427333f | note | TP
5e6ed717-471c-5ba3-a402-6f7032b471a8 | note | RESPONSIBILITY: Project Engineer
e02f530d-6bea-59c2-88f1-6b09eed7e90f | date | Date Completed:
0857343e-eb8b-4433-8cbc-3720ee716148 | checkpoint | 1.7 - Mortar material classification
d8f8d42c-3a0e-5ae8-86ce-0dc9207efdcd | note | FREQUENCY: Prior to start
6e8353f0-0634-5aad-83e6-99cef8c024da | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
730385f9-ce6f-55e3-b4b5-103836aa13c2 | note | REFERENCE DOCUMENTS: 610.33
048cb87e-e996-54cd-ae85-d751f17da7c9 | note | INSPECTION/TEST METHOD: Verify
fdffce28-4a63-5b7c-b8f4-9d153bd60d70 | note | RECORD OF CONFORMITY: Test Reports from supplier
7a8443b2-44b2-5a2b-b9da-1cba74957ec2 | note | TP
046a3d23-d568-56c6-a310-7adb0c880cc6 | note | RESPONSIBILITY: Project Engineer
f73c7b5d-4b62-5c82-9ff7-0ec39a54624b | date | Date Completed:
377c88e7-7a77-47ac-9d89-dea686395bc3 | section | 2 - Construction Works
ad67868c-c9e2-4e38-a891-e72d408ff2ef | checkpoint | 2.1 - Excavation Permit
83f30895-fd74-5c23-af61-9365fdd68f3e | note | FREQUENCY: Each lot
fa1f7b2a-9cc8-5729-9222-2b0fac41de60 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
a235a823-baa4-5669-9658-3f4f36199882 | note | ○ Plant and equipment shall be appropriate for the task.
c0b45662-2680-51c2-9ac8-97b5f28b59ae | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
8e9bd3b9-64a1-5121-8387-3f8ee5ec8e6f | note | REFERENCE DOCUMENTS: Excavation permit
c3ad451d-2a0f-560f-b40d-138ae818232b | note | INSPECTION/TEST METHOD: Verify
83da3d48-82f3-52ee-a126-7484074d5d73 | note | RECORD OF CONFORMITY: ITP Signed
a583f229-8a4f-5f9a-9942-82f95189da7d | note | HP*
f8bf8282-d1f5-5689-b1ac-853c20101aa9 | note | RESPONSIBILITY: Project Engineer
c799ef23-0922-5cf7-a5cb-bcd366adc3c9 | date | Date Completed:
869bcfed-0946-45e4-9219-0799630b2220 | checkpoint | 2.2 - Set out drainage
5aaf50c6-c996-5c1f-9dfe-6565ea4a8e2b | note | FREQUENCY: Prior to excavation
561d5f00-cd95-52c0-bc88-676ffccc26d8 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
288c5d01-0e05-5461-a4e3-4b9a24ba42bf | note | REFERENCE DOCUMENTS: Drawings 701.10
e923f7fa-4453-56ee-b431-8e5693462fa1 | note | INSPECTION/TEST METHOD: Visual Inspection
aa716a4b-0993-5919-b409-f19f40a5b699 | note | RECORD OF CONFORMITY: ITP Signed
0ee9cb80-ef81-54b3-b5bc-34cbc1b293c1 | note | HP
a8441dc1-3903-51fd-a29f-68a0c9197a64 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
cd25eeef-372d-5143-a740-f99b079030f7 | date | Date Completed:
265fc2af-ee51-49bc-9db9-d7688b4e7de2 | signoff | AUTHORITY HOLDPOINT
b4be48a7-8268-47b7-9b29-8ffbbfda9ad0 | checkpoint | 2.3 - Excavation (pipes)
1f38fa72-2e0a-53f6-8572-4c7963ed73c9 | note | FREQUENCY: Each Trench
43f068f9-bc9a-592f-b205-55fb4e4b0216 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts.
ab5c6ae2-074a-5f0f-a7b3-ae5b0a25f8e6 | note | ○ Trench walls to be vertical where practical
ac514aa2-6da0-5e9b-b625-089918ba365c | note | Depth of trench:
e53f16bc-0fde-561b-8288-a0d15cacf7f1 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
4e973cc1-73db-5c63-9811-9e0ba3382795 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
3a400e78-7f14-5e26-9e43-3ecb7b7c54a8 | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
c82d9353-0ce3-524c-9584-7fb3d0a831d9 | note | INSPECTION/TEST METHOD: Visual Inspection
b16123e6-3037-5971-9323-8f7fbf705abb | note | RECORD OF CONFORMITY: ITP Signed
559f2630-3f7c-5f1c-9b11-92e62af4f73a | note | IP
a5e8af43-eb18-5d26-9f81-0990c2790d25 | note | RESPONSIBILITY: Site Foreman
68acec74-7738-50b7-be21-c3073553ccf7 | date | Date Completed:
734496cf-34a1-4ce7-aac9-d62423b3a9b6 | checkpoint | 2.4 - Compact base of trench
da11d062-4386-59da-ba2a-c387a18f98e8 | note | FREQUENCY: Each Trench
8d7634c4-94ec-5a35-8c59-27878280a0de | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
0e2e3567-bd41-5b22-b274-090cbeaef0c8 | note | REFERENCE DOCUMENTS: 701.1
0cd5b8f5-c3af-5dd1-924a-7f0ca2181309 | note | INSPECTION/TEST METHOD: Visual Inspection
e1d62650-e4f2-5852-9237-3d4783f0b08c | note | RECORD OF CONFORMITY: ITP Signed
f903b71a-de5e-5c98-be57-4050f638bd1f | note | IP
db708e4a-a95e-557f-8d43-431525f7ad8a | note | RESPONSIBILITY: Project Engineer
d0d6c696-374b-58b6-bbbc-8880b9878707 | date | Date Completed:
ed83b8c8-4223-4bac-9ee6-630f234a4c2d | checkpoint | 2.5 - Place bedding material & compact
470b1054-960c-5a19-ac05-9bd175b207a2 | note | FREQUENCY: Each Trench
292fc490-d938-52e9-8498-6df18cf67360 | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
aa4f455b-c18e-57e1-a65a-52e4bc80c598 | note | ○ 100mm under pipes.
dd878335-1df5-515d-b0b3-a9698086b40a | note | ○ 80mm (earth foundation)
57ddabc9-4eb3-56b1-84ff-9eee7b6f62eb | note | ○ 150mm (rock foundation)
c0837b69-217c-5528-8de6-945cc673b32e | note | REFERENCE DOCUMENTS: 701.19
9cee01dd-2b6a-5b82-842a-024e64ceb61c | note | INSPECTION/TEST METHOD: Visual Inspection
6e509d92-e137-5703-a2d6-f9ea09cb1f9b | note | RECORD OF CONFORMITY: ITP Signed
64d3b2ef-fbf5-53cf-af81-19ce732bdcf8 | note | IP
732d39b9-5cd0-5364-b6e5-03237077c22c | note | RESPONSIBILITY: Project Engineer
3dc7304c-db96-5dfe-ae70-65e699961824 | date | Date Completed:
efb6a40a-a910-41f0-8590-70d864b40b05 | checkpoint | 2.6 - Place pipes
8cf75589-db3b-589c-b9f7-8c190d0188b0 | note | FREQUENCY: Each Line/Pit
92a9809f-786c-54cc-95d6-a3e83b20c7da | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
88383ac2-620e-59cc-b760-b94fe5bfb15b | note | REFERENCE DOCUMENTS: Drawings 701.17
dc4537ca-4591-5778-9267-e3e60f718f80 | note | INSPECTION/TEST METHOD: Visual Inspection
dd96c1ab-96cf-5624-ba6d-36722e2c058b | note | RECORD OF CONFORMITY: ITP Signed
089c8835-d9db-5722-9c2d-67c813a31413 | note | IP
4189a50e-3f4f-558a-b080-a2df16af4507 | note | RESPONSIBILITY: Project Engineer / Site Foreman
ab64fd15-0a92-541b-b163-e98f7f689801 | date | Date Completed:
de7e9bab-965d-4457-ab0e-adcacc0f1d63 | checkpoint | 2.7 - Jointing pipe sections
d6f7005f-0cff-5d36-b7f4-94d0175b08e9 | note | FREQUENCY: Each Line
e49066cd-506e-5e1d-8982-04d0ba451191 | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
4ac94805-1d62-5723-8d34-40e063d5d646 | note | REFERENCE DOCUMENTS: 701.18
b225240a-d1d4-5913-be91-66320e06b54d | note | INSPECTION/TEST METHOD: Visual Inspection
af03dd0b-0de5-5a76-9e91-e9131a1e7a75 | note | RECORD OF CONFORMITY: ITP Signed
01e76717-8f9a-5625-9abb-75938f8e707c | note | IP
80c30a7f-a26d-52c5-9094-f93c2fc8f4f9 | note | RESPONSIBILITY: Project Engineer / Site Foreman
a92d6034-ad36-577d-bcfa-f95a747bb3b0 | date | Date Completed:
697dcd7f-4cca-421e-9fc9-55b18fe4b3b2 | checkpoint | 2.8 - Place & compact backfill material over pipes
e06cbdc9-1010-5556-80c9-2669807b81a5 | note | FREQUENCY: each lot
578c5900-c116-5549-91b6-e16ca577c4a0 | note | ACCEPTANCE CRITERIA: Backfill under paved area:
0cce0603-41fa-55c2-af25-44b74339997f | note | ○ fill trench with selected back fill material to subgrade level
91beff23-a81a-5ccf-aef3-d19ecb5dfc66 | note | Backfill under area not paved:
23db5a14-9bd7-5f3b-8708-d345fb4c0c2d | note | ○ Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
5da14718-4683-5808-b393-f77f476b08a7 | note | ○ Loose layer thickness <= 150mm.
ba192ef5-cfd0-5432-a686-2c8b67f9ce10 | note | ○ 1 lot = 150mm layer
f0176452-1fc3-59bc-9446-954584a770d9 | note | REFERENCE DOCUMENTS: 701.14, 701.15
d550b4b3-8aac-5a1c-92b3-7ba27a6c563c | note | INSPECTION/TEST METHOD: Visual Inspection
2d9ac8b7-caf5-52e5-91c0-a0dd5085d342 | note | RECORD OF CONFORMITY: ITP Signed
a8becfa7-c147-5ad1-8ead-3c8deb0a2f13 | note | IP
74a68879-9750-5a51-a3a4-58030de37714 | note | RESPONSIBILITY: Site Engineer / Site Foreman
466e02df-8cdd-5520-919c-6f4aa39a075c | date | Date Completed:
f128ed7e-3ab0-47f5-bc37-ad64b08c19f4 | checkpoint | 2.9 - Repairs to damaged pipes
dc08b476-7c11-5b1f-bd01-df6252b9e67f | note | FREQUENCY: Each damaged pipe
fc29933b-cd0e-5b84-9d1c-578c9a2deeb0 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
6710847d-24b1-511a-97fa-ccaa86760459 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
d11fd8d7-dddb-5291-b1d9-48e4d4319838 | note | REFERENCE DOCUMENTS: 701.31
9c64439a-1763-550b-846e-e36393a54058 | note | INSPECTION/TEST METHOD: Verify
8b850e21-df9a-5c78-9f7e-06e2c8014093 | note | RECORD OF CONFORMITY: ITP Signed
636a29a1-1475-5c8c-ab5e-67eb852488ff | note | HP
d0c80bac-e556-5bc2-b934-118ccc03eec0 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
c4452fbf-692f-538e-8ef7-3ba714934d90 | date | Date Completed:
996b66b0-47f6-4b8a-8d5f-698cf7fc3aaa | signoff | AUTHORITY HOLDPOINT
13df14af-6f6a-4739-b5bd-7610328d9b69 | section | 3 - Testing & Completion
da634b78-c31e-4cdd-bc00-7e1f81f40fd1 | checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
9331c531-a063-5ded-973b-1f31ba55f8ee | note | FREQUENCY: as required/requested
beb09b03-1de1-5954-82f4-2fcae6c7d452 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
64a661c7-d900-5f1c-8cbe-b700129075a9 | note | ○ Bedding material shall be compacted using a compaction plated to refusal.
4fd1a0ac-08ae-5910-8c18-97200677c35a | note | REFERENCE DOCUMENTS: 701.2
99e45b8c-3791-5bb1-b6c1-2842f682fac8 | note | INSPECTION/TEST METHOD: Verify
5d5aeeb7-2bc2-5c12-bbc5-9513b058dae7 | note | RECORD OF CONFORMITY: Test Reports
381edd83-0f3e-51e6-8b1b-452ffcf17070 | note | TP
400cf12c-14ff-5735-8b82-d422282681c1 | note | RESPONSIBILITY: Project Engineer
3b64d5ec-8789-5ec1-967c-1d6c45620311 | date | Date Completed:
94de3470-fa67-4ba2-8bb9-ce5dfa875be2 | checkpoint | Final Inspection
04f5fda8-35e6-58d3-bd04-278aed0afdca | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0010d50f-f2b1-50d7-98c6-448a2d51d924 | textbox | Print Name:
63e9b0f5-c41f-5e87-b827-5f3a5f5d626b | textbox | Position:
96d29750-944a-56b1-b58a-2ea81e2de3e7 | date | Date:
0d80655f-30a2-4f03-ac79-11df4e654c9d | checklist | ITP-003 - Earthworks Foundation Rev0 | itp | ITP-003 - Earthworks Foundation
5ef7fee5-62e9-4f8f-b869-5f53de5c5b43 | section | 1 - Preliminary Works
91a461e7-c296-423a-8287-4ad47020af77 | checkpoint | 1.1 - Induction
017ee41d-e953-519a-a8e6-869d1131c9b2 | note | FREQUENCY: Prior to Commencing Work
f95e8422-2304-5818-b5ba-0800baed0b22 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
1fcf7553-b835-502b-9331-384b12c99607 | note | REFERENCE DOCUMENTS: Induction Register
23168625-2ddd-51df-95d9-c36815b57bf5 | note | INSPECTION/TEST METHOD: Document Review
a2c33e97-0d69-57e1-95f0-7ed863545601 | note | RECORD OF CONFORMITY: This ITP signed
f6ec6cd3-5bd3-5f7d-9b33-d9033b9db3d9 | note | HP*
bc87ccb3-7694-5865-b053-1d05a73af751 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b1372d35-2069-57c8-a767-5ec593750752 | date | Date Completed:
d353418b-5a58-4772-ae64-5120c541d6f7 | checkpoint | 1.2 - Implementation of all measures and controls
9ec83b60-f7e2-5adc-be44-dc962a302988 | note | FREQUENCY: Prior to commencing any activity
556ec027-cb59-509b-a0c5-297c8961decf | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
7dc908fe-1ea7-5be2-940e-f490cba64f8e | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
95e907ca-184a-571b-b48f-970b70daf1f4 | note | INSPECTION/TEST METHOD: Document Review
a33539ed-bedb-5d5d-8109-eab1a498f521 | note | RECORD OF CONFORMITY: This ITP signed
0a318db1-7e5f-55a8-bb27-392177d3b78e | note | HP*
c433511c-3742-5811-9b8d-bdca814eb69a | note | RESPONSIBILITY: Site Engineer / Site Foreman
6cd0e60b-dbe6-5dde-b64c-1a1f2254b11f | date | Date Completed:
8909bd5a-c6ed-435d-a56c-877a0db10dc2 | checkpoint | 1.3 - Excavation Permit issued
15763861-cf8b-5341-9f2d-d4d43c9373b6 | note | FREQUENCY: Prior to commencing
2f19ece7-68eb-5817-aac9-15dc7b730a26 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
5ceed452-8a94-5b49-adc8-c7cb31c09ff7 | note | REFERENCE DOCUMENTS: Excavation Permit
4d492faf-6ea6-5398-a2a0-eef035d2d66e | note | INSPECTION/TEST METHOD: Document Review
047489b7-2264-5a86-ae20-100cd96c9b1d | note | RECORD OF CONFORMITY: Excavation Permit No.
777f4648-0ee4-535f-94b9-23954c116a8d | note | IP
b31fe2f3-ab90-5b5d-8943-906e08ed22eb | note | RESPONSIBILITY: Site Engineer & Superintendent
debbf484-e85e-5c30-865a-e3d8821a13e4 | date | Date Completed:
fc0c2ac3-14bd-400b-8eb9-3c1d3a9af234 | checkpoint | 1.4 - Check that current revision drawings are being used
dcec1f48-5e60-59dc-9027-2acd53605882 | note | FREQUENCY: Prior to Commencing Work
10247af5-504f-59be-850a-ed4f053337fb | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
565a1ae0-196c-5aeb-baed-ef9abb435bb7 | note | REFERENCE DOCUMENTS: IFC Drawings
40233ac6-db02-574b-9c2c-49476db87db4 | note | INSPECTION/TEST METHOD: Document Review
4ea5a1fd-d19a-5f8f-afec-ca9964c4f805 | note | RECORD OF CONFORMITY: This ITP Signed off
8ce494b1-fc30-5525-85c4-26e3f6a22c73 | note | IP
d9e14bc0-8d18-52ef-85a3-16f97722a3e2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b8f4e339-4ac5-5542-8411-3fc4e2c1f726 | date | Date Completed:
86d7ac4d-0c6e-476e-8ec6-461df8d6073f | checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
b52d4c72-ee28-54b8-b1ee-9a9ba1c5386c | note | FREQUENCY: Prior to Commencing Work
ab590e4b-1d57-58bb-8b88-ab5de8fa2a77 | note | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
02e8f317-dfb0-5f87-9c78-e433f4da96d8 | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
a747c8b8-eaa2-5d99-bf73-8aaae0db30a4 | note | INSPECTION/TEST METHOD: Document Review
be733498-c4c6-5f4b-b4a6-02b487a1be96 | note | RECORD OF CONFORMITY: This ITP Signed off
8d71c2bc-f09f-5235-837d-62c5f03a96f6 | note | IP
6217583b-3c2b-5d79-b71b-d6a4aa0ab4fe | note | RESPONSIBILITY: Site Engineer / Site Foreman
78bcbbb5-b55f-5dd6-aab0-e8d0d669245a | date | Date Completed:
b032702d-8642-46f5-b933-7f83edc6b1ac | checkpoint | 1.6 - Verification of Site Clearing
89ecbbde-bb42-5216-bda1-0e5aca9f273c | note | FREQUENCY: Prior to Commencing
685cd55f-74d1-5e93-8377-e174a9b7216d | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
c8153148-fcfa-5429-a14a-d6558460105e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05, ITP-001
f71d5a17-bfdf-5f1b-a1c6-3e02bbbdc915 | note | INSPECTION/TEST METHOD: Visual Inspection
22244fe0-1de7-5c9b-a78b-c4cc39ea19d8 | note | RECORD OF CONFORMITY: This ITP Signed off
71ec6180-1c39-5a63-9fc8-5c490fd839b8 | note | IP
570a985a-2d5a-542b-87b1-25016f757a8f | note | RESPONSIBILITY: Project Engineer
029050c6-0dfd-51bc-994f-691fdcaf9b75 | date | Date Completed:
f1da9924-39a6-4094-a062-aba15be80a6d | checkpoint | 1.7 - Material Category
71a5c51d-a3a0-5832-bcf9-bf1a59fa240d | note | FREQUENCY: Prior and During Excavation
7e7c8c68-bbb3-50fd-930d-96fd977cd7e1 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of material in accordance with Clause 204.04
8f182439-0ffe-5c0a-9591-0ed118a5edbb | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.04, Cl.204.06(c)
d12dc5cb-2f22-5168-9f80-c9e685190c10 | note | INSPECTION/TEST METHOD: Visual Inspection
d1eb9547-4976-5985-ba87-bcd1db3272f4 | note | RECORD OF CONFORMITY: This ITP Signed off
8e9eb054-a995-5c34-befa-6e21045876c4 | note | IP
beb1ccaf-d4a0-5f05-b139-7e59c77c10aa | note | RESPONSIBILITY: Project Engineer
a0e309ee-1927-5170-a08b-53dc4cd63d75 | date | Date Completed:
bbc42839-852f-44a7-a655-53929f9fed42 | checkpoint | 1.8 - Placing Fill
caf27933-a4da-51f7-b339-6f9c9fa67c9b | note | FREQUENCY: Prior to Commencing Fill
b55e4146-1779-58ab-87ab-3347cfdbd6fd | note | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
2f7235fb-b697-5e18-b6a5-45b5f5ebdf73 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
379a95ef-6d95-584b-a506-52f68d70e5b6 | note | INSPECTION/TEST METHOD: Visual Inspection
fb36b502-a287-5143-a3d0-9a777f235c3f | note | RECORD OF CONFORMITY: This ITP Signed off
b6f9ea91-fceb-5e61-bac3-62cd2ea6f64c | note | IP
f62e4afd-0be7-5806-a01f-0e6764f405d8 | note | RESPONSIBILITY: Project Engineer
aba3d3bd-f911-5d94-8e09-4864beadb453 | date | Date Completed:
d0a28080-af4d-41b3-b6ff-52945b7c8d30 | checkpoint | 1.9 - Rock Subgrade
98630f64-033b-50a3-b7a1-7de0959c10f0 | note | FREQUENCY: During Excavation
5e05aec1-d7f9-58b7-b804-c4272632ac50 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
2afd0232-089d-5cfe-94d3-4d31ed72066e | note | ○ Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
6af19867-456c-587c-9b68-02111753bc2a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
91e0882d-9bc4-5d65-933b-6561470da83d | note | INSPECTION/TEST METHOD: Visual Inspection
ba1af56e-cf26-590c-8068-400385b80637 | note | RECORD OF CONFORMITY: This ITP Signed off
5a0bcbbc-c8d8-5e5e-b182-fbbda71130dd | note | IP
fced3cef-c7e9-50b7-8169-17a4ba95e743 | note | RESPONSIBILITY: Project Engineer
3c36afe2-2af0-5d9c-b437-02a355de15b2 | date | Date Completed:
963b28e1-68e4-4925-bb07-200861b61f7d | checkpoint | 1.10 - Ground Water
8270140e-df91-5ea4-8904-2ab49007938a | note | FREQUENCY: During Excavation
aca97987-1239-54d4-8c5e-d06b729af53b | note | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
915bce54-db29-5874-b10f-5579ed9fece3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
f844913a-7739-517d-b952-4662704c15f4 | note | INSPECTION/TEST METHOD: Visual Inspection
7f68a805-614c-5bbc-bf82-08189d031831 | note | RECORD OF CONFORMITY: This ITP Signed off
d8b9ded6-a870-598a-a903-756de56a004e | note | IP
2aceb7dd-9a1b-5cd7-beae-4ebb187af7f6 | note | RESPONSIBILITY: Project Engineer
84d2e1f2-e6bb-51af-9bea-d5242add44a8 | date | Date Completed:
3d799801-5a99-4163-87f5-98de35390681 | checkpoint | 1.11 - Unsuitable Material
cbb2609b-d6d6-5ca3-9524-8173f98f6d85 | note | FREQUENCY: During Excavation
a85ca6f8-51bf-5706-b406-d65ea12ef8b8 | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
f3fd9316-2518-5026-a75c-27a10a04307a | note | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
b9a90fce-2cea-52a2-9f35-c30b514b5461 | note | REFERENCE DOCUMENTS: IFC Drawings
724a5ea5-8458-5487-b026-d509ffab53be | note | INSPECTION/TEST METHOD: Visual Inspection
25b96234-218a-592e-902d-729785fd3f33 | note | RECORD OF CONFORMITY: This ITP Signed off
d182e2da-88b3-52a4-a15d-310257981443 | note | IP
76fad3c3-3d2d-5dd8-ac22-b5d50de0e4b8 | note | RESPONSIBILITY: Project Engineer
92bbac3d-274e-5714-bbab-1c19f9b21b96 | date | Date Completed:
a0d55a7f-0149-4839-8ef0-bc01be69011a | section | 2 - Construction Works
28a8039a-9895-48c8-91eb-1c99c3d4c451 | checkpoint | 2.1 - Survey set-out
9854e985-9ee3-5ccb-ab42-56805c98135b | note | FREQUENCY: Prior to Commencing
dcc683ba-36c8-5d35-98aa-6a1c56ebab9a | note | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
929b21f5-8e65-5f76-9c44-7d1eea8b99bd | note | REFERENCE DOCUMENTS: IFC Drawings
de67ed89-bb7f-5c85-8660-a008d042a108 | note | INSPECTION/TEST METHOD: Site Inspection
80f509fc-5766-52fa-9d2d-523e4c823999 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
29c377d8-ed46-59e0-88aa-b68fd8c97f1a | note | SCP
592b657d-97d0-58aa-b477-84ea480b404a | note | RESPONSIBILITY: Project Engineer/ Superintendent
fd64d966-b086-5b32-9416-7757846932d5 | date | Date Completed:
6d260d43-c186-4286-8161-f01035eafe56 | checkpoint | 2.2 - Surface Preparation
91c80d26-a8bb-550c-8873-83654bb14afc | note | FREQUENCY: During Excavation
32e25991-44c8-5c6d-ad25-ea996e2715a7 | note | ACCEPTANCE CRITERIA: For areas where the subgrade height is less than one metre above cut height, the cut should be scarified to 150mm and recompacted with Type B material
8cd28bcf-7a9c-5b2b-9eed-a7b2be306223 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06
e3a2cfad-8498-5ff8-ad22-bd2556cff069 | note | INSPECTION/TEST METHOD: Site Inspection
bbca0cc1-989b-5bae-b45c-938efffd6859 | note | RECORD OF CONFORMITY: Signed ITP
a2ff76c6-f8c3-5573-932d-5fd3a2e5d172 | note | HP
9e5e174c-856b-5f49-b744-4ffdf0cdedb9 | note | RESPONSIBILITY: Project Engineer/ Superintendent
2720395c-8749-5382-87ae-b92d834d31ec | date | Date Completed:
c9c7229e-fcf4-4fbc-906f-f750fddb45e7 | signoff | AUTHORITY HOLDPOINT
638064ff-04a4-4140-a113-d1931f23c5b3 | checkpoint | 2.3 - Foundation Treatment (if required)
d4cfc877-b65b-505a-8ca5-00ced8b12134 | note | FREQUENCY: Prior to Treatment (if required)
89c6a852-5779-5c75-81ac-0716660ee5ed | note | ACCEPTANCE CRITERIA: Proposed method reviewed, refer relevant ITP
89783dec-c47b-58eb-8d12-e24d24d5e20e | note | REFERENCE DOCUMENTS: Relevant ITP
ee69c3ac-7bea-5ef4-b409-42529c56ffcd | note | INSPECTION/TEST METHOD: Document review
ec1c29b7-6780-504f-9614-1775f52355d8 | note | RECORD OF CONFORMITY: Signed ITP
c3fb8ef8-456c-5140-ac63-e62d3fd779e6 | note | IP
efa94203-100a-5322-998e-62cd30dcac8f | note | RESPONSIBILITY: Site Engineer / Site Foreman
9a1eb7d0-a319-570a-8ab5-9f22e59eb091 | date | Date Completed:
a221c50a-8fc9-4c18-acdd-220de2160a65 | checkpoint | Final Inspection
01e08c05-8f68-5171-98b2-b5a74fc08d6a | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9612507d-4ea1-599e-b75b-0f82c725a63a | textbox | Print Name:
528368c1-fb30-5610-bbaa-6ed15c3ef93e | textbox | Position:
f67c8c1b-4342-558f-b07c-55a7665af3df | date | Date:
e012d6ac-a96e-48d7-a731-58730ccffa62 | checklist | ITP-004 - Underground Drainage Rev1 | itp | ITP-004 - Underground Drainage
6ce345c6-c200-4606-a1ac-9a4baa29951f | section | 1 - Preliminary Works
9272322d-f54f-4a71-be7a-b5b799e4c2bb | checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
6e4b9483-8802-526c-b8ac-b5a5a536619c | note | FREQUENCY: Frequency: Prior to commencing works
77430200-ed65-5e15-919e-b8af0f6b1a6e | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
b687720e-c61b-54f0-b153-1cc602a954a4 | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
ed404d65-ee2c-53c2-9d2e-782f344f003d | note | METHOD: Visual Inspection
23b52aba-4f59-528e-bbf1-d4d13089e4de | note | RECORD: Signed ITP
dc000240-eed8-5323-b3cc-eb5cdc680c6e | note | IHP
b34d4ea9-0104-575b-9ecf-7be9e346f60d | note | RESPONSIBILITY: SWA Project Manager
5c534846-c3bb-53e1-b930-1239c70f0723 | date | Date Completed:
0885602b-7f7c-432d-8de6-17282899d500 | checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
5fb78a66-3330-5177-adf6-ec1de7f600a7 | note | FREQUENCY: Frequency: Approval prior to placement of order
e39bc629-f8b0-5fe5-92cc-ccf8a619ba62 | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
83e52f7c-10bf-536e-8c55-74951e5a4412 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
ad320693-17ed-5cc5-a0bd-c2f2b68a5600 | note | METHOD: Review and approval of documentation
7b0bdc47-cba1-5c2a-a6ff-54a452a13ef9 | note | Visual inspection
bec40d3c-be10-5815-b8eb-8e315773a18f | note | RECORD: Signed ITP
653bfe85-83b3-593a-bf83-12b0df0b3cea | note | IHP
92e9dcf7-9e4b-5acb-a0e7-2c007375d1d8 | note | RESPONSIBILITY: SWA Project Manager
cf4be28c-1b52-5762-9cb1-b08c1e5c580d | date | Date Completed:
c1d9c0f8-dd67-4082-b847-fd0de15f5af1 | section | 2 - Construction works
ef793fac-9e81-47ad-b142-b2d8f3ad0037 | checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
c43aff76-7ae4-56cb-88aa-96e1fd7be46a | note | FREQUENCY: Frequency: Each lot as required
52c4f826-973e-5d49-9068-af134063cb71 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
13c4de20-3492-50ec-ac03-e734501e0875 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
e228a664-7bab-5edb-a580-11704fd014c8 | note | METHOD: Construction Drawings
345900db-af88-5ac8-9ddc-fa9123a45198 | note | RECORD: Signed ITP
74bbd262-b43e-5f13-84ac-b2ae2c18e5f8 | note | IHP, SWA
79bb93c0-50a3-5aab-8da2-22dbb58b3b63 | note | RESPONSIBILITY: Project Manager, Site Supervisor
d7453a42-79e4-5102-b788-fea64e04ae94 | date | Date Completed:
63913344-b377-4591-9bf4-fbee69835ef7 | checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
1bc82336-d274-5520-bdac-a3220fbc8d1e | note | FREQUENCY: Frequency: Each Lot
06f1410b-c22d-5ffc-9e36-910b7d0b149a | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
7c0e6cef-687c-5ffa-a519-9a0b833a7782 | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
d44958dd-9e4f-550b-91d7-39e5206a885f | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
c39e309d-2cb4-5e80-ad22-cb6fbab9fa41 | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
2c39263e-2c15-5ee6-b372-6d7194dfbf50 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
8015318a-e504-54c4-868f-818fafa95fb4 | note | METHOD: Construction Drawings
15fa0a7e-f666-50e3-9d94-6c72d460896a | note | RECORD: Signed ITP
544bc282-0734-5ea4-85c3-02afafc4e360 | note | IHP, SWA
dd3c0869-9beb-5e56-b1ac-7184b0a46c2c | note | RESPONSIBILITY: Project Manager, Site Supervisor
d51f1600-0cd2-5b50-ace3-f42b98d380b2 | date | Date Completed:
4203993c-681d-4d80-9010-21ba7c144bbf | checkpoint | 2.3 - EXCAVATION
8abe7a08-ba15-5d70-a9f4-3f98aac3f118 | note | FREQUENCY: Frequency: Each Lot
073773fc-48e0-55d6-a491-559c0e00f163 | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
410ce573-eeaf-50a6-ba03-90118e35c3c0 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
5008587a-5df9-523c-919e-39aad1a2f725 | note | METHOD: On-site Measurement
698166f6-cf50-5d6c-989f-96ed5a48cc45 | note | RECORD: Signed ITP & Drainage Checklist
4e45f9bd-6cf9-5182-af68-6a84d607bebb | note | WP
a711cdda-2050-5bf0-83d7-885822ad4e60 | note | RESPONSIBILITY: Project Engineer, Site Supervisor
7b1b3f84-3beb-5a38-890f-f9e94c018eec | date | Date Completed:
e0cd4c65-f35d-4a5f-9df6-78bc3fc0c4b4 | checkpoint | 2.4 - CULVERT BEDDING – Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
61f85ee8-beb9-577d-a09c-3d0232fa1f02 | note | FREQUENCY: Frequency: Each Lot
8476766d-b161-58f7-bbf0-8a84f64821ac | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
87939d02-5e46-541d-b5c9-0f8fb8b38e53 | note | ○ 100 mm where D < 1500 mm
f25a3aee-3697-58ab-9665-faa3af04e046 | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
e8251ee3-874b-5f13-9e00-8d45d341e902 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.15
1b4e146e-5428-5f7b-9ed9-d58be49e0751 | note | METHOD: Site Inspection
91aeedb4-44ca-51c8-982c-f1a465556c1f | note | RECORD: Signed ITP
e57c3a05-39ea-54d3-8bb1-61e0c49ee0f1 | note | WP
2b18b2dd-faba-5624-9ef4-1ebdbb2b3ba3 | note | RESPONSIBILITY: Project Engineer, Site Supervisor
c61fb90f-2e56-5a77-bb01-205170329e36 | date | Date Completed:
a49bae2a-5182-4de8-aa08-ca79e77a23b2 | checkpoint | 2.5 - PLACEMENT OF FILLING
f259b5d6-62f8-5b86-b340-aea0616abc7f | note | FREQUENCY: Frequency: Each lot as required
cbffe36b-ef70-57dc-b16b-53b64d40232b | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
12ee964a-98eb-5c38-a1b8-db2040a5a6b9 | note | (I) Culvert Under Area not to be Paved. The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
3d26075d-9144-5e09-995d-d5fa62614fae | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.18
81bfe4cf-d63d-5d87-94a8-d6a81f98cc91 | note | METHOD: Site Inspection
dbba3dc8-0442-5cc9-9ac6-2fb9f15421d3 | note | RECORD: Signed ITP
a7f36c8d-9c46-5904-a288-718c23020b67 | note | WP
6f1a338f-e33d-5d24-b4d4-d96743a60008 | note | RESPONSIBILITY: Project Engineer, Site Supervisor
c9383513-4150-5ba1-8974-e0a2a34f9889 | date | Date Completed:
583a005d-b853-40f9-b95e-bc4fb47b6674 | checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
79319afa-0a9f-5262-bda3-eeee0acfac2d | note | FREQUENCY: Frequency: Each lot as required
2b919827-3d01-531c-9d15-1d1fc8edf16c | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
4bae0381-0c34-5370-839c-8f682fd14840 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.28
871288a6-e2bf-5f22-9078-fe12f8966957 | note | METHOD: Visual inspection
261585cf-b479-5dfb-9cec-e396bf65c8c1 | note | RECORD: Signed ITP
210f0da6-8696-52ee-9f62-0e6a662d936c | note | HP
1596a05e-dbc1-5b01-b758-90ccaecf1c26 | note | RESPONSIBILITY: Project Engineer
5ed98743-890f-586e-8d16-09db3f928d3b | note | AP
2c4c61da-e071-517a-b1d7-4cf40db4275e | note | RESPONSIBILITY: Clients Superintendent
e2ec20fe-2e1e-59e9-b1e5-9ec9184887e7 | date | Date Completed:
7417ec5c-e2d5-4efc-848d-5d0271ca6070 | signoff | AUTHORITY HOLDPOINT
f83bb1f1-0aca-4ad7-a620-3892a06136ea | checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
cb5acfe6-b5c0-5377-b0dd-6fbe712a7532 | note | FREQUENCY: Frequency: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
21505dc6-b89a-5175-85ff-4ebf3583adcd | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows.
2f251c14-ed02-5d29-b7d4-0f63687f1394 | note | ○ Rock shall be placed with a geo-textile liner.
9805cdea-c92e-50aa-9188-3c57ad88e797 | note | REFERENCE DOCUMENTS: NIL
4612f305-fe8a-556f-861d-4073f9b9ebe8 | note | METHOD: Visual inspection
721a9869-f59c-5035-8c03-7614f071b1b8 | note | RECORD: Signed ITP
ed0154bd-c42c-59f1-950a-cd8369b94de4 | note | IHP
54846c12-51de-5884-abd4-dff697fb0086 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8a9ba396-4f9a-55f2-9639-6f0b0a43084d | date | Date Completed:
cbce69ae-6c50-4ce3-a22f-da2a3c30666a | section | 3 - Testing Requirement
e4b6438a-6efd-4759-a62d-d9ada64612d9 | checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
bc5b2f8e-6f15-56cb-9f43-106d9e31db79 | note | FREQUENCY: Frequency: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
92ee820c-f253-52a8-8eee-57bf64fd9c0a | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
e3bed635-9e8c-50c6-add7-624d6b4f9f32 | note | (b) Backﬁll
be5aa7f2-7e44-58a2-b8d3-506e3430f445 | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
ef51a040-2191-52e1-8293-a6d444a8d8ae | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
9869f9fc-3d28-55f7-813c-4aaba07bf777 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
3d0a6bbd-9e5f-556d-98c9-aa9e9eeb0cd5 | note | METHOD: Lab Test
8dbf8103-3f47-5343-bacf-a906ca00cf34 | note | RECORD: Signed ITP
2b7882dc-15e6-5377-8b97-76f6001f7212 | note | IHP, SWA
34c2ea96-dbb5-5d56-9fb7-ee59365cf173 | note | RESPONSIBILITY: Project Manager
ccec5bce-c575-550c-b21c-07b3db5bf719 | date | Date Completed:
f3fc747b-1c1f-4beb-961d-175b44599074 | checkpoint | Final Inspection
47811a26-87cb-5499-b365-1a9dafb8d25e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c18a6927-4b57-5b9c-a789-256f6ce2354a | textbox | Print Name:
2088751b-8699-56ed-ae44-fa1b4d37ea12 | textbox | Position:
b49f9ad0-159f-5515-b9fa-831b84bc0ceb | date | Date:
947f66f0-e6fd-4271-87f6-b76aad0784ff | checklist | ITP-005 - Crushed Rock Classed Rev0 | itp | ITP-005 - Crushed Rock Classed
2020fb0e-41c1-4e40-996f-1578b23f4b8f | section | 1 - Preliminary Works
838a352b-01b0-452b-9b14-6666f769bd94 | checkpoint | 1.1 - Induction
9a7c1ad8-12fe-5aad-8285-66da3382ff01 | note | FREQUENCY: Prior to Commencing
d053697e-9a09-5861-90b9-2c9ad43b2323 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
c97b3bbc-cdc2-56e0-ab1c-e8a32ee0d3e6 | note | REFERENCE DOCUMENTS: Inductions Register
ee3734fd-8cc1-5b98-b1fb-9f90f82a1f6a | note | INSPECTION/TEST METHOD: Document review
ea57fd3b-896e-5762-b3ea-c15e51c0234f | note | RECORD OF CONFORMITY: Site induction signed.
18ae9647-1906-594d-b04d-916b54141c17 | note | AP
abfade16-9e27-57e0-a55c-be950ca64393 | note | RESPONSIBILITY: Site Engineer / Site Foreman
da634a3d-4c34-5635-a8e0-7ca2562d7346 | date | Date Completed:
942baf78-7613-4bcc-9ede-9f1208f6faf3 | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
511f9c74-602a-59c1-8afb-5b4e82842073 | note | FREQUENCY: Prior to commencing
0e1a7179-1e06-58a3-96e3-cbd40f127a76 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
4a95c7a4-7830-5d09-a1ef-e67ce8f58479 | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
734f745e-52d0-5d7e-a9b1-65ff0446fe99 | note | INSPECTION/TEST METHOD: Document Review
06b43a78-70a4-5b13-bf3a-0ca106ecc6d8 | note | RECORD OF CONFORMITY: SWMS(s) signed
620eeef1-7480-5151-bded-d21c428fbd37 | note | HP
4d5de37e-4c1b-5dd9-b762-39884a8367c6 | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
bddfbf86-3da0-5fd1-a8d1-49ae58f86d77 | date | Date Completed:
0a30d3d4-deab-4400-bb7e-bbe5d594ac5f | signoff | AUTHORITY HOLDPOINT
63aca20c-74c3-42da-b9bd-71739eda6797 | checkpoint | 1.3 - Check that current revision drawings are being used
8c1c3405-cb2e-528f-9078-21e07e7159d1 | note | FREQUENCY: Prior to Commencing
7230fb2b-ec1d-5d46-bef6-035272e57f99 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
ae40544e-76bb-52b6-8efd-c750e0627b08 | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
5229eb0f-118f-57ed-a57d-b15ae721e9b5 | note | INSPECTION/TEST METHOD: Document review
8bd220fe-6dbf-5848-914e-fa544b79e4a2 | note | RECORD OF CONFORMITY: Latest Revision Drawings
e5bfe400-941b-53ee-938e-3e7b9c41e78e | note | AP
ce130d85-ae5a-5683-8ab6-af4ee095fa3b | note | RESPONSIBILITY: Site Engineer / Site Foreman
857cfbb8-c9a4-5ed3-bc28-bed1aeb047cb | date | Date Completed:
1b6daf88-7f20-4a0e-82bb-36d8c9a35de5 | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
e7e098b0-0704-517d-8d53-b8cd80394d1f | note | FREQUENCY: Prior to Commencing
a73f1d28-9514-5851-a724-eadc19670b42 | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
43ae5ada-aef6-5b8f-8a06-668890d1bca3 | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
7b7d76ca-6da3-5709-9052-4b3aca016a01 | note | INSPECTION/TEST METHOD: Document review & Site inspection
09bd5583-b971-58f5-8904-5736e4a61fb5 | note | RECORD OF CONFORMITY: Signed ITP
ada71b1e-9704-5356-8470-e64bbbf4cbd8 | note | IP
cc3226e0-5c99-50ff-8f4b-2f466cc2ad71 | note | RESPONSIBILITY: Site Engineer
6fc26210-508b-5bab-a031-d43496063fe5 | date | Date Completed:
ef854423-ce1a-45d6-9ea9-d0c36f75cc61 | checkpoint | 1.5 - Excavation Permit issued
c0c7c67a-7918-575a-b39e-78197087be45 | note | FREQUENCY: Prior to Commencing
70b9e721-f045-5ec1-af7d-547d10d58d89 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
6f361567-0130-5781-ba5f-4e08e12ad304 | note | REFERENCE DOCUMENTS: Excavation Permit
1ef73bb7-952f-562b-a8d7-4a3a499355ac | note | INSPECTION/TEST METHOD: Document review
489ed476-5dd4-5c5a-803b-a6fe894f80a5 | note | RECORD OF CONFORMITY: Excavation Permit #
5f9f9fea-c440-53d2-88c5-254a7ee38608 | note | IP
d66470db-afc4-57a3-bfb8-d00f722d1f4d | note | RESPONSIBILITY: Site Engineer
46248ac0-2ae7-52be-b9e6-6f8eb3098acb | date | Date Completed:
2895d82b-3f03-44b2-8204-1dfd4cffa6e3 | checkpoint | 1.6 - Crushed Rock Mix design
705a6315-2150-5d3f-a8ab-b77a6f84bba3 | note | FREQUENCY: Prior to Commencing Work
f03d2c9b-6637-5c9a-a466-aa700a678cd9 | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
2eab0edd-64e8-5bf1-b8d4-e65679d54bec | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
0a30e1e9-ebe5-5437-b7a4-49d43bcb11aa | note | INSPECTION/TEST METHOD: Document Review
75b0366f-e6d0-5e7b-8694-afeb33aa28b5 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
a47b1cff-8ba1-5154-845a-d48785a27c0a | note | HP*
13d1b9ec-7cb0-5447-9f98-2e07b0c9e9c6 | note | RESPONSIBILITY: Site Engineer
9785b454-4d15-5a5c-a6ae-968ac0a50f44 | date | Date Completed:
f27f9961-da6c-43f9-b99a-02ff22325314 | section | 2 - Placing Fill
6105a92e-bc6a-4054-a176-0c47328a747e | checkpoint | 2.1 - Transverse Joints
b13b61f4-6f44-5a5e-95d0-eabd3dd4854f | note | FREQUENCY: Check prior to placing material
51e10262-7898-5ba0-b384-9da56a1df0f8 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
17f08495-cbac-5e5b-be5c-3adf6769df04 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
3549b656-3824-5b9a-8273-9ca028ec5ce5 | note | INSPECTION/TEST METHOD: Site Inspection
adf4e63c-03cb-5d96-b90d-44dff1a0cacc | note | RECORD OF CONFORMITY: Signed ITP
baf6a29a-edc9-53fa-af8f-0cd3624ba826 | note | IP
7a590476-660d-561e-b9cf-15e1f7d723bc | note | RESPONSIBILITY: Site Engineer
84aa847d-4f7a-55a0-9f6d-5704b88d4ef8 | date | Date Completed:
62a79b75-0649-4fc9-aba3-073927d2d487 | checkpoint | 2.2 - Longitudinal Joints
7359ce22-36bc-5ccd-819f-3d5b8f6e3c75 | note | FREQUENCY: Check prior to placing material
e5c262b6-3435-5010-b5e4-4c6ea90b4eb2 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
3944b4d8-4fcd-56e3-b30f-c886a3751e86 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
d9a56e3c-be0d-5dbc-9eb9-9fd598db46d0 | note | INSPECTION/TEST METHOD: Site Inspection
32510b69-6ca2-509f-b4a8-ac11f6f82834 | note | RECORD OF CONFORMITY: Signed ITP
99d69840-72d0-5ce8-829f-455b53413272 | note | IP
99d5573a-a3a2-5def-84d6-282dceda6491 | note | RESPONSIBILITY: Site Engineer
563ecdc9-e5d6-5c34-9749-4668712e760f | date | Date Completed:
6a5196cd-ed6a-47c3-ab2e-1a6239544615 | checkpoint | 2.3 - Lot Size
7767dc07-2ae6-5b65-a417-c6e5104db629 | note | FREQUENCY: Check prior to placing material
43b7b35c-e503-5c0c-a5d9-eaddfa24c3b1 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
7c1e9d56-56f7-519f-aec6-595c6c2c0ab2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
cff6583f-386b-52ae-9a6e-97b79fceabef | note | INSPECTION/TEST METHOD: Site Inspection
68b2024f-e153-5529-b2d3-8266b5317cfe | note | RECORD OF CONFORMITY: Signed ITP
15f3377d-ba57-5002-af5e-892607a812c7 | note | IP
50d908c8-c456-51aa-9f32-6043aa839f2e | note | RESPONSIBILITY: Site Engineer
9852563b-6462-5d45-a896-a5a457d990d3 | date | Date Completed:
fc9097d5-19b4-4c66-8c36-f3d1e48be65a | checkpoint | 2.4 - Proof Roll
cccb6cf0-821e-5976-ab4f-a6af8baf8bd8 | note | FREQUENCY: After placing material
bcc5e73b-6cb3-5a8b-9ee8-c80943750c03 | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
111f7b66-ef03-5faf-b2d7-dc636158d64b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
dfd80e9e-c479-50e5-8997-ded6750f4807 | note | INSPECTION/TEST METHOD: Site Inspection
b12226af-a495-5aaf-9e08-687bf94b20c1 | note | RECORD OF CONFORMITY: Signed ITP
8c16e54b-77d7-56a5-bff8-63d3208bca28 | note | WP
ba82a8a1-fab9-57b3-86ad-300bd5ca1826 | note | RESPONSIBILITY: Site Engineer & Superintendent
db29232d-9657-52d7-b60b-6cf1dd46a677 | date | Date Completed:
1090f299-4497-4ca0-8a11-bc8d8abf0af0 | section | 3 - Testing Requirements
ec30cc44-a7c7-4cd1-a37e-de32507c3220 | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
da9ca79c-2c1b-505e-8fe1-e25ffedc8437 | note | FREQUENCY: Prior to Testing
1b6f3c96-1e2e-5ad6-80e7-9989fd72be18 | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
a8c9cb90-7a13-518c-a823-a0cb9ef09350 | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
3b33450b-fb18-5da1-bc81-9e9f5bec5a23 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
a61c0f18-533c-5c46-bd8e-471455082774 | note | ○ VicRoads Spec. Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i) Table 304.111
10656384-3ed5-58ca-988b-b70882b74fb6 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
8ae39310-f798-5c5f-a94b-09626238cc43 | note | RECORD OF CONFORMITY: Signed ITP
f01f60c0-9fe9-5f1b-8fd9-ee66c6cb26bd | note | IP
8472f391-3bc2-5cd5-8f33-a910eddec296 | note | RESPONSIBILITY: Site Engineer
b5b78e86-4b2b-54f9-adb3-434c4279aecf | date | Date Completed:
96680e86-bbf5-4d3c-a032-de91c83371b6 | checkpoint | 3.2 - Modified Compactive Effort
3e19fc62-a8d9-5585-a30c-3996dc813047 | note | FREQUENCY: As per 3.1
ddecc0b8-ba11-5361-bbcd-a5333dc87bd2 | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test Initial Frequency
d93217ba-288c-5cb7-9e28-44073433a416 | textbox | Test No. |  |  | — > 97.0%
b332720d-0595-5b47-aaf7-7e30d6f655df | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
bc0b88ec-8356-56fb-a501-aed16e57eb15 | note | INSPECTION/TEST METHOD: Site Inspection
7f37363b-bade-5041-966e-ead3d52dfae6 | note | RECORD OF CONFORMITY: Test Records
f5eb93b4-8557-5a4f-abbd-1284acecb79c | note | TP
dae4d601-ffac-53d5-aa57-0ac78a273d81 | note | RESPONSIBILITY: Site Engineer
649328f9-c3e2-5db2-9745-8f54aa0c79b1 | date | Date Completed:
854ae4e2-f8b4-45a3-b212-e34764074981 | checkpoint | 3.3 - Permeability Testing
f8342f2d-2169-5525-b33a-a9721b4f2597 | note | FREQUENCY: As per 3.1
f5da747d-7758-581c-89f1-ec776f0500d5 | note | ACCEPTANCE CRITERIA: Class 4 Crushed rock max 5x10^-9 m/sec.
0f3c9c8b-17eb-5d63-b3a3-6f669c8cfe3d | note | ○ Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051 and allows FH to use 9x10-9 m/s Max permeability
66070fe7-dd9d-51a6-86b3-602f4f5f5618 | note | REFERENCE DOCUMENTS: Project Spec. Cl.3040.05(a) Table 3040.051, RFI-0085.01
9d995c64-da74-53da-b025-30c870b747ea | note | INSPECTION/TEST METHOD: Site Inspection
4904977d-1fd7-57e1-8a56-bf79e397e1b5 | note | RECORD OF CONFORMITY: Test Records from Supplier
55e4b06c-a6c5-5d0f-8abd-8c1b644b84c7 | note | TP
38e481fc-a612-558a-8b0a-a63e760fbbb6 | note | RESPONSIBILITY: Site Engineer
939d3a63-2c01-55b1-8963-17202a79b0c4 | date | Date Completed:
3ad6291a-6f60-4145-8d1c-f7d0e0486f76 | checkpoint | 3.4 - Survey Level
5404c62a-84d2-5035-99e4-b1f54de58289 | note | FREQUENCY: At completion
d37022b3-224e-5e3a-a739-a6ebfc10c2dc | note | ACCEPTANCE CRITERIA: Scale A:
8278bb1f-166f-5d40-8e35-1875c2f21828 | note | — Minimum number of measurements per lot: 80 For Upper
f4bf8f28-c6c6-567b-a44f-4c9d950add3a | note | — Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm
b65eddca-3edc-542b-8e9d-2d956c889f1d | note | — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm.
ad8f82e4-fe3e-5402-aa82-c24875e3bccd | note | — Base: Mean ± 5 with a maximum Standard Deviation of 8mm.
de589f28-f1c6-553b-80fc-35a908b37793 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
8e3a6e2a-a1c3-5b7f-955d-c9d3ed703449 | note | INSPECTION/TEST METHOD: Site Inspection
c3a5dc37-f187-5d3e-88dd-11f6c8ce24ad | note | RECORD OF CONFORMITY: Test Records
c33a84b6-faa7-5fa0-951a-6aa695547cc0 | note | TP
7705c659-6eb2-5410-95fa-b021b83d5e61 | note | RESPONSIBILITY: Site Engineer
e6ad65d9-4f1f-5ae9-baeb-28faf70bb4fd | date | Date Completed:
74210593-5a4f-4976-b9ea-07167cdc89ae | checkpoint | Final Inspection
8834ca9f-b52e-58de-918b-98fa256a5d80 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6da7603e-0cfb-5e77-8a7f-b5c1fd716619 | textbox | Print Name:
0ea56476-a592-5af2-9ff0-7bc7702e3ded | textbox | Position:
69cac457-f869-5c13-b318-4b4a5eaa5b9b | date | Date:
af6af302-cfc6-48d7-b352-7bd5b20df8a9 | checklist | ITP-006 - Subgrade Preperation Rev0 | itp | ITP-006 - Subgrade Preperation
0734be7c-9dde-48c7-a7d8-4bd38fecdfca | section | 1 - Preliminary Works
ab92e78b-223d-4677-8448-ea3c14afb2c2 | checkpoint | 1.1 - Induction
c8e2971f-bed5-528f-a7f7-ae301d5610b5 | note | FREQUENCY: Prior to Commencing
0ce2ec9f-42ba-5934-8f38-79a381c2fe36 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
2771fdc2-9ba5-58ca-9f43-377bc6b0fc7b | note | REFERENCE DOCUMENTS: Inductions Register
f2c79a0d-380d-597f-83ef-e2fe45e271dc | note | INSPECTION/TEST METHOD: Document review
c2c5990e-58ad-51b2-9ad1-a4b9f068d5b7 | note | RECORD OF CONFORMITY: Site induction signed.
bb494315-bec1-5b75-b76f-ff3b9e823292 | note | AP
5f38268b-b15a-50c9-8733-19295fff2dab | note | RESPONSIBILITY: Site Engineer / Site Foreman
67b4fef3-2bcd-510f-b146-c01a22871ab6 | date | Date Completed:
990506d2-27b4-43fb-b469-205772e36f06 | checkpoint | 1.2 - Check that current revision drawings are being used
8ef19664-d42e-5458-9420-b44f6b6eb7db | note | FREQUENCY: Prior to Commencing
b2ebbdb9-d168-5abc-a8ca-db19d55b2ff4 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
620c4b71-354a-5379-a396-77ad8ab8431f | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
026908bd-8240-5c8c-89fe-d9f689034952 | note | INSPECTION/TEST METHOD: Document review
3d2d0d69-f077-598e-81ca-97b78a12cd89 | note | RECORD OF CONFORMITY: Latest Revision Drawings
c55ef584-5371-5a0e-bd1d-30ae6c698b48 | note | AP
3ab7f6a1-2edf-5c33-b065-cf25cbba1854 | note | RESPONSIBILITY: Site Engineer / Site Foreman
fdaad0a8-39c5-5016-b689-5b522b9b8883 | date | Date Completed:
03b7bc6c-e89c-484b-a890-704d58751bde | checkpoint | 1.3 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
c40a5a30-94f5-52ef-a736-a40dddc1d355 | note | FREQUENCY: Prior to Commencing
34748353-60da-5fe9-b32f-34cc72475d08 | note | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
7d88f4b5-f4bb-5cf2-b084-e95a8b7a869d | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
c15eab8f-fb2c-5104-a63d-568d4fbfbb1d | note | INSPECTION/TEST METHOD: Document review & Site inspection
ab99d194-0bd7-5a2b-8399-c43b2a41704f | note | RECORD OF CONFORMITY: Signed ITP
2645e5ac-c9e0-5c8f-99bd-c85e7d0d3d0f | note | IP
12533ff3-8a65-5f5e-a657-1a5cd3fdb466 | note | RESPONSIBILITY: Site Engineer
5b5ff844-1b43-5ebc-9172-87fca2a9543a | date | Date Completed:
9e2a8777-3e40-41a8-9fd6-ed9408b5d950 | checkpoint | 1.4 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
d6f31d26-1a10-5a72-b6aa-b7db21986283 | note | FREQUENCY: Prior to commencing
c8d9fa78-566c-5785-a790-eaab79cb7769 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
a2e3b362-f594-5cae-af05-d9cc124a9f9d | note | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
df80d37d-aaf1-5420-80b4-ad2f78b78074 | note | INSPECTION/TEST METHOD: Document Review
f19258a3-1e79-584e-85ba-5c1fe2d10f71 | note | RECORD OF CONFORMITY: SWMS(s) signed
f172d820-1b2d-5901-b193-a3acbb32324e | note | IP
58385ce5-35db-5411-bd7a-73d4065ac0bc | note | RESPONSIBILITY: Site Engineer & Superintendent
3d1324ca-cd81-54a8-9a96-3ba71e5e42e4 | date | Date Completed:
aff9f0a8-0dbd-4983-98cd-228379ac4704 | checkpoint | 1.5 - Excavation Permit issued
6e914de4-3233-55f8-bdf4-da7f764042f7 | note | FREQUENCY: Prior to commencing
f3095d8f-7b94-54fa-ba69-8948c2746602 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
fbcd4168-0ce6-5eb5-a236-6547c48fdc2f | note | REFERENCE DOCUMENTS: Excavation Permit
392dc257-ef46-5e7b-a675-a0039773e83b | note | INSPECTION/TEST METHOD: Document Review
9e9cdf0b-1c5a-5318-a850-a68f2c1b5922 | note | RECORD OF CONFORMITY: Excavation Permit No.
074c00ff-594a-5b75-86ae-d9e90958b06b | note | IP
7967b249-308e-593f-a564-2ccd2f32953d | note | RESPONSIBILITY: Site Engineer & Superintendent
d9d149c0-e319-5ba7-9b1d-77e3be018199 | date | Date Completed:
c54d28ec-32df-4561-bb7d-29d363da1328 | section | 2 - Construction Works
f439331c-af9c-43fb-8720-449d062bca99 | checkpoint | 2.1 - Survey set-out
3ad27ee7-36b8-5281-902e-7e7aa60a5a4a | note | FREQUENCY: Prior to Commencing
b0852492-68cf-555b-93e5-b3c94671a18c | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
5225fb40-0e3f-5db4-a615-1e92bc2964da | note | REFERENCE DOCUMENTS: Project Spec. Cl.1190.07, Latest IFC Drawings
fdd0abdf-fc20-5e6f-8740-75f3aa5f61e0 | note | INSPECTION/TEST METHOD: Site Inspection
b10412f6-cdcd-505c-8b0d-7474b6ec29e0 | note | RECORD OF CONFORMITY: Compliance with latest IFC drawings. Survey records & pegs on the ground.
0c6e7b83-be66-59fa-9082-cdba7841f229 | note | SCP
29a690cf-504d-57fb-9c8d-dae53a479911 | note | RESPONSIBILITY: Site Engineer & Surveyor
a3bdc6c0-6f10-53f0-bc0c-8003f977b4d7 | date | Date Completed:
b82d1bcc-ab75-4539-9569-c0e1879eb7f6 | checkpoint | 2.2 - Unsuitable Material
b79e6a7c-45f4-5a07-99fd-b7d760535fc9 | note | FREQUENCY: During Excavation
43a64b8f-02a2-503f-8699-1a14c785b3cd | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
8c992155-c9d8-5ac9-b75f-eafbd9e3717c | note | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
8240e54f-9e37-59c8-a56c-4a68553e53f1 | note | REFERENCE DOCUMENTS: IFC Drawings
fdf5be83-f8f8-572f-bfb1-47f372d72e00 | note | INSPECTION/TEST METHOD: Visual Inspection
715a68f3-1716-5845-8f68-2cdcf5a5b79d | note | RECORD OF CONFORMITY: This ITP Signed off
e9dc5bf8-2faf-589f-9d54-7bfa0de49bfe | note | IP
6663746a-11c4-54a1-83fa-b7870cd99704 | note | RESPONSIBILITY: Project Engineer
b1f6d050-1c8d-5f16-af7e-b9829ac2719b | date | Date Completed:
a16cfc11-ba3c-41bb-b6ba-d484b05c12d3 | checkpoint | 2.3 - Material Category
2703bf70-19e5-5322-ba6f-a38100cbc902 | note | FREQUENCY: Prior to Commencing
419d4853-a2be-5615-8cf6-a8bf626966f8 | note | ACCEPTANCE CRITERIA: Prior excavation, Superintendent and Fulton Hogan responsible shall inspect each type of material encountered and, subject to verification by laboratory testing, agree on category of material in accordance with VicRoads Spec Section 204.04
dcb72d91-eca8-5a9e-a935-888774787bdd | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06(c)
ac0d3eca-0eeb-5c33-a363-dce2ccfe0cfe | note | INSPECTION/TEST METHOD: Document Review
0a1afb63-ee43-5549-a8bb-d1800209840f | note | RECORD OF CONFORMITY: Superintendent agreement, Signed ITP
df6ff53f-f201-5c2b-8774-382e047d7b5b | note | HP
f57f9633-b85d-5ffa-8ddd-a7040158b188 | note | RESPONSIBILITY: Site Engineer & Superintendent
f6e2cda8-c235-5c7d-9829-32b6772f7a83 | date | Date Completed:
978cc5f6-7868-4dc1-81e2-0217622a83bd | signoff | AUTHORITY HOLDPOINT
107ddb06-e610-4dd5-bec0-532935e3a75c | checkpoint | 2.4 - Trimming and level conformity
c2588e32-7964-55a3-880a-b2c40ba28c40 | note | FREQUENCY: Each Lot (one day's production) prior to Commencing
5bf36b9d-dd73-59d9-bff4-44545fe09067 | note | ACCEPTANCE CRITERIA: Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping not differ by more than 5 mm above or 15 mm below the specified level. Level at any point of sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns. Water shall not pond at any point. The mean and standard deviation of the departures from the theoretical surface level within each lot shall meet the requirements of Table 204.031.
a4875b87-c5d2-53e8-8ba4-805b694a9987 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.03(f), Cl. 204.03(g) Table 204.031
0149ff36-276a-5fb9-9e8c-ced4ca30aa21 | note | INSPECTION/TEST METHOD: Survey Report
ac8692e7-ff48-5374-8e6d-a4d4a88de03f | note | RECORD OF CONFORMITY: Survey Record
7b6a6daf-4133-57e5-a1d3-2a2cad029046 | note | SCP
821a7aa1-c3c7-51d1-84ca-b03345d34680 | note | RESPONSIBILITY: Site Engineer & Surveyor
e337acd3-38b4-59e9-ad14-4b0c549ab5db | date | Date Completed:
a87c5134-9559-4832-9c7c-3537e5f432f1 | checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
39f6d40b-9bd8-5895-9d90-a8ae577e8d41 | note | FREQUENCY: Prior construction of the regulating layer
c90571db-37c0-5c61-9dbe-1ce72aafd94d | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
7ee5a9d6-f93d-5383-a9e9-14522ce794a1 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
f8378d64-4473-5c39-bc42-e1593f414db0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
1e0dcc0c-0596-55cf-a8b1-3174ad98ed97 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
1436b050-0708-5103-9b61-7d5414f2609a | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
92e79faa-3706-59bd-b7f3-668c193d2195 | note | HP
abc3d384-8f83-570a-ba97-090a0f73608c | note | RESPONSIBILITY: Site Engineer & Superintendent
51f7dbf5-5261-5fcc-9a05-a9f81efb27df | date | Date Completed:
3ef5ca4e-894a-4935-929f-215600fff1f1 | signoff | AUTHORITY HOLDPOINT
9519b8c4-7050-4f3d-b24e-5c0fff3d1b51 | checkpoint | 2.6 - Cut to Fill Zones
10e2d395-3325-5f16-9491-32d81ec82b31 | note | FREQUENCY: Each Lot (one day's production) prior to Commencing
959a249c-f29f-5e17-9932-207dc61a4169 | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
7431c4bd-72a2-571e-a13b-4e0590e74f58 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(g)
e7690213-9d3a-55df-bac3-3ce9ffcc5207 | note | INSPECTION/TEST METHOD: Site Inspection
4d5d68cf-14dd-59e4-b122-12dd0d9560cc | note | RECORD OF CONFORMITY: Signed ITP
c8f9c907-38cf-5c1b-b589-907b2307ccf0 | note | IP
6b958a8b-5b36-5d7e-953a-b3e979438a90 | note | RESPONSIBILITY: Site Engineer
276632e7-40f1-5209-9d04-8527bde5ea51 | date | Date Completed:
2135921f-3b87-48c3-8094-5ed8e26362df | section | 3 - Testing for Compaction and Material Properties
16679cff-95e2-47d0-8641-439a17592ff2 | checkpoint | 3.1 - Proof Rolling
666a02e1-8d94-56fd-a2ce-08c85326c124 | note | FREQUENCY: Each Lot (one day's production), prior to Commencing Fill
af6d003b-65d3-5483-ba07-ace2606d1249 | note | ACCEPTANCE CRITERIA: Test rolling of all fill layers and subgrade shall be in accordance with Section 173 and 204 of the VicRoads Standard Specification.
100aa308-74f1-5b0e-a5e8-e1cb847180b2 | note | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
c59ed4e9-7a40-577c-985d-21fa18e68b2b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.03, Cl. 204.12
9ac8641f-bac2-5f96-8a6e-84fa864fff57 | note | INSPECTION/TEST METHOD: Site Inspection
ea37bcc6-d732-5b26-8b5a-2e9fb96c98f2 | note | RECORD OF CONFORMITY: Proof Rolling Register signed.
e5c047bd-0654-5657-8054-bc28f108814a | note | WP
a7b85dcc-028b-5098-abd7-8c4a02b89911 | note | RESPONSIBILITY: Site Engineer & Superintendent
76f77700-0397-51bb-967b-9d3c9a2d77b1 | date | Date Completed:
f3a031d7-1f65-494c-8492-8083a08774f4 | checkpoint | 3.2 - Testing for Compaction and Material Properties
6ce08fc4-9407-5ca5-b6a0-407378063dba | note | FREQUENCY: Testing as per table 204.141 of VicRoads Spec. for Roadworks and Bridgeworks
8daab0fb-107f-5552-8ce2-fe4c3df1d36c | note | ACCEPTANCE CRITERIA: Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level= minimum compaction 99% MDD.
fb064a4b-42c4-50a7-bb14-7c05a7710b49 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of cuts= minimum compaction 97% MDD.
35638771-a2de-5730-a504-62814986677d | note | REFERENCE DOCUMENTS: VicRoads Spec.
4fa47374-1abf-5b60-9bff-518083f3abf3 | note | ○ Cl. 173.04
1eeb6f36-5090-523c-9364-c890e2279bf7 | note | ○ Cl. 204.13
12fae326-ac3f-5640-bc26-9ca34a684803 | note | ○ Cl. 204.14
ae31703c-d9e8-5d38-adbf-a640a3d85c5d | note | ○ Table 204.131
6fa84784-ccd4-509c-bc15-0deb39435085 | note | ○ Table 204.141
5686e113-10fe-5f8e-843d-0d2bf7f7f1da | note | INSPECTION/TEST METHOD: Site Inspection
e61dc14d-5454-5c6a-b065-de14e94fa263 | note | RECORD OF CONFORMITY: Test Results
3a4cfd71-92e5-5332-96e5-d4669e3f62a0 | note | TP
b5dcc3f6-3077-5c72-b8fa-0657ffe2cdd0 | note | RESPONSIBILITY: Site Engineer
427a990d-14df-56c7-84da-6e7b49ced1d8 | date | Date Completed:
5c349b03-d103-4eb5-baa9-8e496984d996 | checkpoint | Final Inspection
9283c039-3e93-5b35-84cc-9e1b9043b64d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
19d95070-1f1c-5392-9cfb-9e12f585a417 | textbox | Print Name:
ce91d8c4-9da7-5f2d-8ee4-16aca492ab29 | textbox | Position:
bba0426f-768e-5cc3-929f-0a24f430c6fd | date | Date:
44521c77-b1ab-4eed-a78d-a6bc8e1b91d7 | checklist | ITP-007 - Guardrail Installation Rev0 | itp | ITP-007 - Guardrail Installation
115a6542-7acb-4332-b0c4-d29b78e9f913 | section | 1 - Preliminary Works
27271d66-64a4-4a44-84a0-f2f132676621 | checkpoint | 1.1 - Induction
58e3998c-d219-5012-80b7-efeead370d49 | note | FREQUENCY: Prior to Commencing
72c2d0af-de7d-570f-beb6-570eb1ad7676 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
86df2608-bcff-53cf-b3f9-41205a3d2ae9 | note | REFERENCE DOCUMENTS: Inductions Register
3b7eecfd-b8da-5553-a393-aa0c091899f0 | note | INSPECTION/TEST METHOD: Document review
a8f8fb3c-86e0-5e73-a859-4b6404b03f8e | note | RECORD OF CONFORMITY: Site induction signed.
1fa5ba39-e128-51f5-a03f-f4fafae27c3d | note | AP
fd8a72a5-f795-5945-8bac-9b75745d0b15 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0e9a4028-705b-54a1-a1ce-df9c63814a3f | date | Date Completed:
39aa4c59-4cac-4cfc-a61a-4f6b97f71511 | checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
0fd52697-1ef9-56bd-801e-5fb0966f2e89 | note | FREQUENCY: Prior to commencing
dad768d0-6935-5805-a5ad-37708474a117 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
75c68f4f-c445-5364-b69f-5222d059d78b | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
127403cb-75a3-5c70-b044-d4655fe7c47c | note | INSPECTION/TEST METHOD: Document Review
54fbe426-c35f-55ec-ba56-0988c7304376 | note | RECORD OF CONFORMITY: SWMS(s) signed
45644572-dca0-5434-a0df-9a6872c7f326 | note | IP
bb7bd5c8-e4ff-5086-8ba0-7ef578b414d9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
da1f270f-75b8-540e-b2dc-56fd40e8ad65 | date | Date Completed:
bcdba2c8-2341-42d5-b319-cf6b1b7f7a0a | checkpoint | 1.3 - Check that current revision drawings are being used
35d75b36-69f9-5281-9d95-d7516167d0b2 | note | FREQUENCY: Prior to Commencing
b5869517-ee48-5a61-82af-07bed64bcabd | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
d6be4142-225b-5db4-a956-bc15a964a017 | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
b2a82650-9350-50eb-a51d-cfc9511ede85 | note | INSPECTION/TEST METHOD: Document review
baf96729-c683-58b1-8062-1012982f70f4 | note | RECORD OF CONFORMITY: Latest Revision Drawings
16f8838a-426d-5456-a06d-3801fde430f1 | note | AP
7ece7bb5-53d0-5055-9958-bbe21bb4b95e | note | RESPONSIBILITY: Site Engineer / Site Foreman
fbcf4e37-43f1-57d1-a2a0-a259f65ff26b | date | Date Completed:
dd74fb4c-b0ac-4e51-aac8-e18981686b2d | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
36dbe40d-02c7-5c10-b2c7-b113ceeaffa6 | note | FREQUENCY: Prior to Commencing
a490e40c-b247-5bda-92f3-05d78a5fb6be | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
bd16730c-bbd6-5267-924e-25bc77dd961a | note | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
ba5097df-c9f4-5b94-a5b2-168ab21a498d | note | INSPECTION/TEST METHOD: Document review & Site inspection
42a3e52b-308a-534f-a8d3-ee5a7a3a9f08 | note | RECORD OF CONFORMITY: Signed ITP
a1f7243b-e4c5-5c5d-a85b-69eb406c2e55 | note | IP
13c4c3ac-2395-5418-86a9-5eb839e3d7d9 | note | RESPONSIBILITY: Site Engineer
1167a06e-44ac-57b0-951f-73b9104eadd0 | date | Date Completed:
89d1b01d-9202-4e89-b607-3a4616b42ecf | checkpoint | 1.5 - Excavation Permit issued
522d881b-e80a-585f-8770-99e60b42ee57 | note | FREQUENCY: Prior to Commencing
7be3efbc-ed70-56f5-9ab5-c3fd37af9fbc | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
873803cd-e604-58bc-a877-b9c398516536 | note | REFERENCE DOCUMENTS: Excavation Permit
07b62893-db71-5525-9202-b3a748bc3b80 | note | INSPECTION/TEST METHOD: Document review
c4759259-560f-51ad-89cc-b4697427f759 | note | RECORD OF CONFORMITY: Excavation Permit #
84962162-91fb-54b7-96b6-0afb7b0984ef | note | IP
11a3f365-53af-509d-829b-a614552640d6 | note | RESPONSIBILITY: Site Engineer
cd22406d-e2a2-5b4a-92ae-3e8a3ee3f92f | date | Date Completed:
fb800d3f-dfde-4dd9-882d-4505359a7de9 | checkpoint | 1.6 - Approval of Guardrail System
a1fba43e-23cd-5779-9415-3527af2639db | note | FREQUENCY: Prior to Commencing
7e7b3e24-63b5-5745-94b8-0a389dddb554 | note | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
a3ddf4a6-b492-5fc8-b113-d96305e1729c | note | REFERENCE DOCUMENTS: RDN 06-04
feeec57c-856f-5802-8d76-0e469d7daf64 | note | INSPECTION/TEST METHOD: Document review
294feade-6845-55e7-98bf-f44536a326db | note | RECORD OF CONFORMITY: Signed ITP/Email
c5e5cec3-adc0-554d-a7a3-504cc9618361 | note | HP
0f81d139-a3c0-59cb-bc5d-6471fccb5182 | note | RESPONSIBILITY: Superintendent / Site Engineer
7212149a-f1bd-5233-8149-ca49661bbb5f | date | Date Completed:
f336b375-73f1-430e-a552-0a166ce69922 | signoff | AUTHORITY HOLDPOINT
d37f8ca6-77be-46a4-8811-a40f47ea5ee2 | checkpoint | 2.1 - Approved steel supply
2824854a-371c-5689-8820-8a352efc839e | note | FREQUENCY: Prior to Commencing
014a40d4-47b2-54ec-8ffb-b6decdc15f07 | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
18d4ead3-de85-59e7-8d0f-c07cfe8ebcc0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(b)
cb784e97-555e-51e7-bd07-70d283d1e322 | note | INSPECTION/TEST METHOD: Document review
2186da8c-a37e-5b7d-b632-aa83ae37f846 | note | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved), Material Test Certificates
6501f1bb-5480-5162-90a5-1197c64cbda9 | note | HP
6be467b4-cf34-55aa-9753-3c016b0ce0d3 | note | RESPONSIBILITY: Superintendent / Site Engineer
c854b5c9-0970-5a58-93eb-7715a990a346 | date | Date Completed:
ceaaaa3e-050c-4b8b-85bd-228ddf1911ca | signoff | AUTHORITY HOLDPOINT
2fbc8541-30bd-421f-8e4e-0ab752adee34 | checkpoint | 2.2 - Approved Galvanisation records
94405c3f-f746-5f3d-b8ee-bc38027f61e7 | note | FREQUENCY: Prior to Commencing
cb44635b-9d55-50e7-8d7f-7f88e27b31d9 | note | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform
05b1c165-3d5b-55eb-b39b-2f4d4b09b81b | note | REFERENCE DOCUMENTS: VicRoads Spec.Cl.708.05(d)
45d76e44-6e1a-5d79-ba5d-1e69df6110e7 | note | INSPECTION/TEST METHOD: Document review
55787c1c-0bb7-5010-b32a-0b22ee9836c2 | note | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance, Test Certificates
8e649a07-b952-50d0-abec-c0151b93fc50 | note | HP
1d8b5a43-3212-5fe5-9bd7-be25ed66c986 | note | RESPONSIBILITY: Superintendent / Site Engineer
00c8cf44-81f7-5109-bdd5-f117a2109cb6 | date | Date Completed:
710c909c-7125-4bd4-8e8c-3f4ae0c52e71 | signoff | AUTHORITY HOLDPOINT
b0ccaf79-ce42-4cf5-a57a-a6069797ac86 | checkpoint | 3.1 - Survey set-out
2e7fb669-f179-50ad-942f-0dc8538674ea | note | FREQUENCY: Prior to Commencing
166d4570-7cd9-503a-aa5b-e604698afc51 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.. IFC and latest available revision used
b98ec056-16a9-5932-a0a7-fb778541a944 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
6e89d3f0-28e6-5720-9a6e-df65c553170f | note | INSPECTION/TEST METHOD: Site inspection
67c2c154-06fe-5b2e-b1ac-543c16ecccd1 | note | RECORD OF CONFORMITY: Signed ITP
3dcb878d-1afc-5c46-a88f-e8d56775e880 | note | SCP
ea80aa42-feda-5c19-a790-cf45f246477a | note | RESPONSIBILITY: Superintendent / Site Engineer
3a7a41ee-bd0f-5211-a336-a35918bc699a | date | Date Completed:
cc919ad6-b022-4fb7-8f8d-a0f63fbf6ff6 | checkpoint | 3.2 - Service Location
c19d1df9-ede8-573b-b1b5-0cf879a384d2 | note | FREQUENCY: Prior to Commencing
151b21ca-d2e2-53e8-a395-117f0dfa6d90 | note | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
8c6edda3-2f40-5707-a3b7-2caa1cf34d9c | note | REFERENCE DOCUMENTS: Services file & Current DBYD notifications
ba534e48-a37a-5485-ad37-d6836f020bf0 | note | INSPECTION/TEST METHOD: Site inspection
632c847e-5b1a-5ec5-bd40-8bdad09234d7 | note | RECORD OF CONFORMITY: Services marked on the ground
1ae99238-6ce5-5009-bc12-39d90ead1c93 | note | IP
2bccbcd6-b82e-5220-ba61-53205632060a | note | RESPONSIBILITY: Site Engineer
cba3b36f-8453-55c1-892d-32f45e77c1a5 | date | Date Completed:
b5b84645-941d-4e42-83c6-793adb1da405 | checkpoint | 3.3 - Approval of location and length
5a43f6cf-c576-5ed9-aaa0-5e368f4a27f8 | note | FREQUENCY: Prior to Installation
fe7b91f7-4661-5eb5-97cd-e9b1032619c9 | note | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the superintendent the required location and length of all guard fence.
14b2bcd3-3793-589d-933b-8ce4dc49d4e3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
1c9bec6b-07e7-5cf1-85b3-93cb5fa16d15 | note | INSPECTION/TEST METHOD: Site inspection
ebb6913b-6eb2-5a73-b1a5-2a88de9e0560 | note | RECORD OF CONFORMITY: Signed ITP
8a405d9f-eba1-5f09-83fd-d2d522acba79 | note | HP
e1e4f5ac-19de-5ad5-a056-8f6c2cc356b3 | note | RESPONSIBILITY: Superintendent / Site Engineer
1a11237a-ff8a-5c3d-a76a-8722e8451619 | date | Date Completed:
b1b878f6-e3f1-48b0-be43-cf96a70a207a | signoff | AUTHORITY HOLDPOINT
014b833b-ea46-49ac-9691-a189da071b54 | checkpoint | 3.4 - Install posts, rails and terminations
a21b26b1-14ac-52d8-9a95-c91618425f80 | note | FREQUENCY: During construction.
1f65ddba-dabc-5c7f-b040-51cf4eb134fb | note | ACCEPTANCE CRITERIA: Tolerances
66336c1e-078f-5697-b3e3-39e560bc0512 | note | W-beam guard fence shall be erected to the following tolerances:
73d8d01c-a55c-51ef-84f0-b1add2e5d083 | note | (i) Variation from true plan position of posts ±20 mm
5ce7eff7-c04e-5eac-865a-09be85e2ab19 | note | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
c7c5d14c-5c36-5ded-adcc-f7e5ec34233c | note | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
b58b3d9b-1405-50da-823e-6b3725567845 | note | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
9d651196-b0c5-56ee-848f-de12ed840dbb | note | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
e97f956f-79fc-5539-b457-ee3d3fd2d9f2 | note | (vi) Dimension of holes -0 mm, +50 mm
d47adc3d-480a-5c14-97d7-9b070187c4ad | note | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
16917ee3-e21b-5a2d-994c-28dad4bdffd8 | note | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length
90376f35-d6cb-55fa-9637-4c0f3057ccd3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(d)
707ea454-f248-508c-82ed-006748e0253b | note | INSPECTION/TEST METHOD: Document Review
f0980076-2864-5809-88df-643d4670faf0 | note | RECORD OF CONFORMITY: Signed ITP
0635ed63-45e9-59c6-8328-7fe86cbfed5c | note | IP
7abefc54-d409-5d58-be2e-6be81c0f5bef | note | RESPONSIBILITY: Site Engineer
3c5566f2-e6a5-5073-b507-9d4312e2495b | date | Date Completed:
828ee5bd-3dbe-4030-a56e-fb5046b28ffa | checkpoint | 3.5 - Construct crushed rock base for maintenance strip
fc31b90a-1af5-5688-986e-c60e56d2c2a6 | note | FREQUENCY: During construction.
98419c15-7607-56da-a380-1d9c10628844 | note | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
d71ae87a-2fea-54af-854d-9a4883b81203 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
68cd5b9e-a297-5782-997a-7f715d2e9f15 | note | INSPECTION/TEST METHOD: Site inspection
3b74bd26-9379-55db-a77d-e638c2aca521 | note | RECORD OF CONFORMITY: Signed ITP
5cdee808-8dae-5504-8e6e-bdaff8837e45 | note | WP
4a2ce3b6-7dbc-59ac-b70f-698d608a0ecd | note | RESPONSIBILITY: Superintendent / Site Engineer
e9fb456d-fd46-5fcb-b33a-61241254220c | date | Date Completed:
6f5f98db-a496-4921-a111-8abd5e89ab65 | checkpoint | 3.6 - Construct concrete maintenance strip
177f7b80-1c6e-5954-982e-3f68a8b739c3 | note | FREQUENCY: During construction.
38d78070-84b9-5fb4-93cd-4daff0693591 | note | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam. Separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative), full depth expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
d3b28528-7875-5aca-b562-8fedb9a34759 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
a7c063cc-99e4-5f29-9f40-05a5cbd6013a | note | INSPECTION/TEST METHOD: Site inspection
ef236b72-bbbe-5307-94a4-42bfde3b04e9 | note | RECORD OF CONFORMITY: Concrete dockets/Signed ITP
cfcf021a-7d85-5bfa-86cb-6a99d53b6e78 | note | WP
f98e52c5-b5c0-51de-844f-317aed5cc38c | note | RESPONSIBILITY: Superintendent / Site Engineer
8c503a30-1e16-59fc-ab6d-a4ce6330739d | date | Date Completed:
1348f2dd-daf2-4bde-8304-85e7987666c3 | section | 4 - Testing
48579230-fceb-4b86-986d-4c2dca3db2e3 | checkpoint | 4.1 - Compliance Audit of Barrier System Installation
fb657447-5c16-5c8f-8e68-2d239c192319 | note | FREQUENCY: Prior the issue of the Certificate of Practical Completion
df89dd80-937a-59fb-8226-6b34bc176498 | note | ACCEPTANCE CRITERIA: Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract and the Contractor shall complete and submit to the superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual.
92bce446-93ff-5732-9c70-1f3729776931 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.10
64998ba2-0a05-5c13-a9c5-697a6851558d | note | INSPECTION/TEST METHOD: Document Review
ffb99d10-37c8-57f7-a004-10a439e07186 | note | RECORD OF CONFORMITY: Safety barrier compliance audit, Manufacturer compliance certificate
55039405-2f74-5671-a479-7d1ce2f45f0b | note | HP
efb7d9dd-f9f0-5610-87ca-be3ed11223cf | note | RESPONSIBILITY: Superintendent / Site Engineer
a7fc56d7-b2ff-5c97-a635-f22fc792e439 | date | Date Completed:
f8579f5e-28e6-4a9b-8dcb-a17cc913fa11 | signoff | AUTHORITY HOLDPOINT
7e46ef57-319f-40c7-98ef-bcd32151841d | section | 5 - Completion
95ec7897-900f-420d-899d-2002796751fc | checkpoint | 5.1 - Delineators
4af5537e-1d0c-59d6-b6f5-6f310367d335 | note | FREQUENCY: Once installation of assets is completed
53038654-7bbf-5800-bd52-2146b72ee01c | note | ACCEPTANCE CRITERIA: The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see:
100bb5c7-8413-59bc-a37d-055f88773876 | note | ○ red delineators on the left side of one-way and two-way roadways;
1c12e77d-236d-5bae-a32f-118060e419bf | note | ○ white delineators on the right side of two-way roadways; and
90499a90-8e7b-5aa0-9534-bdd718f23478 | note | ○ yellow delineators on the right side of one-way roadways.
d24d52b5-8702-5a39-9937-6c5569be5b76 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.11
553a23af-1b71-5b43-9f37-8a244e5a9e10 | note | INSPECTION/TEST METHOD: Site inspection
696e0a3d-d624-5bf1-aa34-906703cc236b | note | RECORD OF CONFORMITY: Site Photos/Signed ITP
f6e149b9-d95b-59d1-a44b-8db46bebf412 | note | IP
3485c8fe-ae25-5aac-a8cf-971fae75c7bd | note | RESPONSIBILITY: Superintendent / Site Engineer
38fe475a-4a92-5ac5-a2eb-b0d5e0542f83 | date | Date Completed:
0a9854d4-8401-4679-b416-5b4b4c8c7488 | checkpoint | 5.2 - Survey data captured for As-Builts
dd61fd17-4c9e-5d0d-b52d-9cfdc8902245 | note | FREQUENCY: Completion of Works
416c2102-fdba-5c19-b4e6-b254cee4a123 | note | ACCEPTANCE CRITERIA: As-Built drawings to be submitted to client
a58a5562-10da-507c-8421-db5d0c30deda | note | REFERENCE DOCUMENTS: VicRoads Spec. 708
c2e597db-19b3-5d27-80da-2c5e509af27b | note | INSPECTION/TEST METHOD: Document Review
8ba1f304-1d3c-5114-86b9-283c70b780f5 | note | RECORD OF CONFORMITY: As-Builts, Survey reports
21e57b5f-139d-5a68-a90b-c45c1b94d809 | note | IP
55b7d1aa-15d0-58ee-90e8-8996e37e965e | note | RESPONSIBILITY: Superintendent / Site Engineer
85a4e9f8-f960-5e0e-88cc-f916c85aca2f | date | Date Completed:
c1583f17-01a3-4a5a-95f0-d66ade50d2b0 | checkpoint | Final Inspection
a843f010-a584-5154-89b3-15c1cbc40af7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d0e491e9-6046-5c0f-8539-9c7d9773dab9 | textbox | Print Name:
2fc48ca1-c783-5d8f-a8ab-1cdef7bb58db | textbox | Position:
41794ddf-0063-5af2-8492-c5a569d384d1 | date | Date:
0edc48ce-2b10-43fb-ad5b-59ace9187753 | checklist | ITP-008 - Insitu Pit Construction Rev1 | itp | ITP-008 - Insitu Pit Construction
0ab0c4e6-e091-4938-9315-8b10502306d3 | section | 1 - Preliminary Activities
f77b99fa-1d7b-4431-95a0-cb23193a8cc9 | checkpoint | 1.1 - Check for correct documentation
23f6aa79-d434-596d-b8b2-79117a514978 | note | FREQUENCY: Prior to commencing any activity
214b26ad-6684-5c1e-97a0-0f344ca9b475 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
727d9fc3-bfe1-5556-830f-05b6d06d1747 | note | — using the correct and complete set of drawings
a4b2b8c4-bfdb-5b9a-8061-38d0e2f5b7c2 | note | — all drawings are the latest revision
967565cb-bad1-5f61-a930-3ab54c2ff718 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4526e758-4273-5a5f-b4e2-0c83426022af | note | INSPECTION/TEST METHOD: Visual inspection
edc28a11-4501-58d1-9c0e-fc322c55181c | note | RECORD OF CONFORMITY: ITP signed
18d7d0f1-3239-5b43-8022-910e0ab9bb7c | note | HP*
ebf0dcb3-3992-5ede-9ed4-135d0af40bc1 | note | RESPONSIBILITY: Site Engineer/ Supervisor
0b379046-7418-5027-84c2-0e042001c47a | date | Date Completed:
456e7708-ceda-40a2-96f4-5d98b189898d | checkpoint | 1.2 - Implementation of all measures and controls
5085d797-0781-57bb-a16b-14f1b6760b57 | note | FREQUENCY: Prior to commencing any activity
1c11fa2a-38a8-5048-b397-e2b9469a7636 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
761caeee-38e5-5e7b-80f7-9e3b2c5c323b | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
4215354d-b274-56e9-9d4a-909dfb45fac3 | note | INSPECTION/TEST METHOD: Visual Inspection
376f4fc0-bb49-5390-894e-01bfce637709 | note | RECORD OF CONFORMITY: ITP signed
e9cc4829-d9a1-50d2-98a7-87cc22fe267b | note | HP*
b38bf112-24eb-5c5c-84a5-ee0a9c02f696 | note | RESPONSIBILITY: Site Engineer/ Supervisor
da832720-0cb5-5ab5-9ec3-c7d5693f1030 | date | Date Completed:
08fac749-f738-4574-afff-291701633183 | checkpoint | 1.3 - Use of approved mix design
7d302c48-baa9-5f27-90eb-651e052aa5fb | note | FREQUENCY: Prior to commencing any activity
13e0cda0-2b27-545b-86b2-cec67459765f | note | ACCEPTANCE CRITERIA: Concrete mixes used will be inline with Table 705.041 - VR330/32 for drainage pits
301c883d-8f43-52cc-b172-38b4c8d8764d | note | REFERENCE DOCUMENTS: Cl 705.04
3d6c894a-2f5a-5fe4-bf4a-09329975b001 | note | INSPECTION/TEST METHOD: Verify
3bc756f8-89ac-5bf1-9b43-3dbc5275691c | note | RECORD OF CONFORMITY: ITP signed
5d17d23c-545e-5f4e-8b82-040d85cd4eaf | note | HP
493be4bf-19ea-5a70-be7b-2c48a3e95c3c | note | RESPONSIBILITY: Site Engineer
bd5a5f96-28c8-57ef-a06c-69703bdc4871 | date | Date Completed:
973df2b8-7ec0-4bb5-96e2-79c4ee5e7623 | signoff | AUTHORITY HOLDPOINT
983ed09b-0138-484a-bd32-76a71545aadd | checkpoint | 1.4 - Excavation Permit
196c2ae1-7cb9-5f97-9b3e-1b588094969e | note | FREQUENCY: Each lot
9a1c1aeb-aa38-5e0c-b04e-f6b86eb01aec | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
26b1b699-ac71-585b-a0e6-4369af10c9e6 | note | ○ Plant and equipment shall be appropriate for the task.
3fa0b148-2258-5f22-89af-f9c81527be5f | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
01d07845-9fa2-5aa9-80c8-d578fd0de3f1 | note | REFERENCE DOCUMENTS: Excavation permit
07c66ba9-7d66-53b6-b27c-f9bf5f85cced | note | INSPECTION/TEST METHOD: Verify
bfe4966c-592a-532c-99d1-ae487e2c5439 | note | RECORD OF CONFORMITY: This ITP Signed Off
3e132cca-777f-505f-82a9-8fae3fe5112a | note | HP*
be2f59dd-1fd3-50e3-88e0-d9c237ac6623 | note | RESPONSIBILITY: Site Engineer
ac2c849d-e7d8-5a1f-9c42-0f03b2127697 | date | Date Completed:
0363b036-0fb4-4b3f-9222-64724e10e1dd | section | 2 - Excavation and erection of falsework/formwork
fcce9f65-34fa-4b53-8880-8345329fe57f | checkpoint | 2.1 - Excavation
1ed3488f-d138-50ed-8203-d0a9c36b1f54 | note | FREQUENCY: Prior to concrete pour
b545408d-b702-5b05-9d0e-cd00ab644c68 | note | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
ebcc28f6-2f9f-5b2e-82af-11a507b88fd2 | note | REFERENCE DOCUMENTS: Cl 705.05
d199898c-0332-5c79-8f16-c00750449355 | note | INSPECTION/TEST METHOD: Visual inspection
1042beed-3c08-5ba5-b4dc-fb3bb4c20720 | note | RECORD OF CONFORMITY: ITP signed
f55c4d58-f69f-5ecc-a7b0-c9258bc198fd | note | IP
2487a208-f9ee-5885-abdf-b74079195003 | note | RESPONSIBILITY: Site Engineer/ Site Supervisor
5c054e68-4782-5ebb-9ad6-5b79a4177da2 | date | Date Completed:
842b24e4-1fd1-4156-a40f-ceb38a989129 | checkpoint | 2.2 - Construction Methodology
ef3fc1cc-aca5-51f9-a53b-a60556820935 | note | FREQUENCY: Prior to erection
8d5b140d-01fe-5dfa-b792-baa6ab8cf669 | note | ACCEPTANCE CRITERIA: Formwork shall be used in such a manner that it can be removed without damage to the concrete. Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction.
e5339a48-0823-5ed7-ac0f-6d45d2deab0e | note | REFERENCE DOCUMENTS: Cl 703.12
1dff8d48-f258-5ce3-b250-a8bc727b0e74 | note | INSPECTION/TEST METHOD: Verify
5fd0e4d3-15db-5d02-bcfa-287000435cb5 | note | RECORD OF CONFORMITY: ITP signed
e19061be-f5a5-5740-a18f-9f0a9dce98ce | note | IP
242a6b60-907a-57e0-b4e9-4c301c940552 | note | RESPONSIBILITY: Site Engineer/ Site Supervisor
1020c6b3-18ed-5e5c-900b-5605e960268c | date | Date Completed:
482d09bc-77e5-4c73-bd09-3967900d2ba6 | section | 3 - Steel reinforcing
01b53656-71b3-4671-b656-238678e60340 | checkpoint | 3.1 - Placement methodology
d05b1d18-332a-5533-a040-37d66086eb45 | note | FREQUENCY: At all times
57c089ba-4b22-5ee0-8c15-c8090095dca7 | note | ACCEPTANCE CRITERIA: All steel reinforcement to be securely held during placing and compacting of concrete
db154724-450a-583c-8e56-1eba3cf22946 | note | ○ Supports shall be of a material durable to impose loads without movement of the reinforcement
cd514c34-b513-5bc4-95e7-e2c9771a0b66 | note | ○ The placement method shall not allow the reinforcement to become contaminated by contact with other steel
8662e414-1fb5-50a2-be4b-bf13b061c74e | note | REFERENCE DOCUMENTS: Cl 703.13
28791ac8-a58b-5b7c-a364-aa3d8d7f1a61 | note | INSPECTION/TEST METHOD: Verify
f0d094a1-a173-5c5d-80ce-9d6c3ebc90af | note | RECORD OF CONFORMITY: ITP signed
83fb5d13-28fa-57f4-86fc-bba93903b5b6 | note | IP
3730b61b-23ab-588c-b7b1-d1107cf0954d | note | RESPONSIBILITY: Site Engineer/ Site Supervisor
4047ba6b-14dd-5e78-b329-0eebe4c79e92 | date | Date Completed:
e70961a1-9195-4de3-a0d2-14ae92bebf17 | checkpoint | 3.2 - Minimum Cover
6c7392de-bae4-5de7-8652-4024ecb89721 | note | FREQUENCY: At all times
d6863a57-2ba8-59e9-a4be-c66290cac147 | note | ACCEPTANCE CRITERIA: The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed.
3eb5bc27-408f-5478-a21c-7fb74d95ab1c | note | REFERENCE DOCUMENTS: Cl 703.13
86ca816c-bbc8-5f58-a44d-ebbc6f408216 | note | INSPECTION/TEST METHOD: Visual Inspection
56c179d0-0925-5f82-88c7-65f48e8cf8a1 | note | RECORD OF CONFORMITY: ITP signed
1b449b0f-542b-533f-b88d-4c203587a00b | note | IP
b4f25641-a4fd-50b9-ab50-b63208a014e6 | note | RESPONSIBILITY: Site Engineer/ Site Supervisor
a5470634-0f5e-5c25-8293-a4ad1c38e0d0 | date | Date Completed:
1416c019-b4fc-4d95-abb8-07f1c2168ac4 | section | 4 - Pre-pour Planning and Inspection
c440fe84-e730-409c-bde4-afc338f6c4b8 | checkpoint | 4.1 - Pre-pour inspection
17a75825-43ba-52b0-91d6-267c4f0fea7f | note | FREQUENCY: Prior to concrete pour
81ed00d0-a7da-541a-8db6-2db04ed8e6cb | note | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications.
4d2e93a1-91a5-5c54-8c8d-a1475cea40ad | note | ○ Hold Point released by the Superintendent.
89b0b6b0-6935-5390-acc0-d10680a36929 | note | REFERENCE DOCUMENTS: CL 705.06
1461ddf7-561b-526d-a8c8-02f595eb1891 | note | INSPECTION/TEST METHOD: Verify
cc7f821b-ad6d-549e-87c7-d467c0000e15 | note | RECORD OF CONFORMITY: ITP signed
b0f852c7-b725-5ac0-b61b-648f0f3ae096 | note | HP
38391552-dcdc-5a97-a2f3-a6de40c22c48 | note | RESPONSIBILITY: Site Engineer/ Superintendent
953cf08b-3cd8-5ed7-9525-c7e6cd2598b3 | date | Date Completed:
5e958d63-05c2-447d-9644-e1ca3aa8cfe6 | signoff | AUTHORITY HOLDPOINT
d5095156-ec4c-42b4-86a4-d2f50c2ba387 | section | 5 - Placing Concrete
d50472be-b078-4e50-be32-3563a4574e82 | checkpoint | 5.1 - Carry out sampling of concrete
98699f9c-37cc-589b-b349-890e3ad19bdd | note | FREQUENCY: 0-50m3 - 1 sample
cab8f6a8-650e-5879-b642-b87a19ea88d2 | note | ACCEPTANCE CRITERIA: No. of Samples: 0 to 50m3 - 1 No.
ec1fa2a2-109d-554f-90e0-d53238871df2 | note | REFERENCE DOCUMENTS: Cl 703.11
281fa0a3-b74f-5edb-a25e-9f58e343d8c3 | note | INSPECTION/TEST METHOD: Checklist
40d7dfe6-7d47-546f-a546-cdb368bb521e | note | RECORD OF CONFORMITY: CLB, CLC
3fa6e5b2-647e-5f70-945f-bb29ccb4598a | note | TP
0fa5fa35-c3dd-5b8a-ae88-d771d99720e8 | note | RESPONSIBILITY: Site Engineer
88b4d809-2c95-52a9-8960-eb5310e0f8ea | date | Date Completed:
7cd39a47-83a7-49d6-9970-2ea091c96a37 | checkpoint | 5.2 - Compressive testing
81f4f20b-9516-5269-9e3b-75e925bb9365 | note | FREQUENCY: 0-50m3 - 1 sample
2f13aed9-f686-5818-83aa-0462b2000c87 | note | ACCEPTANCE CRITERIA: A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days.
29f8e9ba-b1ee-513b-aac3-c4c1ef20d070 | note | ○ The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength. Additioinally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days.
c37c7b4f-54b4-5d8e-8268-01f417b08d74 | note | REFERENCE DOCUMENTS: Cl 703.11
7e5d2dc8-207c-5aa6-9dca-b4c66ec3f6a4 | note | INSPECTION/TEST METHOD: Verify
c5fc0613-2243-5747-a8dc-266c8686f665 | note | RECORD OF CONFORMITY: Concrete test records
2b0c744a-1b92-5984-b130-ea7ff28dcb7d | note | TP
4c968511-0d04-5631-8b51-9dc8c45757a0 | note | RESPONSIBILITY: Site Engineer
5d4e8d12-c496-5133-ab8f-2c694f908ee7 | date | Date Completed:
f1335cce-1f57-4ae9-b43e-1853e1b0419d | checkpoint | 5.3 - Placement methodology
1c3a3d82-1d63-5792-a4df-f66594551974 | note | FREQUENCY: Each concrete pour
e3ac0302-dc83-5e4d-94ce-592655b36e46 | note | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
8abb3e53-8bb9-52b9-86f5-8935594c74cc | note | ○ Concrete shall not be freely dropped from height >2m
d2928123-c1d5-513a-b6ef-d3e625b65d83 | note | ○ Concrete shall not be moved horizontally by vibrators
d60ce0a2-bc73-54f5-8da8-b021eed3beba | note | REFERENCE DOCUMENTS:
21c254c5-f3cf-5046-aace-1fa0793d31ba | note | INSPECTION/TEST METHOD: Verify
38058536-9f65-582e-8de3-a57272aaa60b | note | RECORD OF CONFORMITY: ITP signed
0a6fa04a-a49a-547f-b633-d8f2ae7fe5a6 | note | IP
7f2ee64f-544f-53de-b9b8-70417d2bdf82 | note | RESPONSIBILITY: Site Engineer/ Site Supervisor
226ea59a-5f43-58ad-98e1-349054605e4c | date | Date Completed:
c0b79f9d-ef8f-4929-95c5-769a0e003a05 | checkpoint | 5.4 - Compaction
1fe5bed0-b5f3-5266-b029-3591d81b88a0 | note | FREQUENCY: Each concrete pour
82a11a56-2097-5ef1-b2c9-4ea642a5c7cd | note | ACCEPTANCE CRITERIA: Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
2b27818b-fb1e-56de-94a9-6545206eb870 | note | REFERENCE DOCUMENTS:
6dec2d10-6dd2-5154-b545-86ff14218672 | note | INSPECTION/TEST METHOD: Verify
62150c62-7966-592b-8f88-5dbc4517411f | note | RECORD OF CONFORMITY: ITP signed
7d5ef1e1-bf04-56a8-8a1f-e456d8f26afa | note | IP
48d73636-5532-5785-a6bf-d6bf1d93f92e | note | RESPONSIBILITY: Site Engineer/ Site Supervisor
256768de-0643-53e6-b388-6aaebf97591b | date | Date Completed:
ec2bff5e-f705-421d-b0fa-79725d0c7931 | checkpoint | Final Inspection
de35f5ea-43ae-52a0-bc53-29a188fdd8ea | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0b1afa89-3132-5f45-96f8-ba25a9605a46 | textbox | Print Name:
57dc9bc5-cbc6-5078-a2ef-974796787e4f | textbox | Position:
27d55d92-44e9-5d15-81f2-2efbc81177f7 | date | Date:
aae66d97-8e5d-4853-9476-05c099ce49e7 | checklist | ITP-009 - Bored Piling Rev1 | itp | ITP-009 - Bored Piling
f1934d0b-42cc-470e-8188-ba3761cd1451 | section | 1 - Design and Submissions
769208b3-69cd-4193-b444-ba0f7c50121f | checkpoint | 1.1 - Check for correct documetation
8e3abb1d-1e93-550f-bbed-e2485869bfa3 | note | FREQUENCY: Before commencement of activity
9f64e5d1-e0b4-5f5a-9f73-f0f532879d77 | note | ACCEPTANCE CRITERIA: Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering
29deca08-cb14-5a3b-b0ca-6ef32d6921b4 | note | REFERENCE DOCUMENTS: Drawings
3f97fd26-d672-5751-a067-c69361c29e4c | note | INSPECTION/TEST METHOD: Current revision of drawing
55b4da9e-6702-5687-8d77-a179bceadf55 | note | RECORD OF CONFORMITY: Current revision of drawing
338e855a-526d-535d-b94f-97acd6e31e0b | note | HP*
8b4f0a41-209c-561b-a4e1-ed57cdcb7fe4 | note | RESPONSIBILITY: Project Engineer Site Engineer
ac55d441-48b5-5f2d-ab71-678ed75cfc6b | date | Date Completed:
b97fa150-a86b-4429-a6f2-598b1a1921c9 | checkpoint | 1.2 - Approval of Mix Design
e6abf671-4f7f-5997-83c5-4854c020f074 | note | FREQUENCY: No less than 4 weeks prior to commencement of activity
6a66a7f5-09e3-5894-968c-4d8339ebab39 | note | ACCEPTANCE CRITERIA: Mix design reviewed and approved by superintendent.
d8f5100b-8954-564f-b998-6eb9d43793ed | note | REFERENCE DOCUMENTS: Cl 610.07(b
54b3a75e-b9c6-50f3-ab0b-0b9798ceeef0 | note | INSPECTION/TEST METHOD: Approval
03bb38f0-aa9a-5afc-8525-b948d2b408aa | note | RECORD OF CONFORMITY: VicRoads letter of approval
690e7777-66ac-5962-a8d7-9ce568977417 | note | AP
a91e8c5b-a04f-552b-a1e1-b89e3c532158 | note | RESPONSIBILITY: Superintendent
93e1a49a-db6e-5c01-9ff8-975b2ae7a2b0 | date | Date Completed:
fa0c8fb0-45d6-4b84-8baf-5ae1d215efa3 | checkpoint | 1.3 - Approval of Quality Procedure
9179fa18-7e7e-5848-9882-b3452e94e319 | note | FREQUENCY: No less than 4 weeks prior to commencement of activity
cd4f1ce0-5dd9-575b-bd99-94a5e984ff82 | note | ACCEPTANCE CRITERIA: Proposed materials and pile construction procedures reviewed by the superintendent
3e482f41-8de9-5f93-9550-0660a58fb47f | note | REFERENCE DOCUMENTS: Cl 606.03(a)
71e3bbb6-e5a0-58d1-bc76-e2744ad89052 | note | INSPECTION/TEST METHOD: Approval
4349ebb2-23bc-5f0d-af0c-856ccfc8e113 | note | RECORD OF CONFORMITY: VicRoads letter of approval
1a2b74fd-2a3c-5682-bb56-af1c506ace7d | note | HP
43ff51b6-ff6d-5755-8492-88f67e3c8f7e | note | RESPONSIBILITY: Superintendent
1906d8d1-42ee-5f43-95e4-d6ad443ce8b4 | date | Date Completed:
eb3b73ec-09f0-476a-93cc-207bee7ea11e | signoff | AUTHORITY HOLDPOINT
d71f2a09-b8cc-4759-92c8-6c4acd0a5596 | checkpoint | 1.4 - Ensure Traffic, Safety, Quality and Environmental management measures are in place
274dee11-6a86-5687-a53d-add74f378bcb | note | FREQUENCY: Prior to commencement of activity. EMP at least 2 weeks prior
ece7ba2f-1865-5d38-87e8-cacf060b6819 | note | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
15f99129-2174-5248-9339-d1e80fc50601 | note | REFERENCE DOCUMENTS: PSP, TMP & EMP
855713f3-5a67-5df5-bfa7-76f77baaebc5 | note | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
1227fbd7-cf9b-5bdf-8c37-1e71e2b8b6d4 | note | RECORD OF CONFORMITY: Inspection
ae4d791e-fe18-544d-8cb0-813edde5627b | note | HP
05d10584-6a8e-580a-9128-a9f19c5314f0 | note | RESPONSIBILITY: Site Engineer Superintendent
a7045d6c-73eb-54c2-a2b5-cb2fe0f9f4cb | date | Date Completed:
9be0fe2f-ef6e-4c0f-a568-1e88b6aeb4f9 | signoff | AUTHORITY HOLDPOINT
2d92fe03-03c3-4696-95a4-ff9a60b89103 | checkpoint | 1.5 - Certification of approved Hot Dip Galvanising
1534acd6-160e-56f1-a0bc-ec0c4eeb0e3a | note | FREQUENCY: Prior to Epoxy coating
76b846cd-ae6c-5c99-8863-e2b017d967cd | note | ACCEPTANCE CRITERIA: Galvanising treatment in accordance with appropriate Standard documents and Design specification
aec51e43-1373-53d5-91f1-a457270f949b | note | ○ 200 microns
a0b33735-f778-5126-a278-6cde097e6077 | note | REFERENCE DOCUMENTS: Drawings AS/NZ4680
a1736b1e-3f76-5f6d-8a9b-13c90e0a327a | note | INSPECTION/TEST METHOD: Verify
b611d010-4fc9-5b24-a983-21ad739e3917 | note | RECORD OF CONFORMITY: Manufacturers certificate
fed663b9-93cd-5f24-8ddd-79f7ec707917 | note | HP*
af776616-52ca-54f6-b2ee-6985d5775eca | note | RESPONSIBILITY: Project Manager Site Engineer
4ce9542c-d1cb-5e0e-a9fb-c632f38f15c1 | date | Date Completed:
d528634a-64cf-4c07-b89c-e72e583d3850 | checkpoint | 1.6 - Certification of approved Epoxy coating
dc4e13bc-911e-53e8-8815-c2852c6cdbcc | note | FREQUENCY: Prior to arrival on site
c1ac517e-6434-5664-8494-b0a870d9ac91 | note | ACCEPTANCE CRITERIA: Epoxy treatment in accordance with appropriate Standard documents and Design specification 2 x Base Coat GFX @ 250 microns
9e1a9356-6f0e-5674-a33e-77e492a5f13a | note | ○ 1 x Top Coat Polyurethane, 100 microns
cb27c23f-56de-54b8-bd37-37d46c0baf9e | note | REFERENCE DOCUMENTS: Drawings AS2312
62478846-b4b1-5a88-a4ed-115fc648f672 | note | INSPECTION/TEST METHOD: Verify
7d230368-3144-5e59-b2eb-2ee9b4d571ed | note | RECORD OF CONFORMITY: Manufacturers certificate
0b29f4fb-e60f-54d4-9f15-bbbe3fbb6685 | note | HP*
ed91895a-3b19-503a-b771-68f8a2e20579 | note | RESPONSIBILITY: Project Manager Site Engineer
7d406737-630e-5598-85fc-4f9bef6c07e2 | date | Date Completed:
9e7ca4ef-4112-4ea7-86cd-acc5d6cf6c99 | section | 2 - Bored Piling
880d3948-8409-4b6f-a6e3-ea40c365a8c5 | checkpoint | 2.1 - Survey and setout
cc41345d-dfd5-5cc4-bd4c-34fe85ca9116 | note | FREQUENCY: Each Pile
4331cd48-9b4f-5d01-8d2b-7c6ab0c58a60 | note | ACCEPTANCE CRITERIA: Survey and confirm position and depth as per drawing
7474ff11-b603-5168-a17d-f3095180a12e | note | REFERENCE DOCUMENTS: Drawings
4471b22d-eecc-5358-b0f6-02fb476a0d96 | note | INSPECTION/TEST METHOD: Survey
8b088a59-fdb4-5dee-99f7-d03e340b86b4 | note | RECORD OF CONFORMITY: This ITP Signed off
dbedc2bd-052d-5ef9-ac93-21df44e45019 | note | IP
893748c3-1671-5bd9-b814-69e78d4c93f2 | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
abbd5c45-4901-5390-99ec-9011b4ace2f7 | date | Date Completed:
75ba87d8-3411-4da6-b489-9d37721a1237 | checkpoint | 2.2 - Excavation Levels
a03badcf-c8fa-5ec2-bf68-561650fa2d0a | note | FREQUENCY: Each Pile
24c231fe-1c60-5993-87e2-6a67f2f2c674 | note | ACCEPTANCE CRITERIA: Check the excavation levels and base are acceptable and conform to the drawing prior to commencement of piling works.
30383190-f608-5278-871b-3cf0f3a31fe1 | note | REFERENCE DOCUMENTS: Drawings
a9c549f7-cc4f-57ed-8eed-b735a4b39ff3 | note | INSPECTION/TEST METHOD: Verify
54774d96-d819-59aa-8d9f-5d44df8f7238 | note | RECORD OF CONFORMITY: Drilling check sheet
dfabdbc4-aa59-583d-bbc8-53c2751457df | note | HP
e6855dc2-7457-57d2-9f5c-9520e00f859e | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
92b5a4a2-92ec-5eab-bd3b-219801b1bd46 | date | Date Completed:
e25556ac-be7b-4b1f-b06c-26c5e7ebe0ad | signoff | AUTHORITY HOLDPOINT
49349120-5a3a-4b9a-945a-efd1b4edaf34 | checkpoint | 2.3 - Inspection of Pile Excavation
f5134181-8d11-5b88-b6f2-a2dd690f3afd | note | FREQUENCY: Each Pile
41f52940-2320-5616-b8b3-863acea4e2e7 | note | ACCEPTANCE CRITERIA: First 3 piles to be inspected by Geotechnical Engineer to check dimensions and toe level are correct and within tolerance. Correct Toe level.
ce746da5-7419-54cb-8564-dedb0b2ce82c | note | ○ Material encountered consistent with design.
f4763f69-558c-5723-bb09-afa2468ccfdd | note | REFERENCE DOCUMENTS: Drawings Cl 606.06
4b5e7099-49af-5cb7-93fb-23205a4cb79a | note | INSPECTION/TEST METHOD: Inspection / Test Method
de967b6b-70db-5071-b84c-074c3f6f8f2d | note | RECORD OF CONFORMITY: This ITP Signed off
82892884-8a7a-50b0-949e-a8dc0637de1e | note | HP
9da4677d-8f18-5934-b3cd-6d07efae90cf | note | RESPONSIBILITY: Site Engineer Geotechnical Engineer
b5e2fb7d-d132-55f7-a989-fe7a6167ee8a | date | Date Completed:
ff039edd-cf9c-4577-b1f6-eb4bd5de0b2f | signoff | AUTHORITY HOLDPOINT
22489814-7727-422d-8f27-7fdb62f594bd | checkpoint | 2.4 - Bore Logs
1c57fb79-ceed-5218-bc45-0ea6b2d3119f | note | FREQUENCY: Each Pile
a73c7514-a37e-5c8f-b443-87da8738c965 | note | ACCEPTANCE CRITERIA: All bore logs and pile installation records to be sent to and reviewed by designer
d0681afe-ecf7-587a-b4eb-b18f8021a37a | note | REFERENCE DOCUMENTS: Bore logs
bc9d5f27-cfe7-515a-bd47-859ec606d1a6 | note | INSPECTION/TEST METHOD: Verify
4ffd26fd-cc9f-59da-bcc0-8f5df0a03572 | note | RECORD OF CONFORMITY: Drilling check sheet
da720652-9620-57ae-8041-be37caeabb06 | note | HP
9cdd7631-1b5b-5e18-b7c7-8ee113c430da | note | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
5f78c849-0c03-58d6-8794-5b7d216fa301 | date | Date Completed:
1eccbd35-186c-4d3e-b758-e0b96e719316 | signoff | AUTHORITY HOLDPOINT
77fa2db4-a568-492b-b028-c65d213e3567 | checkpoint | 2.5 - Spacers installed on Reinforcement Cage
0e7b5bb4-3188-5da1-866b-29f87fe1b910 | note | FREQUENCY: Each Pile
008159d6-e979-56b7-8102-a56ea5e3edfc | note | ACCEPTANCE CRITERIA: Spacers/supports to be placed along steel reinforcement at a maximum 2m intervals
fac553b2-96d7-5c63-b021-83755684e7b1 | note | REFERENCE DOCUMENTS: Cl 611.10
b938b076-f8b0-5ab0-bb8b-6114b31121c6 | note | INSPECTION/TEST METHOD: Inspection
ccc91078-d308-5504-9fac-832d3f00b380 | note | RECORD OF CONFORMITY: This ITP Signed off
4e8af69d-b91b-5b8f-b663-9fa3c5c9e091 | note | HP*
00ab3f58-51a4-5c75-b048-49f5d40af094 | note | RESPONSIBILITY: Site Engineer, Superintendent
3ac11ef8-0801-5a5f-b17f-1d6776d5d2c7 | date | Date Completed:
d13e9189-5389-4085-816e-8ce99c3167fc | checkpoint | 2.6 - Inspection of column and cage height and centre
4f2ae505-31b3-575f-80c6-4c8afd7050ea | note | FREQUENCY: Each Pile
8ad9a5c6-d49b-5190-9abe-47c4e0c560f3 | note | ACCEPTANCE CRITERIA: Ensure heights, centre and spacing of reinforcement cage and column are in accordance with drawings and within tolerance
5684c2a4-6e59-5501-b2cc-8389192c59bd | note | REFERENCE DOCUMENTS: Drawings Cl 606.08
0d6ec25e-9ed2-5dc8-aff6-a0d1be2b4dc8 | note | INSPECTION/TEST METHOD: Inspection
af5db7f1-c985-502c-9e0f-d9b524068101 | note | RECORD OF CONFORMITY: This ITP Signed off
acb11cfa-10cc-5cfa-99aa-d878f1e0345c | note | IP
de03f06c-7559-5447-af8a-3d506d781f9c | note | RESPONSIBILITY: Site Engineer Superintendent
c4d81b91-fe98-5cbf-9e61-cfd2b78f7ea1 | date | Date Completed:
e2fc2ec2-80a8-42c9-92c4-6d3316d9ee57 | section | 3 - Placing and Finishing Concrete
387e06a2-f9a0-48be-9826-291553c0644e | checkpoint | 3.1 - Quality Checks
91e30870-e6a1-5faa-a959-b7d45c872bdb | note | FREQUENCY: Prior to each concrete pour
d7a0885f-56e9-524d-9161-b7e142893c13 | note | ACCEPTANCE CRITERIA: Relevant ITPs and Quality Control checklists completed and reviewed
e7f16360-2150-5d0c-b92b-9c12b3200ec7 | note | REFERENCE DOCUMENTS: Cl 610.18
3d037c3a-ca91-581a-9c8a-43b7c1e15426 | note | INSPECTION/TEST METHOD: Inspection
b3211170-1f23-5e09-b6b3-f1d2aaef2c59 | note | RECORD OF CONFORMITY: This ITP Signed off
1f30ddf7-342d-531d-bac2-909dcde91bdf | note | HP
774e66d4-f54d-5aa1-a831-4091eef6343e | note | RESPONSIBILITY: Site Engineer Superintendent
d2e3ef41-4cc4-5e60-b0f2-c1c4fe06133e | date | Date Completed:
6b4671c8-5a9c-4983-9cbe-84965e89ad44 | signoff | AUTHORITY HOLDPOINT
392344a4-4c13-45d9-bccc-5acca8f7a6db | checkpoint | 3.2 - Carry out sampling of concrete
b4746f66-d06b-5f12-bffc-daddfa1c8cb2 | note | FREQUENCY: Each concrete pour
b5b8dc41-dd34-549b-9480-17a68658d85a | note | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16 Slump: As per VR450/50 mix 675mm (+/- 125mm) (550mm - 800mm)
1e49a0db-c223-5a62-8d9f-1fb0a6c369d5 | note | REFERENCE DOCUMENTS: Cl 610.16 Table 610.161
681c6f77-2089-5b79-94d2-d5dbe531cc1e | note | INSPECTION/TEST METHOD: Verify
c45dd032-3542-515f-a326-998bf41baa3e | note | RECORD OF CONFORMITY: Checklist
a9a71f8e-a89c-5062-9ae3-13c675fb19ed | note | IP
10796c92-d132-5abe-86c4-ffbc71eb9653 | note | RESPONSIBILITY: Site Engineer
bc36a231-ede2-537e-96c9-ef063ad1dcdc | date | Date Completed:
64c5e701-0446-4fdd-b7d2-d6e81d642598 | checkpoint | 3.3 - Record location of each batch
0428751f-da62-557f-8948-0fdda81a7d76 | note | FREQUENCY: Each concrete pour
90b3f051-b2da-542d-bfb1-de4d5ab5df0b | note | ACCEPTANCE CRITERIA: Batch location recorded
ca643a70-2596-5a3d-ae5b-1dca77779484 | note | REFERENCE DOCUMENTS: Cl 610.15
401ef771-431b-5347-9db9-df2e15367373 | note | INSPECTION/TEST METHOD: Verify
24149d8f-426a-57af-b618-aa23267e3027 | note | RECORD OF CONFORMITY: Checklist
ad2ade95-c668-54cd-bbf8-8148ce241166 | note | IP
a3d0cce7-4f1f-50a0-a8f7-ec12b0961eea | note | RESPONSIBILITY: Tester
d1bbafe9-32cd-51f1-861d-e7ea9451dc5a | date | Date Completed:
99931c94-14eb-43b2-b047-f35e775184db | checkpoint | 3.4 - 7 Day concrete test result
3d7d1844-4241-5019-8e04-102585862fbd | note | FREQUENCY: Each sample
0b240a4a-5466-547a-8819-21334cbf3828 | note | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 35MPa
fba8cd26-e150-5761-9e2e-3297609b0414 | note | REFERENCE DOCUMENTS: Cl 610.05
c6d7921a-6741-5a9a-a928-2fd3c02905d8 | note | INSPECTION/TEST METHOD: Test Report
7d788576-81bd-5769-b4c6-c2a21f67d9e9 | note | RECORD OF CONFORMITY: This ITP Signed off
d33cd26f-fb40-5686-bad1-3c9f5fb8143c | note | TP
291946ac-d048-583a-9bba-d7690ffdcb4e | note | RESPONSIBILITY: Site Engineer
74a06815-392d-5541-badf-26e34cdc1b2b | date | Date Completed:
7e8ffda1-1189-4700-8e31-2a476853557d | checkpoint | 3.5 - 28 Day concrete test result
45d5852b-bab0-5a28-87d5-a0b49f96619b | note | FREQUENCY: Each sample
4628d298-e632-5aff-a255-3fd89363f390 | note | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 50MPa
5cccf942-e941-5fc1-96a8-89eb191793c6 | note | REFERENCE DOCUMENTS: Cl 610.05
ac6dc122-60f8-5b8e-ad19-8d0b12ff286f | note | INSPECTION/TEST METHOD: Test Report
a2e577e7-688d-58cb-9545-1346520a6a92 | note | RECORD OF CONFORMITY: This ITP Signed off
dd623305-a5d6-5d29-b785-463af93ef2a1 | note | TP
99a4158c-d5eb-5f45-a177-969677e3c92d | note | RESPONSIBILITY: Site Engineer
2afe59d4-7a7c-503c-942e-4989313cc5b0 | date | Date Completed:
0022166a-944d-4863-86fc-9b011de00bdd | checkpoint | 3.6 - Tolerance Check and As Built Survey
d43098d4-23ed-55bf-a1a0-e1c04b830351 | note | FREQUENCY: Each Pile
c1fc8dfa-2c26-52a6-9d4d-3f2780fa53d0 | note | ACCEPTANCE CRITERIA: Check tolerances and survey pile positions. Mark all details correctly on as-builts. Pile head position and verticality
d7bbe94c-eb32-5f73-ba8e-65af6b215eca | note | REFERENCE DOCUMENTS: Cl 605
efdf2e4a-9547-597d-b511-9decab732f60 | note | INSPECTION/TEST METHOD: Survey
96084797-e649-5868-a92f-7a2e10427837 | note | RECORD OF CONFORMITY: Survey report
e16fc574-a1a5-53af-b2c1-e187b0504cfe | note | WP
600742b7-4809-5eec-9a16-856c75b43e05 | note | RESPONSIBILITY: Site Engineer
f5f29684-235f-515b-b5f8-2957aba5a3d2 | date | Date Completed:
1e6a2026-d528-4638-99cb-b59df4b85cf1 | checkpoint | Final Inspection
5ae6ad07-ce6e-59f3-b27c-f0768d02d785 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c1193138-e6a7-5688-900b-cf171cd06c6b | textbox | Print Name:
5a41302c-bf19-5e76-9e6c-8fad6767ad89 | textbox | Position:
7ef970d7-a86d-510e-92fe-05b2d7a7638e | date | Date:
e3c1681a-aef1-4e1d-93bd-baf61b3d425a | checklist | ITP-010 - Miscellaneous Concrete Paving Rev1 | itp | ITP-010 - Miscellaneous Concrete Paving
23862c28-622d-4273-9a65-3753065ae0b1 | section | 1 - Preliminary Works
e4ed6f6d-85ea-4093-b0de-bf22bf1cc5a5 | checkpoint | 1.1 - Check for correct documentation
0e81a673-4f72-5cc3-9977-255e923b4870 | note | FREQUENCY: Prior to commencing any activity
b35a8a83-e8ff-5119-9dd8-b310e3334b10 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b59d0c13-b22a-5332-9fc1-a380ef91d8a5 | note | — using the correct and complete set of drawings
5a8d04bf-e5cb-5f2d-8bc2-8284b515e168 | note | — all drawings are the latest revision
0a1dd31d-54a8-5900-9440-e0ecc0104485 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0d0e9743-34b0-5c2d-80ed-d423b4c96556 | note | INSPECTION/TEST METHOD: Visual inspection
b42503be-428f-594a-b52b-6d2ea93afbec | note | RECORD OF CONFORMITY: ITP Signed
6eac7707-0582-5b5c-9eaf-dbd9514b0254 | note | HP*
87d5762d-736d-50b7-8f11-2947417ce821 | note | RESPONSIBILITY: Engineer/ Site Foreman
2182d198-2f97-5cb6-ba43-dfef9237dd66 | date | Date Completed:
b2511477-8310-45ce-89f2-4b709db19260 | checkpoint | 1.2 - Implementation of all measures and controls
d53d0d65-acc0-5d3b-a328-4a41ec822a4a | note | FREQUENCY: Prior to commencing any activity
70ed89c7-24e7-5fa9-9fdb-d07fc9305aea | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
33477b5d-2a8b-566b-a63c-5336c2048292 | note | REFERENCE DOCUMENTS: QMP, TMP, SWMS, WP
c7c3c751-7e10-5b8e-8b22-df2888f089a2 | note | INSPECTION/TEST METHOD: Visual Inspection
ea226b11-c128-5319-9af4-1d237b113ba1 | note | RECORD OF CONFORMITY: ITP Signed
1cf11ceb-5638-5a26-a501-9c0481f47c48 | note | HP*
fd09d201-1753-5e3c-bc99-a0773c529825 | note | RESPONSIBILITY: Engineer/ Site Foreman
8b1b21c5-1ced-519f-a6f6-f40a67dd5d06 | date | Date Completed:
6c6ba8bd-f139-4463-8088-be9598e18405 | section | 2 - Construction Works
eff860a4-2fc4-4784-ab63-8e650317c70f | checkpoint | 2.1 - Setting Out
eb142b6d-32a5-55aa-8b17-203c0887f9cb | note | FREQUENCY: Prior to start
31bf5a5e-1d9f-5d10-939c-fed139654fea | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
5220e742-2df9-533b-819c-3eb77e786bb4 | note | REFERENCE DOCUMENTS: 703.17
513fc668-b72b-59c2-8e76-6fbde14770b2 | note | INSPECTION/TEST METHOD: Verify
b5d8bfac-9497-50d9-a000-508ce2f5b6e4 | note | RECORD OF CONFORMITY: This ITP Signed
bda38267-b807-5035-9bd7-63cdcfea92f3 | note | HP
9315b489-b131-5a55-a7d9-4ea9048627ab | note | RESPONSIBILITY: Engineer/ Superintendent
a4ce686a-3e9a-5be9-9dcc-00d7674559c8 | date | Date Completed:
73e8fe8e-27eb-4b94-8dfb-d81f05f7295d | signoff | AUTHORITY HOLDPOINT
1dd4e186-6981-4caf-b446-774208a12760 | checkpoint | 2.2 - Excavation Permit
9d7aa8b8-16f9-5a20-9005-88360db695fb | note | FREQUENCY: Each lot
0e548ebf-b59d-56e4-8a5a-132dbc0ea528 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
7ed2e2c9-8f1b-5107-a0e3-85d9e987517d | note | ○ Plant and equipment shall be appropriate for the task.
0a5bbd61-d20b-5b8d-a487-209f9264642d | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
43712fef-0f04-55b9-ba8b-3f9cf562eb5b | note | REFERENCE DOCUMENTS: Excavation permit
7d59f713-88c1-5f6d-9cf8-b4a2121d3ab8 | note | INSPECTION/TEST METHOD: Verify
addac397-5e65-509a-9b51-739b92e9ae2f | note | RECORD OF CONFORMITY: ITP Signed
fda4cb4b-4693-554d-81e6-2338658fb50e | note | HP*
fedd4447-2ed0-589d-8823-b6a502e9a2ec | note | RESPONSIBILITY: Engineer
7347459f-1347-5b22-b842-c3a0d2985021 | date | Date Completed:
a6158478-65c4-420c-b743-9cd7d42d8f12 | checkpoint | 2.3 - Excavation
02f29b9c-f224-57c7-a37c-6fa8a37aecd2 | note | FREQUENCY: Each Lot
bd2d1158-6080-5d01-85fa-df5d03fdc921 | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
0ef48aa9-b2c8-5bf4-94ca-07cc2b4471ef | note | REFERENCE DOCUMENTS: 703.2
214278c3-4917-55c2-87af-2bec5dfa5fdc | note | INSPECTION/TEST METHOD: Verify
db95087d-75cc-589b-b9ac-c316dddf3d4c | note | RECORD OF CONFORMITY: ITP Signed
eac9caa0-017d-5b0a-bf54-dcc524a712d5 | note | IP
c3fc5174-2482-5c05-859c-03ff10d8bbc3 | note | RESPONSIBILITY: Engineer
fd212b35-eb46-55e2-a526-3fd87aa0ce1d | date | Date Completed:
b6e9daa5-8c46-4c97-88f1-63d80d1f6c83 | checkpoint | 2.4 - Bedding
ed8a2b99-00c7-55f2-98b1-9021bd39d06f | note | FREQUENCY: Each Lot
b91f5311-04c1-5686-8337-812ae5222f7f | note | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
1d7a677a-c123-5cdb-9e93-c88d4a647230 | note | ○ 75mm thick layer of 20mm Class 2 crushed rock bedding for median infill
1fe757f9-a6f1-5461-9ef9-0fd71b584abc | note | ○ Bedding trimmed, moistened, and compacted as per Section 304
3ddc4d2f-bd73-5796-83af-75d6c5cd6007 | note | REFERENCE DOCUMENTS: 703.21 Drawings
6f805fe9-dc3e-5a95-8867-506e9b6b02ca | note | INSPECTION/TEST METHOD: Visual Inspection
bb1eb003-a458-5a9c-8ba1-5dda88cabc98 | note | RECORD OF CONFORMITY: ITP Signed
81c44d09-122b-5423-bbbf-ea8f05f978a2 | note | IP
61d2730b-9274-5894-850d-05a3f8c4fb26 | note | RESPONSIBILITY: Site Foreman
eb804a08-21fb-5722-81cc-44f6aa2bf13c | date | Date Completed:
567f285f-77fe-4ad7-8686-4bfe28948b5b | checkpoint | 2.5 - Formwork
802889e9-b4d6-5a07-8e1a-9adea98a7b71 | note | FREQUENCY: Each Lot
387c816d-c2af-5d20-be01-cc640e26dfce | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
d61714bf-728f-56cb-a8c8-a3ab7681dabe | note | REFERENCE DOCUMENTS: 703.12, AS 3610
0546dffd-0225-517a-9f20-29f911002271 | note | INSPECTION/TEST METHOD: Verify
726cfef1-1c1e-5775-b613-bcc278a4b5cd | note | RECORD OF CONFORMITY: ITP Signed
b14c75f8-0b2b-59e2-9ec6-9b79a804c2cf | note | IP
e410f457-fcc8-5104-947f-59ddd2c7d07f | note | RESPONSIBILITY: Engineer
1e3e3f0c-3f3d-5e8b-a869-526fd7a0dd5e | date | Date Completed:
bc73117f-c5f4-41fd-9cfe-4f13382aa2cd | checkpoint | 2.6 - Reinforcement
3253bfd8-8e09-59a0-a817-52ee86a3748e | note | FREQUENCY: Each Lot
6a50f8ac-1721-5ddc-992a-1748d272ea78 | note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL62 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
3b7aa0e2-716e-52c2-97be-5615983ee20d | note | ○ Reinforcement must comply with the requirements of AS/NZS 4671.
a54f62fb-4705-5b3a-a93c-5fec39b00318 | note | REFERENCE DOCUMENTS: 703.13
086f0ad4-8d72-5cc5-81b6-50f043e21de7 | note | INSPECTION/TEST METHOD: Verify
7fa37037-2288-50b7-aef0-14cfffad805e | note | RECORD OF CONFORMITY: ITP Signed
a1f90251-777d-596c-a1cc-32170a716e62 | note | IP
1a515241-93d8-5ea1-a057-962829772623 | note | RESPONSIBILITY: Engineer
aa6c66a6-beb5-5605-ba17-65c1e2bc6a57 | date | Date Completed:
59cba7d4-3040-4c8b-b1c7-6545708d484e | checkpoint | 2.7 - Concrete Quality
625037b2-1d66-5602-a5fa-5c30ab354d04 | note | FREQUENCY: Each Batch
c0a5ec47-84f9-5505-bc90-7b0c18003162 | note | ACCEPTANCE CRITERIA: Check the deleivery of the batch is an approved concrete mix as ordered. VR330/32. Check for the time from plant to site,Check for the water qty added.
c8714103-cea9-5452-b9c0-d3463c2ac6d6 | note | REFERENCE DOCUMENTS: 703.13
c889d9d4-77ff-5fbb-92eb-4820e731a570 | note | INSPECTION/TEST METHOD: Visual Inspection
312cfd8b-12eb-5528-a705-368b716f5a2a | note | RECORD OF CONFORMITY: ITP Signed
d0ceaf4a-8bfc-5174-aa84-1036755eb37a | note | IP
6f4c2f05-ba81-562e-ac3e-2ab04ffb6119 | note | RESPONSIBILITY: Engineer
d0177f6a-7779-53f9-8031-92cbdd9ca4bc | date | Date Completed:
b984503b-f490-4085-8a4c-12d53c6e7f73 | checkpoint | 2.8 - Concrete Placement
437cdb3d-5d47-5d9a-82ee-ca30a55a97d5 | note | FREQUENCY: Each Lot
473412cd-eb48-52d6-8469-89a0e3d628ec | note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
2d6f0a0a-9e3b-5b00-bb2a-6fb289d3936e | note | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
9dcf9f88-9034-5181-8464-c3763f608a0a | note | — N32 for concrete infill
9cc2d4bb-1cc9-5618-9d32-208dbd902245 | note | REFERENCE DOCUMENTS: 703.05(a), 703.08
9f0c9408-15ac-5970-8e2f-4b3e14569017 | note | INSPECTION/TEST METHOD: Visual Inspection
066704f7-e766-59da-a6a4-35bf4d55b0eb | note | RECORD OF CONFORMITY: ITP Signed
b02cc616-12c7-5d09-9629-b61aa06467f2 | note | IP
aa1681d3-6a9a-55ff-aa5b-1142dee1ffd0 | note | RESPONSIBILITY: Engineer/ Site Foreman
c7421047-519e-5b6f-8cef-15ab7de69209 | date | Date Completed:
c026a580-8785-4eb2-b1d7-3310aebc6d9a | checkpoint | 2.9 - Record location of each batch
78efd099-8d49-59a5-99db-335d070e24c0 | note | FREQUENCY: Each concrete pour
b8c276da-7747-553e-bd7e-9ab1a95a354f | note | ACCEPTANCE CRITERIA: Batch location recorded on Load Batch Traceability Checklist
b052d02b-4741-52f3-9f19-620db4d959f9 | note | REFERENCE DOCUMENTS:
541d0e4e-453d-5ad8-a2ec-a1aa744491f2 | note | INSPECTION/TEST METHOD: Checklist
9c6cc6e4-db1b-5c0c-a31b-a355c4495bfa | note | RECORD OF CONFORMITY: This ITP Signed
f83536e6-5c6f-5d8f-80bc-76314b25580f | note | IP
8adeb638-ff92-5681-b2bc-9c4402d149cc | note | RESPONSIBILITY: Engineer
c72747e3-a082-5eff-acb4-5f0e7a6d22b3 | date | Date Completed:
e6ad1dbf-01d4-48fa-9123-07051b26dcd5 | checkpoint | 2.10 - Surface Finish
b3ca57e5-6028-5ad9-9121-313932db0871 | note | FREQUENCY: Each Lot
22f0f753-10f6-503e-a1c4-537a3d74e1b1 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing shall be compelted with a wooden float.
5cfecd8e-20be-5116-92cb-f0a1d43dc8de | note | REFERENCE DOCUMENTS: 703.25
7f47ec82-4e68-5186-9b85-2a0c3b54498e | note | INSPECTION/TEST METHOD: Visual Inspection
8e4d45e9-d4b5-518c-8add-b613ad2452b3 | note | RECORD OF CONFORMITY: This ITP Signed
0554ba0b-3b75-5d99-9653-68eeac225898 | note | IP
ae15dc98-0a37-5351-af45-a0013d130c3b | note | RESPONSIBILITY: Engineer
e3a68014-a40d-5f52-87a8-0d1c4370f7eb | date | Date Completed:
135deec4-4608-4811-817c-7f2eda3112e9 | checkpoint | 2.11 - Pram Crossings
d8d98ef5-3f8f-507f-b72d-08b49cadb3c8 | note | FREQUENCY: Each Lot
757aeac1-44ac-5e8f-b6ba-98456ca93bcc | note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
82f7154f-706e-568d-bf11-c38f78e03911 | note | REFERENCE DOCUMENTS: Booroondara Standard drawings
17a1a56a-1315-5f31-a3ec-d208898b5266 | note | INSPECTION/TEST METHOD: Verify
38b84a8a-7d24-5ec5-8844-ba10d20157fa | note | RECORD OF CONFORMITY: This ITP Signed
2508dea4-0dad-543f-9956-3122192e3e60 | note | IP
d48940db-a3f8-5bc3-b2b3-5052224bcac9 | note | RESPONSIBILITY: Engineer/ Site Foreman
6532c16f-98c7-503c-9a1a-afe73e5af0de | date | Date Completed:
ca23f082-13ae-4b5b-92c1-76c896d58ce1 | checkpoint | 2.12 - Joints
23b363d6-a882-57e2-84d7-99fa349c16a6 | note | FREQUENCY: Each Joint
60a7d393-5801-523a-9178-f7441df5ed37 | note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
be70dd6a-ccd0-5a02-a44b-99e35b65dae6 | note | ○ Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
6bf604cf-c46e-5522-ba4b-e65f6c8676e7 | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
0f970ce0-ef91-5713-bdf9-c5f5a8bd5c16 | note | REFERENCE DOCUMENTS: 703.26
5554252c-ed6c-55d7-9f4e-1c56456726ce | note | INSPECTION/TEST METHOD: Visual Inspection
a2f027e7-1107-5a7a-a238-7fff80698023 | note | RECORD OF CONFORMITY: This ITP Signed
f55019be-a80e-527a-b328-e90e51898b20 | note | IP
a305e3e3-6da9-5c04-8d89-a137d207b438 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f5e02981-a665-5628-80fa-3afd3b793746 | date | Date Completed:
20b10bb1-b0e1-45f4-868a-daf0af040945 | checkpoint | 2.13 - Protection of concrete
fcbb294e-e642-5e29-a061-8ea680c8367e | note | FREQUENCY: Each Lot
49774e5a-0994-574b-b53d-e2a957009dad | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
9c892937-cc59-5d6a-94a8-a8ea440097dc | note | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
2d2fec56-d994-58cc-a797-7a019af031c7 | note | REFERENCE DOCUMENTS: 703.27
e015623e-37e2-5afb-9767-eb9e25c26269 | note | INSPECTION/TEST METHOD: Verify
12e622df-8889-50c5-b177-7dd2ea15acce | note | RECORD OF CONFORMITY: This ITP Signed
f8d17526-03cf-5663-ad84-6072a427d9f9 | note | IP
db04e0ff-83ec-5ba3-93ab-bc44fa47e801 | note | RESPONSIBILITY: Site Foreman
24ac9e87-615d-5a50-bc9b-82f4f561ea01 | date | Date Completed:
f395fdb8-6f85-487d-9d76-f3d7e739e850 | section | 3 - Completion
c34cdec1-61e7-4b1a-a471-e2786f12d4cb | checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
a6c0b9ab-a230-5b8d-842f-99ffeb34cea0 | note | FREQUENCY: Lot
c6bc8ff5-8dea-5c2c-a403-1bcdf34bf97a | note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
bac622e2-5a67-5d7f-94da-fffcd6883d79 | note | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
621d263f-5bda-52a5-9cd6-3afcaf1f426a | note | REFERENCE DOCUMENTS: 703.11
e053c590-4f90-53c3-9d07-de6fcd0a68f7 | note | INSPECTION/TEST METHOD: Checklist
e2e5eff4-cb0a-54ab-b81e-cb40242a348c | note | RECORD OF CONFORMITY: ITP Signed/Test Records
2257eb82-57c0-57c3-87cd-58104190d258 | note | TP
da9c4624-4457-5a0b-821d-c1c9adb7717e | note | RESPONSIBILITY: Engineer
ea2af13d-7d7c-5cbe-b508-8dbc2f4d87ca | date | Date Completed:
71243291-453e-486a-9437-7204a52ddb8a | checkpoint | 3.2 - Tolerances
51ec8ec8-6223-5f1a-8f0f-fabb65ebe2f9 | note | FREQUENCY: Each Lot
21a3426d-9097-5760-984b-f59a40dedf3a | note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
23401a6b-07c2-5535-bb22-4d7e98a5785c | note | Section dimensions shall be constructed within the following tolerances:
88f83aa6-fb5b-5059-ac37-3e0561194dc1 | note | ○ 5mm and 15mm for width; or
507c8fad-7240-5c64-8582-5e1403d6be81 | note | ○ ±3mm for dimensions less than 25mm.
38e307fc-dffd-5f0d-9903-c124da7821e0 | note | REFERENCE DOCUMENTS: 703.15 Drawings
6b3690a0-5ebe-58bd-acc9-90f230ca7c7f | note | INSPECTION/TEST METHOD: Visual Inspection
28719ff0-151a-5b8e-8c08-68b26a98f744 | note | RECORD OF CONFORMITY: This ITP Signed
f0723075-d043-5e0f-abe5-4a3a8ca789ff | note | IP
d7d3aae0-4619-556b-a625-c24326ac2d46 | note | RESPONSIBILITY: Engineer/ Site Foreman
f11bd646-e136-559d-a5b0-de79c632085e | date | Date Completed:
0a7d676c-b2ef-4440-a38d-d593ac90a9f0 | checkpoint | Final Inspection
91bbe586-40cc-59d9-bded-b8c8386af1a0 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0ec08e64-12da-546c-af4d-fe313bf7f855 | textbox | Print Name:
6def63a1-ae3e-52b1-817b-79d829cec6ad | textbox | Position:
921e83c5-4bc5-5fa9-bc76-77bbe288ca8e | date | Date:
02ab52af-9fde-4035-8264-c90fc0b37c7a | checklist | ITP-011 - Construction of Subsoil Drainage Rev1 | itp | ITP-011 - Construction of Subsoil Drainage
7fc7004e-2199-4d13-acba-d8c40910b7bb | section | 1 - Preliminary Works
30ca1870-ca73-4e02-9b7e-e24101e939a5 | checkpoint | 1.1 - Check for correct documentation
80472a82-0b59-5c28-971a-6f668b9af563 | note | FREQUENCY: Prior to commencing any activity
2c701692-b1d7-529c-a83c-2e07900afa98 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
8587b330-0914-56a2-b0fd-52eef93fe0a2 | note | — using the correct and complete set of drawings
1cbfd28f-f23f-58fd-ac81-c325aa8c10f8 | note | — all drawings are the latest revision
7933b434-6836-5819-9123-a70f6ccdd630 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
81914b62-6312-5011-86c6-0c412e5df58f | note | INSPECTION/TEST METHOD: Visual inspection
598dbdb0-9e36-5e19-8712-8eaa6c42ac70 | note | RECORD OF CONFORMITY: This ITP signed off
b17ebc5b-b58a-5067-931e-98977f332ffa | note | HP*
1a7be79b-3d61-5120-bc43-dbc0f713fccb | note | RESPONSIBILITY: Site Engineer / Site Foreman
42b7733b-6d54-55c8-b9f7-ed0799654500 | date | Date Completed:
b5099dc3-7100-49fa-987e-4a6d2e30838e | checkpoint | 1.2 - Implementation of all measures and controls
95589d89-9f2a-590b-811f-b81d8edd2056 | note | FREQUENCY: Prior to commencing any activity
eab69d0c-71cf-5db9-ad6a-a5afd69a039f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
229730e2-7b2a-5b58-b7a7-8c26d4b7c66d | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
27c02f53-e121-598a-83b2-17bfb2a6cead | note | INSPECTION/TEST METHOD: Visual Inspection
12f5f335-506e-58a8-a349-8890d1171033 | note | RECORD OF CONFORMITY: This ITP signed off
b68b541f-1e16-5ef4-bef6-7fa7ca9b6719 | note | HP*
c4cd3ca4-f386-50d5-ad8c-4478abecc711 | note | RESPONSIBILITY: Site Engineer / Site Foreman
3149f263-f619-5e0d-a353-d9839f2f1a2f | date | Date Completed:
890a1bd3-d82d-44e2-bc44-e29249438bd0 | checkpoint | 1.3 - Material Classification
49a55aa4-6aba-5224-a029-d7778caea7fc | note | FREQUENCY: Each Lot
6163aaff-997d-5484-bab5-d6320cfb67f3 | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
c2c947b2-420d-59fe-b167-49acf3028ebf | note | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
efc0e69d-7016-5e8c-9375-b5a06ec88511 | note | ○ Geotextiles: Shall comply with Cl 702.06.
eb6c70fa-7858-5a58-b5c6-3053e6af9227 | note | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
21857258-5c3b-50c7-8cb7-700a2e55b5af | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
20bd1886-6079-50b6-8381-eb7f06165ed9 | note | ○ Flushout risers: constructed to the detail of SD 1631
95930c9e-e7ce-569d-8ec3-d4340dfd82a7 | note | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
200ea2d9-7f8d-5268-97ba-e71660e3a226 | note | INSPECTION/TEST METHOD: Verify
45dee328-4bd7-59d0-8f51-87faa87d5658 | note | RECORD OF CONFORMITY: This ITP signed off
e462359a-ebba-5236-a8f0-7ccaf2b7e435 | note | WP
5d99110d-7656-56cb-8a19-6adf1f600ad9 | note | RESPONSIBILITY: Site Engineer
61316b55-e026-5bfe-9ab2-a601ecf9bb66 | date | Date Completed:
5e7902dc-3144-4665-962e-80930fc8105f | section | 2 - Construction Works
00480b2f-0d29-4801-8126-48dae003fa92 | checkpoint | 2.1 - Excavation Permit
2ba698b1-1179-5a84-839e-9b1792a21e75 | note | FREQUENCY: Each lot
816eed86-bffe-5040-8408-a93255e706c4 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
52599e0b-c854-500b-83b7-b54bdbf0a37c | note | REFERENCE DOCUMENTS: Excavation permit
f4513784-ea85-56dd-8483-c74d0277ddac | note | INSPECTION/TEST METHOD: Verify
c032c7c1-9e5f-5aa7-93de-3fa560d1355f | note | RECORD OF CONFORMITY: This ITP Signed Off
9103cd10-e060-5660-b88b-4f1bf10a97a1 | note | HP*
44a34572-7122-520b-a167-96bd84e946ec | note | RESPONSIBILITY: Site Engineer
42961d71-0778-51fd-b246-9b41279b6734 | date | Date Completed:
453a12c7-43c0-40cc-8db4-d8286c626aac | checkpoint | 2.2 - Excavation of Trench
b88c9985-94fe-57a5-90b5-de9ae356b7cb | note | FREQUENCY: Each Lot
4f453abc-45b8-57c4-9bd2-efbb9784cd94 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
5e880e28-bba2-5065-83e3-899d21505db0 | note | REFERENCE DOCUMENTS: Cl 702.08
3be1b69f-0d86-56b4-9ea6-0e988961792b | note | INSPECTION/TEST METHOD: Visual Inspection
2efc4153-1a74-5a10-9bee-fa12ed506c9f | note | RECORD OF CONFORMITY: This ITP signed off
a0d0e294-3f41-5592-93a5-6bfec648fc94 | note | HP
1799327c-b42d-514f-a019-0e7df0007840 | note | RESPONSIBILITY: Site Engineer/ Superintendent
1ff23b80-4ac9-5322-a430-049325be4d05 | date | Date Completed:
a1312edd-7497-4563-8b40-623e52f47517 | signoff | AUTHORITY HOLDPOINT
71a263cd-cb47-4198-b92e-879cf821faa4 | checkpoint | 2.3 - Placement of bedding
7b553d0c-cbc1-5ceb-b466-2244321e4b6e | note | FREQUENCY: Each Lot
11e51126-58a5-5759-bc08-fce23e70dd72 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
03efed11-7ad5-59e2-843e-9c9e89a00fc2 | note | REFERENCE DOCUMENTS: Cl 702.09 (c )
74342f0f-0b53-5bb6-9816-3975b41eb7f8 | note | INSPECTION/TEST METHOD: Visual Inspection
e803d614-0827-51d3-9273-93417740eda7 | note | RECORD OF CONFORMITY: This ITP signed off
e9283394-f776-5b82-929f-f93bb88e600e | note | IP
04bf8167-5085-584c-b76a-db7efc46da07 | note | RESPONSIBILITY: Site Engineer / Site Foreman
aa515d5e-fd05-5990-a728-2ed911a84160 | date | Date Completed:
75be1cb9-08be-49ca-b52b-8373cd35b08f | checkpoint | 2.4 - Placing pipes and geofabric (if required)
617a52af-807c-5660-9f40-0a13668b683b | note | FREQUENCY: Each Lot
6b590930-ed12-52b2-9a97-089c62bb4470 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
8a06a068-27da-5cc5-8465-a1406e77f7c1 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
9420f1bf-0b59-5763-a54a-7743a3622e88 | note | REFERENCE DOCUMENTS: Cl 702.09
0292bb9e-ddb8-52f6-9ba9-ff6811dc9a8f | note | INSPECTION/TEST METHOD: Visual Inspection
246fa718-914c-5d98-bc32-aecf24215313 | note | RECORD OF CONFORMITY: This ITP signed off
5bf201f4-6d1b-5636-9c76-bd213d6db649 | note | WP
b584d5f0-1219-5e79-bf5d-e86856ddf330 | note | RESPONSIBILITY: Site Engineer / Site Foreman
08ec4be8-2527-5324-be92-c2b5e55ae5f4 | date | Date Completed:
54c53278-72a2-4a93-a6be-5d5db7a508bf | checkpoint | 2.5 - Placement of granular backfill
906c8e5a-8b2b-5e3e-a076-ada415d8431d | note | FREQUENCY: Prior to backfilling
cf0a7878-6dda-5466-9877-3ce718a191b1 | note | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
a1ce5a78-d295-5d31-ad69-c82f77a23800 | note | REFERENCE DOCUMENTS: Cl 702.09
76814f58-0dfd-5d32-be99-f49d22bc9925 | note | INSPECTION/TEST METHOD: Visual Inspection
70362a40-55cf-508f-babe-e482f01ff60f | note | RECORD OF CONFORMITY: This ITP signed off
03ea3833-38c3-5df3-a7a6-213a55bbabd6 | note | HP
b2645fd2-662d-5eec-b5b2-a5f648d430a5 | note | RESPONSIBILITY: Site Engineer/ Superintendent
6773925f-2769-52ba-9840-6c25bcd4e3d4 | date | Date Completed:
7f3b1202-7315-48b6-bdf6-3e5a611f3441 | signoff | AUTHORITY HOLDPOINT
b061e256-27bb-4598-b9af-8c0155ca1023 | checkpoint | 2.6 - Placement of backfill
701a46cf-fa28-5a88-a3d0-699afa289d17 | note | FREQUENCY: Each Lot
9c3a8b76-5d4c-5395-bdd8-088a4842a228 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
78510ce7-0039-5391-8166-644d91bcc2ad | note | REFERENCE DOCUMENTS: Cl 702.09 (g)
4878493e-2fd0-5026-95b6-fe63450860e1 | note | INSPECTION/TEST METHOD: Visual inspection
a51094f3-b8f2-5500-95ce-22cae5b109a4 | note | RECORD OF CONFORMITY: This ITP signed off
325cd6b1-9528-5af7-9b47-f0fae1351bc1 | note | IP
52b5bbf3-9d10-5145-986d-535b8fa9adfe | note | RESPONSIBILITY: Site Engineer / Site Foreman
d5bbbffe-1857-5e3b-9824-81ec84395c83 | date | Date Completed:
1b4f623c-eb24-4c7f-bf12-574d4aa49469 | checkpoint | 2.7 - Install Pits and Flushouts
2a4366e2-dcf1-5c0b-bb6f-ebaf7a4be91a | note | FREQUENCY: Each Lot
668d9a5a-64c9-5ae1-923b-0d6034f5d77f | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
19a7be88-50fc-5fc9-a4f5-409b476dc190 | note | REFERENCE DOCUMENTS: Cl 702.10
5e158ba5-47db-5f2c-a114-7253a48d95df | note | INSPECTION/TEST METHOD: Verify
78adfea9-c51d-5559-b4dd-505c2eff4a1c | note | RECORD OF CONFORMITY: This ITP signed off
a2dda074-5a96-52d9-be66-e8fc6f6071f9 | note | WP
9763ad8c-e9fc-5993-95fb-8da8786247c9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
efc12fbf-1599-5bb7-a547-e05618d00b36 | date | Date Completed:
783e02d3-5e78-4856-ae85-6a7082c8422a | checkpoint | 2.8 - Flushing Test
bb30ba8b-0b43-5590-b4cb-a28e691b6798 | note | FREQUENCY: At completion of stage
44f8d526-28fb-5007-947e-aca93c12e370 | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
7e9f58cd-8cf9-5f0a-847b-5ea46aa20a8b | note | REFERENCE DOCUMENTS: Cl.702.09(h)
019dd3fe-b152-5af8-aa09-93e5d1e2259c | note | INSPECTION/TEST METHOD: Site inspection
a6397aaf-1f45-5e25-a41c-a909d9e1257f | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
bc5fc6b0-13a8-5a70-b120-3d71e3b2bfd1 | note | WP
87cdf912-580f-5b56-86d1-380adbc3d5c0 | note | RESPONSIBILITY: Superintendent / Site Engineer
1a042d7e-3001-52a6-a2cf-bbae672fd154 | date | Date Completed:
9bf2f607-804d-45fa-9d52-51d253ab91a7 | checkpoint | Final Inspection
b3db5e25-9d04-5cff-9a3c-d4f901f67c87 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
97941d87-f04e-5fd9-ad21-05f08e9bf1c9 | textbox | Print Name:
833a0cec-6c5c-5266-9a5a-8a5d2b5d36d9 | textbox | Position:
c02f2d2c-3ddd-5c2d-81ac-aeaede008316 | date | Date:
6cc620a7-e9fa-46fb-b3a0-621a3c23c896 | checklist | ITP-012 - Pavement Construction Rev0 | itp | ITP-012 - Pavement Construction
01cf0114-4b7a-48c0-b24a-d587c9cfd1e6 | section | 1 - Preliminary Works
2f1b981c-6830-4c19-a3cc-a03dd2b93b45 | checkpoint | 1.1 - Check for correct documentation
5296e973-225c-5caa-8a1f-f5ba872e1c76 | note | FREQUENCY: Prior to commencing any activity
b9a4910f-ced8-5552-bf08-66f835bd0506 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
10f48c51-477c-5d26-a7c9-b149d75358e3 | note | — using the correct and complete set of drawings
a61c242f-efa8-5c40-bb13-859c665f4537 | note | — all drawings are the latest revision
20975446-f33f-55ff-b22b-283b9e293ded | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4550d9bf-b674-50c8-afc7-6d344c623bc6 | note | INSPECTION/TEST METHOD: Visual inspection
f66f8648-9c5d-55c0-b1c6-3128553ec06d | note | RECORD OF CONFORMITY: This ITP signed off
e4fb3df0-b3cd-5c59-81e6-670985835162 | note | HP*
3db1b17a-e463-560f-8bac-309addf37a58 | note | RESPONSIBILITY: Project Engineer / Site Foreman
698b9a36-a787-5261-ac4d-4139867c4245 | date | Date Completed:
8d1ce7d1-a737-43fb-812b-b35948908292 | checkpoint | 1.2 - Implementation of all measures and controls
43695eb7-c98f-5abf-9a37-6c36065ac843 | note | FREQUENCY: Prior to commencing any activity
ff9a72f6-4100-5c2a-9d51-df0c035dfcae | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
c4ce432b-1cd7-5370-b612-c3acbd07ddb5 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
bed115d9-6824-5346-81ed-8b3ecd336eb9 | note | INSPECTION/TEST METHOD: Visual Inspection
02ce9464-4b3d-5fda-a515-da51ef432875 | note | RECORD OF CONFORMITY: This ITP signed off
01b54045-be9a-5f9b-8114-d5115f5de02f | note | HP*
69bad26c-78e4-5c1a-b7af-cdaaf6dd7764 | note | RESPONSIBILITY: Project Engineer / Site Foreman
79633c92-558c-5b52-95d6-ab66a12cee68 | date | Date Completed:
70053c05-ca98-46e9-9b52-9afd340ae68b | section | 2 - Construction Works
ba8eee4a-b3f4-49f9-901c-b2302ecb1719 | checkpoint | 2.1 - Survey Set-Out
abb55144-3c84-55f7-a4ad-17f0778e8fe2 | note | FREQUENCY: Prior to commencement of excavation
56d98c78-4a7d-5ca0-b79e-0811eac98317 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
d6b6a825-c761-51c5-821f-b90d582bfe3e | note | REFERENCE DOCUMENTS: Work Procedure
7cd954a7-0a22-5db9-9468-2ea6f8553cb4 | note | INSPECTION/TEST METHOD: Verify
15da7d7f-403f-5bd3-b47f-1ca4723c3c8d | note | RECORD OF CONFORMITY: This ITP signed
d1167697-3a3d-5ec1-8d55-2bfc08863d9b | note | IP
6a2dfbe7-0433-5693-b92f-995d107c6d79 | note | RESPONSIBILITY: Engineer/ Surveyor
c14a5aef-e4c2-5eb1-a0a5-177a21c141ca | date | Date Completed:
a8fc880d-d077-4f88-a2b2-36a8a5a9347a | checkpoint | 2.2 - Excavation Permit
31d5c22e-38e2-59a2-840b-98bcb26ead96 | note | FREQUENCY: Lot
73a136c5-707f-596f-b38c-e4c9dd459c00 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
512ab59c-099f-5aed-90fa-093813552275 | note | ○ Plant and equipment shall be appropriate for the task.
e1024cc4-e60a-5fcf-ac3e-072483a00f84 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
fcbe2409-0aec-5b2d-b80c-da12a48f4834 | note | REFERENCE DOCUMENTS: Excavation permit
af58042c-9adc-551f-8b49-accdebf8fe37 | note | INSPECTION/TEST METHOD: Verify
d9bf37c6-6a87-5bc8-9fed-06032f925d2e | note | RECORD OF CONFORMITY: This ITP Signed Off
8f352114-5afb-53a7-96b1-b8213e48a341 | note | HP*
e0638eac-8a9b-550f-b2b7-ff28b280cd5c | note | RESPONSIBILITY: Project Engineer
5b1cdf1a-12db-5951-8d48-77db61257e0a | date | Date Completed:
2bf46cc1-2899-4136-8082-ecff524fec62 | checkpoint | 2.3 - Material classified as silt
71a7a131-6c94-5c50-bda1-57279c2fee17 | note | FREQUENCY: Prior to Commencing
4d9870df-8e65-52ed-9101-100314a37912 | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
ae52477a-2778-5dae-b193-e7d2ee79baba | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
d525323d-1f50-5891-b82c-ca12b57618bc | note | INSPECTION/TEST METHOD: Document Review
f2205fe6-f10d-5606-8a9d-2106d29ba910 | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
c3447893-655e-53a5-bb6b-8ccc367ab6d1 | note | HP
863b9f06-1ad6-54ea-b594-89d63932138b | note | RESPONSIBILITY: Engineer or Forman / Superintendent
1f374fa6-0e02-5887-94df-e4f191a85548 | date | Date Completed:
8acc94de-f55c-4fd0-a3ee-603bb66445d3 | signoff | AUTHORITY HOLDPOINT
c2ef85bf-81f7-4431-a4af-35b8891a32b9 | checkpoint | 2.4 - Acceptance of Rock Subgrade (when applicable)
d76088b4-829b-5b50-a561-426ebe454654 | note | FREQUENCY: Prior construction of the regulating layer
513c6007-0570-5576-80c4-7be546e25080 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
0cb423bc-a774-5cdf-b78a-c86bbd0ef53f | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
eba8172d-6cf8-52af-ab7a-19e0c17c5df5 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
834d5dac-93c9-5fff-9516-cbb4a1214e11 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
cf4b2134-56bd-5cee-a13f-219b73a2d1bd | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
8cc5d4ec-5a73-58b5-bfa5-e0e019b94cbe | note | HP
cbcef55d-b3fc-5762-a864-dc90600e950f | note | RESPONSIBILITY: Engineer or Forman / Superintendent
2185e854-793f-5aa8-b001-1ebad743d588 | date | Date Completed:
cedf1ab4-a2b6-484c-9cc5-a208a5f32d95 | signoff | AUTHORITY HOLDPOINT
0de7e9c8-413b-4a67-bd4e-870bd22dadfa | checkpoint | 2.5 - Unsuitable Material
45e0e898-8361-55c1-ae0b-de3673798cbf | note | FREQUENCY: Each Lot
47476c7f-2799-5424-8039-d5f4ba85833b | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
af42a7ed-1f4e-5d8e-b8c9-2ca62f197f35 | note | REFERENCE DOCUMENTS: 204.07(d)
dbad4f73-b1f3-5553-975b-e12228a8301a | note | INSPECTION/TEST METHOD: Visual Inspection
fe1f8d17-1aa7-51fe-8e3f-04eabfb78895 | note | RECORD OF CONFORMITY: This ITP Signed Off
7edd9ca0-d885-5a40-b5ea-12b54e4e820f | note | HP
2abc1515-d450-54da-a12d-de6b5cce8b11 | note | RESPONSIBILITY: Engineer or Forman / Superintendent
9269b4fa-0fb0-572d-8d96-a06c81f2dd05 | date | Date Completed:
517f122b-8049-406c-ad72-eaa8c5af926e | signoff | AUTHORITY HOLDPOINT
da512126-6dc9-4fa9-9c05-10aa907bbade | checkpoint | 2.6 - Groundwater
0731af14-9d60-5da2-89a7-ba0deae14b36 | note | FREQUENCY: Each Lot
cd360c54-9b61-5f19-a35f-ab3f450e3ab6 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
8a99f236-96d5-5e44-ae0d-b61812d631c1 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
7400a0d5-c61b-5653-b188-f676e45d8aca | note | REFERENCE DOCUMENTS: 204.06 (h)
f31f8d34-7ed5-55c2-862a-1fcb56a9a399 | note | INSPECTION/TEST METHOD: Visual inspection
8ae15c23-b45c-568c-8e8d-6f0c0c18b235 | note | RECORD OF CONFORMITY: This ITP signed off
2e2bf217-e13f-5d56-9fa3-8fcba13c206c | note | HP
8c7cb966-a92c-512d-910e-1e884d787369 | note | RESPONSIBILITY: Engineer or Forman / Superintendent
7acfb394-6cd1-5503-b7af-506c42ff0fbe | date | Date Completed:
f5603fa9-5c06-4846-9aa8-d720063d53ab | signoff | AUTHORITY HOLDPOINT
3a1130f5-bb38-4cb4-bb87-660bee5bb33b | section | 3 - Testing
f456afb2-e9cb-49c2-b9bc-80ca55b2a49a | checkpoint | 3.1 - Proof Rolling
c79a9495-0e84-5a45-9446-64a48064dd9d | note | FREQUENCY: Each Lot
a5dc083b-a5d5-5f05-8012-78ab105b5f0c | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
7a5ec305-d4a2-5514-88bb-6e96d9d104fa | note | REFERENCE DOCUMENTS: Cl 204.12 Section 173
1ae485b2-0908-5ed8-84fc-b89e139b7c3c | note | INSPECTION/TEST METHOD: Visual Inspection
ae70fe27-6c74-5e55-8ca3-eccc4a19e81c | note | RECORD OF CONFORMITY: This ITP signed off
b0beb963-8324-55bb-b8d6-c752fe8e988b | note | HP*, WP
33180720-7b77-548c-82f6-41834669dfe3 | note | RESPONSIBILITY: Engineer or Forman / Superintendent
df327974-0a64-5b27-b5e7-18b71db6275c | date | Date Completed:
71754151-94d0-4bf5-8547-8a0b692a1246 | checkpoint | Final Inspection
fe65111e-d184-52e0-b7b0-9831c8399ebe | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
53109aa4-78b6-5c16-a8d1-e3caa61b84f7 | textbox | Print Name:
72c9e543-cba9-5f8a-bc89-1188d4496b06 | textbox | Position:
d1684282-133f-504e-827d-672a5dfae3b3 | date | Date:
79ea1d3f-8765-4edd-9548-8ae5059b108b | checklist | ITP-013 - Construction of Kerb and Channel Rev1 | itp | ITP-013 - Construction of Kerb and Channel
90eec311-b27f-4e37-80be-556b3cc81c1b | section | 1 - Preliminary Works
8602d197-d54f-43df-938c-4269b2cc4adf | checkpoint | 1.1 - Check for correct documentation
39f7bea3-91c0-5fd9-883e-bdb2d05c3ce4 | note | FREQUENCY: Prior to commencing any activity
80749327-39fa-5315-95b7-4607747878d6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3aac3b69-ddd1-5a8c-a924-ecfcda1e52d5 | note | — using the correct and complete set of drawings
68299b68-b118-5ba0-bf1a-37f1d57c7a2d | note | — all drawings are the latest revision
ca066c87-66a6-5df5-b753-b6dbc2acdf43 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ece7c942-9e87-599b-adc3-c5e28960851d | note | INSPECTION/TEST METHOD: Visual inspection
df4af7fc-4253-52be-9088-e75321d8b5de | note | RECORD OF CONFORMITY: ITP Signed
a1cbbf59-7785-5af1-9877-d528009e83f6 | note | HP*
c981ca90-b078-5df9-bd93-93f8864c28b9 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
26b40087-80ff-5afa-a1ae-e79473946c8d | date | Date Completed:
85002ab4-5939-45e6-873e-6b504b678ec3 | checkpoint | 1.2 - Implementation of all measures and controls
0ea2ba02-08e5-5784-8b9d-dffaf3046174 | note | FREQUENCY: Prior to commencing any activity
af1026a9-1484-59e8-8602-f5dae314fb5f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
286706ef-15a6-5a14-9329-66513d50349a | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
d29a6e2f-b06d-595d-aac1-12603dd4f65a | note | INSPECTION/TEST METHOD: Visual inspection
3bd18792-4987-52fc-a3d4-48fd85f6c1c7 | note | RECORD OF CONFORMITY: ITP Signed
cf221ed0-56da-5b86-b092-a5c7279e6fc1 | note | HP*
08ece24e-ff1d-5bfe-a987-d1b03929334b | note | RESPONSIBILITY: Project Engineer/ Site Foreman
847e48b1-7503-5e33-b4e3-fb486042307d | date | Date Completed:
4e8c4c7c-9402-4978-8379-dd523540aa9e | section | 2 - Construction Works
98bd1bd3-ab0a-4508-a385-88fd2d26d438 | checkpoint | 2.1 - Setting Out
46d693b7-5bf8-57a5-9362-6344c3cf9a7f | note | FREQUENCY: Prior to start
00b697c5-7166-5012-8576-0c2f7aa767fd | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
b9ed640a-9e3c-5217-8545-c2b67f20ccd6 | note | REFERENCE DOCUMENTS: 703.17
c41016fe-a683-56b5-8617-ebffb4878691 | note | INSPECTION/TEST METHOD: Verify
8bc9df32-ac27-5e1f-9bc4-54e578a31e82 | note | RECORD OF CONFORMITY: ITP Signed
37812bc0-7ff9-534a-852a-aa5999e238bf | note | HP
e0eea56c-382e-5828-a848-a953d51d3860 | note | RESPONSIBILITY: Project Engineer/ Superintendent
8398eeea-bf78-56ad-9d51-d5f11dffead5 | date | Date Completed:
fdc733c0-5e83-4cd5-9ad6-0d6e43f50aef | signoff | AUTHORITY HOLDPOINT
423a5f59-af16-4192-ab12-e9a09474bda2 | checkpoint | 2.2 - Temporary Drainage Provisions
85f409fb-8bdb-5b0a-9882-16f590967fcc | note | FREQUENCY: If Required
0e76a466-883e-587d-9eba-2f2a6e68c0d2 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
56ac0e01-0d11-5bf5-b10c-f74f98c77755 | note | REFERENCE DOCUMENTS: Cl 703.18
1c183fdc-5e91-5206-9086-4202b3c8e73f | note | INSPECTION/TEST METHOD: Visual inspection
458a1fab-8b1e-57c4-9af8-fbc01fc24080 | note | RECORD OF CONFORMITY: ITP Signed
bd5d88a0-1f19-5135-8d36-4f8a8ad56c3e | note | WP
94d00e60-5443-5338-bafd-06a3239db78f | note | RESPONSIBILITY: Project Engineer/ Site Foreman
3a66d715-1470-5e64-970f-d27aa21064cf | date | Date Completed:
d758f86e-55a8-4a1a-b8f6-10430466a714 | checkpoint | 2.3 - Bedding
3041e9f7-3174-56b2-9315-64ad07b5cbda | note | FREQUENCY: Each lot
fff8b9c2-7a7f-51bd-932c-580454b94b68 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
d0d1b64c-7105-5df1-919a-0e55104d86a3 | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
f2c456bc-1f5d-5d48-b039-397b98b9edf7 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
e9284bd9-41c2-5864-8b25-7eb35073f5ae | note | REFERENCE DOCUMENTS: Cl 703.21
ee3b6efe-54a3-50df-bf7d-74218738303b | note | INSPECTION/TEST METHOD: Visual inspection
67dbc242-0038-5360-a4d2-9e21be5c7405 | note | RECORD OF CONFORMITY: ITP Signed
474c7344-03c1-530e-bc1b-cf25152b8dab | note | WP
f2d4394c-a746-5862-a0c6-1e8ca8f0d80f | note | RESPONSIBILITY: Project Engineer/ Superintendent
90513cd4-0fe4-5e29-87e1-a4d6fa177d2d | date | Date Completed:
2c7d014f-7a51-4568-95b9-aa2a693db66b | checkpoint | 2.4 - Pre-concrete check
400ff1e3-0f2a-5cbc-a9cd-dc5c7bdbeb25 | note | FREQUENCY: Each lot
3f8958ba-a02c-5179-aa0e-817c32611284 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
e4315b01-2fdf-5029-856d-8ab663141576 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
e05bef05-ad2b-5e7e-8d0b-0f4fdac7a7cb | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
d0a6d7ad-84d6-5b9f-9061-0c8629a0eebc | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
a400779a-5c7f-5edc-bf59-c1faa5948c7e | note | REFERENCE DOCUMENTS: Cl 703.08
00adae63-c01b-565f-a3fa-368022ba96d8 | note | INSPECTION/TEST METHOD: Verify
f668b848-d884-5ca9-a196-195a65a01078 | note | RECORD OF CONFORMITY: ITP Signed
c52b0dc2-ff9f-522a-a929-c5680f9d7775 | textbox | Ambient Temperature |  |  | °C
2ddb83e4-1269-5a6c-a2fb-5aab6096cb62 | textbox | Concrete Temperature |  |  | °C
d3d8241c-7568-52c7-83ca-150744947740 | note | HP*/ WP
5a50a6e8-b2cf-5d45-956b-1f5cca579c15 | note | RESPONSIBILITY: Project Engineer/ Superintendent
c5dd900d-0694-5dd4-a807-2ee83a43126d | date | Date Completed:
dbc560bf-6c21-48e5-924e-e6c08078666a | checkpoint | 2.5 - Concrete Placement
22c91d96-8906-506e-99f0-e1c2737355c7 | note | FREQUENCY: Each lot
bec44aaa-2711-5ee4-a712-b75a4ab60e0d | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
00094792-0976-5f7b-82e3-a4b7be67d79b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.23
044114be-06c2-5c24-a980-56bb4e07e3f0 | note | INSPECTION/TEST METHOD: Site Inspection
d0926436-aa02-528b-8271-7b9271c1ecc8 | note | RECORD OF CONFORMITY: ITP Signed
6418e38a-12aa-5a87-a5e5-f564a5980ddb | note | IP
4cb9af68-d0f0-5e61-83ed-2d379a8b7cdf | note | RESPONSIBILITY: Project Engineer
0daf6290-8a9b-58c8-a192-1519efaa8eb0 | date | Date Completed:
147f0faf-f505-46be-8954-22c8318a86c0 | checkpoint | 2.6 - Finish Surfaces
e2347f17-33ce-5d90-9abb-c6ed61cb7ff9 | note | FREQUENCY: Each Lot
e41cad60-9420-5dc6-9b59-ae179aa89aad | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
52a12aae-ed9c-51a6-9ae6-ef1ea56f5c41 | note | ○ Concrete to have a neat appearance and uniform colour
17642c3c-b038-5881-9abb-d182f927d3ef | note | REFERENCE DOCUMENTS: 703.25
ea16171f-7a8f-515a-b759-e344f766ee18 | note | INSPECTION/TEST METHOD: Visual inspection
31c9b3d1-0c2a-58b3-bc3f-0e0a66204784 | note | RECORD OF CONFORMITY: ITP Signed
de1210c8-07e4-5da5-b783-ec5b2d521f85 | note | IP
1db22826-b215-510d-9564-fe1efe1d564e | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ba31d0a5-b92e-5ace-a7a0-f48bc015414c | date | Date Completed:
fba932bf-8735-42d2-a16a-3ec57ea0d933 | checkpoint | 2.7 - Joints
d85f467f-03bb-5931-a186-9f936a4f200b | note | FREQUENCY: Each joint
09723b02-9b8e-5faf-92fc-e72abd638fb2 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
32b2a9a1-83b3-5bf1-ba55-6ff7d6f4d363 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
9a6194d0-c22c-5d02-9684-8dee75784ac2 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
a04730a2-e49b-5626-8542-4b88a4e7e0d5 | note | REFERENCE DOCUMENTS: 703.26
b0f4fb61-7ad4-53d8-a1af-b826f227e52f | note | INSPECTION/TEST METHOD: Verify
506639a6-f6c0-5abb-b6a7-c4aaf4a02c37 | note | RECORD OF CONFORMITY: ITP Signed
0585253b-6756-57bb-a1ac-06e9b94cb8c3 | note | IP
cc637b4a-0f85-5854-8b77-f7e04ec54a55 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
a05cdb14-2949-5646-939a-68f5bbdc2a0e | date | Date Completed:
8de61362-cbec-4df4-9661-a7b8df5c8438 | checkpoint | 2.8 - Backfilling
c1d67d68-e0a9-5ece-ae68-cd805ba4c4df | note | FREQUENCY: Each Lot
02f6ea83-7c51-50bf-aa57-415dd5e35424 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
543ae9bb-2e9f-5800-8bb8-2a57fb3a283e | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
14bca983-23c9-5965-abfd-f9f20356a923 | note | ○ Layers shall not exceed 150mm compacted depth
53886cd2-af60-599d-a5c1-3a1d59ec5a0b | note | REFERENCE DOCUMENTS: 703.29
d90f90e5-544d-5778-ae22-f4af6bd2e187 | note | INSPECTION/TEST METHOD: Verify
5f057ed5-b240-5767-9de6-1a1bb5d351db | note | RECORD OF CONFORMITY: ITP Signed
f52f2b68-6770-5c38-b2a9-1f23d7fb9911 | note | IP
4a14986d-db1c-5094-9839-501e62e27cd3 | note | RESPONSIBILITY: Project Engineer
dfd0f817-2ae7-52d7-ac31-41505a8cdde6 | date | Date Completed:
b89a89d9-6fcc-4ea9-ba1d-05adca556825 | checkpoint | Final Inspection
9dbd8abd-9dc6-56e1-b8db-a2d596adbc1a | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
0b53c536-ee9d-5e3b-bfcd-a612f4e6b89e | textbox | Print Name:
b9c4a1d7-c7f1-5e6e-a347-1f65f2aaae2f | textbox | Position:
b7d10f8b-eef7-597f-aa58-b173dc7b2c00 | date | Date:
3de7cbe3-db42-4056-acfa-75cf5db7b916 | checklist | ITP-014 - Sealing works - Asphalt laying works Rev1 | itp | ITP-014 - Sealing works - Asphalt laying works
228271c8-7740-426f-9d40-fb0c43bf6552 | section | 1 - Construction Works
2df4ae93-650b-411d-8100-868359082198 | checkpoint | 1.1 - Submission of Mix Design
b6d384d3-fcad-531a-b1d8-ff943cc0a6f7 | note | FREQUENCY: Prior to commencing paving
953afa5f-b6b9-50e7-8216-be11d4b5ccaf | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
ff320dbe-109a-5c7e-8131-8c52661834b0 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
fb740e8d-d904-541c-9a5d-66fb0f5e4ba2 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
2c3555c1-b7e1-53e0-b5e0-7e911dad50d1 | note | RECORD OF CONFORMITY: VR approval Completed ITP
4bcdd786-6363-540f-83a0-ce956aac94f9 | note | HP
ba642214-d2b6-5456-a74e-4ad3522d5718 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
419385b2-b01b-5aab-924c-25f4fb250d01 | date | Date Completed:
dddb0e92-de4c-4271-801b-2653d346fd44 | signoff | AUTHORITY HOLDPOINT
8a6f065f-9fa6-4aea-a5e3-97caa0be14d5 | checkpoint | 1.2 - Implementation of all measures and controls
d0fc7f1b-ace4-56b9-842d-5e89cb38b968 | note | FREQUENCY: Prior to commencing any activity
bc2ea8b6-2788-5a75-9e56-ed04f21466db | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
d51c310b-80ae-5095-8b0c-79cafb189e88 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
1ae011d3-30ba-5f5d-b042-35672bd24ce0 | note | INSPECTION/TEST METHOD: Visual Inspection
2c20f96e-b7a9-5b78-9339-cd69e34b225e | note | RECORD OF CONFORMITY: This ITP signed off
754a2681-e2e2-518d-a805-5890926b5086 | note | HP*
83badfd4-0374-5135-bc4e-03248b5ada54 | note | RESPONSIBILITY: Site Engineer / Site Foreman
626707fe-8e5d-5398-8e16-1be38d1c0441 | date | Date Completed:
afa49fda-794d-4748-9ff1-461692e13fe8 | checkpoint | 1.3 - Site Inspection and Base Condition
fac7f5d9-33aa-5864-a0dd-92d55731e0e6 | note | FREQUENCY: Prior to commencing paving
44ee2e33-b395-5302-a794-30f2fb40ce75 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
352c055e-55f9-5ae1-aaf1-f8f0161c9784 | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
ba6b9365-a45f-51c9-8136-67d7ad80da14 | note | INSPECTION/TEST METHOD: Visual Inspection
ba1c46fb-8e08-54e3-86bc-c67efd729d27 | note | RECORD OF CONFORMITY: ITP Signed
7c947ade-c2b0-5f4c-b557-10ec4ae197e1 | note | WP
7782dd3f-4bae-5a79-bde2-8f6b490e046d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cce5c328-379e-52e0-8585-15e00b134cbf | date | Date Completed:
164deabb-6b77-4830-86f2-4ae590e371f9 | checkpoint | 1.4 - Ambient Conditions for Placing
ccdcccff-a3ce-5d4a-a869-daa4c479820b | note | FREQUENCY: Prior to commencing paving
7c5201c4-2228-5405-bb72-50c20621cd79 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
7f7b20d0-7d9c-5978-aee2-c58697b1fcb6 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
ee8a8d48-0c15-52c3-b7e2-01a47bd037c6 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
79b0b66c-c141-5c43-931b-ac2b8bc752f5 | note | REFERENCE DOCUMENTS: 407.13
76bad7e6-9760-59b4-9e2e-0191904f6837 | note | INSPECTION/TEST METHOD: Verify
e4e6ec10-3318-5ac3-acfe-d25b2b3ae38e | note | RECORD OF CONFORMITY: Thermometer
bbaf6a13-d7e2-572d-9b83-f2043bec6c98 | note | IP
960ad784-a7b4-5eda-b0b5-5153bcf12675 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b9faab01-7d88-508f-b22c-7ce4b3d04ed4 | date | Date Completed:
baae36e8-1221-40d6-bb20-979468a81d4e | checkpoint | 1.5 - Planning of Joints
44fcb42a-136e-52bd-b0a7-529c1cad1df5 | note | FREQUENCY: Prior to commencing paving
130bb1f6-b4de-52ce-b261-8e5101ce46a8 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
236f9ce4-660b-59ed-aaea-3991f51c75c0 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
2dcf44ae-e1bd-5a2e-825b-444a9334a962 | note | ○ Longitudinal Joints Offset from layer to layer by at least
9276945c-b5b3-5a1d-8d31-97d39716e39f | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
b3d7b137-3ae0-54ad-b381-fcca675ab992 | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
2fb1510f-bee6-5eee-a862-6fa220054aa7 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
c6f4f893-8c4a-50d1-a4a2-6edbe5dd866e | note | RECORD OF CONFORMITY: Paving Plan
cbc43510-34b3-50eb-a0db-a7f77eb4df72 | note | WP
12e2f69f-c3f1-5c9c-bc27-df134fbc9f55 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
651d8a5e-17eb-5348-b750-9f9ed3217d49 | date | Date Completed:
4c24b16a-b4c7-4843-8bbf-9f77df3ebfe9 | section | 2 - Asphalt Placement works
5bc4ffa8-ffc4-4000-87ea-d20334802f69 | checkpoint | 2.1 - Tack Coat
fa53dcb9-3851-50bf-b030-d9a35551be64 | note | FREQUENCY: Prior to commencing paving
83c335da-c587-5e12-b839-28a758ccb62b | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
61cb1ba0-91ca-51f8-97db-6570da6159dc | note | REFERENCE DOCUMENTS: 407.15, AS2150 11
c83fa240-18f7-5b37-9563-49c8ab8f7c5a | note | INSPECTION/TEST METHOD: Visual Inspection
840a561b-34d8-5633-809d-d7d6cd9a8fc4 | note | RECORD OF CONFORMITY: Spray area
0e68cd21-fbc1-5417-8a46-cfb04cb51394 | note | WP
bdffc780-8cd0-5a91-bddb-c96464a35e6c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
a4fc0234-5dbc-5a86-8e8e-b87748b92b43 | date | Date Completed:
62b57f05-dcc6-4378-92b1-4f9048e5cfe5 | checkpoint | 2.2 - Commencement of Placing
35127022-62b2-5e56-b901-eef932e78029 | note | FREQUENCY: Prior to commencing Paving
ce50ca2a-4331-524b-813e-e9f72ec352a1 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
678441ab-d77b-5b91-b52b-1b2b42506f72 | note | REFERENCE DOCUMENTS: 407.18
6eba937e-79c5-53dd-87a0-297b5e14ecce | note | INSPECTION/TEST METHOD: Visual Inspection
f7942e92-7537-58ef-a86c-d936d349708a | note | RECORD OF CONFORMITY: ITP Signed
e1be9962-9ca3-538a-9bd5-3e0807256c47 | note | HP
1d644fc1-5d73-51a4-871e-a86096254646 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
4cc54357-37d2-5adc-beb9-a08ac3592c7f | date | Date Completed:
5f7fe87b-fab9-4083-9eba-52ad86fd1dc0 | signoff | AUTHORITY HOLDPOINT
fce359f2-e0e3-4d03-89f3-28079a13d46f | checkpoint | 2.3 - Delivery of Mix
bc5c0654-cbbb-5e56-bb34-3b4d321eaee9 | note | FREQUENCY: Each load
ac38fdbe-c8b9-510d-b6fb-94837d94e30a | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
301a23f9-f4d1-5924-8fb7-572e909f6342 | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
c645dbb8-83b5-54bc-ae23-a17253e4b0ce | note | INSPECTION/TEST METHOD: Visual Inspection
bb782ae3-b32e-529f-826c-42b25a1b9a5e | note | RECORD OF CONFORMITY: Delivery Docket
7e6fac75-55d3-53aa-819e-943d311f019c | note | WP
ed186415-f325-5379-abff-b27c38936439 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
26407551-0532-5330-b053-264fa340f23e | date | Date Completed:
ff87dde4-8a63-4b7f-aeb6-db3c13b0bce0 | checkpoint | 2.4 - Traceability
785a1ab0-a86a-52a1-a2fd-a4dab5a00d4e | note | FREQUENCY: Each lot
2f7339bf-97f5-5673-a035-afdd9f306652 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
a5b8e272-b8c2-5119-be9a-7de9aaabc95a | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
5fbe7598-520c-5d1b-a4b5-a93df5fc2b00 | note | INSPECTION/TEST METHOD: Verify
b8a8184d-7e41-5577-8d49-7126e36c1573 | note | RECORD OF CONFORMITY: Daily Lot Record
46e684f9-fd63-5853-a1b1-c1b87fdf0b5a | note | IP
e02b7351-3ba5-5397-89d6-4e5fa5f970a9 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
805134c5-158f-54d2-ab3a-a5271191befe | date | Date Completed:
ac2eeddf-716b-411f-a7cd-5b636c2b6918 | checkpoint | 2.5 - Layer Thickness and Level Control
1b31894b-b656-514a-bdfa-693d7da32abf | note | FREQUENCY: Regularly during paving
0d4c1cb0-6880-5def-8af0-600ea65dce99 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
785f06e5-11a5-5e92-8acc-8ba53166d0ae | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
445098ae-12b6-53ca-a0cd-c32586b0ce24 | note | INSPECTION/TEST METHOD: Verify
5e2016e3-7982-5c2e-b1e8-5959d67fcd77 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
2a0398dd-b30f-5638-af5f-e1e86daa0ebd | note | WP
a588a30f-d41c-5d59-b57a-45d2c2b52a65 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
f178fbc1-20c5-57ab-ae6a-33f0a1417d9b | date | Date Completed:
29bc79a8-8692-42b2-a97f-d3ca7cb1ad67 | checkpoint | 2.6 - Surface Finish of Wearing Course
eebaae17-aafc-562c-911e-e34bbfd1a57e | note | FREQUENCY: During paving and after final roll
a1cf1170-de9b-5a0f-8309-61ae53efb757 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
e660480d-d122-5595-999d-b13ff44ed6a4 | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
741a696b-0097-50f1-8639-312ed8ff8ae5 | note | INSPECTION/TEST METHOD: Visual Inspection
de284dfd-97ff-56c9-9626-b21b24bef8ef | note | RECORD OF CONFORMITY: ITP Signed
4cabea89-b682-5cc7-9bb2-2d644bc84518 | note | WP
80f17930-a5aa-5341-b33b-eef0bf9f6b08 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3c59740b-59d8-53de-b7bb-8eb631a6371b | date | Date Completed:
1c065079-be72-4708-af40-7a160f42d158 | checkpoint | 2.7 - Kerb and Channel
918f5f27-c402-588d-88ae-e7867db4d0ce | note | FREQUENCY: During paving and after final roll
9da541af-175e-539a-b3c4-43fa152717ac | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
de253442-5c0e-5248-90bc-3bf2b6f1c600 | note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
e49baa96-814c-5210-8915-356f934d58f7 | note | INSPECTION/TEST METHOD: Visual Inspection
ab42d365-b5aa-543f-a363-415d30105674 | note | RECORD OF CONFORMITY: ITP Signed
e4cddb17-c119-5c62-a1b9-83cab626f6d4 | note | WP
39bc31cc-c8df-5fe4-a2fa-524639625696 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
973ea80e-65a6-5bf4-a33d-830fdf50d9a9 | date | Date Completed:
23376877-0ec1-4171-88af-f8e59f17dd6e | checkpoint | 2.8 - Alignment of layers not placed against concrete edge
018b4d53-a9e6-516a-95a4-4f3b8508e7de | note | FREQUENCY: During paving and at completion of work
cc95a69e-6e4c-591a-a62f-06663d90903a | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
fd4d968a-f507-5101-a111-d55926a9f0e3 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
a009401f-38f6-56d7-bb79-4826ebb58a00 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
8d53114c-ed92-5ddd-8df8-74dc83761e60 | note | INSPECTION/TEST METHOD: Visual Inspection
0e682e64-9566-56d7-b905-f6a798a8606f | note | RECORD OF CONFORMITY: ITP Signed
906178e7-dbf0-535c-8444-178ca080903a | note | IP
b8e85c05-b429-5d60-94ae-28dd52370732 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
5911abb5-5e45-59da-b5c1-ff9d4b94f424 | date | Date Completed:
b3a1cbaa-b641-46fd-8881-60b7d482729c | section | 3 - Testing
df6ab3d2-37f1-4f6f-a7f1-63a1c1fe1b48 | checkpoint | 3.1 - Compaction
2f46de3a-9285-54c8-a4a0-e96cf83fd197 | note | FREQUENCY: Per Lot
b3c255ae-0462-500d-b5a1-050dfc6b3edc | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
1e539e4e-bc73-533a-ad5b-8985b6b19164 | note | ○ 94.0% or greater Accept lot
21731254-8e75-5a98-b8ca-95b3358fd42e | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
29412a19-facd-56ac-aa58-e5077daab70c | note | For layers ≥50mm, if characteristic thickness is:
65c6e915-99e9-5c7d-b98a-f1eb35ac7cf7 | note | ○ 96.0% or greater Accept lot
72f67ad1-306b-57df-9dc6-c5e36c2ba735 | note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
ef58f9f9-012d-57e6-b122-5cf56dd07c4d | note | REFERENCE DOCUMENTS: Table 407.221
af64b7c0-b46a-5881-8cb8-45b461c3690f | note | INSPECTION/TEST METHOD: Verify
c6396b58-669d-5aac-b49b-e6d5bddf6e88 | note | RECORD OF CONFORMITY: Test Report
6cd86109-3736-5d38-b08e-8d53b45887fe | note | TP
b38ad67f-b8fe-5035-9a32-45b6c05faaa2 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
809f19c7-e038-5d15-8a83-8905351f221c | date | Date Completed:
31f01ab5-2a98-4501-b906-e83f8b6da5ab | checkpoint | 3.2 - Level Conformance
150fad4b-cac2-5909-a45c-f8092192416f | note | FREQUENCY: Per 4,000m2 at completion of work
b37c09de-f39e-5b48-ae13-4b46860f42e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
0143a52a-5c2a-50be-a85f-15e85a739a88 | note | REFERENCE DOCUMENTS: Table 407.232
af77d831-e133-53c0-98ab-2ff38eb0ee96 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
72f161b5-39b9-5a5e-a104-8a030c321d43 | note | RECORD OF CONFORMITY: Survey Conformance
372e82bb-54f4-5656-a35a-c0f51549f275 | note | SCP
44416e71-51e1-5b7a-a0a6-e302339f71bc | note | RESPONSIBILITY: Site Engineer/ Surveyor
6133358a-9893-595d-bd36-0141949484d4 | date | Date Completed:
1f117a52-b190-4d93-b11d-acd206c97a19 | checkpoint | Final Inspection
47fadab9-0ff1-5af2-abd5-3be9e97dee5f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
34626ee2-d0c0-5c96-84fe-18a2fe2dfa44 | textbox | Print Name:
435f408a-76e2-53d2-8c54-04f491a54c4d | textbox | Position:
5dd4d329-d1bd-5c6d-8eeb-3c28474a8501 | date | Date: