## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Rock Fill - Redesign works | itp |  |  |  |  | ITP - Rock Fill - Redesign works Rev0
section | 1 - Preliminaries and Submissions
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized
label | REFERENCE DOCUMENTS: Current Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | CONFORMANCE RECORD: Current revision of drawing
label | HP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works /Rock Filter Layer / Permeable material
checkpoint | 2.1 - Site set out
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Site inspection with DTP Geotechnical engineer
label | REFERENCE DOCUMENTS: Site meeting required with Geotech to confirm base of Rock Platform
label | INSPECTION/TEST METHOD: Site inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Client/ Fulton Hogan
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Rock Toe material 1 meter minus spalls
label | FREQUENCY: Prior to placing rock fill 600 minus
label | ACCEPTANCE CRITERIA: Site inspection with DTP Geotechnical engineer
label | REFERENCE DOCUMENTS: Site meeting required with Geotech to confirm base of Rock Platform
label | INSPECTION/TEST METHOD: Site inspection
label | CONFORMANCE RECORD: ITP
label | HP
label | RESPONSIBILITY: Client
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Geofabric layer placed over bridging layer
label | FREQUENCY: Prior to placing rock fill 600 minus
label | ACCEPTANCE CRITERIA: A44 Bidum or greater required to be placed over bridging layer
label | REFERENCE DOCUMENTS: Delivery Docket
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.4 - Placement of rock fill
label | FREQUENCY: 3 inspections
label | ACCEPTANCE CRITERIA: Site inspection with DTP Geotechnical engineer
label | REFERENCE DOCUMENTS: Photo weekly meeting with DTP Geotechnical engineer
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.5 - Geofabric layer placed over rock fill 600 minus
label | FREQUENCY: 3 inspections
label | ACCEPTANCE CRITERIA: Site inspection with DTP Geotechnical engineer
label | REFERENCE DOCUMENTS: Photo Record Weekly meeting with DTP Geotechnical engineer
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.6 - Batter Grade to be 32 degrees
label | FREQUENCY: 20 meter chainages
label | ACCEPTANCE CRITERIA: Measurement of grade to hinge point
label | REFERENCE DOCUMENTS: Table provided to confirm angle of slope
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 3 - Class 3 Crushed Rock Placement
checkpoint | 2.01 - Rock Supply
label | FREQUENCY: Prior to delivery
label | ACCEPTANCE CRITERIA: Class rock mix registration to be approved
label | REFERENCE DOCUMENTS: Section 304
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | AP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.02 - Compaction Testing
label | FREQUENCY: Days productivity
label | ACCEPTANCE CRITERIA: 98% modified density required 3 lot Test
label | REFERENCE DOCUMENTS: Section 304
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.03 - Face of Rockwork
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: Site inspection with DTP Geotechnical engineer
label | REFERENCE DOCUMENTS: Photo record weekly meeting with DTP Geotechnical engineer
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.04 - Ground water Monitor groundwater at top 2 meters of fill
label | FREQUENCY: Daily
label | ACCEPTANCE CRITERIA: Discuss with DTP Geotechnical engineer
label | REFERENCE DOCUMENTS: Inspection
label | INSPECTION/TEST METHOD: Inspection ITP
label | CONFORMANCE RECORD: ITP
label | WP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Date: