## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-004 Ground Support [B] | itp |  |  |  |  | SYM-0388-ITP-004 Ground Support [B]
section | 1.0 Preliminaries
checkpoint | 1.1 - Construction Program and Method Statement
note | Ref docs - TfNSW R64
note | Acceptance criteria - Clause 3.1 - TfNSW R64
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Submittals of Construction Program and Method Statement prior to start the activity.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Mix Design: Soil Nails
note | Ref docs - TfNSW R64
note | Acceptance criteria - Clause .2.27 - TfNSW R64, As per relevant MAR
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Cement Grout Mix Design for Soil Nails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Mix Design: Shotcrete
note | Ref docs - TfNSW R64, TfNSW R68
note | Acceptance criteria - Clause 3.8.1 - TfNSW R68, As per relevant MAR
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Exposure Classification B2 shotcrete mix design.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Material: Soil Nail
note | Ref docs - TfNSW R64
note | Acceptance criteria - Clause 2.1 - TfNSW R64, As per IFC Drawing / MAR
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Material Certificates for the structural components.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Suitability Test: Soil Nail
note | Ref docs - TfNSW R64
note | Acceptance criteria - Clause 5.1 - TfNSW R64
note | • Clause 5.2.1 - TfNSW R64
note | • Clause 5.4 - TfNSW R64
note | ○ The number of test nails to be assessed by Suitability Test must be the greater of:
note | (i) the number specified on the Design Documentation drawings; or
note | (ii) 1% of the permanent nails but not less than 2.
note | ○ The Suitability test will be considered successful if all of the following are satisfied:
note | (i) A total creep movement of less than 2 mm between the 6 and 60 minutes readings is measured during Cycle 4; and
note | (ii) A total creep movement of less than 1mm between the 60 and 180 minutes readings is measured in Cycle 4; and
note | (iii) The creep rate is linear or decreasing, when plotted against the logarithm of time throughout Cycle 4.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Suitability Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Test Equipment
note | Ref docs - TfNSW R64
note | Acceptance criteria - Clause 5.3 - TfNSW R64
note | • Submit NATA Calibration Certificate (issued within 12 month) accompanied by the related calibration curve and tabulated record of hydraulic pressure against jack load.
note | • The identification numbers on the field test equipment must match the identification numbers on the calibration data sheets.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Calibration Certificates for hydraulic jack, pressure gauge and load cell as a set.
note | • Hydraulic jack with a minimum travel of 150 mm.
note | • Dial gauge with a minimum accuracy of 0.01 mm.
section | 2.0 Operations
checkpoint | 2.1 - Surface Preparation
note | Ref docs - TfNSW R64 Cl. 3.3
note | Acceptance criteria - Witness of exposed slope face after clearing of each section.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Unless otherwise shown on the Drawings or directed by the Principal, construct soil nail slopes in an incremental, “top-down” manner.
checkpoint | 2.2 - Soil Nail Installation
note | Ref docs - TfNSW B64
note | Acceptance criteria - Clause 3.4 - TfNSW R64
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Drill Record
note | • As-built Drawing
note | • Soil Nail Installation Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Soil Nail Grouting
note | Ref docs - TfNSW R64, ASTM C940, ASTM C939, TfNSW T375
note | Acceptance criteria - Clause 2.2.7 - TfNSW R64
note | • Clause 3.4.3 - TfNSW R64
note | • Final Bleeding <0.5%
note | • Fluidity <20s
note | • Compressive Strength (7 Days) > 32MPa
note | • Compressive Strength (28 Days) >40MPa @28Days
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Grout Record
note | • Compressive Strength Test Report
checkpoint | 2.4 - Soil Nail Acceptance Test
note | Ref docs - TfNSW R64
note | Acceptance criteria - Clause 5.1 - TfNSW R64
note | • Clause 5.2.2 - TfNSW R64
note | • Clause 5.4 - TfNSW R64
note | ○ A total of 3% of permanent nails must be subjected to Acceptance Test.
note | ○ The acceptance test will be considered successful if all of the following are satisfied:
note | (a) A total creep movement of less than 2 mm between the 6 and 60 minutes readings is measured in Creep Test hold period; and
note | (b) A total creep movement of less than 1 mm between the 60 and 180 minutes readings is measured in Creep Test hold period; and
note | (c) The creep rate is linear or decreasing, when plotted against the logarithm of time throughout Creep Test hold period.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Acceptance Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Slope Preparation
note | Ref docs - TfNSW R64 CL. 6.2, TfNSW R68 CL. 4.2
note | Acceptance criteria - Inspection and approval of surface preparation for mesh placement and shotcreting.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.6 - Horizontal Drains Installation
note | Ref docs - TfNSW R40
note | Acceptance criteria - Clause 3 - TfNSW R40
note | • Clause 4 - TfNSW R40
note | • As per IFC Drawing
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Horizontal Drains Installation Record
note | • Horizontal Drainage Installation Checklist
note | • As-built Drawing
checkpoint | 2.7 - Sl72 Galvanised Mesh
note | Ref docs - IFC Drawings
note | Acceptance criteria - Steel reinforcement SL72 2N12 1200mm long is centrally located in both direction at each soil nail.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.8 - Grassroot Mattress
note | Ref docs - IFC Drawings, Manufacturer's Specification
note | Acceptance criteria - Grass roots erosion control geotextile matting (or equivalent) is correctly installed.
note | • Mat reinforcement pins are corrected installed.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Shall be installed as per IFC Drawings / Manufacturer's Specification.
checkpoint | 2.9 - Preparation for Shotcrete Placement
note | Ref docs - TfNSW R68
note | Acceptance criteria - Clause 4 - TfNSW R68
note | • Protect the drainage system against contamination to ensure proper functioning.
note | • Steel mesh support anchor bars are correctly installed.
note | • Firmly fix steel reinforcement to prevent movement and vibration while the shotcrete is being applied.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Shotcrete Inspection Checklist
checkpoint | 2.10 - Shotcrete Application
note | Ref docs - TfNSW R68
note | Acceptance criteria - Clause 7 - TfNSW R68
note | • Apply shotcrete in two successive layers of 50mm (and not exceeding 75 mm) thickness for a total of 100mm and with adequate adhesion to the surface or previous layers of shotcrete to prevent slumping or sagging.
note | • Shotcrete must not cover or impair the function of slotted pipe drain or strip drain outlets which protrude through the shotcrete layer.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Pouring Record
checkpoint | 2.11 - Shotcrete Test
note | Ref docs - TfNSW R68
note | Acceptance criteria - 6.4.4 TfNSW R64, In accordance with mix design
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Concrete Test Report
checkpoint | 2.12 - Steel Wire Mesh installation
note | Ref docs - IFC Drawing
note | Acceptance criteria - Steel wire mesh (TECCO® or other equivalent). Shall be installed as per IFC Drawings.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Mesh Installation Checklist
checkpoint | 2.13 - Surface Excavation
note | Ref docs - TfNSW R64 – 3.3
note | Acceptance criteria - 3.3 – TfNSW R64, As per IFC Drawing
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Earthworks Record
section | 3.0 Post Operations
checkpoint | 3.1 - Review of the Site
note | Ref docs - IFC Drawing
note | Acceptance criteria - Completeness of the documentation
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP