## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-006 Mass Block Retaining Wall [B] | itp |  |  |  |  | SYM-0388-ITP-006 Mass Block Retaining Wall [B]
section | 1.0 General
checkpoint | 1.1 - Block Material Type
note | Ref docs - IFC Drawings
note | Acceptance criteria - Blocks to be correct size and approved prior to placement.
note | • 1m (W) x 1m (H) x 1m (L)
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Concrete Core Fill Mix
note | Ref docs - IFC Drawings
note | Acceptance criteria - Core fill material shall be minimum 25 MPa concrete
note | • Material properties meet project specification, AS 3600, AS 1379.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Footing completion
checkpoint | 2.1 - Set out
note | Ref docs - IFC Drawings
note | Acceptance criteria - Extents and levels correct to relevant drawings
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
checkpoint | 2.2 - Footing complete and approved
note | Ref docs - IFC Drawings
note | Acceptance criteria - Retaining Wall Footing completed in line with Drawings and Specification
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Retaining wall construction
checkpoint | 3.1 - Steel reinforcement
note | Ref docs - IFC Drawings
note | Acceptance criteria - Steel reinforcement to be placed as per design drawings with the correct amount of cover.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Setout and positioning correct
note | Ref docs - IFC Drawings
note | Acceptance criteria - Setout of block courses correct to line and level. Wall shall be generally straight and true.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Blockwork jointing
note | Ref docs - IFC Drawings
note | Acceptance criteria - Expansion joints to be installed in accordance with Construction Drawings/ Manufacturer Spec using correct materials.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
checkpoint | 3.4 - Blockwork installation
note | Ref docs - IFC Drawings
note | Acceptance criteria - Blocks shall be installed in accordance with the details of the Civil Drawings/ Manufacturer Spec.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
checkpoint | 3.5 - Core filling
note | Ref docs - TfNSW R53 CL.3.3.4
note | Acceptance criteria - Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
note | • Concrete to be tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 3.6 - Strength testing
note | Ref docs - TfNSW R53 Annexure L AS 1379
note | Acceptance criteria - Samples to be taken from chute. Each sample shall consist of two cylinder specimens for 28 day testing.
note | – – – – – – – – – – – – – – – – – – –
note | No. of samples ¦¦ Volume of concrete (m3)
note | 2 ¦¦ <50
note | 3 ¦¦ 50-100
note | 4 ¦¦ 101-250
note | 5 ¦¦ >250
note | – – – – – – – – – – – – – – – – – – –
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test report
checkpoint | 3.7 - Capping Block
note | Ref docs - IFC Drawings
note | Acceptance criteria - Capping Block is installed along top block of retaining Wall
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
section | 4.0 Backfill
checkpoint | 4.1 - Non-Woven Geotextile
note | Ref docs - IFC Drawings
note | Acceptance criteria - Install 1 layer of Bidim A34 (or equivalent) non-woven geotextile. Ensure geotextile is properly anchored
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 4.2 - Backfill
note | Ref docs - IFC Drawings
note | Acceptance criteria - Install rock fill comprising max 200mm particle size well graded rock.
note | • Symal’s Geotechnical Engineer to detail the maximum installation slope of backfill material
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
section | 5.0 Subsoil
checkpoint | 5.1 - Subsoil Drainage Pipe
note | Ref docs - IFC Drawings
note | Acceptance criteria - DN100 Socked Subsoil Drainage Pipe installed at base of wall before backfill.
note | • Discharge through face of wall at 25m centres
note | ○ Provide clear out riser to surface
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 5.2 - Subsoil Aggregate
note | Ref docs - IFC Drawings
note | Acceptance criteria - Install subsoil layer min. 200mm wide from rear face of wall before backfill.
note | • Aggregate to be nominal 20mm in dimension.
note | ○ Wrapped in approved Geotextile.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
section | 5.0 Conformance check
checkpoint | 5.1 - Subsoil Drainage Pipe
note | Ref docs - Tolerances
note | Acceptance criteria - Surface Level: the top surface level must be as per design levels or as approved.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
checkpoint | 5.2 - NCR Closeout
note | Ref docs - Contract Documents
note | Acceptance criteria - All defects have been rectified and NCR’s closed out and Site is accepted
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - S
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP