## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-009 Pavement Construction [B] | itp |  |  |  |  | SYM-0388-ITP-009 Pavement Construction [B]
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine Site Size
note | Ref docs - IFC Drawings
note | Acceptance criteria - What is the site size.
textbox | Acceptance |  |  | m2
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Survey Set Out
note | Ref docs - IFC Drawings
note | Acceptance criteria - Is the work area clearly pegged out for line and level?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 1.3 - Material Classification and Source
note | Ref docs - IFC Drawings
note | Acceptance criteria - Pavement Base and Subbase meets specification as per TfNSW Specification 3051 and construction drawings.
note | • Pavement Base and Subbase Material:
tickbox | DGB20
tickbox | DGB20
tickbox | DGS40
tickbox | Other
textbox | Other:
textbox | Source
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Conformance of Previous Layer
checkpoint | 2.1 - Conformance of Previous Layer
note | Ref docs - IFC Drawings
note | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
section | 3.0 Pavement Construction
checkpoint | 3.1 - Placement
note | Ref docs - IFC Drawings
note | Acceptance criteria - Fill has been placed in compacted layers as per IFC Drawing.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 3.2 - Moisture
note | Ref docs - IFC Drawings
note | Acceptance criteria - Material must be maintained at optimum moisture content with additional water being added if required during compaction. Review and approve laboratory testing results
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Compaction
note | Ref docs - IFC Drawings
note | Acceptance criteria - Base / Subbase Layer has been adequately compacted achieving minimum either:
note | ○ Subbase
note | • 95%-100% SMDD (Refer to IFC Drawings)
note | ○ Base
note | • 100% SMDD
note | ○ Review and approve laboratory testing results
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Dry Back
note | Ref docs - TfNSW R71
note | Acceptance criteria - The field moisture content of base courses that are not being treated / stabilised and are to receive a bituminous seal must not exceed 70% of OMC.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
checkpoint | 3.5 - Proof Roll Inspection
note | Ref docs - TfNSW R44
note | Acceptance criteria - Proof rolled surfaces must not exhibit visible deformation, rutting or yielding
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Conformance Check
checkpoint | 4.1 - Pavement Finish
note | Ref docs - IFC Drawings
note | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 4.2 - Surface Level and pavement thickness of subbase / base.
note | Ref docs - IFC Drawings
note | Acceptance criteria - Surface Level and Pavement Thickness after compaction and surface trimming conform to the following requirements:
note | ○ Thickness:
note | • Base, - 0mm, + 20mm
note | • Subbase, ± 10mm
note | ○ Surface Level:
note | • Base, - 0mm, + 10mm
note | • Subbase, -10mm, +0mm
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | 4.3 - Surface Deviation
note | Ref docs - TfNSW T183
note | Acceptance criteria - Surface does not deviate more than 5mm from a 3 m straight edge when laid in any direction.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.4 - Width
note | Ref docs - IFC Drawings
note | Acceptance criteria - Width of pavement between outside edges is not less than the width specified on the drawings.
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
checkpoint | 4.5 - NCR
note | Acceptance criteria - Any NCRs have been closed out
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP