## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-012 Signage [B] | itp |  |  |  |  | SYM-0388-ITP-012 Signage [B]
section | 1.0 Preliminaries
checkpoint | 1.1 - Survey set-out
note | Ref docs - TfNSW R143 Construction drawings
note | Acceptance criteria - Has the work area and all required signage been set out for correct positions?
button | Acceptance | Yes, No, N/A
note | • Has the set out been approved by Shoalhaven City Council?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign Date
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
section | 2.0 Signage install
checkpoint | 2.1 - Foundations
note | Ref docs - TfNSW R143 Construction drawings
note | Acceptance criteria - Have all post footings been set in concrete foundations to the depths show in the Sign & Post Schedule with the following diameters:
note | • <32mm Steel Posts: 225mm
note | • 80mm-150mm Steel Posts: 300mm
note | • 180mm x 100mm Frangible: 300mm
note | Is the finished
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
tickbox | Subcontractors ITP
checkpoint | 2.2 - Installation of posts
note | Ref docs - TfNSW R143 Construction drawings
note | Acceptance criteria - Have all posts been installed in accordance with the following requirements:
note | – Posts shall be straight
note | – Posts shall be vertical with a maximum deviation of 1 in 100
note | – Post tops shall be 50mm (+/- 10mm) below the top edge of the sign
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
tickbox | Subcontractors ITP
checkpoint | 2.3 - Installation of signs
note | Ref docs - TfNSW R143 Construction drawings
note | Acceptance criteria - Has all signage been installed as per the design drawings and sign & post schedule and in accordance with the following requirements:
note | – Signs shall be level with a maximum deviation of 1 in 100
note | – Symmetrically (where applicable)
note | – Sign surface shall present an even surface free from faults
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
tickbox | Subcontractors ITP
checkpoint | 2.4 - Tolerances
note | Ref docs - TfNSW R143 Construction drawings
note | Acceptance criteria - Has the signage been installed in accordance with RMS standards, to following tolerances:
note | – Height: +/- 40 mm
note | – Location: +/- 100mm
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Sign Date
checkpoint | 2.5 - Temporary masking
note | Ref docs - TfNSW R143 Construction drawings
note | Acceptance criteria - Have the required signs been masked to effectively and securely cover the signage prior to implementation?
button | Acceptance | Yes, No, N/A
note | Verify of acceptance by
note | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Sign Date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign Date
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP