## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | General Concrete Checklist | itp |  |  |  |  | Quality Control Checklist - General Concrete Checklist
section | 1.0 Pre-Pour Concrete Inspection (Concrete pre-pour check completed in accordance with applicable procedures, drawings, specifications and approved changes)
checkpoint | 1.1 - Concrete supply
label | Result - Concrete Mix on Docket Checked.
label | • All concrete delivered has a delivery docket. Tester onsite.
label | • Visual assessment of quality.
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 1.2 - Ambient weather for concreting
label | Result - Restrictions and treatments to be applied for concreting in hot, cold and wet weather.
label | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10˚C or greater than 32˚C.
label | • Ambient temperature not to be less than 5˚C and no more than 35˚C.
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 1.3 - Steel reinforcing grade and placement
label | Result - Minimum cover shall be 50 mm unless shown on the drawings
label | • Concrete or plastic chairs to be used. Wire chairs (with or without plastic tips), bricks, pieces
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 1.4 - Formwork
label | Result - Stripping of Formwork after casting shall not be less than:
label | • 2 days (Between 12˚C & 20˚C).
label | • 1 day (> 20 ˚C).
label | • 3 days (Between 5˚C & 12˚C).
label | ○ Minimum time shall also not be less than:
label | a). 2 days for vertical formwork on external surfaces and,
label | b). 1 day for vertical forms on permanently hidden surfaces.
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
section | 2.0 Concrete Placement (Concrete Pour completed in accordance with applicable procedures, drawings, specifications and approved changes)
checkpoint | 2.1 - Concrete Placing, Compacting
label | Result - Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment and into corners of formwork or excavations to produce a dense concrete free from voids.
label | • Workable concrete mixes are exempt from vibration requirement. Minimum testing requirements for aggregates to comply to VR Table 610.121 and VR 703.11
label | – – – – – – – – – – – – – –
label | Table 610.121
label | Test ¦¦ Minimum Frequency of Testing
label | – – – – – – – – – – – – – –
label | Grading of Fine Aggregates ¦¦ On each day one per 500 tonne or part thereof
label | Grading of Coarse Aggregates ¦¦ On each week one per 1500 tonne or part thereof
label | Water Absorption of Fine and Coarse Aggregates ¦¦ At 3 monthly intervals
label | Unsound Rock Content ¦¦ On each day one per 500 tonne or part thereof
label | Flakiness Index of Coarse Aggregate 10 mm and Larger ¦¦ At monthly intervals
label | Degradation Factor of Crusher Fines ¦¦ At monthly intervals
label | Organic Impurities other than sugar ¦¦ At monthly intervals
label | Alkali Reactivity of Aggregate Sources ¦¦ At 3 yearly intervals
label | Wet and Dry Strength and Sodium Sulphate Soundness for Pebble Aggregates ¦¦ At 3 monthly intervals
label | – – – – – – – – – – – – – –
label | Table 703.11
label | Portland Cement Concrete Strength Grade ¦¦ Geopolymer Binder Concrete Strength Grade ¦¦ Minimum Compressive Strength at 28 days (MPa)
label | – – – – – – – – – – – – – –
label | N20 ¦¦ 20 ¦¦ 20
label | N25 ¦¦ 25 ¦¦ 25
label | N32 ¦¦ 32 ¦¦ 32
label | VR330 / 32 ¦¦ 32 ¦¦ 32
label | – – – – – – – – – – – – – –
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 2.2 - Testing
label | Result - Compressive Strength Testing
label | • 3 cylinders (1 x 7day, 2 x 28 Day) taken for each sample, minimum no. of samples:
label | • Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade.
label | • Slump (AS 1379-2007)
label | – – – – – – – – – – – – – –
label | Specified Slump, mm ¦¦ Tolerance, mm
label | – – – – – – – – – – – – – –
label | < 60 ¦¦ ±10
label | ≥ 60 ≤ 80 ¦¦ ±15
label | >80 ≤ 110 ¦¦ ±20
label | >110 ≤ 150 ¦¦ ±30
label | >150 ¦¦ ±40
label | – – – – – – – – – – – – – –
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
section | 3.0 Post Pour Check (Post Pour Check completed in accordance with applicable procedures, drawings, specifications and approved changes)
checkpoint | 3.1 - Surface Finish
label | Result - Footpaths, and other surfacings: Finish with a wooden float to produce a lightly textured non-skid surface. Compact with internal vibration and worked until mortar comes to the top.
label | • Edgings: All edgings shall be rendered and have a steel trowel finish. Rendering applied within 30 minutes of placing or extruding concrete. Thickness not exceeding 3 mm. Mortar shall be 2 parts fine aggregate, 1 part cement & sufficient water to produce suitable consistency
label | • Surface finish to comply to VR 703.25.
label | • After finishing, all work shall present a consistently neat appearance of uniform colour. All discoloured concrete shall be cleaned or replaced.
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 3.2 - Jointing between concrete elements
label | Result - Transverse joints shall be constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
label | a). Edgings
label | (i) Transverse joints & expansion joints
label | (ii) Expansion joints & control joints
label | b). Footpaths, other Surfacing and Shared Use Paths
label | (i) Expansion Joints
label | (ii) Control Joints
label | (c) Details on de-bonding methods
label | • Sawcut or tooled joints shall be provided at maximum 2m centres to all footpaths or pedestrian paving. A 19mm expansion joint shall be provided where rigid pavements abut fixed structures or at max 15m centres to footpaths.
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 3.3 - Curing of concrete
label | Result - Exposed concrete surfaces shall commence curing treatment immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days
label | (a) General
label | (b) Geopolymer concrete
label | • Concrete edgings which shall be cured for a period of not less than three days after placing the concrete.
label | • The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance. The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application.
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
checkpoint | 3.4 - Tolerances on line, level, and shape
label | Result - All surfaces shall be finished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as specified, within the following limits:
label | (a) Paving within 5mm
label | (b) Departure of finished work from line & level shall not exceed 10mm at any point
label | (c) Section dimensions overall width shall not exceed >15mm
label | (d) Median surfacing cross fall between 1% and 3% towards the edges
label | Hold/Witness Point Release: Initials - (WP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
section | 4.0 Completion
checkpoint | 4.1 - Inspection of repairs
label | Result - Patch repairs conducted as per relevant ITP and procedure, where required
label | Hold/Witness Point Release: Initials - (HP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Concrete repairs
label | Result - Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
label | Hold/Witness Point Release: Initials - (HP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Crack Monitoring
label | Result - Cracks greater than acceptable widths as per PSDR (section 16.1(e)) are mapped and repaired in accordance with VR 687 and approved methodology specific to location.
label | • Cracks requiring repairs monitored.
label | Hold/Witness Point Release: Initials - (HP)
textbox | Hold/Witness Point Release: Date
textbox | NCR # (if req’d)
holdpoint | AUTHORITY HOLDPOINT