## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Waterproofing ITP
section | Details
checkpoint | 1. Waterproofer to inspect substrate to confirm acceptability. Ensure clean, dry, devoid of contamination and excess dust removed and vacuumed.
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 2. Fillet bond breaker using Aquastop 70 tape and Nanosil to improve adhesion. Ensure all tape is bonded to the substrate.
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 3. Polyurethane fillet to internal vertical corners in shower, at junction of concrete with puddleflange, clearout, pipework
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 4. Primer A Eco to be applied to porous substrate (Data Sheet attached) All concrete and wall linings
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 5. Prime Keragrip Eco for non porous primer (Data sheet attached) Angles, puddlefalnges, threaded pipework
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 6. 1st Coat Kera Trade WPM (Data Sheet attached) Applied to floor, 150mm high including perimeter banding and 200mm above shower rose and extending 200mm past shower screen location. Extend to vanity 150mm min. surround to side and above vanity shelf. Extend 150mm below level of vanity.
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 7. 24hr Curing (Typical*) *curing time are typical, refer to manufacturer spec for product curing times
note | *curing time are typical, refer to manufacturer spec for product curing times
label | Inspection: visual and touch
text | Inspected By:
date | Date:
checkpoint | 8. 2nd Coat Keratrade WPM applied
label | Inspection: visual and touch
text | Inspected By:
date | Date:
checkpoint | 9. 48hr Curing (Typical*)
note | *curing time are typical, refer to manufacturer spec for product curing times
label | Inspection: visual and touch
text | Inspected By:
date | Date:
checkpoint | 10. Dry Film Thickness (DFT) Test completed min 1.13mm
label | Inspection: electronic testing
text | Inspected By:
date | Date:
checkpoint | 11. 24hr Water Test
label | Inspection: visual and marker
text | Inspected By:
date | Date:
checkpoint | 12. Final Water Test Measure Completed - AS3740-2010
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 13. Drain Down by waterproof installer
label | Inspection: visual
text | Inspected By:
date | Date:
holdpoint | 14. Waterproof installer to check / provide go ahead
section | 15. RECTIFICATION ITEMS
checkpoint | RECTIFICATION ITEMS
checkpoint | 16. Area Handover to Tiler
holdpoint | Verify with Tiler
section | 18. Quality Assurance from Builder
checkpoint | Quality Assurance from Builder
section | 19. Final Inspection
checkpoint | Final Inspection (1)
text | Position:
date | Date:
holdpoint | Prepared By:
checkpoint | Final Inspection (2)
text | Position:
date | Date:
holdpoint | Approved By:
checklist | Tiling ITP
section | 1. Check Drawing
checkpoint | Confirm Drawing, specification and revision #
label | Inspection: admin
text | Inspected By:
date | Date:
section | 2. Substrate Prep - Wall
checkpoint | Inspect for wall quality to accept tiles and ensure that substrate free from debris
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Clean and dry
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Joints Sealed
label | Inspection: visual
text | Inspected By:
date | Date:
section | 3. Substrate Prep - Floor
checkpoint | Inspect concrete substrate free from debris Cracks >0.2mm to be filled with Polyurethane
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Clean and dry
label | Inspection: visual
text | Inspected By:
date | Date:
section | 4. Tile Termination Points
checkpoint | Locate termination points and set for Angle location at door entry.
label | Inspection: visual / setout / laser
text | Inspected By:
date | Date:
checkpoint | Set angle / termination points under door leaf
label | Inspection: visual / setout / laser
text | Inspected By:
date | Date:
checkpoint | Correct RL as per architectural drawings
label | Inspection: visual / setout / laser
text | Inspected By:
date | Date:
section | 5. HOLD POINT
checkpoint | Waterproofing membrane inspected by Toga and approved to receive screed beds. Check with waterproofer for go ahead
label | Inspection: site foreman / waterproofing contractor
text | Inspected By:
date | Date:
holdpoint | HOLD POINT
section | 6. Sand and Cement Bedding
checkpoint | Screed mixed by machine ratio1:4
label | Inspection: 100L stand mixer
text | Inspected By:
date | Date:
checkpoint | Floorwastes protected to prevent debris entering into drains with compressible sponges
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Clearout pipework to finish at screed bed level
text | Inspected By:
date | Date:
section | 7. HOLD POINT
checkpoint | Setout and starting point verified with Builder and Drawings
label | Inspection: laser / visual / chalk line
text | Inspected By:
date | Date:
holdpoint | HOLD POINT
checkpoint | Ensure standard sceed thickness minimum of 15mm.
label | Inspection: visual / guage
text | Inspected By:
date | Date:
holdpoint | HOLD POINT
checkpoint | Screed areas lower than 15mm to minimum 10mm to recieve engineered binder (Keracem ECO in replacement of Grey cement)
label | Inspection: visual / guage / markup
text | Inspected By:
date | Date:
holdpoint | HOLD POINT
checkpoint | Where screed beds lower than 10mm use Keralevel LR with Universal Primer
label | Inspection: visual / guage / markup
text | Inspected By:
date | Date:
holdpoint | HOLD POINT
checkpoint | 24hrs curing minimum
label | Inspection: visual / guage / markup
text | Inspected By:
date | Date:
holdpoint | HOLD POINT
section | 8. Acoustic
checkpoint | Ensure substrate free from loose material to maximise bond to acoustic mat / screed bed
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | 4mm notch trowel / bioflex grey adhesive
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Ensure acoustic matting has no gaps / weighted roller
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Any gaps to be filled with Polyurethane and finished flush
label | Inspection: visual
text | Inspected By:
date | Date:
section | 9. Inspect Tile Laying
checkpoint | Quality (Set-out, tile cuts, even joints & flatness)
label | Inspection: visual / straightedge
text | Inspected By:
date | Date:
checkpoint | Set-out as per drawing
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Verify strip drain size and position of waste outlet
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Falls to waste as per drawing / isolate falls to waste
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | No lipping tiles exceeding A.S tolerances 1.5mm
label | Inspection: visual
text | Inspected By:
date | Date:
section | 10. Preseal
checkpoint | General sweep clean of terrazzo floors
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Wet wipe excess dust off tile surface
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Lambs wool application of presealer to terrazzo floor surface prior to grouting - 1 coat
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Allow preseal to cure minimum 8 hours before grouting. Area to be baricaded off from entering.
label | Inspection: visual
text | Inspected By:
date | Date:
section | 11. Grouting
checkpoint | Grout mixed by machine
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Joints free from debris / spacers
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Surface is uniform and clean / no grout build up / internal corners free of grout
label | Inspection: visual
text | Inspected By:
date | Date:
section | 12. Protection
checkpoint | Corflute taped down (no black corflute) cover entire tiled surface
label | Inspection: visual
text | Inspected By:
date | Date:
checkpoint | Make allowance for toilet pans, partitions / glass installation
label | Inspection: visual
text | Inspected By:
date | Date:
section | 13. Repair Any
checkpoint-no-status | Repair Any
section | 14. Final Inspection
checkpoint-no-status | Final Inspection
holdpoint | Prepared By:
text | Position:
date | Date: