## Training QA Folder structure
QA Folder Structure |  |  |  | Checklists
Site QA
Site Management
Site Setup
|  |  | Various | SSU
Site Closure & Exit
|  |  | Various | SCE
Adhoc Activities
Investigation of Lot 8
|  |  | Internal | AA1
Apartments
Apartment 14
|  |  | External | 14
|  |  | Internal | 14.1
Apartment 301
|  |  | External | 301
|  |  | Internal | 301.1
Apartment 302
|  |  | External | 302
|  |  | Internal | 302.1
Apartment 303
|  |  | External | 303
Apartment 304
|  |  | External | 304
|  |  | Internal | 304.1
Apartment 305
|  |  | External | 305
|  |  | Internal | 305.1
Apartment 306
|  |  | External | 306
|  |  | Internal | 306.1
Apartment 307
|  |  | External | 307
Apartment 308
|  |  | External | 308
Apartment 309
|  |  | External | 309
Apartment 201
|  |  | External | 201
Apartment 202
|  |  | External | 202
|  |  | Internal | 202.1
Apartment 203
|  |  | External | 203
Apartment 204
|  |  | External | 304
Apartment 205
|  |  | External | 205
|  |  | Internal | 205.1
Apartment 206
|  |  | External | 206
|  |  | Internal | 206.1
Apartment 207
|  |  | External | 207
Apartment 208
|  |  | External | 208
Apartment 209
|  |  | External | 209
|  |  | Internal | 209.1
Apartment 210
|  |  | External | 210
Apartment 211
|  |  | External | 211
Apartment 212
|  |  | External | 212
|  |  | Internal | 212.1
Apartment 213
|  |  | External | 213
|  |  | Internal | 213.1
Apartment 214
|  |  | External | Leave as folder
|  |  | Internal | Leave as folder
Apartment 101
|  |  | External | 101
|  |  | Internal | 101.1
Apartment 102
|  |  | External | 102
Apartment 103
|  |  | External | 103
Apartment 104
|  |  | External | 104
|  |  | Internal | 104.1
Apartment 105
|  |  | External | 105
Apartment 106
|  |  | External | 106
|  |  | Internal | 106.1
Apartment 107
|  |  | External | 107
|  |  | Internal | 107.1
Apartment 108
|  |  | External | 108
|  |  | Internal | 108.1
Apartment 109
|  |  | External | 109
Apartment 110
|  |  | External | 110
Apartment 111
|  |  | External | 111
Apartment 112
|  |  | External | 112
Apartment 113
|  |  | External | 113
Apartment 114
|  |  | External | Leave as folder
|  |  | Internal | Leave as folder
Apartment 1
|  |  | External | 1
|  |  | Internal | 1.1
Apartment 2
|  |  | External | 2
|  |  | Internal | 2.1
Apartment 3
|  |  | External | 3
Apartment 4
|  |  | External | 4
Apartment 5
|  |  | External | 5
|  |  | Internal | 5.1
Apartment 6
|  |  | External | 6
|  |  | Internal | 6.1
Apartment 7
|  |  | External | 7
|  |  | Internal | 7.1
Apartment 8
|  |  | External | 8
Apartment 9
|  |  | External | 9
|  |  | Internal | 9.1
Apartment 10
|  |  | External | 10
Apartment 11
|  |  | External | 11
Apartment 12
|  |  | External | 12
Apartment 13
|  |  | External | 13
Basement Carpark
Adjacent to Car Space 213
|  |  | Internal | BC213
Above Car Space 212
|  |  | Internal | BC212
Above Car Space 207
|  |  | Internal | BC207
In Front of Car Space 11
|  |  | Internal | BC011
Stairs in Front of Stair Foyer
|  |  | Internal | BCSSF
Concrete Injections and Cleaning of Carpark Soffit
|  |  | Internal | BCCI
Common Area Hallways
Level 3
|  |  | Internal | CAH3
Level 2
|  |  | Internal | CAH2
Level 1
|  |  | Internal | CAH1
Level G
|  |  | Internal | CAHG
Planter Boxes
Ground Floor
|  |  | External | PB
Roof Area
Roof
|  |  | External | RC
West & South Elevations
Front & Side Entry
|  |  | External | WSE
Scope Of Works Document

## ITP Checklists
type | name | values | prefix | postfix | usage count | user addable
checklist-flat | 1
checkpoint | 1.00 Demolition & Removal of Existing Balcony Surface - 35M2
checkpoint | 1.01 Provide movement joints within the tile surface as required p/m2 - 35M2
checkpoint | 1.02 Apply First Membrane - 35M2
checkpoint | 1.03 Screed - 35M2
checkpoint | 1.04 Apply Second Membrane - 35M2
checkpoint | 1.05 Tiles Supplied - 35M2
checkpoint | 1.06 Tile & Grout balcony surface - 35M2
checkpoint | 1.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 1.08 Skirting Tile and Caulking as required - 42LM
checkpoint | 1.09 Remove any rubbish and clean area - 1A
checklist-flat | 1.1
checkpoint | 1.10 Remove moisture damaged skirting - 4LM
checkpoint | 1.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint | 1.12 Supply and install new plasterboard - 4LM
checkpoint | 1.13 Supply and install new skirting boards - 4LM
checkpoint | 1.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint | 1.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 2
checkpoint | 2.00 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint | 2.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint | 2.02 Apply First Membrane - 37M2
checkpoint | 2.03 Screed - 37M2
checkpoint | 2.04 Apply Second Membrane - 37M2
checkpoint | 2.05 Tiles Supplied - 37M2
checkpoint | 2.06 Tile & Grout balcony surface - 37M2
checkpoint | 2.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 2.08 Skirting Tile and Caulking as required - 45LM
checkpoint | 2.09 Remove any rubbish and clean area - 37M3
checklist-flat | 2.1
checkpoint | 2.10 Remove moisture damaged skirting - 4LM
checkpoint | 2.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint | 2.12 Supply and install new plasterboard - 4LM
checkpoint | 2.13 Supply and install new skirting boards - 4LM
checkpoint | 2.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint | 2.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 3
checkpoint | 3.00 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint | 3.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint | 3.02 Apply First Membrane - 37M2
checkpoint | 3.03 Screed - 37M2
checkpoint | 3.04 Apply Second Membrane - 37M2
checkpoint | 3.05 Tiles Supplied - 37M2
checkpoint | 3.06 Tile & Grout balcony surface - 37M2
checkpoint | 3.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 3.08 Skirting Tile and Caulking as required - 45LM
checkpoint | 3.09 Remove any rubbish and clean area - 37M3
checklist-flat | 4
checkpoint | 4.00 Demolition & Removal of Existing Balcony Surface - 16M2
checkpoint | 4.01 Provide movement joints within the tile surface as required p/m2 - 16M2
checkpoint | 4.02 Apply First Membrane - 16M2
checkpoint | 4.03 Screed - 16M2
checkpoint | 4.04 Apply Second Membrane - 16M2
checkpoint | 4.05 Tiles Supplied - 16M2
checkpoint | 4.06 Tile & Grout balcony surface - 16M2
checkpoint | 4.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 4.08 Skirting Tile and Caulking as required - 20LM
checkpoint | 4.09 Remove any rubbish and clean area - 16M3
checklist-flat | 5
checkpoint | 5.00 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint | 5.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint | 5.02 Apply First Membrane - 37M2
checkpoint | 5.03 Screed - 37M2
checkpoint | 5.04 Apply Second Membrane - 37M2
checkpoint | 5.05 Tiles Supplied - 37M2
checkpoint | 5.06 Tile & Grout balcony surface - 37M2
checkpoint | 5.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 5.08 Skirting Tile and Caulking as required - 45LM
checkpoint | 5.09 Remove any rubbish and clean area - 37M3
checklist-flat | 5.1
checkpoint | 5.10 Remove moisture damaged skirting - 4LM
checkpoint | 5.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint | 5.12 Supply and install new plasterboard - 4LM
checkpoint | 5.13 Supply and install new skirting boards - 4LM
checkpoint | 5.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint | 5.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 6
checkpoint | 6.00 Demolition & Removal of Existing Balcony Surface - 29M2
checkpoint | 6.01 Provide movement joints within the tile surface as required p/m2 - 29M2
checkpoint | 6.02 Apply First Membrane - 29M2
checkpoint | 6.03 Screed - 29M2
checkpoint | 6.04 Apply Second Membrane - 29M2
checkpoint | 6.05 Tiles Supplied - 29M2
checkpoint | 6.06 Tile & Grout balcony surface - 29M2
checkpoint | 6.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 6.08 Skirting Tile and Caulking as required - 35LM
checkpoint | 6.09 Remove any rubbish and clean area - 29M3
checklist-flat | 6.1
checkpoint | 6.10 Remove moisture damaged skirting - 4LM
checkpoint | 6.11 Remove moisture damaged plaster board sheet - 4LM
checkpoint | 6.12 Supply and install new plasterboard - 4LM
checkpoint | 6.13 Supply and install new skirting boards - 4LM
checkpoint | 6.14 Paint new plasterwork and skirting with a 3-coat paint system - 8LM
checkpoint | 6.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 7
checkpoint | 7.00 Demolition & Removal of Existing Balcony Surface - 14M2
checkpoint | 7.01 Provide movement joints within the tile surface as required p/m2 - 14M2
checkpoint | 7.02 Apply First Membrane - 14M2
checkpoint | 7.03 Screed - 14M2
checkpoint | 7.04 Apply Second Membrane - 14M2
checkpoint | 7.05 Tiles Supplied - 14M2
checkpoint | 7.06 Tile & Grout balcony surface - 14M2
checkpoint | 7.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 7.08 Skirting Tile and Caulking as required - 17LM
checkpoint | 7.09 Remove any rubbish and clean area - 14M3
checklist-flat | 7.1
checkpoint | 7.10 Remove moisture damaged skirting - 4LM
checkpoint | 7.11 Supply and install new skirting boards - 4LM
checkpoint | 7.12 Paint new plasterwork and skirting with a 3-coat paint system - 4LM
checkpoint | 7.13 Remove all rubbish created by repair work. - 1P
checklist-flat | 8
checkpoint | 8.00 Demolition & Removal of Existing Balcony Surface - 12M2
checkpoint | 8.01 Provide movement joints within the tile surface as required p/m2 - 12M2
checkpoint | 8.02 Apply First Membrane - 12M2
checkpoint | 8.03 Screed - 12M2
checkpoint | 8.04 Apply Second Membrane - 12M2
checkpoint | 8.05 Tiles Supplied - 12M2
checkpoint | 8.06 Tile & Grout balcony surface - 12M2
checkpoint | 8.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 8.08 Skirting Tile and Caulking as required - 15LM
checkpoint | 8.09 Remove any rubbish and clean area - 12M3
checklist-flat | 9
checkpoint | 9.00 Demolition & Removal of Existing Balcony Surface - 45M2
checkpoint | 9.01 Provide movement joints within the tile surface as required p/m2 - 45M2
checkpoint | 9.02 Apply First Membrane - 45M2
checkpoint | 9.03 Screed - 45M2
checkpoint | 9.04 Apply Second Membrane - 45M2
checkpoint | 9.05 Tiles Supplied - 45M2
checkpoint | 9.06 Tile & Grout balcony surface - 45M2
checkpoint | 9.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 9.08 Skirting Tile and Caulking as required - 54LM
checkpoint | 9.09 Remove any rubbish and clean area - 45M3
checklist-flat | 9.1
checkpoint | 9.10 Remove moisture damaged skirting - 4LM
checkpoint | 9.11 Supply and install new skirting boards - 4LM
checkpoint | 9.12 Paint new plasterwork and skirting with a 3-coat paint system - 4LM
checkpoint | 9.13 Remove all rubbish created by repair work. - 1P
checklist-flat | 10
checkpoint | 10.00 Demolition & Removal of Existing Balcony Surface - 66M2
checkpoint | 10.01 Provide movement joints within the tile surface as required p/m2 - 66M2
checkpoint | 10.02 Apply First Membrane - 66M2
checkpoint | 10.03 Screed - 66M2
checkpoint | 10.04 Apply Second Membrane - 66M2
checkpoint | 10.05 Tiles Supplied - 66M2
checkpoint | 10.06 Tile & Grout balcony surface - 66M2
checkpoint | 10.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 10.08 Skirting Tile and Caulking as required - 80LM
checkpoint | 10.09 Remove any rubbish and clean area - 66M3
checklist-flat | 11
checkpoint | 11.00 Demolition & Removal of Existing Balcony Surface - 36M2
checkpoint | 11.01 Provide movement joints within the tile surface as required p/m2 - 36M2
checkpoint | 11.02 Apply First Membrane - 36M2
checkpoint | 11.03 Screed - 36M2
checkpoint | 11.04 Apply Second Membrane - 36M2
checkpoint | 11.05 Tiles Supplied - 36M2
checkpoint | 11.06 Tile & Grout balcony surface - 36M2
checkpoint | 11.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 11.08 Skirting Tile and Caulking as required - 44LM
checkpoint | 11.09 Remove any rubbish and clean area - 36M3
checklist-flat | 12
checkpoint | 12.00 Demolition & Removal of Existing Balcony Surface - 66M2
checkpoint | 12.01 Provide movement joints within the tile surface as required p/m2 - 66M2
checkpoint | 12.02 Apply First Membrane - 66M2
checkpoint | 12.03 Screed - 66M2
checkpoint | 12.04 Apply Second Membrane - 66M2
checkpoint | 12.05 Tiles Supplied - 66M2
checkpoint | 12.06 Tile & Grout balcony surface - 66M2
checkpoint | 12.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 12.08 Skirting Tile and Caulking as required - 80LM
checkpoint | 12.09 Remove any rubbish and clean area - 66M3
checklist-flat | 13
checkpoint | 13.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 13.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 13.02 Apply First Membrane - 0M2
checkpoint | 13.03 Screed - 0M2
checkpoint | 13.04 Apply Second Membrane - 0M2
checkpoint | 13.05 Tiles Supplied - 0M2
checkpoint | 13.06 Tile & Grout balcony surface - 0M2
checkpoint | 13.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 13.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 13.09 Remove any rubbish and clean area - 0M3
checklist-flat | 14
checkpoint | 14.00 Demolition & Removal of Existing Balcony Surface - 81M2
checkpoint | 14.01 Provide movement joints within the tile surface as required p/m2 - 81M2
checkpoint | 14.02 Apply First Membrane - 81M2
checkpoint | 14.03 Screed - 81M2
checkpoint | 14.04 Apply Second Membrane - 81M2
checkpoint | 14.05 Tiles Supplied - 81M2
checkpoint | 14.06 Tile & Grout balcony surface - 81M2
checkpoint | 14.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 14.08 Skirting Tile and Caulking as required - 98LM
checkpoint | 14.09 Remove any rubbish and clean area - 81M3
checklist-flat | 14.1
checkpoint | 14.10 Remove all skirting boards, architraves and door frame in bedroom 1 - 16LM
checkpoint | 14.11 Remove all the bottom section of plasterboard linings at the horizontal joint within bedroom 1 & 2 - 16LM
checkpoint | 14.12 Remove carpets within the bedrooms 1 & 2 - 16LM
checkpoint | 14.13 Isolate and disconnect the wall mounted GPO's at the base of each wall where the plaster lining is to be removed - 2L
checkpoint | 14.14 Remove all debris and dispose into bins - 6L
checkpoint | 14.15 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 14.16 Supply and install new plasterboard linings to the internal walls were removed - 32LM
checkpoint | 14.17 Supply and install new skirting boards - 16LM
checkpoint | 14.18 Paint all internal areas 1 undercoat and 2 top­ coats to all walls and woodwork - Paint colour to match the existing - 32LM
checkpoint | 14.19 Reconnect GPO's when work is completed - 4L
checklist-flat | 101
checkpoint | 101.00 Demolition & Removal of Existing Balcony Surface - 21M2
checkpoint | 101.01 Provide movement joints within the tile surface as required p/m2 - 21M2
checkpoint | 101.02 Apply First Membrane - 21M2
checkpoint | 101.03 Screed - 21M2
checkpoint | 101.04 Apply Second Membrane - 21M2
checkpoint | 101.05 Tiles Supplied - 21M2
checkpoint | 101.06 Tile & Grout balcony surface - 21M2
checkpoint | 101.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint | 101.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint | 101.09 Skirting Tile and Caulking as required - 26LM
checkpoint | 101.10 Remove any rubbish and clean area - 21M3
checklist-flat | 101.1
checkpoint | 101.11 Remove water damaged skirting boards - 4lm
checkpoint | 101.12 Supply and install new skirting boards - 4LM
checkpoint | 101.13 Paint new skirting with a 3 coat paint system. - 4LM
checkpoint | 101.14 Remove all rubbish created by repair work. - 1P
checklist-flat | 102
checkpoint | 102.00 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint | 102.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint | 102.02 Apply First Membrane - 8M2
checkpoint | 102.03 Screed - 8M2
checkpoint | 102.04 Apply Second Membrane - 8M2
checkpoint | 102.05 Tiles Supplied - 8M2
checkpoint | 102.06 Tile & Grout balcony surface - 8M2
checkpoint | 102.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint | 102.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint | 102.09 Skirting Tile and Caulking as required - 10LM
checkpoint | 102.10 Remove any rubbish and clean area - 8M3
checklist-flat | 103
checkpoint | 103.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 103.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 103.02 Apply First Membrane - 0M2
checkpoint | 103.03 Screed - 0M2
checkpoint | 103.04 Apply Second Membrane - 0M2
checkpoint | 103.05 Tiles Supplied - 0M2
checkpoint | 103.06 Tile & Grout balcony surface - 0M2
checkpoint | 103.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 103.08 Painting of Internal Balaustrade as required (including materials) - 0M2
checkpoint | 103.09 Skirting Tile and Caulking as required - 0LM
checkpoint | 103.10 Remove any rubbish and clean area - 0M3
checklist-flat | 104
checkpoint | 104.00 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint | 104.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint | 104.02 Apply First Membrane - 8M2
checkpoint | 104.03 Screed - 8M2
checkpoint | 104.04 Apply Second Membrane - 8M2
checkpoint | 104.05 Tiles Supplied - 8M2
checkpoint | 104.06 Tile & Grout balcony surface - 8M2
checkpoint | 104.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint | 104.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint | 104.09 Skirting Tile and Caulking as required - 10LM
checkpoint | 104.10 Remove any rubbish and clean area - 8M3
checklist-flat | 104.1
checkpoint | 104.11 Remove moisture damaged skirting - 4LM
checkpoint | 104.12 Supply and install new skirting boards - 4LM
checkpoint | 104.13 Paint new skirting with a 3 coat paint system - 4LM
checkpoint | 104.14 Remove all rubbish created by repair work. - 1P
checklist-flat | 105
checkpoint | 105.00 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint | 105.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint | 105.02 Apply First Membrane - 8M2
checkpoint | 105.03 Screed - 8M2
checkpoint | 105.04 Apply Second Membrane - 8M2
checkpoint | 105.05 Tiles Supplied - 8M2
checkpoint | 105.06 Tile & Grout balcony surface - 8M2
checkpoint | 105.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint | 105.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint | 105.09 Skirting Tile and Caulking as required - 10LM
checkpoint | 105.10 Remove any rubbish and clean area - 8M3
checklist-flat | 106
checkpoint | 106.00 Demolition & Removal of Existing Balcony Surface - 13M2
checkpoint | 106.01 Provide movement joints within the tile surface as required p/m2 - 13M2
checkpoint | 106.02 Apply First Membrane - 13M2
checkpoint | 106.03 Screed - 13M2
checkpoint | 106.04 Apply Second Membrane - 13M2
checkpoint | 106.05 Tiles Supplied - 13M2
checkpoint | 106.06 Tile & Grout balcony surface - 13M2
checkpoint | 106.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint | 106.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint | 106.09 Skirting Tile and Caulking as required - 16LM
checkpoint | 106.10 Remove any rubbish and clean area - 13M3
checklist-flat | 106.1
checkpoint | 106.11 Remove moisture damaged skirting - 5LM
checkpoint | 106.12 Remove moisture damaged plaster board sheet - 16LM
checkpoint | 106.13 Supply and install new plasterboard - 16LM
checkpoint | 106.14 Supply and install new skirting boards - 5LM
checkpoint | 106.15 Paint new plasterwork and skirting with a 3-coat paint system - 16LM
checkpoint | 106.16 Remove all rubbish created by repair work. - 1P
checklist-flat | 107
checkpoint | 107.00 Demolition & Removal of Existing Balcony Surface - 12M2
checkpoint | 107.01 Provide movement joints within the tile surface as required p/m2 - 12M2
checkpoint | 107.02 Apply First Membrane - 12M2
checkpoint | 107.03 Screed - 12M2
checkpoint | 107.04 Apply Second Membrane - 12M2
checkpoint | 107.05 Tiles Supplied - 12M2
checkpoint | 107.06 Tile & Grout balcony surface - 12M2
checkpoint | 107.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 107.08 Skirting Tile and Caulking as required - 15LM
checkpoint | 107.09 Remove any rubbish and clean area - 12M3
checklist-flat | 107.1
checkpoint | 107.10 Remove moisture damaged skirting - 8LM
checkpoint | 107.11 Remove moisture damaged plaster board sheet - 18LM
checkpoint | 107.12 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 107.13 Isolate and disconnect the wall mounted GPO's at the base of each wall where the plaster lining is to be removed - 2L
checkpoint | 107.14 Remove all debris and dispose into bins - 8L
checkpoint | 107.15 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 107.16 Supply and install new plasterboard linings to the internal walls where removed - 18LM
checkpoint | 107.17 Supply and install new skirting boards - 8LM
checkpoint | 107.18 Paint all repaired internal surfaces with 1 undercoat and 2 top­ coats - Paint colour to match the existing. - 24LM
checkpoint | 107.19 Remove all rubbish created by repair work. - 1P
checklist-flat | 108
checkpoint | 108.00 Demolition & Removal of Existing Balcony Surface - 9M2
checkpoint | 108.01 Provide movement joints within the tile surface as required p/m2 - 9M2
checkpoint | 108.02 Apply First Membrane - 9M2
checkpoint | 108.03 Screed - 9M2
checkpoint | 108.04 Apply Second Membrane - 9M2
checkpoint | 108.05 Tiles Supplied - 9M2
checkpoint | 108.06 Tile & Grout balcony surface - 9M2
checkpoint | 108.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 108.08 Skirting Tile and Caulking as required - 11LM
checkpoint | 108.09 Remove any rubbish and clean area - 9M3
checklist-flat | 108.1
checkpoint | 108.10 Sand and fill skirting below the window sill in the living area - 8LM
checkpoint | 108.11 Paint all repaired internal surfaces with 1 undercoat and 2 top­ coats - Paint colour to match the existing. - 8LM
checkpoint | 108.12 Remove all rubbish created by repair work. - 1P
checklist-flat | 109
checkpoint | 109.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 109.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 109.02 Apply First Membrane - 0M2
checkpoint | 109.03 Screed - 0M2
checkpoint | 109.04 Apply Second Membrane - 0M2
checkpoint | 109.05 Tiles Supplied - 0M2
checkpoint | 109.06 Tile & Grout balcony surface - 0M2
checkpoint | 109.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 109.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 109.09 Remove any rubbish and clean area - 0M3
checklist-flat | 110
checkpoint | 110.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 110.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 110.02 Apply First Membrane - 0M2
checkpoint | 110.03 Screed - 0M2
checkpoint | 110.04 Apply Second Membrane - 0M2
checkpoint | 110.05 Tiles Supplied - 0M2
checkpoint | 110.06 Tile & Grout balcony surface - 0M2
checkpoint | 110.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 110.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 110.09 Remove any rubbish and clean area - 0M3
checklist-flat | 111
checkpoint | 111.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 111.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 111.02 Apply First Membrane - 0M2
checkpoint | 111.03 Screed - 0M2
checkpoint | 111.04 Apply Second Membrane - 0M2
checkpoint | 111.05 Tiles Supplied - 0M2
checkpoint | 111.06 Tile & Grout balcony surface - 0M2
checkpoint | 111.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 111.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 111.09 Remove any rubbish and clean area - 0M3
checklist-flat | 112
checkpoint | 112.00 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint | 112.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint | 112.02 Apply First Membrane - 15M2
checkpoint | 112.03 Screed - 15M2
checkpoint | 112.04 Apply Second Membrane - 15M2
checkpoint | 112.05 Tiles Supplied - 15M2
checkpoint | 112.06 Tile & Grout balcony surface - 15M2
checkpoint | 112.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 112.08 Skirting Tile and Caulking as required - 18LM
checkpoint | 112.09 Remove any rubbish and clean area - 15M3
checklist-flat | 113
checkpoint | 113.00 Demolition & Removal of Existing Balcony Surface - 81M2
checkpoint | 113.01 Provide movement joints within the tile surface as required p/m2 - 81M2
checkpoint | 113.02 Apply First Membrane - 81M2
checkpoint | 113.03 Screed - 81M2
checkpoint | 113.04 Apply Second Membrane - 81M2
checkpoint | 113.05 Tiles Supplied - 81M2
checkpoint | 113.06 Tile & Grout balcony surface - 81M2
checkpoint | 113.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 113.08 Skirting Tile and Caulking as required - 98LM
checkpoint | 113.09 Remove any rubbish and clean area - 81M3
checklist-flat | 201
checkpoint | 201.00 Demolition & Removal of Existing Balcony Surface - 21M2
checkpoint | 201.01 Provide movement joints within the tile surface as required p/m2 - 21M2
checkpoint | 201.02 Apply First Membrane - 21M2
checkpoint | 201.03 Screed - 21M2
checkpoint | 201.04 Apply Second Membrane - 21M2
checkpoint | 201.05 Tiles Supplied - 21M2
checkpoint | 201.06 Tile & Grout balcony surface - 21M2
checkpoint | 201.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 201.08 Skirting Tile and Caulking as required - 26LM
checkpoint | 201.09 Remove any rubbish and clean area - 21M3
checklist-flat | 202
checkpoint | 202.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 202.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 202.02 Apply First Membrane - 0M2
checkpoint | 202.03 Screed - 0M2
checkpoint | 202.04 Apply Second Membrane - 0M2
checkpoint | 202.05 Tiles Supplied - 0M2
checkpoint | 202.06 Tile & Grout balcony surface - 0M2
checkpoint | 202.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 202.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 202.09 Remove any rubbish and clean area - 0M3
checklist-flat | 202.1
checkpoint | 202.10 Remove moisture damaged skirting - 4LM
checkpoint | 202.11 Supply and install new skirting boards - 4LM
checkpoint | 202.12 Paint new skirting with a 3 coat paint systern - 4LM
checkpoint | 202.13 Remove all rubbish created by repair work. - 1P
checklist-flat | 203
checkpoint | 203.00 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint | 203.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint | 203.02 Apply First Membrane - 8M2
checkpoint | 203.03 Screed - 8M2
checkpoint | 203.04 Apply Second Membrane - 8M2
checkpoint | 203.05 Tiles Supplied - 8M2
checkpoint | 203.06 Tile & Grout balcony surface - 8M2
checkpoint | 203.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 203.08 Skirting Tile and Caulking as required - 10LM
checkpoint | 203.09 Remove any rubbish and clean area - 8M3
checklist-flat | 204
checkpoint | 204.00 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint | 204.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint | 204.02 Apply First Membrane - 8M2
checkpoint | 204.03 Screed - 8M2
checkpoint | 204.04 Apply Second Membrane - 8M2
checkpoint | 204.05 Tiles Supplied - 8M2
checkpoint | 204.06 Tile & Grout balcony surface - 8M2
checkpoint | 204.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 204.08 Skirting Tile and Caulking as required - 10LM
checkpoint | 204.09 Remove any rubbish and clean area - 8M3
checklist-flat | 205
checkpoint | 205.00 Demolition & Removal of Existing Balcony Surface - 8M2
checkpoint | 205.01 Provide movement joints within the tile surface as required p/m2 - 8M2
checkpoint | 205.02 Apply First Membrane - 8M2
checkpoint | 205.03 Screed - 8M2
checkpoint | 205.04 Apply Second Membrane - 8M2
checkpoint | 205.05 Tiles Supplied - 8M2
checkpoint | 205.06 Tile & Grout balcony surface - 8M2
checkpoint | 205.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 205.08 Skirting Tile and Caulking as required - 10LM
checkpoint | 205.09 Remove any rubbish and clean area - 8M3
checklist-flat | 205.1
checkpoint | 205.10 Remove moisture damaged section of the plasterboard ceiling - 16LM
checkpoint | 205.11 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 205.12 Remove and replace moisture damage wall framing members - 4LM
checkpoint | 205.13 Supply and install new plasterboard where removed on the ceiling - 16LM
checkpoint | 205.14 Paint entire bedroom ceiling with a 3-coat paint system - 12LM
checkpoint | 205.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 206
checkpoint | 206.00 Demolition & Removal of Existing Balcony Surface - 13M2
checkpoint | 206.01 Provide movement joints within the tile surface as required p/m2 - 13M2
checkpoint | 206.02 Apply First Membrane - 13M2
checkpoint | 206.03 Screed - 13M2
checkpoint | 206.04 Apply Second Membrane - 13M2
checkpoint | 206.05 Tiles Supplied - 13M2
checkpoint | 206.06 Tile & Grout balcony surface - 13M2
checkpoint | 206.07 Rendering of Internal Balaustrade as required (Including materials) - 1M2
checkpoint | 206.08 Painting of Internal Balaustrade as required (including materials) - 2M2
checkpoint | 206.09 Skirting Tile and Caulking as required - 16LM
checkpoint | 206.10 Remove any rubbish and clean area - 13M3
checklist-flat | 206.1
checkpoint | 206.11 Remove moisture damaged skirting - 8LM
checkpoint | 206.12 Remove moisture damaged plasterboard - 18LM
checkpoint | 206.13 Inspect for water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 206.14 Replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 206.15 Replace water damaged plasterboard - 18LM
checkpoint | 206.16 Replace water damaged skirting boards - 8LM
checkpoint | 206.17 Paint new plasterwork and skirting with a 3 coat paint system - 24LM
checkpoint | 206.18 Remove all rubbish created by repair work. - 1P
checklist-flat | 207
checkpoint | 207.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 207.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 207.02 Apply First Membrane - 0M2
checkpoint | 207.03 Screed - 0M2
checkpoint | 207.04 Apply Second Membrane - 0M2
checkpoint | 207.05 Tiles Supplied - 0M2
checkpoint | 207.06 Tile & Grout balcony surface - 0M2
checkpoint | 207.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 207.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 207.09 Remove any rubbish and clean area - 0M3
checklist-flat | 208
checkpoint | 208.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 208.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 208.02 Apply First Membrane - 0M2
checkpoint | 208.03 Screed - 0M2
checkpoint | 208.04 Apply Second Membrane - 0M2
checkpoint | 208.05 Tiles Supplied - 0M2
checkpoint | 208.06 Tile & Grout balcony surface - 0M2
checkpoint | 208.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 208.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 208.09 Remove any rubbish and clean area - 0M3
checklist-flat | 209
checkpoint | 209.00 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint | 209.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint | 209.02 Apply First Membrane - 15M2
checkpoint | 209.03 Screed - 15M2
checkpoint | 209.04 Apply Second Membrane - 15M2
checkpoint | 209.05 Tiles Supplied - 15M2
checkpoint | 209.06 Tile & Grout balcony surface - 15M2
checkpoint | 209.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 209.08 Skirting Tile and Caulking as required - 18LM
checkpoint | 209.09 Remove any rubbish and clean area - 15M3
checklist-flat | 209.1
checkpoint | 209.10 Remove moisture damaged section of the plasterboard ceiling - 16LM
checkpoint | 209.11 Inspect and replace water damaged timber members within the walls - T.B.A.T.B.A.
checkpoint | 209.12 Remove and replace moisture damage wall framing members - T.B.A.T.B.A.
checkpoint | 209.13 Supply and install new plasterboard where removed on the ceiling - 16LM
checkpoint | 209.14 Supply and install new skirting boards - 4LM
checkpoint | 209.15 Paint entire bedroom ceiling with a 3-coat paint system - 12LM
checkpoint | 209.16 Remove all rubbish created by repair work. - 1P
checklist-flat | 210
checkpoint | 210.00 Demolition & Removal of Existing Balcony Surface - 12M2
checkpoint | 210.01 Provide movement joints within the tile surface as required p/m2 - 12M2
checkpoint | 210.02 Apply First Membrane - 12M2
checkpoint | 210.03 Screed - 12M2
checkpoint | 210.04 Apply Second Membrane - 12M2
checkpoint | 210.05 Tiles Supplied - 12M2
checkpoint | 210.06 Tile & Grout balcony surface - 12M2
checkpoint | 210.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 210.08 Skirting Tile and Caulking as required - 15LM
checkpoint | 210.09 Remove any rubbish and clean area - 12M3
checklist-flat | 211
checkpoint | 211.00 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint | 211.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint | 211.02 Apply First Membrane - 15M2
checkpoint | 211.03 Screed - 15M2
checkpoint | 211.04 Apply Second Membrane - 15M2
checkpoint | 211.05 Tiles Supplied - 15M2
checkpoint | 211.06 Tile & Grout balcony surface - 15M2
checkpoint | 211.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 211.08 Skirting Tile and Caulking as required - 18LM
checkpoint | 211.09 Remove any rubbish and clean area - 15M3
checklist-flat | 212
checkpoint | 212.00 Demolition & Removal of Existing Balcony Surface - 15M2
checkpoint | 212.01 Provide movement joints within the tile surface as required p/m2 - 15M2
checkpoint | 212.02 Apply First Membrane - 15M2
checkpoint | 212.03 Screed - 15M2
checkpoint | 212.04 Apply Second Membrane - 15M2
checkpoint | 212.05 Tiles Supplied - 15M2
checkpoint | 212.06 Tile & Grout balcony surface - 15M2
checkpoint | 212.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 212.08 Skirting Tile and Caulking as required - 18LM
checkpoint | 212.09 Remove any rubbish and clean area - 15M3
checklist-flat | 212.1
checkpoint | 212.10 Remove moisture damaged skirting - 4LM
checkpoint | 212.11 Supply and install new skirting boards - 4LM
checkpoint | 212.12 Paint new skirting with a 3 coat paint systern - 4LM
checkpoint | 212.13 Remove all rubbish created by repair work. - 1P
checklist-flat | 213
checkpoint | 213.00 Demolition & Removal of Existing Balcony Surface - 81M2
checkpoint | 213.01 Provide movement joints within the tile surface as required p/m2 - 81M2
checkpoint | 213.02 Apply First Membrane - 81M2
checkpoint | 213.03 Screed - 81M2
checkpoint | 213.04 Apply Second Membrane - 81M2
checkpoint | 213.05 Tiles Supplied - 81M2
checkpoint | 213.06 Tile & Grout balcony surface - 81M2
checkpoint | 213.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 213.08 Skirting Tile and Caulking as required - 98LM
checkpoint | 213.09 Remove any rubbish and clean area - 81M3
checklist-flat | 213.1
checkpoint | 213.10 Remove the luminaries and exhaust fans on the bathroom ceiling and set aside - 2L
checkpoint | 213.11 Remove the existing shower screen and set aside - 2L
checkpoint | 213.12 Plumber to remove the existing laundry trough and set aside - 1L
checkpoint | 213.13 Remove the ceiling in the bathroom - 2L
checkpoint | 213.14 Remove the moisture damage wall linings adjacent to the laundry trough - 16L
checkpoint | 213.15 Inspect wall framing members for moisture damage - T.B.A.T.B.A.
checkpoint | 213.16 Remove and replace moisture damage framing members - T.B.A.T.B.A.
checkpoint | 213.17 Remove the moisture damaged skirting in the hallway cupboard - 3LM
checkpoint | 213.18 Remove the moisture damaged skirting in the living room under the window - 16LM
checkpoint | 213.19 Provide mould remediation to area where mould is identified - 1A
checkpoint | 213.2 Supply and install new plasterboard where removed on the ceiling - T.B.A.LM
checkpoint | 213.21 Supply and install new plasterboard on the wall in the bathroom - 16LM
checkpoint | 213.22 Supply and install new skirting in the hallway cupboard - 3LM
checkpoint | 213.23 Supply and install new skirting in the living room - 16LM
checkpoint | 213.24 Supply and install skirting tile in the bathroom where removed from wall surface - T.B.A.LM
checkpoint | 213.25 Paint entire bathroom ceiling with a 3-coat paint system to provide a consistent surface finish - 24LM
checkpoint | 213.26 Paint all new skirting with a 3-coat paint system - colour to match the existing - 19LM
checkpoint | 213.27 Plumber to reinstate laundry trough - 1LM
checkpoint | 213.28 Reinstall luminaries & exhaust fans - 4L
checkpoint | 213.29 Reinstall shower screen - 1L
checkpoint | 213.3 Remove all rubbish created by repair work. - 1P
checklist-flat | 301
checkpoint | 301.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 301.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 301.02 Apply First Membrane - 0M2
checkpoint | 301.03 Screed - 0M2
checkpoint | 301.04 Apply Second Membrane - 0M2
checkpoint | 301.05 Tiles Supplied - 0M2
checkpoint | 301.06 Tile & Grout balcony surface - 0M2
checkpoint | 301.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 301.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 301.09 Remove any rubbish and clean area - 0M3
checklist-flat | 301.1
checkpoint | 301.10 Remove moisture damaged skirting - 4LM
checkpoint | 301.11 Supply and install new skirting boards - 4LM
checkpoint | 301.12 Paint new skirting with a 3 coat paint systern - 4LM
checkpoint | 301.13 Remove all rubbish created by repair work. - 1P
checklist-flat | 302
checkpoint | 302.00 Demolition & Removal of Existing Balcony Surface - 0M2
checkpoint | 302.01 Provide movement joints within the tile surface as required p/m2 - 0M2
checkpoint | 302.02 Apply First Membrane - 0M2
checkpoint | 302.03 Screed - 0M2
checkpoint | 302.04 Apply Second Membrane - 0M2
checkpoint | 302.05 Tiles Supplied - 0M2
checkpoint | 302.06 Tile & Grout balcony surface - 0M2
checkpoint | 302.07 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 302.08 Skirting Tile and Caulking as required - 0LM
checkpoint | 302.09 Remove any rubbish and clean area - 0M3
checklist-flat | 302.1
checkpoint | 302.10 Remove moisture damaged skirting - 4LM
checkpoint | 302.11 Remove moisture damaged plasterboard - 4LM
checkpoint | 302.12 Supply and install new plasterboard - 4LM
checkpoint | 302.13 Supply and install new skirting boards - 4LM
checkpoint | 302.14 Paint new skirting with a 3 coat paint systern - paint entire surfaces for a consistent finish - 12LM
checkpoint | 302.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 303
checkpoint | 303.00 Demolition & Removal of Existing Balcony Surface - 22M2
checkpoint | 303.01 Provide movement joints within the tile surface as required p/m2 - 22M2
checkpoint | 303.02 Apply First Membrane - 22M2
checkpoint | 303.03 Supply Acoustic Rubber Underlay - 22M2
checkpoint | 303.04 Fitting Accoustic Rubber Underlay - 22M2
checkpoint | 303.05 Screed - 22M2
checkpoint | 303.06 Apply Second Membrane - 22M2
checkpoint | 303.07 Tiles Supplied - 22M2
checkpoint | 303.08 Tile & Grout balcony surface - 22M2
checkpoint | 303.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 303.10 Skirting Tile and Caulking as required - 27LM
checkpoint | 303.11 Remove any rubbish and clean area - 22M3
checklist-flat | 304
checkpoint | 304.00 Demolition & Removal of Existing Balcony Surface - 20M2
checkpoint | 304.01 Provide movement joints within the tile surface as required p/m2 - 20M2
checkpoint | 304.02 Apply First Membrane - 20M2
checkpoint | 304.03 Supply Acoustic Rubber Underlay - 20M2
checkpoint | 304.04 Fitting Accoustic Rubber Underlay - 20M2
checkpoint | 304.05 Screed - 20M2
checkpoint | 304.06 Apply Second Membrane - 20M2
checkpoint | 304.07 Tiles Supplied - 20M2
checkpoint | 304.08 Tile & Grout balcony surface - 20M2
checkpoint | 304.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checklist-flat | 304.1
checkpoint | 304.10 Skirting Tile and Caulking as required - 24LM
checkpoint | 304.11 Remove any rubbish and clean area - 20M3
checkpoint | 304.12 Remove the moisture damaged skirting adjacent to the window in the dining area - 9LM
checkpoint | 304.13 Remove the moisture damaged flooring adjacent to the window in the dining area - 23LM
checkpoint | 304.14 Dispose of all debris - 1P
checkpoint | 304.15 Supply and install new flooring where removed - profile and finish to match the existing flooring - 23LM
checkpoint | 304.16 Supply and install new skirting boards where removed. - 9LM
checkpoint | 304.17 Paint all new skirting with a 3-coat paint system - colour to match the existing - 8LM
checkpoint | 304.18 Remove all rubbish created by repair work. - 1P
checklist-flat | 305
checkpoint | 305.00 Demolition & Removal of Existing Balcony Surface - 35M2
checkpoint | 305.01 Provide movement joints within the tile surface as required p/m2 - 35M2
checkpoint | 305.02 Apply First Membrane - 35M2
checkpoint | 305.03 Supply Acoustic Rubber Underlay - 35M2
checkpoint | 305.04 Fitting Accoustic Rubber Underlay - 35M2
checkpoint | 305.05 Screed - 35M2
checkpoint | 305.06 Apply Second Membrane - 35M2
checkpoint | 305.07 Tiles Supplied - 35M2
checkpoint | 305.08 Tile & Grout balcony surface - 35M2
checkpoint | 305.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checklist-flat | 305.1
checkpoint | 305.10 Skirting Tile and Caulking as required - 42LM
checkpoint | 305.11 Remove any rubbish and clean area - 35M3
checkpoint | 305.12 Remove the skirting board and bottom section of the plaster within the bedroom 1 & 3 - 16LM
checkpoint | 305.13 Remove delaminated section of all parquetry flooring in each room - 8LM
checkpoint | 305.14 Dispose of all debris - 16LM
checkpoint | 305.15 Supply and install new plasterboard linings where removed - 8LM
checkpoint | 305.16 Supply and install new timber parquetry flooring to each room - 23M
checkpoint | 305.17 Fill, sand and polish parquetry timber flooring within entire bedroom 1 & 3. - 1LM2
checkpoint | 305.18 Supply and install new skirting boards where removed. - 16LM
checkpoint | 305.19 Paint all walls and woodwork as required - 1 undercoat and 2 top coats colour to match existing paintwork - 12LM
checkpoint | 305.2 Remove all rubbish created by repair work. - 1P
checklist-flat | 306
checkpoint | 306.00 Demolition & Removal of Existing Balcony Surface - 64M2
checkpoint | 306.01 Provide movement joints within the tile surface as required p/m2 - 64M2
checkpoint | 306.02 Apply First Membrane - 64M2
checkpoint | 306.03 Supply Acoustic Rubber Underlay - 64M2
checkpoint | 306.04 Fitting Accoustic Rubber Underlay - 64M2
checkpoint | 306.05 Screed - 64M2
checkpoint | 306.06 Apply Second Membrane - 64M2
checkpoint | 306.07 Tiles Supplied - 64M2
checkpoint | 306.08 Tile & Grout balcony surface - 64M2
checkpoint | 306.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checklist-flat | 306.1
checkpoint | 306.10 Skirting Tile and Caulking as required - 77LM
checkpoint | 306.11 Remove any rubbish and clean area - 64M3
checkpoint | 306.12 Remove moisture damaged skirting - 4LM
checkpoint | 306.13 Supply and install new skirting boards - 4LM
checkpoint | 306.14 Paint new skirting with a 3 coat paint systern - paint entire surfaces for a consistent finish - 8LM
checkpoint | 306.15 Remove all rubbish created by repair work. - 1P
checklist-flat | 307
checkpoint | 307.00 Demolition & Removal of Existing Balcony Surface - 39M2
checkpoint | 307.01 Provide movement joints within the tile surface as required p/m2 - 39M2
checkpoint | 307.02 Apply First Membrane - 39M2
checkpoint | 307.03 Supply Acoustic Rubber Underlay - 29M2
checkpoint | 307.04 Fitting Accoustic Rubber Underlay - 39M2
checkpoint | 307.05 Screed - 39M2
checkpoint | 307.06 Apply Second Membrane - 39M2
checkpoint | 307.07 Tiles Supplied - 39M2
checkpoint | 307.08 Tile & Grout balcony surface - 39M2
checkpoint | 307.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 307.10 Skirting Tile and Caulking as required - 47LM
checkpoint | 307.11 Remove any rubbish and clean area - 39M3
checklist-flat | 308
checkpoint | 308.00 Demolition & Removal of Existing Balcony Surface - 37M2
checkpoint | 308.01 Provide movement joints within the tile surface as required p/m2 - 37M2
checkpoint | 308.02 Apply First Membrane - 37M2
checkpoint | 308.03 Supply Acoustic Rubber Underlay - 37M2
checkpoint | 308.04 Fitting Accoustic Rubber Underlay - 37M2
checkpoint | 308.05 Screed - 37M2
checkpoint | 308.06 Apply Second Membrane - 37M2
checkpoint | 308.07 Tiles Supplied - 37M2
checkpoint | 308.08 Tile & Grout balcony surface - 37M2
checkpoint | 308.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 308.10 Skirting Tile and Caulking as required - 45LM
checkpoint | 308.11 Remove any rubbish and clean area - 37M3
checklist-flat | 309
checkpoint | 309.00 Demolition & Removal of Existing Balcony Surface - 87M2
checkpoint | 309.01 Provide movement joints within the tile surface as required p/m2 - 87M2
checkpoint | 309.02 Apply First Membrane - 87M2
checkpoint | 309.03 Supply Acoustic Rubber Underlay - 87M2
checkpoint | 309.04 Fitting Accoustic Rubber Underlay - 87M2
checkpoint | 309.05 Screed - 87M2
checkpoint | 309.06 Apply Second Membrane - 87M2
checkpoint | 309.07 Tiles Supplied - 87M2
checkpoint | 309.08 Tile & Grout balcony surface - 87M2
checkpoint | 309.09 Rendering of Internal Balaustrade as required (Including materials) - 0M2
checkpoint | 309.10 Skirting Tile and Caulking as required - 105LM
checkpoint | 309.11 Remove any rubbish and clean area - 87M3
checklist-flat | AA1
checkpoint | AA1.00 Obtain Access to Lot 8
checkpoint | AA1.01 Investigate Lot 8 for Internal Water Damage
checkpoint | AA1.02 Discuss Findings with Client
checkpoint | AA1.03 Raise Contract Variation if Required
checkpoint | AA1.04 Modify Program to include Contract Variation on Acceptance of Client
checklist-flat | BC213
checkpoint | BC213.00 Check to see if leaks continue
checkpoint | BC213.01 Evidence or Efflouresence Removed
checklist-flat | BC212
checkpoint | BC212.00 Check to see if leaks continue
checkpoint | BC212.01 Evidence or Efflouresence Removed
checklist-flat | BC207
checkpoint | BC207.00 Check to see if leaks continue
checkpoint | BC207.01 Evidence or Efflouresence Removed
checklist-flat | BC011
checkpoint | BC011.00 Check to see if leaks continue
checkpoint | BC011.01 Evidence or Efflouresence Removed
checklist-flat | BCSSF
checkpoint | BCSSF.00 Check to see if leaks continue
checkpoint | BCSSF.01 Evidence or Efflouresence Removed
checklist-flat | BCCI
checkpoint | BCCI.00 Plumbing work in Basement Complete (Plumber x 2 x 1 day)
checkpoint | BCCI.01 Electrician work in Basement Complete (Electrician x 1 x 1 Day)
checkpoint | BCCI.02 Labourer Removed Rubbish
checkpoint | BCCI.03 Commercial Clean Required and Completed
checklist-flat | CAH3
checkpoint | CAH3.00 Fire Door Installation Completed
checkpoint | CAH3.01 Service Enclosure Electrical Penetrations Sealed
checkpoint | CAH3.02 Sensors Connected within Electrical Enclosure
checkpoint | CAH3.03 Debris Removed from Service Enclosure
checklist-flat | CAH2
checkpoint | CAH2.00 Fire Door Installation Completed
checkpoint | CAH2.01 Service Enclosure Electrical Penetrations Sealed
checkpoint | CAH2.02 Sensors Connected within Electrical Enclosure
checkpoint | CAH2.03 Debris Removed from Service Enclosure
checklist-flat | CAH1
checkpoint | CAH1.00 Fire Door Installation Completed
checkpoint | CAH1.01 Service Enclosure Electrical Penetrations Sealed
checkpoint | CAH1.02 Sensors Connected within Electrical Enclosure
checkpoint | CAH1.03 Debris Removed from Service Enclosure
checklist-flat | CAHG
checkpoint | CAHG.00 Fire Door Installation Completed
checkpoint | CAHG.01 Service Enclosure Electrical Penetrations Sealed
checkpoint | CAHG.02 Sensors Connected within Electrical Enclosure
checkpoint | CAHG.03 Debris Removed from Service Enclosure
checklist-flat | PB
checkpoint | PB.00 APM PC Allowance to rectify Planter Boxes - 1A
checkpoint | PB.01 Remove soil from planter boxes and set aside - 40L
checkpoint | PB.02 Removal of existing failed waterproofing - 266L/M2
checkpoint | PB.03 Plumber to repair drain outlets if applicable - 4LM
checkpoint | PB.04 Apply first membrane - 266L/M2
checkpoint | PB.05 Apply second membrane - 266L/M2
checkpoint | PB.06 Reinstate soil - 40L
checkpoint | PB.07 Minders Landscaper - Remove & dispose of Tristaniopsis Luscious at front & R/H side planter boxes.
checkpoint | PB.08 Minders Landscaper - Plant 25 Magnolia (Teddy Bear) 40cm pots.
checkpoint | PB.09 Minders Landscaper - Install irrigation drip line and automated irrigation controllers.
checklist-flat | RC
checkpoint | RC.00 New Box Gutter Installed & Connected to Existing DP's.
checkpoint | RC.01 New CB Capping to Perimeter of Building.
checkpoint | RC.02 Zincalume Patches Applied to Roof Sheet Dints.
checkpoint | RC.03 All Missing Slotted Vent Caps Replaced.
checkpoint | RC.04 Roof Plumber Assessment & Rectification of Side Entry Canopy Leak.
checkpoint | RC.05 Management, Documentation & Removal of all Redundant Roof Materials.
checkpoint | RC.06 Plasterer to Supply & Fit new Plasterboard Linings Where Removed.
checkpoint | RC.07 Painter to Patch Water Damaged Plaster within Side Entry Foyer.
checkpoint | RC.08 Painter to Paint Entire Foyer Ceiling - 1 undercoat and 2 topcoats, Colour to match the existing paintwork.
checkpoint | RC.09 Rubbish Removal of Builders Rubbish from Site.
checklist-flat | WSE
checkpoint | WSE.00 Tactile Installation Front Entry
checkpoint | WSE.01 Tactile Installation Side Entry
checkpoint | WSE.02 Handrail Installation for Front Steps
checklist-flat | SSU
checkpoint | SSU.00 Set up Office
checkpoint | SSU.01 Set up Amenities
checkpoint | SSU.02 Set up First Aid
checkpoint | SSU.03 Set up Lock up Area in Basement
checkpoint | SSU.04 Set up Rubbish Removal Area
checklist-flat | SCE |  |  | Dismantle Lock up and Clean Area in Basement
checkpoint | SCE.00 Dismantle Lock up and Clean Area in Basement
checkpoint | SCE.01 Clean Lock up Area in Basement
checkpoint | SCE.02 Dismantle/ Remove Amenities
checkpoint | SCE.03 Clean Amenities Area
checkpoint | SCE.04 Dismantle Site Office
checkpoint | SCE.05 Clean Site Office Area
checkpoint | SCE.06 Dismantle Rubbish Removal Area
checkpoint | SCE.07 Clean up Rubbish Removal Area
checkpoint | SCE.08 Have Bin Removed
checkpoint | SCE.09 Exit Site