## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | ee35a492-419b-4e14-98e5-6283767d1d1a |  | checklist | Trusses |  |  |  |  | Yes | Trusses | 4c3bc4da-acc6-495e-be0a-2635b4dea218
checkpoint-status | eb95c3b6-8345-4edb-b657-b183ed68fb15 |  | checkpoint | Truss hardware completed as specified.
checkpoint-status | e77347dd-48d3-4069-baf2-fce61ffb7918 |  | checkpoint | All fixings in place
checkpoint-status | af796e9e-ba39-4b19-bd0a-14e3b4b8c84f |  | checkpoint | Truss seating checked and accurate
checkpoint-status | f70d5f79-6a9d-4e46-9478-8dbfe75a9cf2 |  | checkpoint | Structural inspection complete
checkpoint-status | 73e03fa6-aba4-4300-98ba-a853c955106d |  | checkpoint | Trusses are completed
holdpoint | 0931c823-a5e1-418a-afe2-accee32d3b6d |  | signoff | Raise Remedial / Request Signoff
checklist-flat | 9ebb6844-e29a-4241-9def-808c73c1fa8e |  | checklist | Internal doors |  |  |  |  | Yes | Internal doors | 9a2f6958-c6de-4968-b53a-f21543a095df
checkpoint-status | 3974207e-dbe0-46a7-9235-0fda2085fa9a |  | checkpoint | Door fitted correctly as per specification (product, size, location, level, swing, fixings etc)
checkpoint-status | b1d1ff30-d47b-4c7f-becd-dd90be30f816 |  | checkpoint | Hardware installed
checkpoint-status | 7a50faac-22d1-45dd-9cfb-5a392b3c8f1d |  | checkpoint | Door install completed, checked, correct and approved
holdpoint | 5f89e061-3681-4817-9f52-83fd45ba8cc2 |  | signoff | Raise remedial/ request signoff
checklist-flat | e9ef29de-f3f1-48dc-abfc-5be375897e82 |  | checklist | Ecoply Board |  |  |  |  | Yes | Ecoply Board | c1861ed9-0e6e-4609-938b-23726b7e1c96
checkpoint-status | fc5e8e3a-d2f4-458c-9b34-be094665850d |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs.
checkpoint-status | 37765652-74a8-4d63-bce7-32a275ebc828 |  | checkpoint | Bracing elements marked on floor
checkpoint-status | 8fc2703f-ae4a-4fea-8788-e34399a7fa82 |  | checkpoint | Fixing off of sheets as per Structural drawings
checkpoint-status | 390786e8-e911-4a4c-9125-b091bdb4173b |  | checkpoint | Penetrations, joints, internal and external corners, and punctures taped and sealed
holdpoint | 24fdf524-aa53-4d29-aef6-ffe640d75211 |  | signoff | Raise remedial/ request signoff
checklist-flat | df4b37ee-0b37-4bed-9cd2-6787d927341e |  | checklist | Timber Framing |  |  |  |  | Yes | Timber Framing | c4887046-03b0-407e-82db-f18726798f55
checkpoint-status | 61aa2741-8da5-44a8-a9ec-c03d3df734a1 |  | checkpoint | Substrate acceptable
checkpoint-status | 729f7642-66d8-4b44-b737-b0d654b02d44 |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status | 20342907-c521-4c86-8607-3d4d81be6e9e |  | checkpoint | All frames are square
checkpoint-status | 609a0463-e83d-4059-9cdd-cee01f134232 |  | checkpoint | Frames are plumb and level
checkpoint-status | 95529eac-0875-4b48-b516-5888adbdbe83 |  | checkpoint | Fixings are correct
checkpoint-status | 9082fa22-58de-4172-a900-fc8a4a116c5f |  | checkpoint | Any bracing requirements installed
checkpoint-status | ac0d629d-eb69-4e87-b1e0-68405141fff4 |  | checkpoint | Any additional photos, comments and observations
checkpoint-status | 965a57bd-75af-4df0-98b8-d1822069ac3a |  | checkpoint | All framing completed correctly within tolerance in respective area
holdpoint | 1838a081-99dd-49c7-a58c-3ba7749d66b7 |  | signoff | Raise Remedial / Request Signoff
checklist-flat | f166eaac-47d2-42ea-b8bc-60213585cd38 |  | checklist | Windows and sliders |  |  |  |  | Yes | Windows and sliders | c6056ff4-315a-4951-8db4-c9d01c841dc7
checkpoint-status | e4bd9643-aa18-4644-baca-cd7428e7a9af |  | checkpoint | WANZ bars are the correct length and have been installed correctly – sufficient fixings and level.
checkpoint-status | 4d9d514a-1cd5-46a7-ab99-a0e7b1518898 |  | checkpoint | flashing tapes and plastic corners have been installed correctly
checkpoint-status | 341d658b-63c1-45a0-9e02-6ac74ccb015e |  | checkpoint | All joinery has been screwed off correctly
checkpoint-status | d63475bd-014c-4ac9-8e89-9defe01957f6 |  | checkpoint | Head and sills are level
checkpoint-status | 0ffab34d-bc5b-4db6-a575-a046edc0801e |  | checkpoint | Air seals have been installed and all perimeters foamed.
checkpoint-status | b174e227-2171-4f53-8008-f4a96227fbda |  | checkpoint | all opening windows do not bind on the sash
checkpoint-status | a5b39a6e-3968-4de4-b5ba-3368b70d6960 |  | checkpoint | General comments, photos or documentation
holdpoint | 005ab34e-4a2f-4d7a-8dc0-aa6edb9ac4f1 |  | signoff | Raise remedial/ request signoff