## ITP
|  |  | Inspection and Test Plan - Asphalt Production of Base Mixes | [7 empty] | Document # ITP-001
[11 empty] | Revision: 1.1 | Date : 14/10/2022
Client: | Melbourne Airport |  | Construction Process: | Asphalt Production of Base Mixes |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: Kevin Embleton |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-001 (10 June 2022), GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer |  | National Technical Solutions Manager
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1 | Mix Production
1.01 | Asphalt production plan |  | Not less than 48 hours prior to the commencement of a work period. |  | Plan demonstrates that the hot storage capacity and production capacity of the mixing plant is capable of supplying asphalt to complete the work proposed to be undertaken within that work period on time and to make the runway suitable for aircraft operation in the event of an asphalt plant breakdown. | GHD-DD-SPC-002 5116(e) HP5116-1 | N/A | Production plan | HP | Production Supervisor
1.02 | Temperature of bitumen |  | Not less than once per work period. To be recorded at the time of taking bitumen volumetric readings. |  | Temperature to be within the below range for the relevant bitumen type when introduced into the mixer: - Residual bitumen C320: 140-165oC - Polymer modified bitumen: 160-175oC - Polymer modified bitumen with warm mix additives: 140-175oC | GHD-DD-SPC-001 5116(f) | Asphalt plant temperature probe | Production records | IP | Plant Operator
1.03 | Temperature of aggregates |  | Not less than once per work period. |  | Temperature to be not more than 10oC above or more than 15oC below the temperature of the bitumen. | GHD-DD-SPC-001 5116(f) | Asphalt plant temperature probe | Production records | IP | Plant Operator
1.04 | Temperature of asphalt |  | Not less than once per work period. |  | Temperature to be within 10oC of the job mix temperature | GHD-DD-SPC-001 5116(f) | Asphalt plant temperature probe | Production records | IP | Plant Operator
1.05 | Daily bitumen usage |  | Once per work period for each production run for each nominal size of asphalt mix. |  | To be reported. | GHD-DD-SPC-001 5131(e) | Inspection of plant digital readouts before and after each production run | Production records | IP | Plant Operator
1.06 | Supplementary bitumen content determination |  | Once per work period for each nominal size of asphalt mix. |  | Not less than the job bitumen content. | GHD-DD-SPC-001 5131(e) Table 5116-7 | Calculation: Daily bitumen usage divided by mass of asphalt produced for each mix type. | Production records | IP | Plant Operator
1.07 | Mass of asphalt produced |  | Once per work period for each nominal size of asphalt mix. |  | To be reported. | GHD-DD-SPC-001 5131(e) | Inspection of plant digital readouts | Production records | IP | Plant Operator
2 | Bitumen properties
2.01 | Sampling of bitumen deliveries. |  | Prior notice (minimum 24 hours) of the time of bitumen delivery to mixing plant and the taking of samples to be given to Contract Administrator. |  | One sample of not less than two (2) litres taken from each separate delivery vessel of bitumen delivered to the mixing plant. Containers are labelled appropriately so that samples are traceable to asphalt lots, manufacturing batch records and conformance reports. Samples are provided to Contract Administrator immediately after sampling. | GHD-DD-SPC-001 5131(c) WP5131-1 | AS 2008 (Appendix B) | ITP | WP | Laboratory Technician
2.02 | Sampling from storage tank at the asphalt mixing plant. |  | Not more than four hours prior to the scheduled production start time for each work period. |  | Duplicate samples are taken from the storage tank at the asphalt mixing plant. Containers are labelled appropriately so that samples are traceable to asphalt lots, manufacturing batch records and conformance reports. One sample is provided to Contract Administrator immediately after sampling; one sample is tested as per Section 2 of this ITP. | GHD-DD-SPC-001 5131(c) | AS 2008 (Appendix B) | ITP | IP | Laboratory Technician
2.03 | Viscosity at 165oC |  | One test prior to each work period (for PMB) or per 250 t of bitumen used (for residual class C320), completed no later than 1 hour prior to start of asphalt production. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AG:PT/T111 (for PMB) or AS 2341.2 (for C320) | NATA-accredited test certificate | TP | Laboratory Technician
2.04 | Torsional recovery at 25oC, 30 s (PMB only) |  | One test prior to each work period, completed no later than 1 hour prior to start of asphalt production. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AG:PT/T122 | NATA-accredited test certificate | TP | Laboratory Technician
2.05 | Softening point (PMB only) |  | One test prior to each work period, completed no later than 1 hour prior to start of asphalt production. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AG:PT/T131 | NATA-accredited test certificate | TP | Laboratory Technician
2.06 | PG MSCR |  | One test weekly conducted on a Monday sampled from storage tank, regardless of whether work proceeds that day or not. |  | To be reported. | GHD-DD-SPC-002 5131(c) Table SP5131-3 | AASHTO T350 | NATA-accredited test certificate | TP | Laboratory Technician
2.07 | Submission of binder test results. |  | No later than 1 hour prior to the scheduled start of asphalt production for each work period. |  | Completion of the specified set of tests on polymer modified binder. Submission of test results and a statement to the Contract Administrator regarding the compliance of the binder in the tank. | GHD-DD-SPC-001 5131(c) HP5131-2 | N/A | ITP | HP | Laboratory Technician
3 | Asphalt properties
3.01 | Mixing efficiency |  | Not less than once per work period. |  | Percentage of coating of particles in the mix, when sampled at the point of loading, must not be less than 97% and a homogeneous mixture must be obtained. | GHD-DD-SPC-001 5116(g) | Visual inspection as per ASTM D2489 methodology | Inspection record | IP | Plant Operator
3.02 | Stability |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | ±3.0 compared to job mix but not less than 12.0 kN | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.03 | Flow |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | Max 3.0 mm for unmodified binder; max ±1.0 mm compared to job mix for PMB | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.04 | Minimum voids in mineral aggregate |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | 13.0% (for 20mm NMS) or 14.0% (for 14mm NMS) | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.05 | Minimum and maximum air voids |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | 3.0-5.0% | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.06 | Minimum and maximum voids filled with bitumen |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | 65.0-75.0% | GHD-DD-SPC-001 5116(j) Table 5116-5 HP5116-2 | AS/NZS 2891.5 (50 blows) | NATA-accredited test certificate | TP | Laboratory Technician
3.07 | Combined aggregate particle size distribution |  | Each test set sampled from asphalt delivery trucks (as per AS 2891.1). See Note 1 for sampling frequency. |  | Within acceptable range of deviation from job mix aggregate particle size distribution. For 14mm NMS: 13.2: ±6 1.18: ±4 9.5: ±6 0.6: ±3 6.7: ±6 0.3: ±2 4.75: ±5 0.15: ±2 2.36: ±5 0.075: ±1.5 | GHD-DD-SPC-001 5116(j) Table 5116-7 | AS/NZS 2891.3.3 | NATA-accredited test certificate | TP | Laboratory Technician
3.08 | Bitumen content in asphalt |  | Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency. |  | Within ±0.3 of job bitumen content by mass. | GHD-DD-SPC-001 5116(j) Table 5116-7 | AS/NZS 2891.3.3 | NATA-accredited test certificate | TP | Laboratory Technician
3.09 | Maximum density |  | Each test set sampled from asphalt delivery trucks (as per AS/NZS 2891.1.1). See Note 1 for sampling frequency. |  | To be reported. | GHD-DD-SPC-001 5132(a) | AS/NZS 2891.7.1 | NATA-accredited test certificate | TP | Laboratory Technician
Note 1: Sampling frequency Number of test sets on asphalt of each nominal size in work period: Quantity of asphalt produced Number of sets of tests First 50t (0-50t) 1 Next 100t (50-150t) 1 Next 200t (150-350t) 1 Next 250t (350-600t) 1 Every 250t thereafter 1 Minimum number of tests per work period regardless of tonnes produced: 3
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-08-12 | N.Wood | Draft document published |  |  | 1
2022-10-14 | N.Wood | Updated Reference Documents to include reference to GHD-DD-SPC-001, added Items 1.01, 2.01, 2.02 and 2.07, removed references to 20mm NMS from Item 3.07, added Table SP5131-3 to Items 2.03 to 2.06 Reference Documents, changed Item 2.06 from Penetration to PG MSCR testing, updated Item 3.01 Reference Documents to 5116(g), added reference to ASTM D2489 to Item 3.01 Test Method, added Table 5116-5 to Items 3.02 to 3.06 Reference Documents, added limits for 19.0mm sieve to Item 3.07 Acceptance Criteria. |  |  | 1.1