## ITP
|  |  | Inspection and Test Plan - Mixing Plant Establishment and Trials | [7 empty] | Document # ITP-017
[11 empty] | Revision: 1.0 | Date : 14/10/2022
Client: | Melbourne Airport |  | Construction Process: | Mixing Plant Establishment and Trials |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melbourne Airport Runway 16-34 Overlay |  |  |  |  | Name: Noriko Wood |  | Name: |  |  | Name:
Contract: | 12554937 |  | Specifications: | Technical Specifications Melbourne Airport Runway 16-34 Overlay Schematic and Detailed Design GHD-DD-SPC-001 (10 June 2022), GHD-DD-SPC-002 (14 June 2022) |  | Senior Pavement Engineer
|  |  | Location: | Fulton Hogan Infrastructure Services 500 Princes Hwy, Noble Park VIC 3174
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
|  |  | Frequency |  | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity
1.04
1.05
1 | Preliminary
1.01 | Bituminous material sources |  | Not less than 5 days prior to the commencement of asphalt mix design. |  | Submission of source, name and address of manufacturer(s), manufacture information and test certificates for bitumen. | GHD-DD-SPC-001 5130(c) HP5130-2 | N/A | ITP | HP | Technical Manager
2 | Mixing Plant Establishment
2.01 | Notification of calibration |  | Not less than 48 hours prior to each calibration of mixing plant. |  | N/A | GHD-DD-SPC-001 5112(i) WP5112-1 | N/A | ITP | WP | Technical Manager
2.02 | Calibration of mixing plant |  | Not less than 48 hours prior to the commencement of production mix trial. Must include: - Establishment of cold feeder rates of flow, batch masses, mixing cycle times, plant production rates. - Adjustment of the aggregate, filler and bitumen feeder compensators to provide accurate readings for the actual materials used. - Confirmation of the accuracy of the plant recorders by checking actual masses on an independent weighbridge. |  | Acceptance of calibration report by Contract Administrator | GHD-DD-SPC-001 5112(i) HP5112-3 | N/A | Calibration report | HP | Technical Manager
3 | Production Trial
3.01 | Assessment of mixing plant. |  | Not less than 4 weeks prior to the commencement of a production mix trial. |  | Submission of production capacity and hot asphalt storage capacity for the primary mixing plant proposed for production of asphalt for the works. | GHD-DD-SPC-001 5112(h) HP5112-2 | N/A | ITP | HP | Technical Manager
3.02 | Mixing plant calibration charts. |  | Prior to each production mix trial. |  | Submission of mixing plant calibration charts to Contract Administrator. | GHD-DD-SPC-001 5110(b) HP5110-1 | N/A | ITP | HP | Technical Manager
3.03 | Notification of production mix trial |  | Not less than 48 hours prior to the commencement of a production mix trial. |  | N/A | GHD-DD-SPC-001 5110(c) WP5110-1 | N/A | ITP | WP | Technical Manager
3.04 | Submission of results for production mix trial. |  | After each production mix trial for each nominal mix size produced in the trial. |  | All test results on each nominal mix size produced in the production mix trial submitted to Contract Administrator, and written advice to the Contract Administrator of any adjustments to the mix which are necessary to achieve the properties of the submitted mix design. | GHD-DD-SPC-001 5110(e) HP5110-2 | N/A | NATA-accredited test certificates | HP | Technical Manager
3.05 | Submission of results of verification testing of asphalt mixing plant devices against direct measurement of bitumen tank with production trial test results. |  | After each production mix trial. |  | Acceptance of verification test results by Contract Administrator | GHD-DD-SPC-001 5112(g) HP5112-1 | N/A | ITP | HP | Technical Manager
4 | Construction Trial
4.01 | Bitumen emulsion. |  | Not less than ten (10) days prior to the commencement of construction trial. |  | Submission of source, name and address of manufacturer(s), manufacture information and test certificates for bitumen emulsion. | GHD-DD-SPC-001 5130(c) HP5130-3 | N/A | ITP | HP | Technical Manager
4.02 | Mixing plant calibration charts. |  | Prior to each construction trial. |  | Submission of mixing plant calibration charts to Contract Administrator. | GHD-DD-SPC-001 5111(b) HP5111-2 | N/A | ITP | HP | Technical Manager
4.03 | Commencement of construction trial. |  | Not less than five (5) days prior to the scheduled commencement of asphalt paving works. Prior notice (minimum 48 hours) of commencement of trial to be given to Contract Administrator. |  | All resources required for a trial of minimum tonnage 40 t of each nominal mix size, placed in a minimum of two paving runs, with a joint suitable for testing, are available and all arrangements for the trial have been made. | GHD-DD-SPC-001 5111(a) HP5111-1 | Inspection | ITP | HP | Site Engineer
4.04 | Extraction of cores from construction trial sections. |  | At the completion of each construction trial, after the asphalt has cooled to ambient temperature and not more than 24 hours after construction. |  | A minimum of six (6) cores are cut from within lanes, and six (6) cores are cut over a joint. Cores are not less than 100 mm diameter and are cut from the finished asphalt construction trial section. | GHD-DD-SPC-001 5111(c), 5132(b) | AS 2891.1.2, AS 1289.1.4.2 | ITP | IP | Site Engineer
4.05 | Repair of core holes in construction trial sections. |  | At the completion of core extraction. |  | All debris, slurry and water has been removed from the core hole and the core walls and floor are completely dry prior to reinstatement. Tack coat has been applied to the walls and floor of core hole, and the hole reinstated with hot mix asphalt approved for use in this project and placed and compacted in lifts not more than 50 mm compacted thickness. The filled hole is flush to the surrounding pavement surface. | GHD-DD-SPC-001 5111(c), 5132(b) | Inspection | ITP | IP | Site Engineer
4.06 | Layer thickness of construction trial section. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | The average compacted layer thickness of a minimum of 4 cores is within the accepted range of: - Minimum of 40 mm and maximum of 85 mm for 14mm NMS asphalt, or - Minimum of 75 mm and maximum of 110 mm for 20mm NMS asphalt. | GHD-DD-SPC-001 5111(c), Table 5120-1, 5132(e) | AS 2891.1.2 | NATA accredited test certificates | TP | Site Engineer
4.07 | Compaction of construction trial section. |  | Within 24 hours after the completion of each construction trial. |  | Characteristic value of air voids are within the range of: - Surfacing layers: 3.0-6.5% inclusive for mat and 3.0-8.0% inclusive for joints, or - Base layers: 3.0-7.0% inclusive for mat. | GHD-DD-SPC-001 5111(c), 5121(c), 5132(c)(d) | AS 2891.9.1, AS 2891.9.2 | NATA accredited test certificates | TP | Site Engineer
4.08 | Finished surface levels of construction trial sections. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | All finished surface levels have been surveyed to an accuracy of 2 mm with readings to 1 mm by a licensed surveyor. | GHD-DD-SPC-001 5111(c), 5132(f) | Survey | Record of finished surface levels | IP | Site Engineer
4.09 | Surface smoothness of construction trial sections. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | Surface smoothness has been tested in each placing lane in longitudinal direction parallel to the centreline, and in the transverse direction at intervals not exceeding 10 m using a mobile straight edge operated at a speed not exceeding 5km/hr. The finished surface complies with Item 3.14 of this ITP. | GHD-DD-SPC-001 5111(c), 5132(g) | Straight edge | Record of location and extent of any surface irregularities | IP | Site Engineer
4.1 | Completion of construction trial. |  | At the completion of each construction trial and prior to the commencement of full scale production and placement of asphalt. |  | Submission of all test results and written advice to Contract Administrator regarding any alterations in procedures or adjustments to plant and equipment as necessary to produce asphalt in accordance with specified requirements. | GHD-DD-SPC-001 5111(c) HP5111-3 | Inspection | ITP | HP | Quality Manager
4.11 | Selection of reference area for surface finish. |  | After the completion of construction trials. |  | Agreement with Contract Administrator of reference area/s for each nominal size mix and photographs of each reference area. | GHD-DD-SPC-001 5111(e) HP5111-5 | Inspection | Photographs of reference areas | HP | Quality Manager
4.12 | Supply of asphalt as per job mix. |  | After the completion of construction trials and not less than two (2) working days prior to the planned commencement of full scale asphalt works. |  | Submission of the complete details of the job mix, job aggregate particle size distribution, job bitumen content, and job mix temperature for each nominal mix size. | GHD-DD-SPC-001 5111(e) HP5111-4 | Document | Job mix report | HP | Quality Manager
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Contract Administrator |  |  | IP Inspection point | Formal Inspection to be completed and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Contract Administrator or Client |  |  | NMS Nominal Mix Size | The nominal size of the asphalt mix
AP | Approval Point | Written or verbal approval given by the Contract Administrator
Document Control
Date | Author | Description of Change |  |  | Revision
2022-10-14 | N.Wood | Document published |  |  | 1